## Slide 1: CIBC CM Simpli – Project Proposal
Project Title: Implementation of CIBC CM Simpli – Enterprise Content Management
Prepared By: Mohammed Taher Yousuf Date: 22/07/2025

## Slide 2: Situation / Problem / Opportunity
Situation: CIBC is currently using a fragmented, outdated content management solution that struggles to meet current operational and compliance demands.
Problem:
Delays in retrieving key documents
System downtime during peak hours
Siloed storage of information across departments
Poor integration with CRM and banking systems
Inability to meet regulatory audit standards
Opportunity:
Implement CM Simpli to centralize and digitize content across the organization
Improve document lifecycle management, collaboration, and compliance
Enhance operational efficiency and employee productivity

## Slide 3: Purpose Statement (Goals)
The purpose of this project is to analyze, select, and implement the CIBC CM Simpli solution. The goal is to deliver a modern, secure, and scalable content management system that supports:
Quick access to structured information
Streamlined workflows
Improved compliance and audit-readiness
Digital transformation of document handling processes

## Slide 4: Project Objectives
Select the CM Simpli solution that aligns with enterprise requirements and scalability goals
Prototype and test the system with real CIBC workflows
Integrate CM Simpli with existing systems (CRM, core banking, portals)
Migrate legacy data and documents without data loss
Provide role-based access and governance controls

## Slide 5: Success Criteria
80% reduction in average document retrieval time
99.5% uptime of the new CM system
Seamless access to forms, collateral, and records for employees
Reduced internal support tickets for document access issues
100% regulatory compliance with ICBS and ISI standards

## Slide 6: Methods / Approach
Establish Selection Committee
Cross-functional team from IT, Compliance, and Operations
Define Requirements
Functional, technical, security, and compliance-based
Vendor Selection through RFP
Review responses, conduct demos and sandbox testing
Implementation
Configure system, migrate data, set up integrations
Training & Support Setup
User onboarding, help desk, knowledge base
Go Live
Rollout in phases, monitor adoption, collect feedback

## Slide 7: Project Timeline
Phase | Duration
Requirements Gathering | 1 Month
RFP & Vendor Evaluation | 1.5 Months
Prototype & Testing | 1 Month
Configuration & Build | 2 Months
Training & Go Live | 2.5 Months
Total Duration | ~8 Months

## Slide 8: Resources Required
People:
  CIBC project manager, ITS team, compliance lead, business users, vendor team
Time:
  8 months total project duration
Budget:
  Software Licensing: ₹5,00,000
  Training & Implementation: ₹4,00,000
  Data Migration & Integration: ₹4,50,000
  Total Budget: ₹13,50,000
Other:
  Evaluation reports, third-party consultancy, site visits

## Slide 9: Risks and Dependencies
Legacy System Dependence: Staff are accustomed to old system interface
ROI Visibility: Benefits like speed and ease of access are hard to quantify
(Note- Return on Investment –ROI)
Integration Complexity: With CRM, compliance platforms, and core banking
Mitigation Strategies:
Include change management and user training plans
Conduct pre/post KPI analysis to demonstrate impact
Use phased rollout to reduce transition risks

## Slide 10: Stakeholder Benefits
Stakeholder | Benefit
Operations | Faster access to forms & customer docs
IT | Easier maintenance, stronger security
Compliance | Audit trail, version control
Employees | Centralized access, reduced wait time
Customers | Faster service delivery

## Slide 11: Governance & Roles
Project Sponsor: SVP – Digital Operations, CIBC
Project Manager: Director – Enterprise IT Delivery
Steering Committee: IT, Compliance, Operations, Risk
Reporting Cadence:
  Bi-weekly standups
  Monthly stakeholder reviews
  Post-Go-Live success review

## Slide 12: Conclusion & Next Steps
CM Simpli will transform how CIBC manages content—faster, more secure, and future-ready
Strong alignment with CIBC’s digital vision and compliance roadmap
Next Steps:
Finalize requirements documentation
Release RFP to shortlisted vendors
Begin vendor demos and evaluations
Initiate planning for data migration and user onboarding

## Slide 13: Thank You