## Slide 1: GCOS Application Porting From Mainframe to IBMi
Prepared By – Uday Hadap
Date – 19/07/2025

## Slide 2: Agenda
Situation/Problem/Opportunity
Purpose Statement
Project Objectives
Success Criteria
Methods/Approach
Resources
Risks and Dependencies
Concluding Points

## Slide 3: Situation/Problem/Opportunity
Customer has an application called as ‘GCOS’, which is currently running on old mainframe server.
The support for this mainframe server is going to stop in near future.
Once the server support is stopped, there is risk of GCOS application getting crash at any time.
Hence Customer need to port this GCOS application on to some other platform, before the Mainframe support stops.

## Slide 4: Purpose Statement (Goals)
The IBMi platform is a comprehensive, integrated system known for its reliability, security, particularly in business applications.
IBMi gives Legacy and Modernization Support. It supports both older programming languages like RPG, COBOL, and CL, as well as modern languages like Java and Python, allowing for a mix of legacy and modern applications.
Hence, we propose to port the GCOS application on IBMi using our services.
Our company has all the required things to port the GCOS application on IBMi (i.e. Infrastructure, Prior IBMi porting project experience, Skilled development team, Good quality work at reasonable rates etc.).
We can smoothly port the GCOS application on IBMi and make it up & running well before the current mainframe support stops.

## Slide 5: Project Objectives:
Analyze the existing GCOS application for Architecture, Number of Users, Security etc.
Analyze how the application data is currently stored and how it is related to each other. Determine a plan to take this data to IBMi database maintaining same relationship.
Analyze the application programs to understand the business rules and determine a plan to take these rules and application logic to IBMi programs.
Analyze how the user is currently interacting with the system (i.e. Forms etc.) and determine a plan to take this User Interface to IBMi screens.
Analyze all the current external interfaces to GCOS system and study in which format data is send/received currently.
Ensure that data privacy is maintained

## Slide 6: Success Criteria:
All the existing data is ported to IBMi database with no errors/data loss.
All the application programs are taken to IBMi programs keeping the business logic as it is.
The user interaction with the application is same as before on IBMi platform.
The IBMi application security is implemented same as current GCOS application.
On IBMi, the GCOS application is running successfully with same or improved performance.
The entire porting is done within given timelines and budget.

## Slide 7: Methods/Approach:
Database Porting:
  DB2 tables will be created using existing GCOS Cobol copybooks.
  Relation among tables will be implemented in IBMi tables using Primary key and views etc.
  The COMP fields will be expanded to their actual sizes.
  The utility will be written to do the data import from existing flat file system to DB2.
Application Programs Porting:
  EC/TCL control scripts will be written in IBMi CL programs.
  The mapping of various EC/TCL commands to corresponding CL commands will be done.
  The utility will be written to convert the EC/TCL scripts to corresponding CL programs.
  The application Cobol programs will be taken as it is to IBMi.
  Necessary changes will be done for some Cobol statements that doesn’t work on IBMi

## Slide 8: Methods/Approach: (Cont.…)
User Interface:
  The utility will be written to parse the current GCOS forms and store the field level information into a file including its position on the screen.
  Then another utility will be written to create the IBMi screens using this parsed field level information.
Utilities/Common programs:
  LFN programs (those are used to read a file in current application) will be taken to IBMi and file will be overridden to corresponding DB2 file.
  The ZNV programs will be written new on IBMi to provide the desired functionality.

## Slide 9: Resources:
People:
  Skilled IBMi development team with experience in Cobol/CL/DB2/RPGLE.
  Project Manager
  Support of current GCOS application support team and users
Time:
  With team of 5 developers, the entire porting will be completed in 6 months as below:
    Existing GCOS application analysis – 2 weeks.
    Porting of database – 4 weeks
    Porting of screens – 4 weeks
    Poring of application programs with unit testing – 8 weeks
    Integration/System testing of new application on IBMi – 3 weeks
    UAT and final signoff – 2 weeks

## Slide 10: Resources (Cont.…):
Budget: The total budget for this entire porting will be $8000 that includes below costs:
  Visit to Customer to Analyze current GCOS application.
  IBMi application development and deployment.
  Training of Users for new application.
  Support to new IBMi application for 6 months.

## Slide 11: Risks and Dependencies:
Risks:
  Mainframe decides to stop the support before given timeline.
  Any unknown interfaces to current GCOS application.
  User resistance to use the new application.
  Downtime during migration can disrupt business operations, and unexpected issues can lead to longer downtimes.
Dependencies:
  Timely required support from current GCOS application support team.
  Purchase and Readiness of new IBMi server with all required configuration.

## Slide 12: Concluding Points:
IBMi is a very good option to port the current GCOS system.
Considering our company services will ensure:
  Timely and Smooth Application Porting.
  Minimum down-time and business impact.
  Quality work.
  Reasonable cost
  Post go-live application support

## Slide 13: Thank You !!!