CAPSTONE PROJECT 2:

Q.1 Write Agile manifesto.

Answer: Definition of Agile:

- Agile is lightweight and can be implemented where faster delivery is required.

- Agile no documentation is required.

- Customer retention since no documentation.

- Agile does not support scalability and extendibility.

Four Main Values in Agile:

- Individuals and interactions over processed and tools.

- Working software over comprehensive documentation.

- Customer collaboration over contract negotiation.

- Responding to change over following a plan.

12 principles of Agile:

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development, Agile processes harness change for the customer’s competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build project around the motivated individual. Give them the environment and support they need and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.

- Working software is primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers and users should be able to maintain constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

- Simplicity the art of maximizing the amount of work not done is essential.

- The best architectures, requirements and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, the tunes and adjusts its behavior accordingly.

Q.2 User Stories-Acceptance Criteria –BV-CP

| User Story No: 1 | Tasks: 2 | Priority: Highest |
| --- | --- | --- |
| As a Delivery Boy I want to register in Scrum Foods So that I can Deliver Orders |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1)Registration Screen |  |  |
| 2)Text Boxes for User Name, Password, Nation ID, Mobile No, Email, Address, Phone Number. 3) Click on Register Button and Send Successful Notification to the user. |  |  |

| User Story No; 2 | Tasks: 2 | Priority: Highest |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW ORDERS SO THAT I CAN VIEW THE LIST OF ORDERS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA 1)Restaurant owner can access view order section 2)List of order is displayed in table format, with essential details like order id, customer name, items, status, date, price |  |  |

| User Story No; 3 | Tasks: 2 | Priority: Highest |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO ADD THE ADDRESS SO THAT I CAN GET THE ORDER TO MY ADDRESS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA 1)Text Box to enter address 2) As per Business Rules address Within the radius of 5 km. 3)Save and procedd if address is valid. |  |  |

| User Story No; 4 | Tasks: 2 | Priority: Highest |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO SELECT THE PAYMENT MODE SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |
| BV: 500 | CP: 03 |  |
| ACCEPTANCE CRITERIA 1)Display payment modes, radio buttons to select payment modes, payments button. 2) Business Rule: Can select only one payment mode. |  |  |

| User Story No; 5 | Tasks: 1 | Priority: Highest |
| --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW THE RESTAURANTS SO THAT I CAN APPROVE THEIR REGISTRATION |  |  |
| BV: 500 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1)List of restaurant, select restaurants. 2)Verify restaurant details and approve or reject using button 3)Notification to the restaurant. |  |  |

| User Story No; 6 | Tasks: 1 | Priority: Low |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE PRICE SO THAT I CAN ORDER THE FOOD |  |  |
| BV: 50 | CP: 1 |  |
| ACCEPT ANCE CRITERIA 1)Display price in the list of menu items. 2)Price display in correct current format(ex: Rs, $) 3)If an item has discount, display both original and discount price. |  |  |

| User Story No; 7 | Tasks: 2 | Priority: Low |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE CONTACT NUMBER OF DELIVERY BOY SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |
| BV: 50 | CP: 1 |  |
| ACCEPTANCE CRITERIA 1. Display delivery boy mobile number 2. Display delivery boy name in tracking field 3. Display delivery boy picture |  |  |

| User Story No: 8 | Tasks: 2 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE CONTACT NUMBER OF DELIVERY BOY SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |
| BV: 50 | CP: 1 |  |
| ACCEPTANCE CRITERIA 1. Display delivery boy mobile number 2. Display delivery boy name in tracking field 3. Display delivery boy picture |  |  |

| User Story No: 9 | Tasks: 6 | Priority: High |
| --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW RESTAURANT REVENUE REPORT SO THAT I CAN VIEW THE RESTAURANT'S REVENUE |  |  |
| BV: 200 | CP: 3 |  |
| ACCEPTANCE CRITERIA Select Reports Selects Revenue Reports Select to and from date Select Region (can select all) Generate Report Download Report in EXCEL |  |  |

| User Story No: 10 | Tasks: 3 | Priority: High |
| --- | --- | --- |
| AS A REG ADMIN I WANT TO MANAGE REGIONAL RESTAURANTS SO THAT, I CAN TRACK THE PERFORMANCE OF REGIONAL RESTAURANTS |  |  |
| BV: 200 | CP: 3 |  |
| ACCEPTANCE CRITERIA CLICK ON PERFORMANCE OF RESTAURANTS SELECTS FROM DATE TO DATE CLICK ON GENERATE REPORT WHICH INCLUDES RESTAURANTS ID, NAME, REVENUE CLICK ON DOWNLOAD REPORT SHOULD BE IN EXCEL |  |  |

| User Story No: 11 | Tasks: 2 | Priority: Medium |
| --- | --- | --- |
| AS AD ADMIN I WANT TO SEE THE REGIONAL REVENUE REPORTS SO THAT, I CAN VIEW THE REGIONAL PERFORMANCE |  |  |
| BV: 100 | CP: 3 |  |
| ACCEPTANCE CRITERIA Select regional dropdown View performance of each rest of that region in tabular form which includes rest name, revenue, generated Download in excel or PD |  |  |

| User Story No: 12 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO CHAT WITH REG ADMIN SO THAT, I CAN REQUEST FOR REFUND |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA BR- All mandatory Text Box Fields Display Order ID Text Box, for Description Submit Button Generate Issue ID Display Successful |  |  |

| User Story No: 13 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A HUNGRY USER I WANT TO BROWSE NEARBY RESTAURANTS SO THAT I CAN ORDER FOOD |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Each restaurant entry displays its name, cuisine type, and rating 2. This list can be sorted by distance or rating |  |  |

| User Story No: 14 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO BROWSE DIFFERENT RESTAURANTS AND MENUS SO THAT I CAN FIND A PLACE TO ORDER FOOD |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. The menu includes dishes, prices and descriptions 2. Show the restaurant is open or closed |  |  |

| User Story No: 15 | Tasks: 1 | Priority: High |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO BROWSE FOR SPECIFIC DISHES AND CUISINES SO THAT I CAN FIND A PLACE TO ORDER FOOD |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA App displays relevant restaurant and dishes matching the query |  |  |

| User Story No: 16 | Tasks: 1 | Priority: High |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO FILTER RESTAURANTS SO THAT I CAN FIND A PLACE TO ORDER FOOD |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA Filter restaurants by cuisine type and dietary options(vegan, veg, nonveg, egg) |  |  |

| User Story No: 17 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO TRACK MY ORDER SO THAT I KNOW THE TIME OF DELIVERY |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. App shows real time update on the order status 2. Display estimated delivery time |  |  |

| User Story No: 18 | Tasks: 3 | Priority: High |
| --- | --- | --- |
| AS A USER I WANT TO RATE AND REVIEW RESTAURANTS SO THAT I CAN RATE AND REVIEW THE RESTAURANTS I HAVE VISITED |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. I can see reviews from other users to help me make dining decisions 2. I can submit a review with a star rating (1 to 5). 3. I can only post a review if I am logged in. |  |  |
| User Story No: 19 | Tasks: 3 | Priority: High |
| AS A USER I WANT TO VIEW PAST ORDER HISTORY SO THAT I CAN ORDER AGAIN |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. I can see the details such as order items, total cost and order date 2. I can reorder a past order with a single click or tap. 3.I can download or print an invoice/receipt for each past order. |  |  |

| User Story No: 20 | Tasks: 3 | Priority: High |
| --- | --- | --- |
| AS A USER I WANT TO RECEIVE NOTIFICATIONS SO THAT I CAN RECEIVE UPDATES |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Notifications for order confirmation 2. Notifications for dispatch 3. Notification for delivery |  |  |

| User Story No: 21 | Tasks: 3 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO CONTACT CUSTOMER SUPPORT SO THAT I CAN SUBMIT QUERIES OR ISSUES |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Customer support section with contact information 2. I can submit a query or issue using a contact form (with fields like name, email, subject, and message) 3. I receive a confirmation message after submitting a query (e.g., Your request has been received). |  |  |

| User Story No: 22 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO RECEIVE AND MANAGE ORDERS SO THAT I CAN UPDATE ORDER STATUS |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Manage order status 2. Notify restaurants about incoming orders |  |  |

| User Story No: 23 | Tasks: 2 | Priority: High |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO ACCESS TO CUSTOMER REVIEWS SO THAT I CAN VIEW AND RESPOND TO CUSTOMER REVIEWS |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Owners can address feedback 2. Owners can improve their services |  |  |

| User Story No: 24 | Tasks: 2 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO APPLY PROMOCODES AND DISCOUNTS SO THAT I CAN ORDER AT LOWER PRICE |  |  |
| BV: 100 | CP: 3 |  |
| ACCEPTANCE CRITERIA 1. Active Promo codes are visible to customers during checkout 2. I can manually enter a promo code in a designated input field at checkout. |  |  |

| User Story No: 25 | Tasks: 2 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO APPLY PROMOCODES AND DISCOUNTS SO THAT I CAN ORDER AT LOWER PRICE |  |  |
| BV: 100 | CP: 3 |  |
| ACCEPTANCE CRITERIA 1. Active Promo codes are visible to customers during checkout 2. I can manually enter a promo code in a designated input field at checkout. |  |  |

| User Story No: 26 | Tasks: 7 | Priority: HIGH |
| --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW THE ORDERS SO THAT I ACCEPT THE ORDER |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Order visibility 2. Real-time updates 3. Order details 4. Order filtering and sorting 5. Order map view 6. Order navigation 7. Order completion and confirmation |  |  |

| User Story No: 27 | Tasks: 5 | Priority: HIGH |
| --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN SO THAT I CAN ACCEPT THE ORDER |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. User Authentication 2. Error handling 3. Password security 4. Multi-factor Authentication 5. Compatibility and Usability |  |  |

| User Story No: 28 | Tasks: 5 | Priority: Medium |
| --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW FEEDBACK SO THAT I CAN KNOW THE CUSTOMERS FEEDBACK |  |  |
| BV: 200 | CP: 3 |  |
| ACCEPTANCE CRITERIA 1. Access to feedback system 2. Feedback Visibility 3. Feedback sorting and filtering 4. Response mechanism 5. User Support |  |  |

| User Story No: 29 | Tasks: 5 | Priority: Medium |
| --- | --- | --- |
| AS A ADMIN I WANT TO VIEW FEEDBACK SO THAT I CAN KNOW THE CUSTOMERS FEEDBACK |  |  |
| BV: 200 | CP: 3 |  |
| ACCEPTANCE CRITERIA 1. Access to feedback system 2. Feedback entries are displayed in reverse chronological order (latest first). 3. Admin can filter feedback by date range, rating (if included), or category 4.Admin can search feedback by keywords (e.g., cold food, late delivery 5.Admin can export feedback data as a CSV or PDF report. |  |  |

| User Story No: 30 | Tasks: 5 | Priority: Medium |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW FEEDBACK SO THAT I CAN KNOW THE CUSTOMERS FEEDBACK |  |  |
| BV: 200 | CP: 3 |  |
| ACCEPTANCE CRITERIA 1. Access to feedback system 2. Feedback Visibility 3. Feedback sorting and filtering 4. Response mechanism 5. User Support |  |  |

| User Story No: 31 | Tasks: 3 | Priority: HIGH |
| --- | --- | --- |
| AS A ADMIN I WANT TO KNOW THE ISSUES SO THAT I CAN RESOLVE THEM |  |  |
| BV: 100 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Display issue section 2. Sorting and filtering of issues list 3. Editing and modifying the issues |  |  |

| User Story No: 32 | Tasks: 3 | Priority: HIGH |
| --- | --- | --- |
| AS A REGIONAL ADMIN I WANT TO KNOW THE ISSUES SO THAT I CAN RESOLVE THEM |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Display issue section 2. Sorting and filtering of issues list 3. Editing and modifying the issues |  |  |

| User Story No: 33 | Tasks: 6 | Priority: HIGH |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW REVENUE GENERATED SO THAT I CAN VIEW RESTAURANTS REVENUE |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Select Reports 2. Select Revenue Reports 3. Select to and from date 4. Select Region (can select all) 5. Generate Report t 6. Download Report in EXCEM |  |  |

| User Story No: 34 | Tasks: 2 | Priority: HIGH |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO KNOW DELIVERY BOY SO THAT I VERIFY THE DELIVERY BOY |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. ID proof 2. Punctuality and reliability |  |  |

| User Story No: 35 | Tasks: 2 | Priority: LOW |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE CONTACT NUMBER OF DELIVERY BOY SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |
| BV: 50 | CP: 1 |  |
| ACCEPTANCE CRITERIA 1. Display delivery boy mobile number 2. Display delivery boy name in tracking field |  |  |

| User Story No: 36 | Tasks: 4 | Priority: Medium |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PROVIDE TIME SLOTS SO THAT CUSTOMER CAN CHECK OPENING AND CLOSING HOURS |  |  |
| BV: 100 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Click on restaurant dashboard 2. Add from time to time 3. Click on submit 4. Display updated successfully |  |  |

| User Story No: 37 | Tasks: 3 | Priority: HIGH |
| --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PROVIDE TIME SLOTS SO THAT CUSTOMER CAN CHECK OPENING AND CLOSING HOURS |  |  |
| BV: 200 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Notifications for order confirmation 2.Notification for dispatch 3. Notification for delivery |  |  |

| User Story No: 38 | Tasks: 1 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO CONTACT CUSTOMER SUPPORT SO THAT I CAN SUBMIT QUERIES OR ISSUES |  |  |
| BV: 200 | CP: 2 |  |
| ACCEPTANCE CRITERIA 1. Customer support section with contact information |  |  |

| User Story No: 39 | Tasks: 4 | Priority: Medium |
| --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE ORDER SO THAT I CAN CANCEL IT |  |  |
| BV: 100 | CP:3 |  |
| ACCEPTANCE CRITERIA 1. Order status 2. Method of cancellation 3. Refund policy 4. Time frame |  |  |

| User Story No: 40 | Tasks: 4 | Priority: HIGH |
| --- | --- | --- |
| AS A REGIONAL ADMIN I WANT TO TRACK THE DELIVERY SO THAT I CAN VIEW THE STATUS OF THE DELIVERY |  |  |
| BV: 100 | CP: 5 |  |
| ACCEPTANCE CRITERIA 1. Real time tracking 2. Security and data privacy 3. User friendly interface |  |  |

Q.3 what is epic? Write 2 epic.

Answer:  Meaning of Epic:

- An EPIC is a large user story or big feature that is too big to complete in a single sprint. It is usually broken down into smaller user stories for development.

- An EPIC- Big feature or function that needs to be divided into smaller tasks.

Example:

- User Registration and Login

- Stories: create signup form, email verification, login, forgot password.

- Shopping cart functionality

- Stories: Add to cart, update quantity, remove item, view cart, apply coupon.

Q.4 what is BV & CP

Answer

Meaning of BV:

BV- BV stands for Business Value, which is given by the client according to the importance of task.

Business Value is how important is this feature (user story) to the business. This is estimated by Scrum currency notes. We provide Rs. 1000. Rs 500. Rs 100. Rs 50. Rs 20. And Rs 10.  Denominations.

Meaning of CP:

CP is also known as story points (SP). CP is the effort required by the Scrum developers to develop this feature (user story) using technology. Efforts include time taken to solve the complexity and write the code. CP is estimated by the Scrum developers by using Poker cards. We provides pokers with values- 1, 2, 3, 5, 8, 13, 20, 40, 100 and Big.

The main difference between BV and CP is that the BV value is decided or given by the client according to the importance or the priority of task to be performed. However the CP value is given by the development team according to the efforts needed to perform the tasks.

Q.5 Explain about Sprint?

Ans.  In the context of software development and project management, a sprint is a time-boxed, iterative development period during which a specific set of tasks and goals are worked on by a development team. Sprint is a core concept in Agile methodologies, such as Scrum, which emphasizes flexibility, collaboration and delivering value to the customer in shorter cycles.

Here are the key characteristics and components of a Scrum:

- Time Frame: A sprint typically has a fixed duration, often ranging from 1 to 4 weeks. The duration is consistent across all sprints to provide a predictable cadence for development and planning.

- Goals and objectives: At the beginning of each sprint, the development team, along with stakeholders, selects a set of user stories, features or tasks to work on during that sprint. These items are collectively referred to as the sprint backlog.

- Planning: During sprint planning, the development team breaks down the selected items from the product backlog into smaller tasks and estimates the effort required for each task. The team commits to completing these tasks within the sprint duration.

- Daily Stand- ups: Throughout the sprint, the team holds daily stand-up meetings to discuss progress, obstacles, and plans. Each team member shares what they have accomplished, what they are working on, and any challenges they are facing. These meetings foster communication and collaboration.

- Development: The development team works on the tasks identified in the sprint backlog. They collaborate closely, often using techniques like pair programming and frequent code reviews to ensure high- quality work.

- Continuous Integration: Developers integrate their code changes into the main codebase regularly, ensuring that the software remains functional and stable throughout the sprint.

- Testing; Testing is an integral part of a sprint. Automated tests are run to validate code changers, and manual testing may be conducted to ensure the quality of the software.

- Review and Demo: At the end of the sprint, the development team conducts a sprint review and demo. They showcase the completed work to stakeholders, gathering feedback and validation. This helps ensure that the delivered features align with expectations.

- Retrospective: Following the review and demo, the team holds a sprint retrospective. They reflect on what went well during the sprint., that could be improved, and actions to take in the next sprint. The retrospective encourages continuous improvement.

- Incremental Development: Each sprint results in a potentially shippable product increment, meaning that at the end of each sprint, a new version of the software is available with additional features or improvements.

- Adaptability: Agile methodologies emphasize adaptability and the ability to respond to changing requirements. If new priorities or insights emerge, adjustments can be made in subsequent sprints.

Sprints allow development teams to iteratively deliver value to customers and stakeholders in a controlled and predictable manner. By breaking down the work into manageable chunks and continuously seeking feedback, Agile teams can enhance collaboration, reduce risk and improve the overall quality of the software being developed.

Q.6 Explain product backlog and sprint backlog?

Answer: Product Backlog- To do list for the whole project.

- A master list of everything that needs to be for the product.

- Includes all features, changes, fixes, and ideas.

- Created and prioritizes by the Product Owner.

- Keeps evolving throughout the project.

Sprint Backlog- To do list for the current sprint.

- A smaller list taken from the Product Backlog.

- Contains only the tasks selected for the current sprint.

- Planned and owned by the development team.

- Helps track what to finish in that sprint (usually 1-4 weeks).

Q.7 what is impediments log? Write 2 impediments.

Answer:    Meaning of Impediments:

- An Impediments Log is a list of issues or blockers that stop or slow down the team’s work during a project or sprint.

- A problem tracker used by the team to keep track of anything that’s getting in the way.

Importance of Impediments Log:

- Helps the Scrum Master or Project Manager Resolve issues quickly.

- Keeps the team focused and productive.

- Improves sprint progress.

Example:

  - Waiting for client feedback.

  - Server is down.

  - Missing tools or access.

  - Unclear requirements.

### Q.8 Explain velocity of a team?

### Ans. Velocity is a measure of the amount of work a Scrum or Agile team can complete during a single sprint. It is usually calculated using story points, ideal days, or other units of estimation.

### Example- Team work in 2- week sprints and finishes the following story points:

### Sprint                                                     Story Points Completed

### 1                                                                  20

### 2                                                                  25

### 3                                                                  22

### Team Velocity= Average of Story Points Completed

### Velocity= 20+25+22/3 = 22

### So team’s average velocity = 22 story points per sprint.

### Q.9 Draw Sprint Burn Charts and Product Burn Down Chart.

### Q.10 Explain about Product Grooming.

### Ans.  Product Grooming is a regular meeting where the team reviews, updates, and improves the Product Backlog to keep it clean, organized, and ready for upcoming sprints.

### Product Grooming is about refining the backlog so the team is always ready to start the next sprint with well-defined and prioritized work.

### Who Attends?

- Product Owners.

- Scrum Mater.

- Development Team.

- Sometimes Business Analyst or Stakeholders.

### Q. 11Explain the roles of Scrum Master and Product Owner?

### Ans. Role of Scrum Master:

- Facilitates Scrum process- Ensures the team follows agile principles and Scrum practices.

- Removes impediments- Helps the team by solving blockers that slow down progress.

- Supports the team- Acts as a coach, encourages collaboration, and protects the team from outside interruptions.

### Role of Product Owner:

- Manages the Product Backlog- Creates, updates, and prioritizes user stories.

- Represents the customer- Acts as the voice of the client or business.

- Defines product vision- Guides the team on what to build and ensures the delivered product brings value.

### The Scrum Master supports the team’s process, while the Product Owner defines what to build and in what order.

### Q.12 Explain all meetings conducted in Scrum project.

### Ans. There are 5 types of Scrum meetings held during the Scrum process which are as follows:

  - Sprint Planning

- When: At the start of each sprint

- Purpose: Decide what work will be done in the sprint.

- Attendees: Scrum Master, Product Owner, Development team

- Output: A sprint backlog (list of task for the sprint).

  - Daily Scrum:

- When: Every day, 15 minutes

- Purpose: Team shares updates and plans for the day

- Each member answers:

- What did I do yesterday?

- What will I do today?

- Are there any blockers?

  - Sprint Review:

- When: End of the sprint.

- Purpose: Show the completed work to stakeholders.

- Attendees: Scrum Team and stakeholders.

- Goal: Get feedback on the product and adjust the backlog if needed.

  - Sprint Retrospective:

- When: After the sprint review, before the next sprint starts.

- Purpose: Team reflects on what went well, what went wrong, and how to improve.

- Attendees: Scrum team only.

- Output: Action items for better teamwork and performance.

- Product Backlog Refinement:

- When: Regularly (e.g., weekly or mid-sprint)

- Purpose: Review, update, and prioritize the product backlog.

- Attendees: Product Owner, Scrum Master, Development Team.

### Q.13 Explain Sprint size and Scrum size.

### Ans. Sprint Size-The whole concept of sprint is to identify User Stories that the Scrum team would work on and complete within a specific sprint duration. Typically  known as the sprint length. Sprints can be of 1, 2,3, or 4 weeks long at the max. anything beyond 4 weeks is never agile scrum project management.

### Scrum Size- Scrum Team Size can 8 to 10 people.

  - Product Owner.

  - Scrum Master.

  - Developers 8

### Q.14 Explain DOR AND DOD.

### Ans. DOR means a user story or task is clear and prepared enough to start working on it. Ready to start- All details, estimates, and dependencies are in place.

### Some examples:

- User Story is clearly written.

- Acceptance criteria has defined.

- Dependencies are identified.

- Team understand the requirement.

### DOD means the work is fully complete, not just coded but tested, reviewed, and ready to deliver. Truly finished- code, test, documentation, and approvals are done.

### Some Examples:

- Code is written

- Code is reviewed

- Unit & functional tests passed

- Accepted by the Product Owner.

### Q.15 What is Prioritization and MVP

Ans. The MoSCoW method is a prioritization technique used in Agile and project management to help teams decide which features or tasks should be completed first based on their importance. The MoSCoW stands for Must Have, Should Have, Could Have, and Won’t Have (for now).

Must Have items are critical and absolutely necessary for the product to function; without them, the system would fail or be unusable. Should Have features are important but not essential, they add value, but the product can still function without them in the first release. Could Have items are nice to have and can enhance the user experience, but they are not needed immediately and can be added later if time allows. Won’t Have (for now) includes features that are either out of scope or not needed at the movement, but may be considered for future versions.

This method helps teams manage scope, time and resources effectively, ensuring that the most important features are delivered first to meet business goals and customer needs.

MVP (Minimum Viable Product), the core of the Agile Methodology. An MVP is a concept from Agile scrum that refers to a product that has just enough features to satisfy the needs of early customers and more importantly, give them something to provide feedback on to shape the future of the product.

Ex-

If building a food delivery app, the MVP might include:

- Sign-up

- Search restaurants

- Place order

(No fancy filters, reviews or chat yet)

Q.16 Difference between Business Analyst n Product Owner – 3 Mark

Ans.

| Aspects | Business Analyst | Product Owner |
| --- | --- | --- |
| Primary Role | Analyzes business needs and defines detailed requirements | Owns the product and ensures it delivers value to users |
| Focus Area | Problem-focused – Understands business processes and gaps | Solution-focused – Defines and prioritizes features |
| Responsibility | Prepares documentation like BRD, FRD, user stories, process flows | Maintains and prioritizes the product backlog |
| Decision Authority | Suggests solutions, but may not have final authority | Has decision-making power over product scope and priorities |
| In Agile | May assist the Product Owner by refining user stories and clarifying needs | Leads backlog grooming and sprint planning sessions |
| Customer Interaction | May or may not directly interact with end-users | Frequently interacts with users/stakeholders to gather feedback |
| Project Involvement | May work across multiple projects or areas | Usually dedicated to one product or project |

Q. 17 Prepare a sample Resume of 3yrs exp Product Owner

65 Maa Vihar Colony, Indore, Phone- + 91-9589666446

EXPERIENCE:

COGNIZANT TECHNOLOGIES, PUNE- JAN 2021 TO FEB 2022

- Work directly with end users to capture and analyse challenges to their workflow.

- Provide key performance metrics to the Head of IT on the deliveries and benefits realization of change implementations.

- Prioritizes work within an agile team and maintain a backlog of future work for consideration/ prioritization.

- Take responsibility for the development of on-going enhancements, create and prioritize user stories with the agile teams.

- Own and drive backlog grooming and management, prioritize user stories, create acceptance criteria and drive testing and delivery.

- Work with Program Management and Battelle leadership to support new business.

- Maximizing the work of the development team.

HITESHI TECHNOLOGIES, INDORE- MAR 2022 T0 MAR 2023

- Provide week-to week tactical objectives to scrum team, and provide quick JIT decisions to system level questions and defect triage.

- Possibly work with 3rd party system integrators to drive process on schedule and on budget.

- Defining the rode map and prioritizing the backlog of work to meet the vision in a timely manner to meet market and customer demands.

- Drive and own backlog grooming and management, prioritize the iteration and drive acceptance testing and delivery of iteration.

- Relating & Networking

- Entrepreneurial & Commercial Thinking

- Track budget and delivery of engineering projects and releases.

VERIF-Y INC, PHILADELPHIA (REMOTE)- APR 2023 TO PRESNT

- Work directly with other product owners, system engineers, program managers, developers, testers, and customers to define features and technical user stories

- Support an Agile Software Development process, working in conjunction with end users/ stakeholders and technical delivery team

- Work closely with counterparts in Product Management to align on the vision, program backlog and roadmap

- Acting as stakeholder of specific product backlog items, work closely with development teams to ensure the output to be aligned with expectations

- Being the voice of the customer and providing a business perspective on value during day –to-day development

- Work with a diverse set of contractor and government personnel to track, manage, and resolve

- Assist in customer workshops and strategic RFX

EDUCATION:

RAJIV GANDHI TECHNICAL UNIVERSITY, BHOPAL

-Bachelor’s Degree in Computer Science

SKILLS:

- Strong communication and technical skills with the ability to quickly grasp technical issues/concepts

- Dissect high-level information into details and is able to communicate details in manner understood by relevant audiences

- Your ability to drill down into the details of a delivery request without losing sight of the bug picture

- Should have good functional knowledge of Investment Banking/Capital markets or Wealth and Investment Management

- Fast learner, able to learn new software solutions, business processes and design techniques quickly and efficiently

- Ability to make critical judgement decisions and solid organization skills

- Prepare agreed deliverables in line with standards, to meet agreed quality standards and timelines

- Proven ability to quickly learn new business domains and technical applications

- Excellent written and verbal communication skills

Top of Form

Bottom of Form