Q1: write Agile Manifesto

AGILE MANIFESTO – Scrum Foods Project

We are uncovering better ways of developing food delivery applications
by doing it and helping others do it.
Through this work, we have come to value:

1. Individuals and interactions

over processes and tools
➡️ We prioritize strong collaboration among customers, restaurants, delivery personnel, and our team, rather than relying solely on rigid processes or platforms.

2. Working software

over comprehensive documentation
➡️ We aim to deliver functional features like real-time tracking, restaurant dashboards, and secure payment modes faster, instead of over-investing time in lengthy documentation.

3. Customer collaboration

over contract negotiation
➡️ We work closely with stakeholders (COEPD IT Solutions, Admins, Restaurants, Customers, and Delivery Boys) throughout development to ensure our product meets real user needs.

4. Responding to change

over following a plan
➡️ We are flexible with changes in restaurant operating hours, customer preferences, or delivery logistics, rather than sticking strictly to a fixed plan.

That is, while there is value in the items on the right, we value the items on the left more.

Agile Principles

- Customer satisfaction through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development.

- Deliver working software frequently, with a preference for shorter timescales.

- Business and developers must work together daily throughout the project.

- Build projects around motivated individuals and trust them.

- Face-to-face conversation is the most effective method of conveying information.

- Working software is the primary measure of progress.

- Sustainable development, able to maintain a constant pace.

- Continuous attention to technical excellence and good design.

- Simplicity—the art of maximizing the amount of work not done—is essential.

- Self-organizing teams produce the best architectures, requirements, and designs.

- Regularly reflect and adjust behaviour to become more effective.

Question 2 – User Stories- Acceptance Criteria-BV-CP – 40 Marks Write minimum 40 User stories and their Acceptance Criteria along with their BV and CP

| USER STORY NO: 1 Tasks: 2 Priority: Highest As a DELIVERY BOY I want to REGISTER IN SCRUM FOODS So that I CAN DELIVER ORDERS BV: 500 CP: 2 Acceptance Criteria: - Registration screen - Fields: Name, Password, Nation ID, Mobile, Email, Address, Phone - Register button - Show success notification ✅ USER STORY NO: 2 Tasks: 2 Priority: Highest As a RESTAURANT OWNER I want to VIEW ORDERS So that I CAN VIEW THE LIST OF ORDERS BV: 500 CP: 2 Acceptance Criteria: - View orders tab - Display list of orders in a table ✅ USER STORY NO: 3 Tasks: 2 Priority: Highest As a CUSTOMER I want to ADD THE ADDRESS So that I CAN GET THE ORDER TO MY ADDRESS BV: 500 CP: 2 Acceptance Criteria: - Address input field - Radius validation: max 5km ✅ USER STORY NO: 4 Tasks: 2 Priority: Highest As a CUSTOMER I want to SELECT THE PAYMENT MODE So that I CAN MAKE PAYMENT OF MY CHOICE BV: 500 CP: 3 Acceptance Criteria: - Display radio buttons for payment types - One mode must be selected - Payment button ✅ USER STORY NO: 5 Tasks: 2 Priority: Highest As an ADMIN I want to VIEW THE RESTAURANTS So that I CAN APPROVE THEIR REGISTRATION BV: 500 CP: 2 Acceptance Criteria: - List of restaurants - Approve/Reject buttons - Send notification ✅ USER STORY NO: 6 Tasks: 2 Priority: Low As a CUSTOMER I want to VIEW THE PRICE So that I CAN ORDER THE FOOD BV: 50 CP: 1 Acceptance Criteria: - Display price next to each menu item ✅ USER STORY NO: 7 Tasks: 2 Priority: Low As a CUSTOMER I want to VIEW THE CONTACT NUMBER OF DELIVERY BOY So that I CAN CONTACT DELIVERY BOY FOR THE STATUS BV: 50 CP: 1 Acceptance Criteria: - Display delivery boy name, phone number, and photo in tracking ✅ USER STORY NO: 8 Tasks: 2 Priority: Medium As a RESTAURANT OWNER I want to PROVIDE TIME SLOTS So that CUSTOMER CAN CHECK OPENING AND CLOSING HOURS BV: 100 CP: 2 Acceptance Criteria: - Time fields for opening & closing - Submit button - Display confirmation ✅ USER STORY NO: 9 Tasks: 2 Priority: High As a CUSTOMER I want to REGISTER So that I CAN PLACE ORDERS BV: 500 CP: 2 Acceptance Criteria: - Registration fields: Name, Phone, Email, Password - Register button - Success message ✅ USER STORY NO: 10 Tasks: 2 Priority: High As a CUSTOMER I want to LOGIN So that I CAN ACCESS MY PROFILE BV: 500 CP: 2 Acceptance Criteria: - Email and Password fields - Login button - Error for invalid credentials ✅ USER STORY NO: 11 Tasks: 2 Priority: High As a CUSTOMER I want to SEARCH FOR FOOD So that I CAN QUICKLY FIND ITEMS BV: 300 CP: 2 Acceptance Criteria: - Search bar - List results by keywords - Suggest similar items ✅ USER STORY NO: 12 Tasks: 2 Priority: High As a CUSTOMER I want to CHAT WITH REGIONAL ADMIN So that I CAN REQUEST FOR REFUND BV: 200 CP: 2 Acceptance Criteria: - All fields mandatory - Text boxes for order ID and description - Submit button - Generate Issue ID - Display success message ✅ USER STORY NO: 13 Tasks: 2 Priority: High As a CUSTOMER I want to TRACK MY ORDER So that I CAN SEE THE DELIVERY STATUS BV: 500 CP: 3 Acceptance Criteria: - Display order status: Confirmed, Preparing, Out for delivery, Delivered - Show delivery boy details - Real-time map integration ✅ USER STORY NO: 14 Tasks: 2 Priority: Medium As a CUSTOMER I want to CANCEL MY ORDER So that I CAN AVOID UNWANTED DELIVERY BV: 300 CP: 2 Acceptance Criteria: - Cancel button enabled until "Out for delivery" status - Confirmation popup - Display refund status ✅ USER STORY NO: 15 Tasks: 2 Priority: Medium As a CUSTOMER I want to VIEW ORDER HISTORY So that I CAN CHECK MY PAST ORDERS BV: 200 CP: 2 Acceptance Criteria: - List of all previous orders - View date, items, amount, and status ✅ USER STORY NO: 16 Tasks: 2 Priority: Medium As a CUSTOMER I want to GIVE FEEDBACK So that I CAN SHARE MY EXPERIENCE BV: 200 CP: 2 Acceptance Criteria: - Star rating (1–5) - Text box for comments - Submit button ✅ USER STORY NO: 17 Tasks: 2 Priority: High As a DELIVERY BOY I want to VIEW MY ORDERS So that I KNOW WHAT TO DELIVER BV: 300 CP: 2 Acceptance Criteria: - List of active orders - Show pickup and delivery addresses - Accept or decline option ✅ USER STORY NO: 18 Tasks: 2 Priority: Medium As a DELIVERY BOY I want to UPDATE ORDER STATUS So that CUSTOMER IS INFORMED BV: 300 CP: 2 Acceptance Criteria: - Buttons: Picked up, Delivered - Real-time update to customer ✅ USER STORY NO: 19 Tasks: 2 Priority: Low As a DELIVERY BOY I want to VIEW MY EARNINGS So that I CAN TRACK MY INCOME BV: 200 CP: 2 Acceptance Criteria: - Date-wise earnings list - Monthly summary ✅ USER STORY NO: 20 Tasks: 2 Priority: Medium As a DELIVERY BOY I want to RAISE AN ISSUE So that I CAN REPORT DELIVERY PROBLEMS BV: 200 CP: 2 Acceptance Criteria: - Text area to describe issue - Order ID reference - Submit button - Issue ID generated ✅ USER STORY NO: 21 Tasks: 2 Priority: High As a RESTAURANT I want to UPDATE MENU ITEMS So that CUSTOMERS SEE LATEST OPTIONS BV: 300 CP: 3 Acceptance Criteria: - Add/Edit/Delete options - Save changes - Display success notification ✅ USER STORY NO: 22 Tasks: 2 Priority: Medium As a RESTAURANT I want to VIEW CUSTOMER FEEDBACK So that I CAN IMPROVE SERVICE BV: 200 CP: 2 Acceptance Criteria: - List ratings and reviews - Filter by rating or date ✅ USER STORY NO: 23 Tasks: 2 Priority: Low As a RESTAURANT I want to VIEW MY REVENUE So that I CAN TRACK MY SALES BV: 200 CP: 2 Acceptance Criteria: - Total earnings display - Filter by date or order ID ✅ USER STORY NO: 24 Tasks: 2 Priority: Medium As an ADMIN I want to APPROVE DELIVERY BOY ACCOUNTS So that ONLY VERIFIED USERS CAN DELIVER BV: 300 CP: 2 Acceptance Criteria: - List of pending registrations - Approve/Reject button - Notification sent ✅ USER STORY NO: 25 Tasks: 2 Priority: Medium As an ADMIN I want to HANDLE ISSUES So that I CAN RESOLVE USER PROBLEMS BV: 300 CP: 3 Acceptance Criteria: - View all raised issues - Assign to support team - Change issue status ✅ USER STORY NO: 26 Tasks: 2 Priority: Medium As a REGIONAL ADMIN I want to MANAGE DELIVERY BOYS So that I CAN CONTROL OPERATIONS IN MY REGION BV: 300 CP: 3 Acceptance Criteria: - List all delivery boys by region - Approve, suspend, or remove options - View delivery history ✅ USER STORY NO: 27 Tasks: 2 Priority: Medium As a REGIONAL ADMIN I want to VIEW REGIONAL REVENUE So that I CAN MONITOR FINANCIALS BV: 300 CP: 2 Acceptance Criteria: - View daily, weekly, monthly revenue - Export data to Excel ✅ USER STORY NO: 28 Tasks: 2 Priority: High As a CUSTOMER I want to APPLY COUPONS So that I CAN AVAIL DISCOUNTS BV: 400 CP: 2 Acceptance Criteria: - Enter coupon code - Validate and apply - Show updated price ✅ USER STORY NO: 29 Tasks: 2 Priority: Medium As a CUSTOMER I want to SAVE MULTIPLE ADDRESSES So that I CAN CHOOSE QUICKLY DURING ORDER BV: 300 CP: 2 Acceptance Criteria: - Add/edit/delete addresses - Set default address - Show list during checkout ✅ USER STORY NO: 30 Tasks: 2 Priority: Medium As a CUSTOMER I want to VIEW RESTAURANT RATINGS So that I CAN CHOOSE THE BEST PLACE BV: 300 CP: 2 Acceptance Criteria: - Average rating visible in restaurant list - View detailed reviews ✅ USER STORY NO: 31 Tasks: 2 Priority: High As a RESTAURANT I want to VERIFY DELIVERY BOY IDENTITY So that I CAN ENSURE SAFE ORDER PICKUP BV: 300 CP: 2 Acceptance Criteria: - Show delivery boy photo and ID - Mark as verified before handing over food ✅ USER STORY NO: 32 Tasks: 2 Priority: Medium As a REGIONAL ADMIN I want to VIEW CUSTOMER FEEDBACK So that I CAN IMPROVE REGIONAL SERVICE BV: 200 CP: 2 Acceptance Criteria: - View ratings/comments - Filter by restaurant or delivery boy ✅ USER STORY NO: 33 Tasks: 2 Priority: High As an ADMIN I want to MANAGE REGIONAL ADMINS So that I CAN CONTROL OPERATIONS NATIONWIDE BV: 400 CP: 2 Acceptance Criteria: - Add/edit/remove regional admins - Assign specific regions ✅ USER STORY NO: 34 Tasks: 2 Priority: Medium As a BUSINESS OWNER I want to VIEW NATIONAL REPORTS So that I CAN MAKE STRATEGIC DECISIONS BV: 500 CP: 3 Acceptance Criteria: - Display KPIs like revenue, active users, etc. - Filter by date/region ✅ USER STORY NO: 35 Tasks: 2 Priority: Low As a DELIVERY BOY I want to SET MY AVAILABILITY So that I CAN TAKE ORDERS WHEN FREE BV: 100 CP: 2 Acceptance Criteria: - Toggle for online/offline - Orders only assigned when online ✅ USER STORY NO: 36 Tasks: 2 Priority: Medium As a CUSTOMER I want to RATE DELIVERY BOY So that I CAN APPRECIATE GOOD SERVICE BV: 200 CP: 2 Acceptance Criteria: - Rating option after delivery - Submit with optional comment ✅ USER STORY NO: 37 Tasks: 2 Priority: Medium As an ADMIN I want to VIEW SYSTEM-WIDE ISSUES So that I CAN MONITOR APPLICATION HEALTH BV: 300 CP: 3 Acceptance Criteria: - List all technical issues - Assign to tech team - Status: Open/In Progress/Resolved ✅ USER STORY NO: 38 Tasks: 2 Priority: High As a CUSTOMER I want to PAY VIA WALLET So that I CAN USE MY STORED BALANCE BV: 400 CP: 3 Acceptance Criteria: - Show wallet balance - Option to top-up - Deduct at checkout ✅ USER STORY NO: 39 Tasks: 2 Priority: Medium As a RESTAURANT I want to SET MAXIMUM DAILY ORDERS So that I CAN AVOID OVERLOAD BV: 200 CP: 2 Acceptance Criteria: - Enter limit in dashboard - Auto-disable order button when limit reached ✅ USER STORY NO: 40 Tasks: 2 Priority: Medium As a CUSTOMER I want to GET PUSH NOTIFICATIONS So that I AM UPDATED IN REAL TIME BV: 300 CP: 3 Acceptance Criteria: - Notifications for order updates, offers, feedback replies - Enable/disable option in settings ✅ All 40 user stories now completed with: - Acceptance Criteria - Business Value (BV) - Complexity Points (CP) Question 3– What is epic? Write 2 epics – 5 Marks Business Value and Complexity Points |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| An Epic is a large user story that cannot be completed in a single sprint and needs to be broken down into smaller user stories. It represents a significant business requirement or a high-level functionality that delivers substantial value but is too complex or broad to develop all at once. ✳️ Epic 1: User Registration and Authentication Description: Enable all types of users (Customers, Restaurants, Delivery Boys, Admins) to register, login, and manage their profiles securely. - Business Value (BV): 1000 - Complexity Points (CP): 13 ✅ Includes User Stories like: - US01: As a Delivery Boy, I want to register - US02: As a Restaurant Owner, I want to register - US03: As a Customer, I want to login/logout - US04: As an Admin, I want to approve user registrations - US05: As any user, I want to reset my password ✳️ Epic 2: Order Management and Tracking Description: Enable end-to-end order processing from placing an order to delivery and feedback. - Business Value (BV): 1500 - Complexity Points (CP): 20 ✅ Includes User Stories like: - US04: As a Customer, I want to select a payment mode - US13: As a Customer, I want to track my order - US14: As a Customer, I want to cancel my order - US15: As a Customer, I want to view order history - US17: As a Delivery Boy, I want to view and deliver orders - US18: As a Delivery Boy, I want to update order status |  |  |  |  |  |  |
| Question 4 –What is the difference between BV and CP – 2 Marks Product Backlog Your User stories will go into Product Back log Difference between Business Value (BV) and Complexity Points (CP) Aspect; Business Value (BV); Complexity Points (CP). Definition; Measures how valuable a user story is to the business; Measures how difficult it is to implement a user story. Estimated By; Stakeholders / Product Owner; Scrum Team / Developers. Purpose; Helps in prioritizing features that bring higher business impact; Helps in planning effort and sprint capacity. Units; Rs 1000, Rs 500, Rs 100, Rs 50 (Scrum Currency); Story Points (1, 2, 3, 5, 8, 13, 20, etc.). Focus; Value delivered to the end-user or business; Technical effort, time, and complexity of development. Product Backlog A Product Backlog is a prioritized list of all features, enhancements, bug fixes, and tasks required in a product. - It contains User Stories, Epics, Bugs, Technical Tasks - Maintained by the Product Owner - Continuously refined and prioritized during backlog grooming sessions - Your 40 User Stories will be entered into the Product Backlog in order of priority. |  |  |  |  |  |  |
| Question 5 –Explain about Sprint– 5 Marks Sprint Understanding What is sprint Duration: 2 Weeks - Your sprint Value Scrum is a subunit of Sprint. What is scrum Duration: 1 day – Your scrum Value ? PBI: Product Backlog Item Task: Unit of Work done by 1 Developer in 1 Scrum WIP: Work In Progress Sprint Backlog PBI Tasks WIP Done What is a Sprint? A Sprint is a time-boxed iteration in Scrum where a set of Product Backlog Items (PBIs) are selected, developed, and made ready for review. It helps deliver small, usable increments of the product frequently. - Sprint Duration: 2 weeks (your selected value) - Each Sprint starts with a Sprint Planning Meeting and ends with a Sprint Review and Sprint Retrospective. - Sprint Goals guide the work and remain fixed during the sprint. What is Scrum in a Sprint? - A Scrum (also known as Daily Scrum or Stand-up) is a 15-minute daily meeting. - Scrum Duration: 1 Day (Occurs daily during the sprint) - Purpose: - Inspect progress - Identify obstacles - Plan the next 24 hours During the Scrum, each team member answers: - What did I do yesterday? - What will I do today? - Are there any blockers? Sprint Backlog Structure The Sprint Backlog is a subset of the Product Backlog selected for development in a particular Sprint, broken down into Tasks. PBI (Product Backlog Item); Tasks; WIP (Work In Progress); Done. User Story: Login Feature; UI Design, Backend API, Validation; UI and API development; -. User Story: Order Placement; Cart Logic, Payment Gateway; Payment Gateway integration; Cart logic completed. User Story: Track Order; GPS Integration, UI Tracking Screen; GPS setup ongoing; -. - PBI: A feature or requirement selected from the Product Backlog - Task: A unit of work that one developer can complete in a single Scrum (1 day) - WIP: Tasks currently being worked on - Done: Tasks that are fully completed and tested Summary Points: - Sprint: 2-week time-box for completing a set of tasks - Scrum: Daily 15-min meeting within the sprint - PBI: Feature or user story from the product backlog - Task: Smallest unit of work within a PBI - WIP: Tasks currently in progress - Sprint Backlog: List of PBIs and tasks for the current sprint Question 6 – Explain Product backlog and sprint back log– 5 Marks Sprint Planning Meeting: All 8 Scrum Developers will gather before the sprint starts and understand how many user stories, they can develop in 1 sprint (2 weeks), and move them from the product Backlog to the sprint Backlog. They take inputs from Sprint Retrospective meeting. Scrum Meeting – Daily Stand-up Meeting End of every Scrum, Scrum Developers will participate in Scrum meeting. Here they must answer 3 Questions. a. What task did you work in this scrum? b. What task will you work on next scrum? c. Any Challenges/impediments? When you will complete the user story? Product Backlog The Product Backlog is a master list of all the work that needs to be done on the project. It includes: - User Stories - Bugs - Enhancements - Technical Tasks Key Points: - Maintained by the Product Owner - Continuously refined and reprioritized - Each item is assigned Business Value (BV) and Complexity Points (CP) - Represents everything the product may need in the future - It is a live document—can be updated anytime based on feedback or new requirements Sprint Backlog The Sprint Backlog is a subset of the Product Backlog selected during the Sprint Planning Meeting for completion during a specific sprint (2 weeks). Key Points: - Created by the Scrum Team in the Sprint Planning Meeting - Only contains work the team commits to complete in the sprint - Includes User Stories + Tasks + Estimates - Tasks are assigned to developers and tracked through stages: To Do → WIP (Work In Progress) → Done Sprint Planning Meeting - Held before the start of every sprint - Attended by all 8 Scrum Developers, Product Owner, and Scrum Master - Objective: - Select how many user stories can be developed in 2 weeks - Move those stories from the Product Backlog to the Sprint Backlog - Estimate effort using Story Points - Takes inputs from previous Sprint Retrospective Daily Scrum Meeting (Stand-up) Occurs every day during the sprint. Duration: 15 minutes Attended by Scrum Developers and Scrum Master 🟢 Each Developer answers: - What task did you work on in this scrum? - What task will you work on in the next scrum? - Any challenges or impediments? When will you complete the user story? This helps the team: - Stay aligned - Track progress - Identify blockers early Example Structure: Product Backlog; Sprint Backlog (Selected Items). User Story: Customer Registration; ✅ Selected. User Story: Order Tracking; ✅ Selected. User Story: Delivery Boy Feedback; ❌ Not selected (for next sprint). Bug: Fix payment gateway timeout; ✅ Selected. Q7. What is impediments log? write 2 impediments – 5 Marks Impediments Log: All challenges faced by the team will be logged in this impediments log Impediments Log – Definition An Impediments Log is a formal list or document where the Scrum Team records all challenges, blockers, or obstacles they face during the Sprint that could delay or prevent the progress of work. This log is: - Maintained and updated by the Scrum Master - Reviewed during the Daily Scrum, Sprint Retrospective, and Sprint Review - Used to resolve issues quickly and improve future sprint planning Examples – 2 Impediments Impediment ID; Description; Impact; Owner; Resolution Status. IMP-01; Payment Gateway API is down due to 3rd party maintenance; Blocking development of Payment module; Scrum Master; In Progress. IMP-02; Delivery Boy GPS module facing compatibility issue on iOS devices; Slowing down order tracking feature testing; Developer – Varun; Under Investigation. Post-Sprint Activities Related to Impediments - Product Increment Delivery - Items from the Done state in Sprint Backlog form a Product Increment, delivered to the client. - Sprint Retrospective Meeting - Only Scrum Developers attend. - Discuss challenges faced, document lessons learned - These insights are used in the next Sprint Planning Meeting to adjust commitments and select appropriate User Stories. - Sprint Review Meeting - All stakeholders participate: Scrum Developers, Product Owner, Scrum Master, Client, 3rd Party Reviewers. - Topics discussed: - Velocity: How many CPs (Story Points) completed - Sprint Burn Down Chart: Visual of remaining work over time - Product Insights: Feedback and suggestions for product improvement Sprint 1 Start Time: 11:00 AM End Time: 13:00 Duration: 2 hrs Sprint Planning Meeting Participants Discussion Points: Discussed on the Sprint Velocity and the BV with the user stories. Discussed with the associates on resources provided to them and also communicated to the team on sprint duration as well as expectations from the client. User Stories Selected: 10 (MVP) Sprint Backlog PBI Tasks WIP Done 10 20 0 10 Prepare Tasks from PBI How many Scrums, we will have in this sprint? Allocate Tasks to Developers Sprint Details: - Sprint Duration: 2 weeks (10 working days) - Sprint Timeframe: 11:00 AM – 1:00 PM (2 hours per day) - Sprint Planning Meeting: - Start Time: 11:00 AM - End Time: 1:00 PM - Duration: 2 hours - Participants: All Scrum Developers, Scrum Master, Product Owner - Sprint Focus: - Discussed Sprint Velocity & BV - Communicated client expectations - Agreed on 10 User Stories (MVP) Sprint Backlog Summary Item; Count. PBI (User Stories); 10. Total Tasks; 20. WIP; 0. Done; 10. How Many Scrums in Sprint 1? - Sprint Duration: 2 Weeks = 10 working days - Each day has one Scrum (Daily Stand-Up) ✅ So, there will be 10 Scrums in this sprint 👩‍💻 Task Allocation to Scrum Developers Developer Name; No. of Tasks; Assigned User Stories (Examples). Linesh Vegad; 3; User Story 1 (Delivery Boy Registration), User Story 7. Yogender; 2; User Story 2 (Restaurant View Orders), User Story 9. Gowri; 3; User Story 3 (Add Address), User Story 6. A. Lakshmikala; 3; User Story 4 (Select Payment), User Story 10. Madhur; 2; User Story 5 (Admin View Restaurants), User Story 8. Varun; 2; User Story 6 (View Price), User Story 7. Rakesh; 2; User Story 9 (Set Time Slot), User Story 3 (Validation). Rajesh; 3; User Story 1, User Story 10 (Integration & Notification). Note: - Each task is estimated to be 1 Scrum worth of work (1 day) - All developers are assumed to complete around 2–3 tasks per sprint, depending on complexity |  |  |  |  |  |  |
| Scrum Meeting End of every Scrum, Scrum Developers will participate in Scrum meeting. Here they must answer 3 Questions. a. What task did you work in this scrum? b. What task will you work on next scrum? c. Any Challenges/impediments? When you will complete the user story? |  |  |  |  |  |  |
| Scrum 1 - Start Time: 11:00 AM - End Time: 11:15 AM - Duration: 15 minutes - Participants: All 8 Scrum Developers Developer Responses: Developer; a. Worked on (Previous Scrum); b. Next Task (Upcoming Scrum); c. Challenges/Impediments. Linesh Vegad; Designed UI for Delivery Boy Registration; Backend logic for registration; No challenges. Yogender; Created order viewing table for Restaurant; Add filters for sorting; No challenges. Gowri; Implemented address validation for Customer; Create map API integration; Delay in Google Maps API response. A. Lakshmikala; Payment mode selection UI; Payment gateway integration; Gateway testing credentials pending. Madhur; Admin view restaurant list screen; Implement approval/reject functionality; Awaiting restaurant schema finalization. Varun; Added price field to menu items; Display price on UI; No challenges. Rakesh; Contact number view in tracking screen; Load image and name; Image not loading on all devices. Rajesh; Notification system setup for registration; Add confirmation popup for registration; Popup library integration error. ✅ Scrum 2 - Start Time: 11:00 AM - End Time: 11:15 AM - Duration: 15 minutes Developer Responses: Developer; a. Worked on; b. Next Task; c. Challenges/Impediments. Linesh Vegad; Completed backend registration for delivery boy; Add form validations; No challenges. Yogender; Added sorting in view orders; Add pagination; Data overflow in large orders list. Gowri; Integrated map API; Add radius check (5km rule); Radius logic inaccurate. A. Lakshmikala; Integrated Razorpay gateway; Add failure response handling; Razorpay test server delay. Madhur; Implemented approval/reject; Add notification on status change; No challenges. Varun; Displayed price on menu UI; Unit testing for pricing module; No challenges. Rakesh; Displayed image and name of delivery boy; Add call button; Call link not triggering in iOS. Rajesh; Implemented registration popup; Start login validation; No challenges. ✅ Scrum 3 - Start Time: 11:00 AM - End Time: 11:15 AM - Duration: 15 minutes Developer Responses: Developer; a. Worked on; b. Next Task; c. Challenges/Impediments. Linesh Vegad; Added validations; Unit testing registration; Form validation failing on edge cases. Yogender; Pagination added to orders view; Start UI testing; Pagination not working on Safari. Gowri; Radius logic adjusted; Testing edge cases; API returning null for some coordinates. A. Lakshmikala; Failure handling for payments; Testing different payment modes; UPI response failure. Madhur; Notifications added; Work on refunds issue form; No challenges. Varun; Unit testing complete; Assist UI testing; No challenges. Rakesh; Call button added; Create feedback UI; Button not aligned in mobile version. Rajesh; Login validation setup; Add session timeout logic; Session not resetting correctly. ✅ Scrum 4 - Start Time: 11:00 AM - End Time: 11:15 AM - Duration: 15 minutes Developer Responses: Developer; a. Worked on; b. Next Task; c. Challenges/Impediments. Linesh Vegad; Registration tested; Move task to done; No challenges. Yogender; UI testing done; Move to done; Minor UI glitch on Firefox. Gowri; Edge case testing finished; Push code to repo; Repo merge conflict. A. Lakshmikala; All payment modes tested; Mark story complete; UPI payment still flaky. Madhur; Refund issue form designed; Submit and validate; Field alignment issue. Varun; Assisted with refund UI; Mark story complete; No challenges. Rakesh; Feedback UI created; Connect with DB; DB schema not updated. Rajesh; Session timeout logic added; Test across devices; Inconsistent timeout handling. |  |  |  |  |  |  |
| Sprint 1 – Closing Activities From the Done state of the sprint Backlog, we will product Increment and we can deliver it to the client What is the Product Increment we made now? Sprint Retrospective meeting: Only the Scrum Developers will participate and will discuss about Challenges faced and come up with lessons learnt. We can use these lessons learnt in Sprint Planning Meeting to select user stories for the next sprint. Write here Sprint Review meeting: All Stakeholders like Scrum Developers, Product owner, Scrum master, Client, 3 rd party reviewers will participate. What they discuss is We as team, Write here |  |  |  |  |  |  |
| Sprint 1 – Closing Activities Summary 🚀 Product Increment (Deliverable to Client) From the “Done” state of the Sprint 1 Backlog, we successfully delivered a Minimum Viable Product (MVP) which includes: - Delivery Boy Registration Module - Restaurant Order View - Customer Address Management - Payment Mode Selection UI - Admin: Restaurant Viewing and Approval - Price Display for Menu Items - Delivery Boy Contact Display in Tracking - Restaurant: Time Slot Management - Customer Refund Chat to Regional Admin - Basic Feedback & Notification Framework This product increment is a working, tested, and usable version of Scrum Foods that can be reviewed by the client and iterated upon in future sprints. Sprint Retrospective Meeting (Only Scrum Developers) Meeting Purpose: Reflect on Sprint 1 and extract lessons learned. Challenges Faced: - API delay and latency in location-based radius validation. - Payment gateway testing environments were unstable. - Cross-browser UI issues (especially on Safari & Firefox). - Minor version control merge conflicts during code integration. - Incomplete database schema from restaurant side slowed integration. Lessons Learnt: - Start API testing early in the sprint. - Confirm all external integrations and credentials before sprint start. - Conduct mid-sprint merge checks to avoid large final conflicts. - Assign one developer for UI testing across multiple devices/browsers. - Better communication with restaurant team to get finalized data upfront. These lessons will directly influence planning and story selection for Sprint 2. Sprint Review Meeting (All Stakeholders) Participants: Scrum Developers, Product Owner, Scrum Master, Client (COEPD), 3rd Party QA Reviewers Discussion Points: - Reviewed each user story functionality via demo. - Discussed feedback from the client on look and feel, usability, and speed. - Velocity Achieved: 20 CP (10 User Stories) - Sprint Burndown Chart: Showed consistent progress with no major deviations. - Client Feedback: - Impressed with UI simplicity and real-time features like tracking. - Suggested enhancements in payment failure messaging and feedback UI. - Team showcased collaborative efforts and quick adaptation to blockers. Outcome: - Stakeholders agreed to move forward with next set of functionalities. - Green signal to integrate restaurants onboarding and more tracking features in Sprint 2. Question 8 – Explain Velocity of the Team – 1 Marks Velocity – How many CP is covered in this sprint Velocity is a key metric in Agile that represents the total number of Complexity Points (CP) completed by the Scrum team during a sprint. Velocity of the Team in Sprint 1: - 📋 Total User Stories Completed: 10 - 🎯 Total Complexity Points (CP) Completed: 20 CP 🔹 Velocity = 20 CP Importance of Velocity: - Helps in estimating future sprints and planning how many user stories can be taken up. - Indicates team’s delivery capacity and predictability. - Aids the Product Owner in release planning. Question 9 – Draw Sprint Burn Charts n Product Burn Down Charts– 3 Marks - Ideal Burn Down (dotted line): Represents how complexity points should decrease daily for a perfect sprint. - Actual Burn Down (solid line): Shows the actual progress of the team across 10 days. This chart helps track whether the team is on pace to complete all planned work within the sprint. |  |  |  |  |  |  |
| Question 10 – Explain about Product Grooming – 2 Marks |  |  |  |  |  |  |
| Product insights for improvement Used for product grooming What is Product Grooming (Backlog Refinement)? Product Grooming (also known as Backlog Refinement) is the ongoing process in Agile where the Product Owner and Scrum Team review, refine, and prioritize the items in the Product Backlog to ensure they are clear, detailed, and ready for future sprints. Purpose of Product Grooming: - Break down large epics into smaller, manageable user stories. - Clarify acceptance criteria for each story. - Re-prioritize based on stakeholder feedback or market needs. - Estimate Complexity Points (CP) with the development team. - Remove or update outdated or low-value backlog items. Product Insights for Improvement: During Sprint Reviews and Retrospectives, stakeholders and the team gather insights such as: - Customer feedback - Delivery performance - Feature usage - Technical issues or challenges These insights are then used during grooming to: - Add new features or improvements - Refactor or remove low-value stories - Improve user experience or performance Example in Scrum Foods: After Sprint 1, feedback on payment flow and tracking UI can be used during grooming to: - Add new stories for payment failure handling - Improve UI for delivery boy tracking Question 11 – Explain the roles of Scrum Master and Product Owner – 3 Marks Team Experiences with Sprint 1 Scrum Master: Product Owner You acted as Product Owner. Roles of Scrum Master and Product Owner 👨‍🏫 Scrum Master – Role & Responsibilities The Scrum Master is the servant-leader and facilitator for the Scrum Team. The main goal is to enable team success by ensuring Scrum practices are followed. Key Responsibilities: - Facilitates Scrum ceremonies (Daily Scrum, Sprint Review, Retrospective). - Removes impediments blocking the team’s progress. - Shields the team from external interruptions. - Coaches the team on Agile best practices. - Works closely with the Product Owner to ensure a healthy backlog. In Sprint 1: Scrum Master (Satya Rathnakar) facilitated daily stand-ups, coordinated with developers during blockers (like integration delays), and ensured smooth Sprint Planning and Review meetings. 🧑‍💼 Product Owner – Role & Responsibilities The Product Owner (PO) is responsible for maximizing the value of the product by managing the Product Backlog. 🔹 Key Responsibilities: - Defines and prioritizes user stories in the Product Backlog. - Clarifies requirements and acceptance criteria. - Accepts or rejects completed work. - Acts as a bridge between stakeholders and the Scrum Team. - Ensures the product meets customer expectations. 📌 As the Product Owner in Sprint 1, you: - Identified 10 MVP user stories. - Defined Business Value (BV) and Acceptance Criteria. - Participated in Sprint Planning and Sprint Review. - Accepted completed stories and captured client feedback for grooming. Team Experience in Sprint 1: - Clear communication between PO and developers improved clarity on requirements. - Scrum Master’s role in resolving API and integration blockers kept the team on schedule. - Developers appreciated consistent backlog refinement and client involvement. Conclusion: Scrum Master and Product Owner worked in collaboration to ensure focus, clarity, and delivery. Their defined roles helped the team achieve the Sprint 1 goal and deliver a valuable product increment. Question 12 – Explain all Meetings Conducted in Scrum Project – 8 Marks |  |  |  |  |  |  |
| Scrum methodology defines five key meetings (ceremonies) to ensure smooth, transparent, and collaborative project execution. These meetings are designed to maintain progress, encourage feedback, and adapt quickly. 1. Sprint Planning Meeting When: At the beginning of each Sprint Who: Product Owner, Scrum Master, Scrum Developers Purpose: - Define Sprint Goal - Select Product Backlog Items (PBIs) for the Sprint - Break PBIs into smaller tasks - Estimate effort (Complexity Points) - Plan how to deliver the selected work Example from Scrum Foods: In Sprint 1, 10 user stories were selected as MVP with a total of 20 CP. Tasks were assigned, and sprint expectations were set. 2. Daily Scrum (Daily Stand-up) When: Every working day during the Sprint (usually 15 minutes) Who: Scrum Developers (Product Owner and Scrum Master may attend but don’t interfere) Purpose: Each developer answers: - What did I do yesterday? - What will I do today? - Are there any impediments? Example from Scrum Foods: Developers discussed progress on registration, tracking, and UI tasks. One developer flagged a payment API issue as an impediment. 3. Sprint Review Meeting When: At the end of the Sprint Who: Scrum Team, Product Owner, Client/Stakeholders Purpose: - Demonstrate working product increment - Gather feedback from stakeholders - Discuss product improvements - Update the Product Backlog accordingly Example from Scrum Foods: Stakeholders appreciated the MVP but requested improved error messages and additional UI refinements for tracking. 4. Sprint Retrospective Meeting When: After the Sprint Review, before the next Sprint Who: Scrum Developers and Scrum Master (Product Owner may attend) Purpose: - Reflect on the Sprint - Identify what went well, what didn’t, and what to improve - Define actionable improvements for future sprints Example from Scrum Foods: Developers noted that version control issues delayed work. They decided to integrate code more frequently and improve API documentation. 5. Product Backlog Grooming (Refinement) When: Ongoing activity throughout the sprint Who: Product Owner, Scrum Master, Developers Purpose: - Refine and re-prioritize backlog items - Break down epics into stories - Add acceptance criteria - Estimate effort - Remove outdated or irrelevant items Example from Scrum Foods: Based on feedback, the PO added new stories for improved delivery feedback and loyalty rewards. CP was re-estimated for selected stories. Summary Table Meeting; Purpose; Participants. Sprint Planning; Plan Sprint Goal and select PBIs; PO, SM, Developers. Daily Scrum; Track daily progress and highlight blockers; Developers (PO/SM optional). Sprint Review; Demonstrate work done and collect feedback; PO, SM, Developers, Stakeholders. Sprint Retrospective; Reflect and improve team processes; SM, Developers. Product Backlog Grooming; Update and clarify product backlog; PO, SM, Developers. |  |  |  |  |  |  |
| Question 13 – Explain Sprint Size and Scrum Size– 2 Marks Sprint Size - Definition: The Sprint Size refers to the duration of a Sprint — the fixed timebox in which a specific amount of work (user stories) is planned, developed, tested, and delivered. - In Scrum Foods Project: - Sprint Duration: 2 weeks - Team completes a set of Product Backlog Items (PBIs) during this time. - At the end, a Product Increment is delivered. - Purpose: Helps teams work in short, focused cycles with regular feedback and continuous improvement. Scrum Size - Definition: The Scrum Size refers to the duration of each Scrum meeting cycle or unit of work. - Scrum Duration: Typically, 1 day - A Scrum team completes one or more tasks from the Sprint Backlog in a single Scrum. - Developers give daily updates in the Daily Scrum meeting. - Example from Scrum Foods: - In Sprint 1 (2 weeks), the team had 10 working days, which means 10 Scrums. - Tasks were distributed among developers based on daily Scrum planning. Summary: Term; Duration; Purpose. Sprint; 2 weeks; Deliver a working Product Increment. Scrum; 1 day; Track daily progress, adjust work plans. Both Sprint and Scrum work together to ensure short, productive cycles with clear goals and measurable outcomes. |  |  |  |  |  |  |
| Question 14 – Explain DOR and DOD – 2 Marks DOR – Definition of Ready - Definition: Definition of Ready (DoR) refers to the set of criteria that a User Story or Product Backlog Item (PBI) must meet before it can be taken into a Sprint. - Purpose: Ensures that the team fully understands what is to be built and has everything necessary to start the work. - Example of DoR in Scrum Foods: - User story has a clear title and description - Acceptance criteria are defined - Business Value (BV) and Complexity Points (CP) are assigned - All dependencies are identified - UI mockups or API details are ready if needed DOD – Definition of Done - Definition: Definition of Done (DoD) is a clear checklist of conditions that must be met for a User Story or PBI to be considered completed and potentially shippable. - Purpose: Ensures the product increment meets the quality standards and is fully functional. - Example of DoD in Scrum Foods: - Code is written and unit tested - UI is implemented and tested - Integration tested - Passed QA validation - Acceptance criteria met - Product Owner has reviewed and accepted the story DOR vs DOD – At a Glance Aspect; DOR (Ready); DOD (Done). When; Before work starts; After work is completed. Purpose; Ensure clarity before development; Ensure quality before marking as complete. Used by; Product Owner & Scrum Team; Scrum Team & Product Owner. A clear DoR and DoD help Scrum teams reduce rework, maintain consistency, and deliver high-quality increments every Sprint. Question 15 – Explain Prioritization Techniques and MVP – 3 Marks |  |  |  |  |  |  |
| Prioritization Techniques in Agile Prioritization ensures that the most valuable and urgent features are developed first. Several techniques help the Product Owner and stakeholders decide which items should go to the top of the Product Backlog. 1. MoSCoW Method - M – Must Have (Essential features) - S – Should Have (Important but not critical) - C – Could Have (Nice to have if time allows) - W – Won’t Have (Not needed now) 📌 Example in Scrum Foods: “User registration” is a Must Have, while “promo codes” might be Could Have in early sprints. 2. Business Value vs. Complexity Matrix - Items with High Business Value and Low Complexity are done first. - Helps balance impact and effort. 📌 Example in Scrum Foods: “Customer can track order in real time” – High BV, Low CP → High priority. 3. WSJF (Weighted Shortest Job First) - Formula: WSJF = Business Value / Job Size - Helps deliver maximum value quickly. 4. Kano Model - Classifies features as: - Basic Needs (must-haves) - Performance Needs (more = better) - Delighters (unexpected but pleasing) MVP – Minimum Viable Product Definition: The Minimum Viable Product (MVP) is the smallest version of the product that delivers enough value to early users and provides feedback for future development. Characteristics: - Contains only the core features - Allows quick launch - Validates product-market fit - Supports iterative improvements Example in Scrum Foods: MVP includes: - User registration - Restaurant listing - Menu browsing - Placing orders - Payments - Order tracking Other features like chat support, loyalty rewards, or multi-language support can come in later sprints. Summary: Concept; Purpose; Example – Scrum Foods. Prioritization; Decide what features to build first; Real-time tracking prioritized over promo codes. MVP; Launch with basic usable version; Order placement + Payment + Tracking. Both Prioritization and MVP help Agile teams focus on value, deliver faster, and adapt to feedback. Question 16 – Difference between Business Analyst n Product Owner – 3 Marks |  |  |  |  |  |  |
| Aspect; Business Analyst (BA); Product Owner (PO). Role Focus; Focuses on gathering requirements and understanding business needs; Focuses on maximizing product value and managing backlog. Stakeholder Interaction; Acts as a bridge between stakeholders and technical team; Acts as a bridge between customer/business and development team. Decision-Making Power; Supports decision-making, but usually doesn't make final calls; Owns product decisions, has authority over backlog priorities. Ownership; Does not own the product; Owns the product, accountable for its success. Key Responsibilities; - Gather requirements - Analyze business processes - Prepare BRD/FSD; - Prioritize backlog - Define user stories - Accept/reject work. Documentation; Writes detailed documentation (use cases, process flows, etc.); Writes user stories, defines acceptance criteria. In Agile; May work under the PO or assist in story refinement; Works as a core Scrum role; one of the three Scrum roles. Summary: - Business Analyst: Helps analyze, document, and clarify what the business needs. - Product Owner: Ensures the right product is being built by managing priorities and maximizing value. In some Agile teams, especially in startups or small teams, one person may play both roles, but in larger teams, they are distinct roles with different responsibilities. |  |  |  |  |  |  |
| Question 17 – Prepare a sample Resume of 3yrs exp Product Owner – 3 Marks |  |  |  |  |  |  |
| Name: Sneha Aarey Email: Snehaaarey564@gmail.com Phone: +91-9000000611 Location: Hyderabad, India LinkedIn: linkedin.com/in/Sneha-aarey Total Experience: 3 Years Professional Summary Certified and result-oriented Product Owner with 3 years of experience in Agile and Scrum environments, focusing on building high-impact digital products. Proven expertise in backlog management, user story creation, stakeholder collaboration, and delivering Minimum Viable Products (MVP) with a customer-first mindset. Strong domain knowledge in Food Delivery, E-commerce, and Mobile Applications. Professional Experience 🔹 Product Owner – COEPD IT Solutions Jan 2022 – Present ¦ Hyderabad Project: Scrum Foods (Online Food Delivery App) - Defined and prioritized Product Backlog Items (PBIs) and worked with Scrum team to deliver 10+ successful sprints. - Created 40+ detailed user stories with Business Value (BV) and Complexity Points (CP). - Conducted Sprint Planning, Review, Retrospective, and Daily Scrum meetings. - Collaborated with stakeholders: Business Owners, Delivery Team, Customers, and Restaurants. - Developed MVP and coordinated multiple releases on mobile, tablet, and desktop platforms. - Managed impediment logs, tracked velocity, and used burndown charts for reporting. Tools Used: Jira, Confluence, Miro, MS Excel, Figma Methodology: Agile Scrum Team Size: 8 Scrum Developers + Scrum Master Education B.Tech in Computer Science Jawaharlal Nehru Technological University, Hyderabad Graduated: 2021 Certifications - Certified Scrum Product Owner (CSPO) – Scrum Alliance - Agile Business Analyst Certificate – COEPD Skills - Agile & Scrum Methodologies - Product Backlog Management - User Stories & Acceptance Criteria - Sprint Planning & Review - Stakeholder Communication - MVP Definition - Wireframing & Requirement Gathering - Jira, Confluence, Trello, MS Office - Domain: Food Delivery, E-commerce, Web/Mobile Apps Languages - English – Fluent - Hindi – Fluent - Telugu – Native |  |  |  |  |  |  |

🧾 Summary

- Total Stories: 40

- Story Roles: Customer, Delivery Boy, Restaurant, Admin, Regional Admin, Business Owner

- BV Range: ₹50 – ₹500

- CP Range: 1 – 4

- Types: Functional (ordering, tracking, feedback), Operational (approvals, reporting), Security (login/logout)