## Slide 1
Agile Project – Audit Data Request Automation (Transition) Work Force Management
Suman Samaiya | Business Analyst
Date: 10/22/2025

## Slide 2: Project Overview
Goal: Centralized platform to manage audit requests
Problem: Manual emails and Excel tracking, lack of visibility
Solution: Web app with request tracking, dashboards, notifications

## Slide 3: Purpose Statement (Goals)
To create a centralized Audit Support Application that helps auditors and business teams manage,
track, and complete audit data requests efficiently — replacing the manual, email-based process.
Eliminate Email Chaos — Move from scattered email chains to a centralized request platform.
Improve Transparency — Track real-time progress of each audit request.
Enhance Accountability — Assign owners, set deadlines, and log audit evidence.
Enable Reporting — Provide dashboards on request status, turnaround time, and SLA breaches.
Ensure Compliance & Security — Control access and maintain data integrity.

## Slide 4: Business Objectives
The current process of handling audit data requests for 401k pension retirement plans is email-based, causing inefficiencies, delays, and lack of transparency.
The project aims to automate and streamline the process using WFM as a centralized platform to track, manage, and fulfill auditor data requests efficiently.

## Slide 5: Success Criteria
Reduced audit request turnaround by 45%.
Improved tracking and accountability.
Enhanced transparency with live dashboards.
Ensured compliance documentation within SLAs.

## Slide 6: Agile Team
Product Owner: Vision & backlog prioritization
Scrum Master: Facilitate Scrum ceremonies
Business Analyst: Suman – Requirements & user stories
Developers: – Build modules
QA: – Test & validate
UX/UI Designer: – UI & wireframes

## Slide 7: BA Responsibilities in Sprint 0
Day | Activity | Output
Day 1–2 | Stakeholder Interviews | Meeting notes & key requirements
Day 3 | Define “As-Is” & “To-Be” process | Workflow diagrams
Day 4 | Draft Epics and Backlog | Product backlog document
Day 5 | Backlog Refinement with Team | Refined user stories with points & acceptance criteria

## Slide 8: Requirement Gathering – Approach and Techniques
As a Business Analyst, the requirements were gathered using multiple elicitation techniques:
1. Stakeholder Interviews: Conducted with auditors, audit support team, and compliance officers.
2. Workshops and JAD Sessions: Collaborated to understand workflow pain points and desired automation.
3. Observation: Monitored live audit request handling to capture bottlenecks.
4. Document Analysis: Reviewed email logs, historical data request forms, and SLA reports.
5. Prototyping: Used process flows to validate initial user stories.

## Slide 9: Current (As-Is) Process
Auditor sends an email to request data from the business team.
Business users acknowledge (or sometimes miss) the request.
Data is collected manually and shared via attachments.
No centralized tracking, reminders, or dashboards.
Auditors often chase updates through multiple threads.
Pain Points:
Missing or delayed responses
No visibility on progress or deadlines
Duplication of requests
Manual tracking using Excel
Poor accountability

## Slide 10: Proposed (To-Be) Process
Auditor logs into the Audit Support Application.
Creates a new data request with fields like: Request Type, Description, Due Date, Business Owner.
Business users receive a notification and upload the requested data.
The system tracks progress, deadlines, and completion status.
Managers view dashboards summarizing SLA performance and bottlenecks.

## Slide 11: Product Backlog
Epic | Sample User Stories
Request Management | Create Request, View Requests, Edit/Close Request
Data Upload & Response | Upload Data, Attach Supporting Documents
Dashboard & Reports | View Request Summary, Download Report
Notifications & Alerts | Email Notifications, Due Date Reminders
User Roles & Security | Role-Based Access, Password Reset

## Slide 12: Sprint Backlog Request management
Epic | User Story | Priority | Story Points | Business Value | Acceptance Criteria (Summary)
E1 | As an auditor, I want to create a new audit data request, so I can request information from business users. | High | 5 | 10 | Form should capture request type, due date, and assign business owner.
E2 | As an auditor, I want to view all my requests so that I can monitor progress. | High | 8 | 9 | My Requests” page lists all open and completed requests.
E3 | Edit / Close Request | High | 8 | 9 | As an auditor, I want to edit or close a request so that I can manage them easily.

## Slide 13: Epics
Epic ID | Epic Name | Description
E1 | Create Request | Auditors can raise and submit new audit data requests.
E2 | View Request | As an auditor, I want to view all my requests so that I can monitor progress.
E3 | Edit / Close Request | As an auditor, I want to edit or close a request so that I can manage them easily.

## Slide 14: User Story
US1: As an auditor, I want to create a new request
Acceptance Criteria:
1. Request form captures mandatory fields: Title, Department, Due Date
2. Unique Request ID auto-generated
3. Request gets assigned to correct support queue
4. Error messages for missing fields
5. Confirmation notification sent automatically

## Slide 15: Sprint 1 Overview
Duration: 2 weeks
Goal: Enable auditors to create, view, and close requests
User Stories: US1 – Create Request, US2 – View Requests, US3 – Edit/Close Request
BA Contribution: Defined stories, ACs, supported Dev & QA

## Slide 16: Sprint 1 Burndown Chart
• User Story 1: Auditors can raise and submit new audit data requests..
• User Story 2: As an auditor, I want to view all my requests so that I can monitor progress.
• User Story 3: As an auditor, I want to edit or close requests so that I can manage them easily.
Sprint Duration: 2 Weeks
Deliverables: Enable auditors to create, view, and close requests.

## Slide 17: Sprint Review & Retrospective
What Went Well: Clear user stories, smooth collaboration, timely delivery
What Can Improve: Deliver UI mockups earlier, start QA mid-sprint,
Action Items:
  BA to prepare ACs before sprint start
  UX to deliver designs before Day 1
  QA to start testing by Day 6