12. Gantt Chart

| Phase / Task | Duration (Weeks) | Start Week | End Week | Primary Resources Involved |
| --- | --- | --- | --- | --- |
| RG - Requirement Gathering | 2 | 30-Jun-25 | 11-Jul-25 | BA, PM, Stakeholders |
| RA - Requirement Analysis | 2 | 14-Jul-25 | 25-Jul-25 | BA, PM |
| Design (High-Level + Low-Level) | 3 | 28-Jul-25 | 15-Aug-25 | BA, Java Dev, DB Admin, NW Admin |
| D1 - Development Phase 1 | 2 | 18-Aug-25 | 29-Aug-25 | Java Dev, DB Admin |
| T1 - Testing Phase 1 | 1 | 01-Sep-25 | 05-Sep-25 | Testers |
| D2 - Development Phase 2 | 2 | 08-Sep-25 | 19-Sep-25 | Java Dev, DB Admin |
| T2 - Testing Phase 2 | 1 | 22-Sep-25 | 26-Sep-25 | Testers |
| D3 - Development Phase 3 | 2 | 29-Sep-25 | 10-Oct-25 | Java Dev, DB Admin |
| T3 - Testing Phase 3 | 1 | 13-Oct-25 | 17-Oct-25 | Testers |
| D4 - Final Development Phase | 2 | 20-Oct-25 | 31-Oct-25 | Java Dev, DB Admin |
| T4 - Final Testing Phase | 1 | 03-Nov-25 | 07-Nov-25 | Testers |
| UAT - User Acceptance Testing | 2 | 10-Nov-25 | 21-Nov-25 | BA, Testers, Stakeholders |

14. Preparer Timesheets of a BA in various stages of SDLC

1. Design Phase: 28 July – 31 August 2024

| Week | Dates | Daily Time | Total Hrs | Activities |
| --- | --- | --- | --- | --- |
| Week 1 | 28 Jul – 03 Aug | 8:00 AM – 6:00 PM | 40 hrs | Review Requirements, Collaborate with Dev/Arch, Specs, Walkthroughs, Diagrams |
| Week 2 | 04 Aug – 10 Aug | 8:00 AM – 6:00 PM | 40 hrs | Continuation of Design Tasks |
| Week 3 | 11 Aug – 17 Aug | 8:00 AM – 6:00 PM | 40 hrs | Finalize Specs, Use Case, and Flows |
| Week 4 | 18 Aug – 24 Aug | 8:00 AM – 6:00 PM | 40 hrs | Walkthroughs, Updates |
| Week 5 | 25 Aug – 31 Aug | 8:00 AM – 6:00 PM | 40 hrs | Final Review & Design Handover |

2. Development Phase (Week 10 – 13)

| Week | Dates | Daily Time | Total Hrs | Activities |
| --- | --- | --- | --- | --- |
| Week 1 | 01 – 07 Sep | 8:00 AM – 6:00 PM | 40 hrs | Clarify Queries, Review Tech Docs |
| Week 2 | 08 – 14 Sep | 8:00 AM – 6:00 PM | 40 hrs | Sprint Meetings, Traceability Matrix |
| Week 3 | 15 – 21 Sep | 8:00 AM – 6:00 PM | 40 hrs | Interim Build Reviews |
| Week 4 | 22 – 28 Sep | 8:00 AM – 6:00 PM | 40 hrs | Aligning Dev Progress with Business Requirements |

3. Testing Phase (Week 14 – 16):

| Week | Dates | Daily Time | Total Hrs | Activities |
| --- | --- | --- | --- | --- |
| Week 1 | 29 Sep – 05 Oct | 8:00 AM – 6:00 PM | 40 hrs | Test Case Review, Test Execution Support |
| Week 2 | 06 – 12 Oct | 8:00 AM – 6:00 PM | 40 hrs | Defect Triage, Req Doc Updates |
| Week 3 | 13 – 19 Oct | 8:00 AM – 6:00 PM | 40 hrs | Business Sign-off Activities |

4. UAT Phase (Week 17 – 18):

| Week | Dates | Daily Time | Total Hrs | Activities |
| --- | --- | --- | --- | --- |
| Week 1 | 20 – 26 Oct | 8:00 AM – 6:00 PM | 40 hrs | Prepare Scenarios, Coordinate with Stakeholders |
| Week 2 | 27 Oct – 02 Nov | 8:00 AM – 6:00 PM | 40 hrs | Walkthrough, Capture Feedback, Sign-off |

5. Deployment & Implementation Phase (Week 19 – 21

| Week | Dates | Daily Time | Total Hrs | Activities |
| --- | --- | --- | --- | --- |
| Week 1 | 03 – 09 Nov | 8:00 AM – 6:00 PM | 40 hrs | Go-Live Support, End-User Training |
| Week 2 | 10 – 16 Nov | 8:00 AM – 6:00 PM | 40 hrs | Update Help Docs, Monitor Issues |
| Week 3 | 17 – 21 Nov | 8:00 AM – 6:00 PM | 40 hrs | Project Closure Review |