## Slide 1: Project Title: Disease Tracking & Public Health Intelligence Application
Domain : Healthcare
Prepared By: Yash Patil Date:25/8/2025

## Slide 2: Situations:
Current Scenario :
Rising spread of infectious and chronic diseases globally.
Manual or fragmented tracking systems limit accuracy and speed.
Delayed data collection hampers timely response and containment.
Limited integration between hospitals, labs, and government portals.
Growing public demand for transparency and quick updates.
Market Trend:
Increasing use of AI and data analytics in healthcare tracking.
High smartphone penetration enables mobile-based reporting.
Governments investing in digital health infrastructure.
Integration with wearable devices and IoT sensors.

## Slide 3: Market Trends - Digital Healthcare Growth:
Chart: 
| AI in Healthcare | Mobile Tracking | Govt Investment | Wearables Integration
Data | 75 | 65 | 80 | 50

## Slide 4: Problems:
Delayed Outbreak Response: Slow data aggregation prevents swift public health intervention, increasing infection rates and mortality.
Ineffective Resource Management: Inability to pinpoint exact needs leads to wastage of scarce medical resources in some areas and shortages in others.
Information Asymmetry: The public lacks a trusted, official source for real-time, location-specific health alerts and guidance.
High Operational Costs: Manual data handling is labor-intensive, expensive, and prone to human error.
Slow disease reporting and data consolidation.
Inaccurate or incomplete data records.
Poor public awareness and lack of real-time alerts.
Limited predictive insights for early prevention.

## Slide 5: Opportunities :
Integrates Data from disparate sources into a single, secure platform.
Provides Real-Time Analytics and visual dashboards for health officials.
Predicts High-Risk Areas using epidemiological models and AI.
Engages the Public directly with verified alerts and preventive guidelines.
Optimizes Response Efforts by directing resources based on data-driven insights.
Real-time tracking and reporting for faster response.
Predictive analytics for outbreak forecasting.
Integration with health organizations for better coordination.
Public engagement through user-friendly apps.

## Slide 6: Purpose Statement :
"To develop a integrated, Disease Tracking and Public Health intelligent surveillance Application that empowers public health officials with real-time data, predictive insights, and streamlined tools to proactively mitigate disease outbreaks, while providing the public with timely, accurate information to safeguard community health.“
Goals:
The Primary goal is Early detection and rapid response.
Provide Situational Awareness and Decision Support.
Public Communication and Empowerment.
Advancing Epidemiological Research.
Ensuring Data Integrity, Security, and Interoperability.

## Slide 7: Project Objectives:
Reduce Reporting Time: Decrease the average time from symptom identification to central database logging from 72 hours to under 4 hours within 12 months of launch.
Improve Prediction Accuracy: Achieve an 85% accuracy rate in predicting potential outbreak zones at least 14 days in advance by the end of Year .
Increase Public Reach: Onboard at least 70% of the target population onto the public-facing alert system within the first 18 months.
Enhance Operational Efficiency: Reduce the man-hours spent on manual data aggregation and reporting by 50% for health departments.
Strategic and long-term objectives: (global Health Security) Contribute anonymized, aggregated data to global disease surveillance networks(eg.WHO,GISAID,ProMED)to support international health security efforts.
Enable real-time data collection and visualization.

## Slide 8: Success Criteria :
Business Goals: Measured by the SMART Objectives (detection time, data accuracy, user engagement, model accuracy).
Stakeholder Satisfaction: >90% satisfaction rate among key user groups (health officials, hospital admins, government bodies) via post-launch surveys.
System Performance: 99.5% application uptime and sub-2-second load time for critical dashboards.
Adoption Metrics: 75% of target healthcare providers integrated and actively submitting data within the first year.
High user adoption by healthcare organizations and citizens.
Integration with multiple data sources and APIs.
Reduction in response time during outbreaks.

## Slide 9: Methods And Approaches :
User Story Mapping: Develop epics and user stories for all user person (e.g., "A Health Official").
Epics and user stories: Written from the perspective of health officials, admins and public users.
Mockups and wireframes: (Using Balsamiq)for clear UI/UX alignment.
Scrum Framework: Work will be organized in 2-week sprints, with sprint planning, Daily Stand-ups,Sprint reviews.
Prioritized Product Backlog: The BA and product owner will maintain a dynamically prioritized backlog based on business value and stakeholder feedback.
Iterative development and releases: A minimum viable product(MVP) will be launched first, followed by incremental feature releases based on validated learning and user feedback.
Continuous Collaboration: Regular communication with stakeholder to ensure alignment and incorporate feedback early and often.

## Slide 10: Resources :
1. People (Project Team Members):
Cross-Functional Agile Teams:
  Product Owner: Defines priorities and ensures alignment with business goals.
  Scrum Master: Facilitates Agile processes and removes blockers for the team.
  Development Team: Includes developers, database admins, and DevOps engineers to build and deploy the system.
  UI/UX Designers: Focus on creating intuitive and user-friendly interfaces.
  QA Testers: Work alongside developers to ensure quality through continuous testing.
  Stakeholders: Provide feedback during sprint reviews.
  Support Team: Assists with post-launch user issues and training.
Team Size:
  3-4 Agile teams of 5-9 members each, based on our project scope and complexity.
  Total team size: 20-30 members, scaled as needed during the project.
2. Time (Project Duration):
Agile Sprints:
  The project will run in 2 week sprints, delivering incremental features.
  Initial MVP (Minimum Viable Product): Delivered within 3-4 months, covering core functionalities like Data acquisition and integration, Analytics and intelligence.
  Full System Rollout: Completed within 10-12 months, with continuous improvements based on feedback.

## Slide 11: Resources:
Key Phases:
  Sprint 0 (Planning): 1-2 weeks for backlog creation and initial planning.
  Development Sprints: 6-9 months for iterative development and testing.
  UAT and Final Deployment: 1-2 months for user acceptance testing and go-live.
  Post-Launch Support: Ongoing support and feature enhancements.
3. Budget
Budget Allocation:
  Cloud Hosting: Azure for scalable and secure infrastructure.
  Software Licenses: Tools for development, testing, and project management (e.g., Jira, Confluence).
  AI Integration: Diverse data ingestion, visualization and reporting dashboard.
  Marketing: SEO, digital ads, and promotional campaigns to drive adoption.
  Training and Support: Training for healthcare professional and users and support tools (e.g., chatbots, helpdesk software).
Estimated Budget:
  MVP Phase: $2 Million for initial development and launch.
  Full Rollout: $8 Million for complete system deployment, marketing, and support.

## Slide 12: Budget Allocation Summary :
Category | Description | Allocated Funds
1. Technology and infrastructure | Cloud hosting (Azure),Software licenses, Ai integration and development tools | $3,000,000
2. Team Costs | Salaries for developers,designers,QA testers, DevOps engineers, and project Management | $3,000,000
3. Marketing and outreach | SEO, digital ads, influencer promotions, and acquisition campaigns | $900,000
4.Training and Support | Employee onboarding, customer support tools(e.g. Chatbots, helpdesk software),and post-launch support. | $500,000
5.Contingency | Buffer for unexpected expenses, scope changes, or additional resources needs. | $600,000
Total |  | $8,000,00

## Slide 13: Technologies :
Java
REACT.js
MySQL
Apache Kafka
O Auth
Microsoft Azure
Google Cloud Platform
GitHub and GitLab
Jenkins (Automated Deployment)

## Slide 14: Risks :
Risks:
Technical Risk: System Performance & Scalability - The platform must handle high and large datasets efficiently across multiple healthcare sources without lag or downtime.
Reputational and Societal Risks - A major privacy scandal, a highly publicized data error, or a failed prediction can shatter public confidence not just in the platform, but in the health authorities behind it, undermining future public health efforts.
Project Risk: Scope Creep - Frequent requirement changes can delay delivery, increase costs, and impact overall project timelines.

## Slide 15: Dependencies :
Technical Dependency: Cloud Infrastructure & Security – The system relies on Azure for hosting, ensuring scalability, security, and uptime.
External Environment Dependency: Government Policy and Priorities, Public Trust Willingness to Participate.
Project Dependency: Cross-Functional Team Coordination – Effective collaboration between business, development, QA, and DevOps teams is crucial for successful execution.

## Slide 16: To Be Completed by Appropriate Manager :
GM Healthcare Mr. Jack
Project Sponsor Project Manager