Project 	Gantt Chart Based on V-Model

Phases:

RG: Requirement Gathering

RA: Requirement Analysis

Design: System/Architecture Design

D1–D4: Development Modules

T1–T4: Corresponding Testing Phases

UAT: User Acceptance Testing

Resources Involved:

PM (Project Manager)

BA (Business Analyst)

Java Developers

Testers

DB Admin

NW Admin

Gantt Chart Table (Simplified Timeline View)

Phase; Duration; Week; Tasks/Activities; Responsible Resources. RG; 1 week; W1; Gather requirements from stakeholders; BA, PM. RA; 1 week; W2; Analyze & validate requirements; BA, PM. Design; 2 weeks; W3–W4; Create technical and functional design; BA, PM, Java Devs, DB Admin, NW Admin. D1; 2 weeks; W5–W6; Develop Module 1 (e.g., product catalog); Java Devs. T1; 1 week; W7; Test Module 1; Testers. D2; 2 weeks; W8–W9; Develop Module 2 (e.g., order system); Java Devs. T2; 1 week; W10; Test Module 2; Testers. D3; 2 weeks; W11–W12; Develop Module 3 (e.g., payment); Java Devs. T3; 1 week; W13; Test Module 3; Testers. D4; 2 weeks; W14–W15; Develop Module 4 (e.g., tracking); Java Devs. T4; 1 week; W16; Test Module 4; Testers. UAT; 1 week; W17; Conduct User Acceptance Testing; BA, PM, End Users, Testers..

### 📌 Additional Notes:

- PM is involved throughout for monitoring, approvals, and issue resolution.

- DB Admin and NW Admin assist during Design (infrastructure planning) and before UAT (deployment setup).

- BA is active during RG, RA, Design, and UAT.