## Slide 1: The Waterfall project: CVLP (Virtual Coding Lab Platform)
CodeBuddy

## Slide 2: Situation
Pimpri Chinchwad College of Engineering, particularly the Computer Science and IT departments, has observed a growing concern among students across various branches. Many students, especially those in their first and final years, face difficulties in writing accurate and logical code independently. Subjects like C, C++, Java, .NET, DBMS, and Algorithms are core to the curriculum, yet students struggle to apply concepts effectively during practical and project work

## Slide 3: Problem
Many students lack confidence and foundational clarity in programming.
Limited coding practice opportunities within regular lab sessions.
Non-CS/IT students (e.g., from Mechanical, Electronics, AIML) also need coding skills for project development but lack structured support.
Absence of a dedicated, interactive platform for self-paced coding practice.
Existing resources are fragmented and do not provide guided, curriculum-aligned support

## Slide 4: Opportunity
Develop a comprehensive coding practice platform that offers:
Step-by-step tutorials (text + video)
Practice problems with logic breakdown
Language selection guidance (C, Java, Python, etc.)
Basic tools, libraries, and IDE usage
Mobile, desktop, and web accessibility
Integrate the platform into practical sessions and offer extended access for extra practice.
Empower students with real-time feedback and structured learning paths.
Boost confidence for academic project work and improve employability.

## Slide 5: Purpose Statement (Goals):
The purpose of this project is to design, and implement a structured coding practice platform for engineering students across various departments at Pimpri Chinchwad College of Engineering.
The platform aims to support students—particularly those struggling with programming—by providing a guided, self-paced environment for learning, practicing, and applying coding skills essential for academic success and project development.

## Slide 6: Project Objectives
Project objectives are specific, measurable goals that a project is expected to achieve by the end of its execution
Solution selection according to design criteria, specifications, and requirements
Solution prototyping and testing
Provide a structured and self learning environment
Enhance coding confidence and project-readiness among students
Ensure cross-platform accessibility and continuous support

## Slide 7: Success Criteria:
Improve accessibility and availability of coding resources and tutorials
Reduce technical issues and ensure system stability
Increase student engagement and coding confidence
Enable cross-department usage and adoption
Provide measurable improvement in coding performance

## Slide 8: Methods / Approach (Waterfall Model) The Waterfall Model is a linear and structured approach where each phase of the project flows sequentially into the next. This model is ideal for CodeBuddy, as the requirements are well-defined and the platform needs to be developed and delivered in a systematic manner.
1. Requirements Gathering & Analysis
Conduct detailed discussions with faculty and students to gather requirements.
Document both functional and non-functional requirements.
2. System Design
Create the system Architecture & data model
Develop UI/UX design & wireframes
3. Implementation (Development)
Develop the CodeBuddy platform in modular phases (tutorial modules, coding editor, tracking system).
Ensure cross-platform support (Web, Desktop, Mobile).

## Slide 9
4. Testing
Perform unit testing, integration testing, system testing, and User Acceptance Testing (UAT).
Test on different devices and browsers to ensure compatibility and performance.
5. Deployment (Go-Live)
Deploy CodeBuddy on college infrastructure (servers or cloud).
Provide installation packages for desktop and mobile versions.
Ensure smooth access for students and faculty.
6. Maintenance & Support
Provide continuous support and resolve post-launch issues.
Regularly update content (tutorials, exercises).
Monitor platform usage and gather feedback for future enhancements.

## Slide 10: Resources
People:
The project team will include members from both the client community and ITS (APT IT SOLUTIONS).
  Client Side: Faculty members from Computer Science, IT, Electronics, and AIML departments who will provide requirements, content guidance, and user feedback.
  ITS Side: Business Analyst, Project Manager, Software Developers, UI/UX Designers, Testers, and Technical Support staff responsible for designing, developing, testing, and maintaining the CodeBuddy platform.
Business Analyst: Rashmi A— Lead requirements gathering, documentation, and coordination.
Project Sponsor: Dr. Satish Borkar (HoD – CSE Dept) — Overall project support and funding approval.
Project Manager: Mr. Vandanam (APT IT Solutions) — Manage project execution and delivery.
Technical Architect: Mr. Karthik — Define system architecture and technical design.
Developers (3 members): Implement web, desktop, and mobile versions of CodeBuddy.
UI/UX Designer: Design user-friendly and responsive interface for students and faculty.
QA/Test Engineers (2 members): Perform testing and quality assurance.
IT Support Engineer: Assist with platform deployment and ongoing maintenance.

## Slide 11
2. Time
Estimated project duration: 6 months
1 month → Requirement Gathering & Design
3 months → Development
1 month → Testing
1 month → Deployment & Training
3. Budget
Total Estimated Budget: ₹7,00,000 INR
Development: ₹4,00,000
Testing & QA: ₹50,000
Training & Support: ₹1,00,000
Hosting & Deployment: ₹50,000
Contingency & Miscellaneous: ₹1,00,000

## Slide 12
4. Other Resources
Infrastructure: Laptops, college servers, internet bandwidth, cloud hosting (AWS / Azure).
Reference Data: Coding syllabus, faculty inputs, industry coding standards, existing online tutorials.
Software Tools: IDEs (Visual Studio Code, Eclipse), GitHub for version control, testing tools.
Waterfall Model is usually used for Fixed Bid / Fixed Price projects because:
The scope of the project is well-defined at the beginning.
The requirements are clear and documented.
The timeline and budget are agreed upon upfront.
Work moves sequentially (step by step): Requirement → Design → Development → Testing → Deployment.

## Slide 13: Risks and Dependencies
Existing Practices & User Adaptation
Cost Justification Challenges
Technical Dependencies
Content Development & Updates
Training and Support

## Slide 14: To Be Completed by Appropriate Manager
Project Sponsor
Dr. Satish Borkar (HoD – CSE Dept)________
Project Manager
Mr. Vandanam (APT IT Solutions)_______________
Business Analyst
Mrs. Rashmi Asole _______________________
Technical Lead
Mr. Karthik (Delivery Head) ______________

## Slide 15
Thank You