## Slide 1: TIMESHEET ALIGNMENT
By-JANHAVI BORHADE

## Slide 2: Situation/Problem/Opportunity
SITUATION
Timesheet completion is the basis for KPI analysis.
Timesheet should be filled and completed on time , it would help the practices to and companies to track the activity rate, billability rate, idle time ,bench time,etc
Based on the above calculations various practices take decisions regarding improving the billability rate, reducing idle time , tagging a bench resource to a project,etc.
Thus timesheet completion is basis for all the analysis and improving the KPIs.
The organization currently gathers timesheet completion data through a dashboard and manually send timesheet reminder mails to the employees to fill TS and their managers to approve it if the timesheet is pending to be approved.

## Slide 3: Situation/Problem/Opportunity
PROBLEM:
Many employees delay or forget to fill out timesheets. This leads to:
Inaccurate billing
Payroll delays
Poor project time tracking
Compliance issues during audits
Inaccurate KPIs (KPIs help in decision making)
Mannual reminder mails lead to time constraint issues,increased chances of errors no effective increase in timesheet completion rate.

## Slide 4: Situation/Problem/Opportunity
OPPORTUNITY:
Automating timesheet compliance reduces manual chasing by operations team and managers
Saves hundreds of hours per year in follow-ups and manual checks.
In service-based firms, unsubmitted hours often lead to unbilled work and thus prevents revenue leakage, potentially recovering thousands in billables per project.
Encouraging timely submission builds a culture of responsibility and gives managers better visibility into team efforts and time usage patterns.

## Slide 5: Purpose Statement (Goals)
Timesheet completion data is tracked on monthly basis to do KPI analysis.
The proposed goal of the project is to implement a automation in the system to send reminder mails using the timesheet completion data on the dashborad on time to time basis to improve the timesheet completion percentage for a particular month.
AS IS
Track the Timesheet Completion Dashboard
Business Operation team Gathers data
Send manual reminder mails to defaulting employees/ managers
TO BE
Timesheet Portal
Provides a dashboard to managers to see real time timesheet completeness percentages
The Portal send automated reminder mails to defaulting employees/ managers

## Slide 6: Project Objectives
Develop and deploy an Automated Timesheet Monitoring & Notification System integrated with the existing system.
Sends emails, app notifications, or Slack/MS Teams pings for pending timesheets.
Escalate non-compliance to reporting managers after a deadline lapse.
Introduce badges, points, or rewards for consistent submissions.
Real-time visibility to managers of team-wise submission rates and defaulters
Weekly/monthly submission trends, department-wise compliance heatmaps.

## Slide 7: Success Criteria
Improved timesheet completeness percentage for the overall month.
Increase in weekly timesheet completion rate (target: from 65% to 95%+)
Reduction in payroll processing delays
Reduction in manual follow-ups by project managers and business operations team.

## Slide 8: Methods/Approach
Requirement Gathering and analysis :
Requirement gathering is done using “Focus Group” as the elicitation technique with cross-section of real users and stakeholders targeted feedback.
Focus groups allow sharing real user pain points and habits,observing common trends and attitudes and generating user-centric ideas
Besides that requirements will also be gathered using “observation” to understand current real workflows.
Preparing BRD (Business Requirement Document) with all the details of the proposed new model, input, output ,audits, risks etc.

## Slide 9: Methods/Approach
System Design:
After the requirement gathering system design is progressed by Working with solution architects and data scientists(Data science team) to define and discuss below points:
How the model will be called (API, batch, etc.)
Input format and schema for the model (validated applicant data)
Output fields (e.g., “Approved” or “Rejected”, along with risk score)
Help design a new UI screen or backend integration for decision support.
Define fallback/manual override rules for edge cases (e.g., insufficient data, model confidence too low)
A FSD(Functional Specification Document) is prepared along with data mapping document as well as workflow document including the integration of New Model.

## Slide 10: Methods/Approach
Implementation:
During the implementation phase working closely with the developers, data science team to ensure below points:
Ensure existing timesheet data (if any) is clean, complete, and migrated accurately. Perform data validation checks to prevent loss or mismatch.
Apply principle of least privilege (PoLP) to limit data exposure.
Validate that all business rules are coded (e.g.when will escalation be done)
Update the CR’s(Change request) if necessary.
Weekly status reports from the Dev and Data science team for any clarification.

## Slide 11: Methods/Approach
Testing(QA+UAT):
Validate the Test cases prepared by the Testers and get them demoed from the responsible tester for every feature that he/she has tested.
Prepare UAT test plan.
Create UAT test cases.
Validate model behavior with sample test data.
Check the test logs
Ensure the model outputs are explainable (required for compliance).
Facilitate User Acceptance Testing (UAT) with employees of a dept and their manager.

## Slide 12: Methods/Approach
Deployment:
Prepare training material and user guide for the new model usage.
Organize user training sessions with impacted users.
Support change management activities – especially for users resistant to automation.
Validate that the system logs predictions for audit/review.
Prepare the training material , business go-live checklist.
User-feedback forms to be circulated and taken.

## Slide 13: Methods/Approach
Maintenance:
Gather feedback post-implementation: Is the model helping? Are there any rejections that should be considered etc.
Monitor performance of the model (with data team) and communicate anomalies to stakeholders.
Collect enhancement requests (e.g., add more variables, improve score thresholds)
Check feedback summary from timely basis.
Change request logs to be checked.
Post go-live review/ report to be taken.

## Slide 14: Resources
Team: Project Manager, Business analyst, data science team, developers, UI/UX designers, QA team.
Technology used: HTML5, JavaScript, Java (Spring Boot), MySQL, Slack API / MS Teams API, Jira/Project Tools
License for : Jira, MySQL, Slack / Teams API.
Hardware: 10 laptops,10 headphones
Time: Approx. 8-12 months for development, testing, and integration.
Budget: Up to Rs. 60 lacs for model development, platform design, and deployment.
Other: Secure hosting, analytics tools, and compliance validation.

## Slide 15: Risks and Dependencies:
Risks:
Employees may resist changing habits or see reminders as intrusive.
Integration with HRMS, email/SMS APIs, or Slack may fail or break existing systems.
Timesheet data may contain sensitive project or payroll info.
Predictive reminders might fail causing false escalations.
SMS/Email APIs (like Twilio, SendGrid) might have downtimes or rate limits.
Resistance from staff relying on existing manual processes.
Dependencies on existing system APIs and IT support.

## Slide 16: Risks and Dependencies:
Dependencies:
Availability of Historical Data
Procurement of Hardware and Software.
Compliance and Legal Approvals.
User Training and Documentation
To be Completed by Manager : Mugdha V Borhade
Project Sponsor : The People’s Bank Project Manager : Mr. Arnav S