## Slide 1: iCRM -Sales and customer 360
Prepared By:
Pradnya Doiphode
Date:
28/07/2025

## Slide 2: Situation / Problem / Opportunity
Situation :
Sales executives currently use personal mobile devices to make customer calls and must return to the CRM system afterward to manually update the call status. This disjointed workflow often results in:
Missed or delayed updates on lead status,
Lack of real-time visibility for supervisors and managers,
Increased chances of human error in data entry,
Low accountability in follow-up actions, and
Inefficiencies in measuring and improving sales performance.
Moreover, without telephony integration, the system cannot track or analyze call outcomes, such as how many leads were actually contacted, how many responded, or how effective a particular executive’s outreach is. This gap leads to incomplete metrics for sales conversions and poor customer experience.

## Slide 3: Situation / Problem / Opportunity
Problem Statement :
The current process of managing calls and updating lead status in ICICI Bank’s CRM Sales Application is semi-manual.
Sales representatives need to manually dial customer numbers and then return to the system to update the outcome of the call.
This often results in delays, missed updates, and lack of accountability in lead follow-up.
There is also no direct integration with a telephony system that can auto-log call activities or track contact success rates.

## Slide 4: Situation / Problem / Opportunity
Opportunity :
Integrate a cloud telephony system (e.g., Exotel/Twilio) to initiate and log calls directly from the ICRM platform.
Enable automatic logging of call results and update contactability metrics in real time.
Improve lead follow-up accountability and reduce dependency on manual processes.
Introduce a fallback mechanism for manual entry if cloud calls fail.
Enhance sales performance visibility through better tracking and reporting.
Boost conversion ratios by ensuring timely customer engagement.

## Slide 5: Project Purpose
This project aims to make enhanced ICRM Sales Application by integrating a cloud telephony system for direct call initiation from the dashboard.
It also includes a fallback mechanism where users can log the call manually if the cloud-based call cannot be completed due to network issues.
It also includes the updation of minutes of meetings of the call.
The purpose is to streamline the sales workflow, improve tracking of contact attempts, and ensure accurate, real-time updates in the system.
Ultimately, it supports faster lead conversion and better customer service.

## Slide 6: Project Objectives
1. Integrate Cloud Telephony into ICRM Dashboard
Seamlessly embed a cloud calling feature (using providers like Exotel or Twilio) within the ICRM Sales Application, enabling sales executives to initiate calls directly from the system without using personal devices.
Ensure smooth API-based communication for call triggering and automatic logging.
2 . Automate Call Status Logging and Activity Tracking
Automatically capture call outcomes (Connected, Not Connected, Busy) and update them in the lead profile.
Eliminate the need for manual data entry and reduce errors in contactability metrics.
3. Introduce Manual Fallback Mechanism
Provide a user-friendly fallback option when the cloud call fails due to network or technical issues.
Allow users to manually select call status and add remarks to ensure no loss of interaction history.
4. Improve Lead Tracking and Sales Workflow Efficiency
Establish a structured and streamlined approach for real-time lead updates and follow-up tracking.
Ensure every lead is accounted for and all communications are traceable within the system.

## Slide 7: Project Objectives
5. Enable Mobile Compatibility for Field Executives
Provide mobile-based access to the ICRM dashboard, enabling on-the-go lead interaction, calling, and logging for field sales personnel.
Ensure the system is optimized for responsive performance on smartphones and tablets.
6. Enhance Visibility and Accountability for Managers
Implement real-time reporting and dashboards showing call performance, contact rates, and pending follow-ups.
Provide better tools for managers to monitor team activities, productivity, and lead conversion efficiency.
7. Support Faster Lead Conversion and Customer Engagement
With direct calling and instant updates, reduce turnaround time (TAT) in customer follow-ups.
Improve customer experience through timely communication and consistent tracking.
8. Ensure Scalability and Compliance
Design the integration to support scaling across different product verticals like loans, credit cards, and insurance.
Ensure that data security and compliance standards are met in handling customer communication records.

## Slide 8: Key Features of ICRM:
ICRM stands for Integrated Customer Relationship Management.
In the context of ICICI Bank, ICRM is an internal digital platform used primarily by the sales and service teams to manage customer leads, follow-ups, sales activities, and interactions across various banking products (like loans, credit cards, and accounts).
Key Features of ICRM:
1. Lead Management:
Captures and tracks sales leads from various sources.
Helps assign, prioritize, and monitor lead progress.
2. Customer Interaction Tracking:
Records interactions with customers (calls, visits, follow-ups).
Maintains a history of communication for accountability.
3. Sales Workflow Automation:
Streamlines processes like scheduling calls, updating lead status, and logging sales activities.
Integrates product-specific flows (e.g., personal loans vs. credit cards).

## Slide 9
4. Real-Time Dashboard:
Gives sales executives and managers a live view of targets, activity logs, and contact performance.
5. Reporting and Monitoring:
Generates MIS (Management Information System) reports to track sales performance.
Helps managers make data-driven decisions.
6. Mobile Accessibility:
Field executives can access and update ICRM from their mobile devices on the go.

## Slide 10: Agile Approach Overview
The Agile methodology will be followed to ensure iterative and incremental delivery, offering continuous value to stakeholders.
Scrum framework will be used, including short development cycles (Sprints), daily stand-ups, sprint planning, reviews, and retrospectives.
Early and ongoing collaboration with ICICI sales users will allow timely feedback, ensuring the solution aligns with real-world needs.
Product Backlog refinement will be a continuous process as new insights emerge during sprint reviews or UAT sessions.
Agile enables quick adaptation to changes, such as integration needs with third-party APIs or evolving compliance requirements.
Sprint-wise delivery ensures risk mitigation by validating small functional increments at every step instead of waiting till the end.
User stories will be prioritized based on business value – starting with core workflows like lead access, call initiation, fallback logic, and dashboard metrics.
Continuous testing and deployment practices will ensure each sprint results in a usable, demonstrable version of the product.

## Slide 11: Sprint 0 – Inception
Establish the Agile team including Product Owner, Scrum Master, and development team members.
Conduct stakeholder meetings to identify core challenges and expectations.
Prepare initial Product Backlog with prioritized user stories such as lead access, call initiation, call logging, and dashboard update features.
Finalize sprint timelines, tools, and communication channels for project collaboration.

## Slide 12: Sprint 1 – Core Features
Design and develop the login functionality and home dashboard for sales users.
Implement the modules to view My Work (Leads, Ongoing Calls, Portfolio, etc.).
Set up basic lead details and activity tracking screens with data placeholders.
This sprint focuses on building the foundation UI and core data connections to CRM.

## Slide 13: Sprint 2 – Cloud Call Integration
Integrate APIs from third-party cloud calling service providers (e.g., Exotel or Twilio).
Enable call button functionality that lets users initiate calls from the dashboard.
Automatically log the status of the call – connected, failed, or no answer.
Ensure that contactability percentage and dashboard KPIs update in real-time based on the call logs.

## Slide 14: Sprint 3 – Manual Call Fallback & UAT
Develop the fallback mechanism to allow manual status entry if a cloud call is not possible.
Users can select the outcome (Connected, Not Connected, Busy) and input remarks.
Conduct User Acceptance Testing (UAT) with selected ICICI sales executives.
Refine features based on UAT feedback before final deployment.

## Slide 15: Key Features Summary
Cloud-based calling directly from within the ICRM dashboard for improved efficiency.
Fallback feature allows manual call status entry if the call fails via cloud.
Auto-updating of contactability score and activity logs.
Mobile compatibility for field sales executives for call tracking on-the-go.
Real-time visibility into sales team performance and communication success.

## Slide 16: User Flow – ICRM Dashboard
Step 1: Sales executive logs into the ICRM dashboard.
Step 2: Opens 'My Active Prospects' or 'Ongoing Calls' module.
Step 3: Clicks on 'Call' to initiate the cloud-based call directly from the UI.
Step 4: The system logs call result automatically. If cloud call fails, fallback option allows manual entry.
Step 5: Dashboard updates in real time, and contactability metrics reflect the changes.

## Slide 17: UI Integration Points
Add a 'Cloud Call' button within the 'Ongoing Calls' and 'My Prospects' sections.
Display a modal dialog with fallback options if the call cannot connect.
Introduce visual indicators for call status (e.g., green for connected, red for failed).
Integrate with 'My Contactability' panel to track real-time conversion efficiency.

## Slide 18: Success Criteria (SMART)
Reduction in lead leakage by 80% through accurate and real-time call tracking.
Improvement in contact-to-conversion ratio by at least 30% within 3 months.
Full rollout of cloud call module within 3 sprints (6 weeks).
Onboard and train 100% of sales executives on the new call management process.
S: Reduce lead leakage by 80% with centralized tracking
M: Increase lead conversion rates by 30% within 3 months post-implementation
A: Train 100% of sales executives with role-based mobile CRM usage
R: Improve TAT for follow-ups and callbacks by automating reminders and updates
T: Complete MVP rollout in 3 sprints (6 weeks), full rollout in 3 months

## Slide 19: Methods / Agile Approach
Sprint 0 (Inception):
Product Backlog creation with key features (Lead Capture, Assignment, Follow-up Scheduler, Mobile App)
Identify Product Owner, Scrum Master, Development Team
Sprint 1:
Develop core lead management dashboard and user login modules
Daily standups, sprint planning, sprint demo
Sprint 2:
Add mobile interface + integration with existing systems (CBS, LOS)
UAT by selected sales executives
Sprint 3:
Add reports, user notifications, and supervisor dashboards
Final deployment and training

## Slide 20: Project Timeline
Week 1–2: Sprint 0 – Inception & Planning Phase
Assemble the Agile team: Product Owner, Scrum Master, Developers, and QA.
Conduct stakeholder workshops to gather initial expectations and pain points.
Create a high-level Product Backlog with prioritized user stories:
Lead access
Cloud call initiation
Call status logging
Dashboard integration
Week 3–4: Sprint 1 – Core Platform Setup
Develop user login system and authentication.
Design and build home dashboard with modules like “My Work”, “Ongoing Calls”, and “Leads”.
Create backend connectivity with CRM data sources.
Define initial UI elements for call status display and user profile views.
Internal sprint demo to stakeholders to validate core layout and flow.

## Slide 21: Project Timeline
Week 5–6: Sprint 2 – Cloud Call Integration
Integrate with cloud calling APIs (e.g., Exotel/Twilio) to enable direct call initiation from the ICRM dashboard.
Implement automatic logging of call outcomes (Connected, Not Connected, Busy, No Answer).
Update real-time metrics in the “My Contactability” panel.
Perform unit and integration testing of the cloud call module.
Week 7–8: Sprint 3 – Fallback Logic and UAT
Develop manual fallback mechanism to allow users to log call outcomes if cloud calling fails.
Add a remarks section and standard status dropdown (e.g., Busy, Switched Off, Callback Requested).
Conduct User Acceptance Testing (UAT) with selected ICICI Sales representatives.
Collect feedback, fix bugs, and implement minor UI/UX adjustments.
Week 9–10: Finalization & Go-Live
Conduct final sprint review and retrospective.
Final rollout across target sales units.
Deliver user training sessions and onboarding guides.
Monitor system performance and adoption.

## Slide 22: Required Resources:
People:
Product Owner (Business team)
Scrum Master
Development team (frontend, backend, QA)
ICICI Sales Team (for UAT)
Time:
3 months total; 2-week sprints
Tools:
Cloud telephony service provider (Exotel/Twilio), secure CRM integration.
Budget (Indicative):
Software Development & Licensing – ₹20,00,000
Training & Change Management – ₹5,00,000
Mobile device provisioning – ₹10,00,000

## Slide 23: Risks and Dependencies:
Resistance to change from sales staff who are used to the manual calling process – mitigated through training and role-based onboarding.
Integration delays with legacy systems like LOS (Loan Origination System) or core banking systems – to be addressed through early sandbox testing.
Data migration and validation issues when syncing lead data across systems.
Dependency on third-party telephony APIs – ensure fallback mechanisms are reliable and tested under various failure scenarios.
Regulatory compliance checks related to recording or tracking call activity – ensure legal approvals and consent mechanisms are in place.
Risk of low user adoption due to new processes – overcome with user-centric design and strong feedback loop during UAT.

## Slide 24: Conclusion
The ICRM Sales Application project under Agile methodology will directly improve lead management efficiency, reduce manual effort, and enable faster customer response. By adopting iterative development, early feedback, and collaboration, the solution will meet ICICI Bank’s strategic sales goals.

## Slide 25: To Be Completed by Appropriate Manager
Role | Name / Designation
Project Sponsor | Mr. Ramesh Patil – Head of Retail Sales, ICICI Bank
Project Manager | Ms. Pradnya Doiphode – Business Analyst & Agile Product Owner