## Slide 1: SMART MIS Reporting Framework
Prepared by: Amandeep Singh

## Slide 2: Problem /Opportunity
Problem:
Reports take days to compile
No centralized data source
Difficulty in tracking KPIs effectively
No real-time insights for management

## Slide 3: Problem / Opportunity
Opportunity:
Design and deliver a scalable, agile-based MIS system that supports SMART (Specific, Measurable, Achievable, Realistic, Time-bound) reporting, improves accessibility, reduces reporting time, and empowers decision-making through dashboards and automation.

## Slide 4: Purpose Statement
To design, develop, and deliver a SMART MIS Reporting Framework using Agile methodology. The system will consolidate data from various sources, automate reporting processes, and provide real-time dashboards tailored to departmental and executive needs.

## Slide 5: Project Objectives
Capture user requirements through Agile user stories and workshops
Create SMART-aligned report templates for all major departments
Automate data integration from ERP, HRMS, CRM, and other internal systems
Build interactive dashboards and drill-down reports
Implement user access controls, security features, and audit trails
Train client users and provide continuous support post-launch

## Slide 6: Success Criteria
At least 90% of recurring reports automated
Report turnaround time reduced from 3–5 days to < 6 hours
Full user adoption in all primary business units within 2 months
Stakeholder satisfaction rating ≥ 8.5/10 in UAT and post-go-live survey
System availability at ≥ 99.5% uptime post-deployment

## Slide 7: Methods / Agile Approach
Sprint 0: Setup and backlog creation
6 Sprints (2 weeks each): Development and delivery cycles
Agile Ceremonies: Daily standups, Sprint Planning, Reviews, Retrospectives
Tools:
JIRA – For backlog, sprint tracking, and velocity reporting
Power BI / Tableau – For dashboard/report development
GitHub / Bitbucket – Version control
Confluence – Documentation

## Slide 8: Methods / Agile Approach
Activities per Sprint:
Sprint Planning with client input
User story implementation
Demo at the end of each sprint
Continuous integration of feedback

## Slide 9: Resources Required
People:
1 Scrum Master
1 Product Owner
3 BI Developers
2 Data Engineers
1 QA Tester
Time:
Total Duration: 3 months (6 sprints of 2 weeks + Sprint 0)

## Slide 10: Resources Required
Component | Amount (INR)
BI Tool Licenses | ₹2,00,000
Development Resources | ₹6,00,000
Data Integration Tools | ₹2,00,000
Training & Documentation | ₹50,000
Contingency/Misc | ₹50,000
Total | ₹11,00,000
Budget:

## Slide 11: Risks and Dependencies
Risk | Mitigation Strategy
Legacy system integration may fail | Conduct data feasibility test in Sprint 0
Stakeholders not available during reviews | Schedule fixed-time sprint demos
Change requests mid-sprint | Handle via backlog grooming and prioritization
Data quality issues | Include early user story for data profiling

## Slide 12: Project Sign-Off
Sponsor: NTT Finance
Project Manager: Sheik Jahangir
Prepared By: Amandeep Singh
Date: 04/08/2025