## Slide 1: Project Proposal – In-house Ticket Management System Prepared By: KIRTY ShARMA Date: 5th September 2025 Project Sponsor: COEPD Project Manager: KIRTY

## Slide 2: Situation
Company currently relies on a third-party ticketing tool for managing support requests.
Increasing dependency on vendor for upgrades, fixes, and customization.
High recurring subscription/licensing costs.
Limited flexibility in customizing workflows and reports.

## Slide 3: Problem
High dependency on vendor → limited control over features, performance, and data.
Data security concerns since sensitive support data is stored on third-party platforms.
Recurring licensing & subscription costs increase operational expenses.
Outages: Downtime should be given to employees in case of outages.
Limited Knowledge: People have limited knowledge on the features and functionality

## Slide 4: Opportunity
Develop an in-house Ticket Management System (TMS) tailored to organizational needs.
Full control over features, workflows, and data security.
Cost savings in the long run by eliminating recurring third-party subscription fees.
Scope to add custom reporting, automation, and AI-driven analytics for future scalability.
Enhances employee experience and service quality with faster resolution and transparency.
Cost and Time effective

## Slide 5: Purpose Statement (Goals)
The purpose of this project is to analyze, design, build, test, and implement a secure, scalable in-house Ticket Management System to replace the current third-party tool, ensuring full data ownership, lower total cost of ownership, and seamless integration with internal systems.

## Slide 6: Project Objectives
Develop an in-house Ticket Management System (TMS) to replace the current third-party tool.
Ensure data security and compliance with internal IT policies.
Provide customizable workflows according to organizational needs.
Reduce operational costs by eliminating recurring licensing fees.
Enable real-time tracking and reporting for better decision-making.

## Slide 7: Deliverables & Success Criteria
Deliverables:
Fully functional in-house Ticket Management System.
User manuals and training materials.
Reports and dashboards for monitoring KPIs.
Post-implementation support plan.
Already created Templates

## Slide 8
Success Criteria:
Improved ticket resolution time by at least 30%.
100% data security with internal hosting.
Reduced operational cost compared to current vendor solution.
Seamless integration with in-house applications.
High user adoption rate (≥ 85% of employees actively using system)
Reducing Down.

## Slide 9: Waterfall Method Approach –It is a Linear approach, where each stage must be fully completed before moving to the next. This ensures clarity and avoids overlap, but limits flexibility.
Requirement Gathering (1 month)
Conducted workshops with IT helpdesk team, managers, and end-users
Studied existing manual ticketing and Excel-based tracking system
Identified business goals: faster resolution, SLA monitoring, escalation handling
Estimated Cost: ₹80,000
Key Deliverables:
  Business Requirement Document (BRD)
  Requirement Traceability Matrix (RTM)
  Stakeholder Analysis Document

## Slide 10
System Design ( 1.5 month)
Designed wireframes for ticket dashboard, reports, and admin console
Defined database schema for ticket ID, status, priority, and escalation matrix
Designed workflow for ticket lifecycle (Raise → Assign → Resolve → Close)
Estimated Cost: ₹1,00,000
Key Deliverables:
  Use Case Diagrams & Flowcharts
Development (1.5 months)
Frontend: Ticket submission forms, SLA countdown timers, role-based dashboards
Backend: Logic for ticket routing, email/SMS notifications, SLA breach alerts
Database: Tables for tickets, comments, history, audit logs
Estimated Cost: ₹3,80,000
Key Deliverables:
Functional and non functional requirement

## Slide 11
Testing (1.5 month)
Performed Unit Testing on each module (ticket creation, escalation, reports)
Conducted Integration Testing with email server and notification system
Executed Regression Testing to ensure stability of legacy modules
Estimated Cost: ₹90,000
Key Deliverables:
  Test Strategy Document
UAT (1 month)
Involved selected IT staff, helpdesk agents, and supervisors
Validated usability, reporting accuracy, and SLA adherence
Gathered user feedback and applied minor improvements
Estimated Cost: ₹1,20,000
Key Deliverables:
  UAT Sign-off Document Total Estimated Budget: ₹8,70,000

## Slide 12: Resources Required
Resources- Estimated duration- 6-8 Months
Role | Count | Company | Involvement Period
Project Manager | 1 | IT Solutions | Entire project (6.5 months)
Backend Developers | 4 | IT Solutions | 2months (Design → Dev)
Frontend Developers | 2 | IT Solutions | 2 months (Design → Dev)
Database Administrator | 1 | IT Solutions | 1.5 month (Design → Testing)
QA Testers | 3 | IT Solutions | 2.5 months (Testing & UAT)
System Engineer | 1 | IT Solutions | 1.5 month (UAT & Deployment)
Business Analyst | 1 | IT Solutions | Entire lifecycle (6.5 months)

## Slide 13
Other Resources
Hardware:
Application hosting server & backup server
Disaster recovery solution with failover support
Software:
Development tools (Eclipse/IntelliJ, SQL Workbench)
Ticket analytics & reporting tools
Automation testing tools (Selenium, JUnit)
Network:
Secure VPN connectivity for remote access
Load balancer for managing high request volume

## Slide 14: Risks & Dependencies
Risks:
Data migration challenges from third-party tool.
Resistance from employees used to existing system.
Possible cost overruns if requirements change mid-project.
Technical challenges in integration with existing in-house systems.
Dependencies:
Availability of skilled technical team.
Timely input from stakeholders during requirements phase.
Management approval for budget and resources.
Vendor cooperation for data export from current tool.

## Slide 15: Conclusion
The proposed Ticket Management System will streamline the process of logging, tracking, and resolving IT and customer support issues.
By adopting the Waterfall model, each phase (Requirements → Design → Development → Testing → UAT) will be delivered in a structured and predictable manner.
The system will improve SLA compliance, reduce resolution time, and enhance transparency across teams.
Estimated budget of ₹8.7 Lakhs and a 6.5 month timeline ensure feasibility within organizational constraints.
With the right resources, tools, and stakeholder collaboration, the project will achieve its goals and deliver a robust, reliable, and user-friendly Ticket Management System.

## Slide 16: Thank you
To Be Completed by Appropriate Manager- Kirty