## Slide 1
Date: 3rd July 2025
Student Management Application
Prepared By: Anushk Porwal

## Slide 2
SITUATION
  Manual maintenance of student records
  Scattered academic and administrative data across departments
  Lack of real-time tracking of student performance
  Difficulties in accessing historical student data
  Inefficient communication between students and administration
  No centralized system for fee management, attendance, and academics

## Slide 3
  As of now, current student management methods only help to track minimum academic information, which leads to high administrative burden and more time spent on manual data entry for various student-related activities.
  Manual tracing of student information has to be done through physical files and various rious disconnected databases, which is less accurate and a time-consuming activity.
Problems

## Slide 4
Opportunity
  Create a centralized platform for all student-related dat
  Enable real-time access to student profiles, attendance, results, and fees
  Improve data accuracy and tracking across academic lifecycle
  Facilitate faster grievance resolution and communication
  Simplify admission, promotion, and graduation processes
  Enhance student experience through personalized dashboards

## Slide 5
To develop and implement a comprehensive Student Management Application that consolidates academic, administrative, and financial data of students into a unified, efficient, and secure digital platform, enhancing institutional productivity and student satisfaction.
PURPOSE STATEMENT (GOAL)
This portal aims to enhance efficiency, accuracy, and user-friendliness to check all the required information at one platform for reducing administrative burdens and improving student support.

## Slide 6
Project Objectives
  Provide a centralized platform for student multiple relationship details (e.g.,
  academic, financial, extracurricular).
  Streamline academic history and administrative cycles (e.g., registration, attendance, grading).
  Ensure robust data security for student records.
  Optimize administrative operations and resources to achieve cost savings without compromising on the quality of student services.
  Reduces manual checking of application and academic forms.
  Easy tracking of student information with address and relevant photos/documents.
  Single platform for multiple student-related inquiries and resolutions.
  Introduce automation features such as student registration, attendance tracking, and grade management to optimize administrative processes.

## Slide 7
SUCCESS CRITERIA
The application will be considered successful if it:
  Digitally captures 100% student records
  Provides role-based access for admin, faculty, and students
  Offers real-time updates and notifications
  Reduces manual tasks by at least 70%
  Improves student query resolution TAT
  Delivers custom reports and analytics dashboards
  Integrates with ERP, exam software, and other existing systems

## Slide 8
Methods/Approach - Using Waterfall Model
Project Planning:
  Understand the project requirements and define the scope of the Student Management Application.
  Identify stakeholders (e.g., administration, faculty, IT, students) and form a project team with roles and responsibilities
Requirements Gathering and Analysis:
  Interview stakeholders, users, and administrative staff to understand their needs and expectations.
  Document detailed functional and non-functional requirements for the system.
System Design:
  Design user interfaces (UI) and user experiences (UX) for various user roles (admin, faculty, student, parent).
  Develop a robust database schema for centralized student data.
  Define the overall system architecture, including integrations.
Implementation:
  Divide the project into smaller tasks and assign them to the development team.
  Development of core modules: Admission, Attendance, Fees, Results

## Slide 9
Methods/Approach - Using Waterfall Model
Testing:
  Develop a comprehensive testing strategy covering unit testing, integration testing, and system testing.
  Conduct careful examinations to identify and fix bugs and ensure the system meets the specified requirements.
Deployment:
  Prepare the system for deployment in a production environment.
  Install the necessary hardware and software infrastructure to support the application.
Maintenance and Support:
  Monitor the system after deployment and address any issues or bugs that arise.
  Provide ongoing maintenance and support to the administrative staff and end-users.
Project Documentation:
  Throughout the project, maintain detailed documentation of every phase and activity.
  Document code changes, user manuals, technical specifications, and other
  project-related information.

## Slide 10
Resources
Project team:
Project manager, Business Analyst, Software Developers, Administrative Staff/Faculty, Subject Matter Experts (SME from academic/admin), Training Specialists, Testers,Technical Support & Security Advisor.
Time: Timeline for Implementation: The project aims to complete within 9 months.
  Requirement Gathering and Analysis: 1 month
  System Design: 1 month
  Development: 3 months
  Testing:1-1.5 months
  Deployment and Go-live:1 month
  Support and Stabilization: 1-2 months post deployment
Budget: Ensure the overall project cost does not exceed Rs. 15,00,000

## Slide 11
Risks...
1. Technical Challenges: Potential issues during development, integration with existing systems, or deployment that could delay the project timeline or impact functionality.
2. Unclear Requirements: Ambiguous or changing requirements may result in
misunderstandings and potential rework during the development phase, impacting
project timelines.
3. User Adoption and Training: Resistance from users to adopt the new system or insufficient training leading to low utilization and productivity dips.
4. Data Migration Issues: During data migration from the old system to the new one,
there could be data integrity problems or data loss, affecting the accuracy of student
information.
5. Security Concerns: Handling sensitive student data online introduces risks of data breaches, unauthorized access, or non-compliance with privacy regulations.

## Slide 12
Dependencies
  Resource Availability: The project's success depends on the availability and
  commitment of project team members from the institution's administration, faculty,
  and IT.
  Timely Decision-Making: Timely decision-making by stakeholders is crucial for
  resolving any project-related issues or changes promptly.
  Third-Party Software Integration: Successful integration with third-party software
  relies on the cooperation and support of external vendors.
  User Training: The effectiveness of the system depends on the training provided to
  administrative staff, faculty, and students to ensure they can use the system
  effectively
  Compliance and Approvals: The project may require compliance with specific
  regulations and approvals from relevant authorities (e.g., educational boards,
  government bodies).
Project Sponsor ___________________
Project Manager ___________________