## Slide 1: CRM Enhancement Project Proposal
Prepared by: Susmita Devi
Date: 5/07/2025

## Slide 2: Situation / Problem / Opportunity
RMs face issues related to
Delays in escalation visibility
Missed client follow-ups
Lack of contextual help for staff
No real-time client feedback loop

## Slide 3: Purpose Statement (Goals)
The purpose of this project is to enhance the CRM system by implementing Agile-based sprints focusing on usability, feedback capture, and improved task follow-ups.

## Slide 4: Project Objectives
Implement Internal Help Overlay
Feedback Loop Integration
Escalation Tracker Dashboard
Smart Notification & Follow-Up Engine

## Slide 5: Success Criteria
15–20% improvement in SLA adherence
25% reduction in RM onboarding time
3-point NPS increase
Improved visibility & accountability

## Slide 6: Methods / Approach
Conduct stakeholder meetings to identify current pain points in CRM
Define sprint-wise product backlog with prioritized user stories
Use Agile ceremonies (sprint planning, daily stand-ups, reviews, retrospectives)
Collaborate with UI/UX and development teams to prototype solutions
Conduct User Acceptance Testing (UAT) with pilot RM teams for feedback
Deploy each enhancement in a phased Go-Live plan, monitor adoption
Collect feedback post-launch to iterate and improve continuously

## Slide 7: Resources
People: PO, BA, Dev, QA, UX
Time: 10–12 weeks (Agile sprints)
Budget: 30 lakhs
Tools: CRM sandbox, training, Agile boards

## Slide 8: Risks and Dependencies
CRM is tightly integrated with legacy systems; changes may impact stability
End-users (RMs, Ops staff) may resist changes to familiar workflows
Training and adoption efforts may require dedicated time during peak cycles
Improvements like feedback loops may not show immediate ROI, affecting management buy-in
Technical dependency on internal IT teams and CRM vendors may delay sprints
Regulatory compliance needs to be considered in all workflow modifications

## Slide 9: Project Governance
Project Sponsor: [ Endrew Jacob]
Project Manager: [ Harish Balli]