## Slide 1: Project Title: Qconneqt (Loan Monitoring Application)
Prepared By Date:22-07-2025
A B Prem Kumar

## Slide 2: Situation:
Union Bank of India is one of the leading public sector banks with a vast customer base and an extensive loan portfolio. The management of loan repayments and loan monitoring is currently manual, inconsistent, and inefficient. Credit Monitoring Officers (CMOs) struggle to effectively track and manage repayments due to inadequate tools, resulting in rising Non-Performing Assets (NPAs) and missed recovery opportunities.

## Slide 3: Problem
Key challenges faced by the Bank and its Credit Monitoring Officers include:
High volume of missed or delayed payments by borrowers
Inefficient Tracking: Manual follow-ups by Credit Monitoring Officers (CMOs) are time-consuming and error-prone.
Lack of Real-Time Data: Delays in accessing Borrower details (over dues, contact info) hinder recovery efforts.
Compliance Risks: Inconsistent documentation of borrower interactions affects audit readiness.
Impact:
Increased NPAs, affecting profitability.
Operational inefficiencies in loan monitoring.
Poor borrower experience leading to reputational risk.

## Slide 4: Opportunity
There is a significant opportunity to digitize and streamline the loan monitoring process. A mobile-enabled application can:
Provide real-time access to critical loan data
Enable proactive borrower engagement
Facilitate timely recoveries
Improve repayment discipline
Reduce operational inefficiencies
Long-Term Benefits:
Stronger loan portfolio health.
Higher customer satisfaction & trust.
Competitive edge in digital banking.

## Slide 5: Purpose Statement
To develop and deploy Qconneqt, a user-friendly Loan Monitoring Application that enhances the effectiveness of Credit Monitoring Officers in tracking loan performance, engaging with borrowers, and recovering dues efficiently.
Streamline Loan Management: Simplify the process for both CMOs and borrowers, ensuring stress-free loan accounts and clear visibility of repayment terms
Improve Recovery Efficiency: Facilitate timely and informed interventions by providing real-time borrower data and integrated navigation tools.
Enhance Accountability & Compliance: Ensure transparent and verifiable borrower interactions, thereby strengthening the bank's financial health and regulatory adherence.

## Slide 6: Project Objectives
Provide Credit Monitoring Officers with mobile access to real-time loan and borrower data
Automate payment reminders and overdue alerts to borrowers
Improve early identification and intervention in potential default cases
Integrate real-time borrower contact information and address details within the application.
Incorporate GPS navigation capabilities to assist CMOs in planning and executing on-site visits for borrower engagement.
Enable CMOs to capture and upload geotagged photos of borrower interactions as verifiable proof of visit.
Provide functionality for CMOs to record borrower commitments through remarks and documentation within the app.

## Slide 7: Success Criteria
30% improvement in recovery timelines and reduction in manual follow-ups
Enhanced borrower satisfaction and repayment consistency
Minimum 25% reduction in overdue loan accounts within 6 months of implementation
Reduction in NPAs: A measurable decrease in Non-Performing Assets due to timely interventions and prevention of defaults.
Improved Borrower Discipline: Evidence of more consistent and timely repayments by borrowers, leading to fewer overdue accounts.
Operational Efficiency: Significant reduction in manual follow-ups and streamlined processes for CMOs, leading to increased productivity.
Strengthened Financial Health: Higher loan recovery rates and improved asset quality, contributing directly to the bank's profitability.
User Adoption: High adoption rate and positive feedback from Credit Monitoring Officers regarding the application's usability and effectiveness

## Slide 8: Methods/Approach
Agile Methodology using the Scrum Framework
Sprint-based development cycles for incremental feature delivery
Sprints will be used to deliver working increments of the application, ensuring early value delivery and stakeholder engagement.
Regular Scrum meetings to track progress and remove blockers
Product Backlog prioritized by business needs
Key Ceremonies: Sprint Planning, Daily Stand-ups, Sprint Reviews, Retrospectives.
Frequent stakeholder demos to ensure alignment and early feedback
End-user UAT (User Acceptance Testing) before each release phase

## Slide 9: Resources
People:
  Project Sponsor (Pankaj Trivedhi)
  Project Manager (K.L. Raju)
  Business Analyst (Prem Kumar)
  Credit Monitoring Officers (CMOs - for user feedback and testing)
  Software Development Team (Frontend, Backend, Mobile Developers)
  Quality Assurance (QA) Engineers
  Database Administrators
  UI/UX Designers
  IT Infrastructure Support

## Slide 10
Time:
  12 months (MVP launch in 4 months)
  Sprint based Project deliverables
Budget:
  ₹1.2 Cr (Development: ₹85L, Training: ₹15L, Contingency: ₹20L).
Other:
  Third-party software evaluation e.g., mapping GPS APIs, communication APIs, Cloud hosting (AWS/Azure)
  Data Sources: Core Banking System (CBS) integration
  Site visits (for requirements gathering and user testing)
  Dataquest reports Monthly Loan Recovery analysis

## Slide 11: Risks and Dependencies
Risks:
Resistance to adoption by CMOs due to change in workflow
Potential data security risks during mobile data access
Delay in integration with existing core banking systems
Dependencies:
Timely availability of internal APIs and loan data from UBI IT systems
Active participation from Credit Monitoring Officers for feedback
Coordination with third-party vendors for GPS and communication tools

## Slide 12: Approval & Acknowledgement
Role | Name | Signature | Date | Remarks / Approval Status
Project Sponsor | Pankaj Trivedi | Gpt | 22/07/2025 | Approved
Project Manager | K Luth Raju | Klr | 21/07/2025 | Approved

## Slide 13: THANK YOU