### Document 1: Definition of Done (DoD)

Project: AU PROUD App Enhancement
 Definition of Done Checklist:

- Acceptance criteria defined and fulfilled

- Code for new/enhanced features written

- AU App builds without any errors

- Unit tests written and passed for each enhancement

- QA testing performed for Android/iOS app

- Cross-browser/device testing done (Android/iOS, Firefox, Chrome, Safari)

- UX approval for each enhancement (UI simplification, faster load)

- Peer code review completed

- Features deployed on UAT/test environment

- Product Owner (PO) reviewed and accepted

- Knowledge base/docs updated

- Refactoring of old code (where applicable) done

- Compliance/security checks passed as per BFSI norms

- Feedback received from internal stakeholders

### Document 2: Product Vision

Scrum Project: AU PROUD App – Feature & Performance Enhancement
 Venue: AU IT & Digital Team Virtual Room
 Date: 03-06-2025 | Start: 10:00 AM | End: 12:00 PM | Duration: 2 hours
 Client: AU Small Finance Bank
 Stakeholders:

- Digital Transformation Head

- Product Manager – Mobile App

- Compliance & Risk Manager

- Customer Support Lead

- Development Team Lead

- End Users (Bank Customers)

Scrum Team

- Scrum Master: Ravi Kumar

- Product Owner: Aditya Sharma

- Scrum Developers:

  - Dev1: Aayush

  - Dev2: Sneha

  - Dev3: Mahesh

  - Dev4: Kavita

  - Dev5: Suraj

#### Vision

To improve the AU PROUD App by enhancing usability, performance, and introducing key features such as personalized offers, faster login, and improved loan application flow, thereby increasing digital adoption and customer satisfaction.

#### Target Group

- Market: BFSI (Banking, Financial Services & Insurance)

- Target Users: Retail banking customers, loan applicants, digital-only customers, and potential millennial clients.

#### Needs

- Reduce app crashes and improve speed

- Simplify customer journey (login, apply loan, pay bills)

- Personalize offers for credit cards, loans

- Increase customer retention and mobile app usage

#### Product

A highly intuitive, secure, fast mobile banking application with enriched digital services, better UI, and AI-driven personalization.

#### Value

- Higher Net Promoter Score (NPS)

- Increase in mobile loan applications

- Reduction in call center load

- Strategic alignment with AU's digital-first strategy

### Document 3: User Stories

| User Story No. | Tasks | Priority |
| --- | --- | --- |
| US01 | Revamp login with biometric & OTP | High |
| US02 | Display personalized credit card offers | High |
| US03 | Add EMI calculator in loan section | Medium |
| US04 | Push loan offer notifications | Medium |

#### Sample User Story – US01

Value Statement:
 As a retail banking user,
 I want to log in using face ID or OTP,
 so that I can access my account securely and quickly.

- BV (Business Value): 8

- CP (Complexity Point): 5

Acceptance Criteria:

- User can choose OTP or biometric (face/fingerprint)

- Login success in < 5 seconds

- OTP validity 2 mins

- Security validation per AU IT policy

### Document 4: Agile PO Experience

As Product Owner for the AU PROUD App Enhancement:

- Conducted market analysis on trending digital banking features

- Aligned the app enhancements with AU Bank’s digital roadmap

- Prioritized features (login, personalization, EMI tool) based on business impact

- Defined product backlog and created EPICs and stories

- Collaborated with compliance and IT to ensure BFSI regulatory standards

- Participated in sprint meetings and stakeholder demos

- Reprioritized based on test feedback and usability metrics

- Ensured value delivery through sprint reviews and customer feedback

Key Learnings:

- Managing stakeholder expectations in BFSI

- Translating business needs into technical features

- Sprint planning and backlog grooming

- Delivering incremental improvements for large-scale user base

### Document 5: Product and Sprint Backlogs & Burndown Charts

#### Product Backlog

| ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | Login enhancement | Design, Develop, Test | High | 8 | 5 | Sprint 1 |
| US02 | Credit card offer section | Create offers UI, Integrate with backend | High | 7 | 6 | Sprint 2 |
| US03 | EMI calculator | Design formula, UI, backend logic | Medium | 6 | 5 | Sprint 3 |
| US04 | Push notification | Write service, Test delivery | Medium | 6 | 4 | Sprint 3 |

#### Sprint Backlog – Sprint 1

| ID | User Story | Tasks | Owner | Status | Est. Effort |
| --- | --- | --- | --- | --- | --- |
| US01 | Login enhancement | Biometric integration | Sneha | In Progress | 8 hrs |
| US01 | Login enhancement | OTP logic | Aayush | Done | 6 hrs |
| US01 | Login enhancement | UI improvement | Kavita | In Progress | 7 hrs |

#### Product Burndown Chart:

(Use Excel or Jira chart showing gradual decrease in pending backlog over sprints)

#### Sprint Burndown Chart – Sprint 1:

Show remaining effort/day vs ideal effort line (create chart from Excel/Agile tool)

### Document 6: Sprint Meetings

#### Sprint Planning Meeting

- Date: 03-06-2025

- Time: 10:00 AM – 11:30 AM

- Location: Teams Call – AU Agile Room

- Prepared by: Aditya Sharma

- Attendees: Scrum Team, Product Manager, QA

- Agenda Topics:

  - Sprint 1 planning – Login enhancements

  - Task estimation

  - Sprint goal definition

- Observers: QA Manager

- Special Notes: Prioritize biometric feature

#### Sprint Review Meeting

- Date: 12-06-2025

- Time: 3:00 PM

- Location: AU Boardroom – Jaipur HQ

- Sprint Status: 80% completed

- Things to Demo: OTP Login, UI updates

- Quick Updates: Feedback from CX Head

- What’s Next: Biometric and security patch

#### Sprint Retrospective Meeting

- Date: 13-06-2025

- Time: 11:00 AM

- Location: Virtual Scrum Room

- Agenda: Review of Sprint 1

  - What went well: Fast development, PO support

  - What didn’t go well: Biometric took more time

  - Questions: How to reduce dependency delays?

#### Daily Stand-up Meeting

| Name/Role | Week “1” (03-06-2025 to 09-06-2025) | Mon | Tue | Wed | Thu | Fri | Sat | Sun |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Developer 1 (Sneha) | Biometric dev | ✅ | ✅ | ❌ | ✅ | ✅ | ✅ | ❌ |
| Developer 2 (Aayush) | OTP flow | ✅ | ✅ | ✅ | ✅ | ✅ | ❌ | ❌ |
| Developer 3 (Mahesh) | API & Test | ✅ | ❌ | ✅ | ✅ | ✅ | ✅ | ❌ |

Questions Tracked:

- What did you do yesterday?

- What will you do today?

- Any blockers?