Agile Model Deliverables Documents

Document 1- Definition of Done

Question 1: As Per Agile Extension to the BABOK® Guide v2, Definition of Done is a technique where the team agrees on, and prominently displays, a list of criteria which must be met before a backlog item is considered done.

That is the team has to create a well-defined, unambiguous, measurable, agreed-upon, and shared Definition of Done between all team members.

The best form of Definition of Done representation is a checklist of activities that has to demonstrate the agreed value and quality of a user story. So, this checklist should include:

- acceptance criteria (to satisfy customer requirements for a product)

- quality criteria (to satisfy quality requirements for a product)

Definition of Done may be defined for different levels of project work. For example, in Agile / Scrum framework these levels of work could be user story, sprint, and release.

Checklist for DOD:

- Produced code for presumed functionalities

- Assumptions of User Story met

- Project builds without errors

- Unit tests written and passing

- Project deployed on the test environment identical to production platform

- Tests on devices/browsers listed in the project assumptions passed

- Feature ok-ed by UX designer

- QA performed & issues resolved

- Feature is tested against acceptance criteria

- Feature ok-ed by Product Owner

- Refactoring completed

- Any configuration or build changes documented

- Documentation updated

- Peer Code Review performed

Answer: The Definition of Done ensures that all project deliverables—whether at the user story, sprint, or release level—are complete, high-quality, and ready for production. It provides a shared checklist across the team, reducing ambiguity and ensuring consistency in delivery across digital platforms, supply chain processes, and compliance requirements.

User Story Level DoD

Each user story (e.g., a customer-facing feature, procurement workflow, or integration point) is considered Done when the following criteria are fulfilled:

- Acceptance criteria are fully implemented and validated

- Feature functionality is developed, committed, and integrated with the latest build

- Business rules and localization requirements (e.g., currency, language, tax rules) are implemented

- Code is peer-reviewed and meets coding standards

- Unit tests are written with minimum 80% coverage and all tests pass

- The feature is tested on required browsers/devices (as per device matrix)

- QA has executed test cases and validated that the story passes all functional tests

- UX review and validation completed (if applicable)

- Any associated error handling or edge cases implemented and tested

- The feature is approved by the Product Owner

- Technical documentation (e.g., API usage, config values) is updated

Sprint Level DoD

A sprint is considered Done when the following conditions are met:

- All committed user stories in the sprint meet their individual DoD

- All changes are successfully integrated and the sprint build passes without errors

- Code is deployed to a test/staging environment that mirrors production

- Integration testing (e.g., between payment gateway, ERP, or logistics APIs) is completed

- Non-functional requirements such as performance, responsiveness, and accessibility are tested (where applicable)

- The Sprint Review is conducted and stakeholders have validated the sprint increment

- Sprint Retrospective is held, with team feedback and improvement actions documented

- All open bugs and critical defects from the sprint are resolved or deferred with stakeholder approval

Release Level DoD

A release (e.g., deployment of the new website, mobile app, or operational readiness for order processing) is considered Done when:

- All features planned for the release meet their sprint and story-level DoD

- Full end-to-end system testing is completed (covering digital ordering to fulfilment)

- Data privacy, security, and food compliance checks (e.g., labelling, shelf-life rules) are passed

- Go-to-market workflows such as logistics, payments, and customer service flows are validated

- Regulatory approvals and certifications required for the country (e.g., FSSAI-equivalent) are obtained

- Technical and user documentation (for internal users, support teams) is finalized

- Production deployment scripts and rollback plans are tested and verified

- Release notes and knowledge transfer sessions are delivered

- Product Owner and key stakeholders formally sign off

- Post-Go-Live monitoring tools are in place and team is ready for support and stabilization sprint

Acceptance Criteria: Defined by the Product Owner or Business Analyst to ensure the feature/story delivers business value and meets end-user expectations

- Product Availability

- All existing SKUs are available on the new country’s app/website with accurate pricing, ingredients, nutritional info, and packaging details.

- Localized Experience

- The digital interface supports the local language, currency, and regional units of measure.

- Legal and tax regulations (e.g., VAT, digital tax) are accurately applied during checkout.

- Functional Integration

- Order flow integrates end-to-end with payment gateways, inventory system, and local logistics partners.

- Users can place, track, and cancel orders successfully.

- User Journey Completion

- Key user journeys (e.g., registration, product search, checkout, support request) complete without errors.

- Edge cases like invalid address, payment failure, and out-of-stock items are handled gracefully.

- Compliance Alignment

- Labels, allergen info, expiry dates, and country-of-origin data meet the local food regulatory body’s standards.

- Customer data is captured and stored per data protection laws (e.g., GDPR equivalent).

- Stakeholder Approval

- Feature is reviewed and accepted by Product Owner and relevant business stakeholders before closure.

Quality Criteria: Defined and enforced by the QA team and technical leads to ensure robustness, performance, and maintainability of deliverables.

- Code Quality & Maintainability

- Code is modular, readable, and follows project coding standards.

- All critical logic is covered by unit tests with at least 80% code coverage.

- Peer code review is completed and comments addressed.

- Cross-Platform Compatibility

- App and website are fully functional and visually consistent across the supported browsers (Chrome, Safari, Firefox) and mobile devices (iOS & Android).

- Performance Benchmarks

- Page load time is under 3 seconds on standard 4G mobile network.

- Backend APIs respond in < 500ms for standard queries under nominal load.

- Security Assurance

- All sensitive data (e.g., payment details, personal info) is transmitted and stored securely using encryption (HTTPS, AES).

- No hardcoded credentials or exposed endpoints.

- Bug-Free Criteria

- No critical or major defects open at the time of deployment.

- All known minor issues are documented, with mitigation or resolution planned.

- Documentation & Traceability

- All user stories, test cases, configs, and technical specs are updated in the knowledge repository.

- Version control tags are correctly applied to each release.

- Test Coverage

- Functional, integration, regression, and user acceptance testing completed.

- All test cases pass and results are documented with evidence/screenshots where required.

Document 2- Product Vision

Question 2:

| Scrum Project Name |  |  |  |
| --- | --- | --- | --- |
| Venue |  |  |  |
| Date | Start Time | End Time | Duration |
| Client |  |  |  |
| Stakeholder List |  |  |  |
| Scrum Team |  |  |  |
| Scrum Master |  |  |  |
| Product Owner |  |  |  |
| Scrum Developer 1 |  |  |  |
| Scrum Developer 2 |  |  |  |
| Scrum Developer 3 |  |  |  |
| Scrum Developer 4 |  |  |  |
| Vision: What is your vision, your overarching goal for creating the product? |  |  |  |
| Target Group Which market segment does the product address? Who are the target users and customers? | Needs What problem does the product solve? Which benefit does it provide? | Product What product is it? What makes it desirable and special? Is it feasible to develop the product? | Value How is the product going to benefit the company? What are the business goals? What is the business model? |

Answer:

Scrum Project Name: Cargill Expansion – Digital & Operational Rollout

Venue: Company HQ (Hybrid with virtual Scrum ceremonies)

Date: July 10, 2024

Start Time: 10:00 AM

End Time: 12:00 PM

Duration: 2 hours

Client: Cargill Industry Company (Global HQ)

Stakeholder List: Chief Product Officer, Regional Business Development Manager, Head of Supply Chain, Marketing Director (New Markets), Legal & Compliance Lead, IT Operations Manager

Scrum Team:

| Role | Name |
| --- | --- |
| Scrum Master | Priya Sharma |
| Product Owner | Rahul Verma |
| Scrum Developer 1 | Ayesha Singh |
| Scrum Developer 2 | Arjun Mehta |
| Scrum Developer 3 | Sneha Reddy |
| Scrum Developer 4 | Kartik Iyer |

Vision: To successfully expand the company's established food product portfolio into new international markets by building a digitally-driven, locally-integrated business model that aligns with regional consumer preferences, regulatory requirements, and operational capabilities.

The goal is to deliver a localized, high-quality customer experience through the launch of a fully functional country-specific website and mobile app, supported by a local procurement and supply chain ecosystem, while maintaining the company’s global standards of quality, trust, and sustainability.

This vision supports the company’s broader objective of becoming a globally accessible, regionally rooted food brand by enabling agile entry into new markets, minimizing launch time, and driving long-term customer loyalty through operational excellence and cultural relevance.

Target Group:

Which market segment does the product address?

- Urban, health-conscious individuals aged 20–45

- Digitally active B2C consumers in the new country

- Customers seeking affordable, nutritious packaged food options

Who are the target users and customers?

- Mobile-first users browsing food products

- E-commerce shoppers looking for local sourcing

- Repeat customers of existing product lines in new regions

Needs:

What problem does the product solve?

- Lack of access to trusted international food brands in the local market

- Limited digital availability of healthy packaged food through native platforms

Which benefit does it provide?

- Regionally tailored e-commerce experience

- Locally sourced, globally trusted food products

- Convenience, transparency, and quick delivery

Product:

What product is it?

- A localized e-commerce website and mobile app integrated with supply chain, payments, and delivery systems

- Operational model for local procurement and fulfilment

What makes it desirable and special?

- Combines global brand trust with local sourcing and delivery

- Customized content, language, and payment options for local relevance

Is it feasible to develop the product?

- Yes, using Agile development with cross-functional teams and proven tech stacks (React, Node.js, AWS, etc.)

Value:

How is the product going to benefit the company?

- Establishes the company’s presence in a new high-potential market

- Diversifies revenue streams and scales global operations

What are the business goals?

- Achieve 15% market penetration within the first year

- Build a repeat customer base and enhance brand visibility

- Lower sourcing and fulfilment costs through regional supply chain

What is the business model?

- B2C direct sales through mobile/web platform

- Subscription and loyalty rewards model

- Regional procurement and in-market production to reduce costs

Document 3- User stories

Question 3:

| User Story No | Tasks | Priority |
| --- | --- | --- |
| Value statement As a user…. I want to……. So that I can…. |  |  |
| BV | CP |  |
| Acceptance Criteria |  |  |

Answer: In Agile development, a User Story is a short, simple, and user-focused description of a feature or functionality. It helps the development team understand what the user needs, why they need it, and what value it provides—without prescribing how to build it.

User Story ID: US001 Tasks:4 Priority:1

Value Statement: As a first-time customer, I want to browse food products in my local language and currency, so that I feel comfortable and confident making a purchase.

BV: 500 CP:8

Acceptance Criteria: - Customer installs the application and registers. - Home screen displays categories and food options. - Customer selects a food category, explores the menu, and adds items to the cart. - Proceeds to checkout and confirms the order. - If the item is unavailable, alternative suggestions are provided. - Notifications on promotions and discounts appear during checkout. - In case of network issues, an appropriate error message appears.

User Story ID: US002 Tasks:3 Priority:1

Value Statement: As a customer, I want to pay using local payment methods (UPI, mobile wallets, cards), so that I can complete transactions securely and conveniently.

BV: 200 CP:5

Acceptance Criteria: - Payment screen displays local payment options dynamically based on region. - Transactions are encrypted and processed securely. - Successful payments show order confirmation with order ID and estimated delivery time. - Failed payments return meaningful error messages with retry options. - Transaction logs are stored in user order history.

User Story ID: US003 Tasks:5 Priority:2

Value Statement: As a customer, I want to receive real-time delivery updates, so that I know exactly when my order will arrive.

BV: 100 CP:3

Acceptance Criteria: - Customer receives a push notification when the order is confirmed. - GPS tracking is enabled once the order is dispatched. - Delivery status (e.g., "Out for Delivery", "Delivered") is shown on the order detail screen. - Customers receive SMS or app notifications for delays. - System auto-closes order once delivery is confirmed.

User Story ID: US004 Tasks:4 Priority:2

Value Statement: As a product manager, I want to localize all app content based on regional language preferences, so that users feel culturally connected and supported.

BV: 200 CP:4

Acceptance Criteria: - Application detects region/language on first install or prompts for selection. - All screens display content (menus, buttons, labels) in selected language. - Content matches translations defined in the localization dictionary. - Users can change language settings later from the profile screen. - LTR (Left-to-right) language support is included where needed.

User Story ID: US005 Tasks:6 Priority:1

Value Statement: As an operations team member, I want to onboard and manage local vendors via an admin panel, so that supply chain readiness is ensured before launch.

BV: 100 CP:6

Acceptance Criteria: - Admin user logs into the vendor management dashboard. - New vendor onboarding form includes business license, contact, and material type. - Vendor records are stored and visible in a searchable list. - Admin can approve, reject, or deactivate vendors. - Vendor profile shows material types, delivery zones, and status history. - Notifications are sent to vendors upon status change.

Document 4- Agile PO Experience

Question 4: The Product Owner has a vision of the product keeping the domain/industry experience and the market need.

- Following are the responsibilities of PO in a project

- Market Analysis

- Analysis of market need/demand

- Availability of similar products in the market

- Enterprise Analysis

- Due diligence on the market opportunity

- Product Vision and Roadmap

- Product vision keeping the need analysis in mind

- Product roadmap with high-level features and timeline

- Managing Product Features

- Managing stakeholder expectations and prioritizing needs

- Prioritization of the epics, stories, and features based on criticality and ROI involved

- Managing Product Backlog

- Prioritization of user stories

- Reprioritization based on stakeholders' needs

- Epics planning

- Managing Overall Iteration Progress

- Sprint progress review

- Reprioritization of sprints and epics if needed

- Sprint retrospectives with Business Analyst

- From this project I have learned how to handle sprint meetings such as

- Sprint planning meeting

- Daily scrum meeting

- Sprint review meeting

- Sprint retrospective meeting

- Backlog refinement meeting

- Also, User stories creation and what things will be included in user stories such as

- Story no

- Tasks

- Priority

- Acceptance criteria

- BV & CP value

- In Scrum, a product owner serves as the liaison between multiple areas of an organization. This person communicates with business stakeholders and collaborates closely with Scrum teams to keep all areas of the business informed on a project's development.

- The product owner develops a vision of a product's function and operation, which in turn allows this Scrum team member to define product features and break those features into product backlog items.

Answer: In my project involving the international market expansion of a B2C food industry company, I performed the role of a Product Owner (PO), where I was responsible for defining the product vision, prioritizing features, and ensuring value delivery through Agile practices.

As a Product Owner, I applied my domain knowledge of the food industry and aligned it with local market needs, ensuring that our digital products (website and mobile app) were both regionally relevant and strategically aligned with company goals.

Key Responsibilities I handled as Product Owner:

- Market Analysis

- Conducted in-depth research on consumer behaviour and preferences in the target country.

- Analysed existing competitors offering similar packaged food solutions, identifying gaps in features like regional language support, local payment methods, and real-time delivery tracking.

- Enterprise Analysis

- Carried out due diligence on the new market’s business potential including customer segments, digital adoption rate, and regional sourcing feasibility.

- Evaluated legal, compliance, and regulatory factors to shape our digital and operational product vision.

- Product Vision and Roadmap

- Developed a product vision that focused on localized access to globally trusted food products through an intuitive digital platform.

- Defined a high-level product roadmap with phased feature releases such as onboarding, catalog browsing, payment integration, vendor management, and order tracking.

- Managing Product Features

- Prioritized epics and features based on market urgency, ROI, and regulatory readiness.

- Facilitated ongoing communication between stakeholders (Marketing, Logistics, Compliance) and the Scrum team to align on deliverables and expectations.

- Managing the Product Backlog

- Owned and continuously refined the product backlog, ensuring user stories were detailed, actionable, and prioritized.

- Reprioritized backlog items based on business input, compliance updates, or user feedback from sprint reviews.

- Managing Iteration Progress

- Actively reviewed sprint progress, addressed impediments, and adjusted scope based on business dynamics.

- Conducted sprint retrospectives with the Business Analyst to capture lessons learned and apply them to upcoming iterations.

Agile Ceremonies I Facilitated:

From this project, I gained strong experience in facilitating core Scrum ceremonies, such as:

- Sprint Planning Meeting – Aligning backlog priorities with development capacity

- Daily Scrum Meeting – Monitoring team blockers and progress

- Sprint Review Meeting – Demonstrating deliverables and capturing feedback

- Sprint Retrospective Meeting – Identifying improvement areas with the Scrum team

- Backlog Refinement Meeting – Grooming and adjusting priorities based on feedback

User Story Management Skills:

I also led the creation and refinement of user stories using the following structure:

- Story Number

- Tasks Breakdown

- Priority Level

- Acceptance Criteria aligned with end-user behaviour

- Business Value (BV) and Complexity Points (CP) for estimation and ROI mapping

This structured approach ensured that all backlog items were value-driven, testable, and ready for implementation, enabling smooth sprint execution and stakeholder satisfaction.

Cross-Functional Collaboration:

As a PO, I served as the bridge between business and technology, working closely with:

- Business stakeholders to gather requirements and define value

- Scrum teams to break down product features into deliverable stories

- QA, UX, and Compliance to ensure readiness, completeness, and compliance before deployment

Through this project, I learned how to balance business value, technical feasibility, and user needs to guide a cross-functional Agile team. I developed a clear product vision, prioritized features based on real market demand, and ensured continuous feedback integration, which are the core responsibilities of a successful Product Owner.

Document 5: Product and sprint backlog and product and sprint burndown charts

Question 5:

Product Backlog

| User Story ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |

Sprint Backlog

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |

Product Burndown

Sprint Burndown

Answer: The Product Backlog is a dynamic, prioritized list of all the features, enhancements, bug fixes, technical work, and knowledge acquisition needed to deliver a product. It is:

- Owned by the Product Owner

- Continuously refined and updated as the product evolves

- Prioritized based on business value, market needs, and stakeholder input

Product Backlogs:

| User Story ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US001 | As a first-time customer, I want to browse food products in my local language and currency, so that I feel comfortable and confident making a purchase. | UI design, Localization integration, Currency conversion setup, Unit testing | 1 | 500 | 5 | Sprint 1 |
| US003 | As a returning customer, I want to view my previous orders, so that I can reorder with ease. | Database schema update, API endpoint, UI component, Testing | 2 | 100 | 4 | Sprint 2 |
| US005 | As a customer, I want real-time order tracking, so that I can know the delivery status of my food. | GPS service integration, UI component, Push notifications, Testing | 2 | 200 | 5 | Sprint 3 |
| US006 | As a user, I want to receive promotions and offers during checkout, so that I can save money on my orders. | Offer engine setup, Rules configuration, UI updates, Testing | 2 | 100 | 4 | Sprint 2 |

The Sprint Backlog is a subset of the Product Backlog. It contains the specific items selected for implementation during a particular Sprint, along with a plan to deliver them. It is:

- Owned by the Development Team

- Created during the Sprint Planning meeting

- Used to track daily progress throughout the sprint

Sprint Backlogs:

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US001 | As a first-time customer, I want to browse food products in my local language and currency so that I feel confident making a purchase. | 1. Enable localization settings in app/web 2. Load language strings dynamically 3. Display currency formatting 4. Test on local devices | Dev1 (Frontend) QA1 | In Progress | 13 hours |
| US003 | As a product manager, I want to localize all app content based on language preferences so that users feel supported. | 1. Build language toggle UI 2. Fetch translations from database 3. RTL support (if needed) 4. Unit + functional test | Dev1 BA QA | In Progress | 11 hours |
| US004 | As a customer, I want to receive real-time delivery updates so that I know when my food will arrive. | 1. Add tracking status component 2. GPS location fetch + map API 3. Push notification setup 4. User flow validation | Dev3 QA | To Do | 16 hours |
| US005 | As an operations team member, I want to onboard and manage local vendors via an admin panel so that supply chain readiness is ensured. | 1. Create admin panel UI 2. Build vendor form 3. Implement CRUD logic 4. User access control | Dev4 Dev2 QA | To Do | 20 hours |

Document 6: Sprint meetings

Question 6:

Meeting Type 1: Sprint Planning meeting

| Date |  |
| --- | --- |
| Time |  |
| Location |  |
| Prepared by |  |
| Attendees |  |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |

Other Information

| Observers |  |
| --- | --- |
| Resources |  |
| Special Notes |  |

Meeting Type 2: Sprint review meeting

| Date |  |
| --- | --- |
| Time |  |
| Location |  |
| Prepared by |  |
| Attendees |  |

| Sprint Status | Things to Demo | Quick Updates | What’s next |
| --- | --- | --- | --- |

Meeting Type 3: Sprint retrospective meeting

| Date |  |
| --- | --- |
| Time |  |
| Location |  |
| Prepared by |  |
| Attendees |  |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week “X” (from dd-mm-yyyy to dd-mm-yyyy) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Mon | Tues | Wed | Thurs | Fri | Sat | Sun |
| What did you do yesterday? | Developer 1. Developer 2. Developer 3. |  |  |  |  |  |  |  |
| What will you do today? | Developer 1. Developer 2. Developer 3. |  |  |  |  |  |  |  |
| What (if any) is blocking your progress? | Developer 1. Developer 2. Developer 3. |  |  |  |  |  |  |  |

Answer: Sprint Meetings are structured, time-boxed events in Scrum that facilitate communication, alignment, and progress tracking within the Scrum team. Each meeting has a specific purpose and timing within the sprint cycle. There are typically five key sprint meetings in Scrum:

| Sprint Meeting | When it happens | Purpose | Why it’s important: |
| --- | --- | --- | --- |
| Sprint Planning | At the start of the sprint | Plan and select backlog items for the sprint | Aligns the team on sprint goals, prevents scope creep, promotes realistic workload estimation |
| Daily Scrum (Stand-up) | Every day during the sprint | Track daily progress, identify blockers | Keeps the team synchronized, promotes accountability and transparency, surfaces problems early |
| Backlog Refinement | Mid-sprint (ongoing) | Update and prepare future backlog items | Keeps the backlog organized and prioritized, helps the team better estimate future work, ensures clarity and shared understanding |
| Sprint Review | At the end of the sprint | Demonstrate completed work to stakeholders | Validates deliverables, allows quick feedback loops, builds trust and transparency |
| Sprint Retrospective | After the Sprint Review | Reflect and improve the process/teamwork | Fosters a culture of continuous improvement, identifies team dynamics or process issues, improves future sprint efficiency and morale |

All sprint meetings together form the heartbeat of Scrum. They ensure the team:

- Knows what to work on

- Stays aligned daily

- Learns from feedback

- Continuously improves delivery and collaboration

Meeting Type 1: Sprint Planning meeting

| Date | July 8, 2025 |
| --- | --- |
| Time | 10:00 AM – 12:00 PM IST |
| Location | Conference Room B / Microsoft Teams (Hybrid) |
| Prepared by | Priya Sharma (Scrum Master) |
| Attendees | Rahul Verma (Product Owner), Arjun Mehta (Dev), Ayesha Khan (Dev), Sneha Reddy (Dev), Kartik Iyer (Dev), QA Lead, Business Analyst |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Welcome and sprint context overview | Scrum Master | 10 mins |
| Review of Product Backlog and sprint goal | Product Owner | 20 mins |
| Discussion and selection of User Stories | Team + PO | 30 mins |
| Task breakdown and estimation | Development Team | 30 mins |
| Finalization of Sprint Backlog | Scrum Master + Team | 15 mins |
| Identification of risks and dependencies | Team | 10 mins |
| Q&A / Clarifications | Open Floor | 5 mins |

Other Information

| Observers | Compliance Officer (to validate regulatory sprint items) Marketing Lead (to ensure alignment with launch campaigns) |
| --- | --- |
| Resources | Jira Sprint Board Product Backlog document Definition of Done (DoD) checklist Velocity chart of previous sprint Market requirements document (localized features) |
| Special Notes | Focus of this sprint: Local language UI, local payments, vendor onboarding module Sprint duration: 2 weeks (July 8 – July 22, 2025) Dependencies with vendor onboarding API to be discussed further in next refinement session Ensure UX designer review for story US004 (Localization toggle) before Day 3 of sprint |

Meeting Type 2: Sprint review meeting

| Date | July 22, 2025 |
| --- | --- |
| Time | 3:00 PM – 4:30 PM IST |
| Location | Conference Room B / Microsoft Teams |
| Prepared by | Priya Sharma (Scrum Master) |
| Attendees | Rahul Verma (Product Owner), Ayesha Khan (Dev), Arjun Mehta (Dev), Sneha Reddy (Dev), Kartik Iyer (Dev), QA Lead, Business Analyst, Marketing Lead, Operations Manager, Compliance Officer |

Sprint Status:

- Sprint Goal: Deliver the localized product browsing experience, basic checkout flow, local payment integration, and vendor onboarding portal.

- Sprint Duration: July 8 – July 22, 2025

- Sprint Velocity: 28 story points completed

- Stories Completed: US001, US002, US004, US005

- Stories Carried Forward: US003 (partially complete due to API delay)

Things to Demo:

| Feature/User Story | Description |
| --- | --- |
| US001 – Localized Product Browsing | Multi-language support and regional currency display |
| US002 – Payment Gateway Integration | UPI, Wallet, and card checkout flow |
| US004 – Language Preferences UI | Language toggle and RTL layout handling |
| US005 – Vendor Onboarding Admin Panel | Form-based onboarding and vendor listing management |

Quick Updates:

- UAT for US002 completed with minor feedback to be fixed in Sprint 2.

- Vendor onboarding data successfully passed to backend.

- QA reported 100% test case pass rate on localized UI.

- Delay in third-party delivery tracking API integration affected US003.

What’s Next:

- Complete and test US003 (Delivery Status) in early Sprint 2.

- Begin work on:

- Loyalty rewards feature

- Notification management system

- Regional logistics integration

- Retrospective scheduled for July 23, 2025.

- Product Owner to reprioritize backlog based on stakeholder feedback during review.

Meeting Type 3: Sprint retrospective meeting

| Date | July 23, 2025 |
| --- | --- |
| Time | 11:00 AM – 12:00 PM IST |
| Location | Conference Room B / Microsoft Teams |
| Prepared by | Priya Sharma (Scrum Master) |
| Attendees | Rahul Verma (Product Owner), Ayesha Khan (Dev), Arjun Mehta (Dev), Sneha Reddy (Dev), Kartik Iyer (Dev), QA Lead, Business Analyst |

Agenda:

- Welcome and objective of the retrospective

- Review of Sprint 1 goal and outcomes

- Team feedback: What went well and what didn’t

- Brainstorming questions and improvement suggestions

- Action items for Sprint 2

- Wrap-up

What Went Well

- Clear sprint goals and well-prioritized backlog

- Strong collaboration between QA and developers led to smooth UAT

- Local payment integration (UPI & Wallets) completed on time and passed testing

- Vendor onboarding module fully functional and demoed successfully

- Language localization UI was appreciated by the business team

What Didn’t Go Well

- Delay in delivery tracking (US003) due to third-party API dependency

- Missed a few UI bugs early due to unclear test cases for RTL layout

- Sprint Planning ran longer than scheduled

- Some developers faced environment sync issues on Day 2 of the sprint

Questions

- How can we better manage third-party integration delays in future sprints?

- Should we introduce a buffer for external dependencies?

- Can we automate more of the UI testing to catch localization bugs earlier?

- Do we need a mid-sprint sync-up with stakeholders for early feedback?

Reference

- Sprint 1 Review Meeting Notes

- Jira Sprint Board – Sprint 1

- QA UAT Report – Localization and Checkout

- API Integration Status Report – Delivery Module

- Definition of Done (DoD) checklist

Meeting Type 4: Daily Stand-up meeting

Date: 22-07-2025 to 28-07-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Developer 1 – Ayesha | Built and tested UI for rewards screen | Finalized responsive layout | Fixed minor bugs in localization toggle |  |  |
|  | Developer 2 – Arjun | Integrated vendor data APIs | Completed backend validation logic | Reviewed payment module logs |  |  |
|  | Developer 3 – Sneha | Wrote UAT test cases for US005 | Executed test plan for loyalty | Logged 2 minor issues |  |  |
| What will you do today? | Developer 1 – Ayesha | Start UI for loyalty history page | Sync with UX for design review | Begin unit testing for rewards |  |  |
|  | Developer 2 – Arjun | Begin API work for loyalty rewards | Write test cases for rewards API | Support frontend integration |  |  |
|  | Developer 3 – Sneha | Continue testing US005 scenarios | Validate loyalty APIs with Postman | Re-test resolved UI bugs |  |  |
| What (if any) is blocking your progress? | Developer 1 – Ayesha | None | None | Awaiting final icons from design team |  |  |
|  | Developer 2 – Arjun | Waiting for DB credentials | None | None |  |  |
|  | Developer 3 – Sneha | Delayed API response for rewards | None | UI test data missing for edge case |  |  |