Project Title: Travel and Compliance Hub

Document 1: Definition of Done (DOD)

The Definition of Done (DoD) is a checklist we used to ensure that every user story meets quality and completeness standards before marking it complete. Our DoD includes:

- User Story acceptance criteria met

- Code developed and tested

- QA validated the feature

- Product Owner approval

- Unit tests written and passed

- Feature deployed on test server

- Peer code review completed

- Documentation updated

- No critical bugs

- UI reviewed by UX Designer

- Work integrated with existing modules

- Security compliance check passed

- Performance testing completed

- Feature flagged (if rollout needed)

- Code coverage maintained above 80%

- Sprint demo conducted

- Code committed and pushed to repository

- All linked Jira tasks moved to "Done"

Document 2: Product Vision

| Scrum Project Name: | Travel and Compliance Hub |  |  |
| --- | --- | --- | --- |
| Venue: | Pune |  |  |
| Date: | 14-07-2025 |  | Duration: 2 Weeks |
| Client: | World Foods LLP |  |  |
| Stakeholder list: | Amit Dhanyakumar Chordia (Project Sponsor) | Vickykumar Sancheti (Scrum Master) | Kunal Kadambande (Product Owner) |
|  | HR Department Representative | Admin Department Representative |  |
| Scrum Team |  |  |  |
| Scrum Master: | Vickykumar Sancheti |  |  |
| Product owner: | Kunal Kadambande |  |  |
| Scrum Developer 1: | Ajay Sharma (Frontend) |  |  |
| Scrum Developer 2: | Priya Deshmukh (Backend) |  |  |
| Scrum Developer 3: | Rakesh Mehta (QA) |  |  |
| Scrum Developer 4: | Sneha Kulkarni (DevOps) |  |  |
| Scrum Developer 5: | Rohit Verma (Full Stack) |  |  |
| Scrum Developer 6: | Anjali Patil (UX Designer) |  |  |
| Scrum Developer 7: | Nikhil Bansode (API Integration) |  |  |

| Vision: To create a cloud-based, scalable Travel and Compliance Hub that replaces all manual, email-based, and spreadsheet-driven travel approval workflows with a centralized, real-time, automated system. |  |  |  |
| --- | --- | --- | --- |
| Target group Which market segment does the product address? 1.Medium to large-scale enterprises where employees frequently travel for business. Who are the target users and customers? 1.Internal users: Employees, Managers, HR teams, Admin department, Compliance Officers. External users: Auditors, IT support (for integration and reporting). | Needs What problem does the product solve? 1.Missed travel document expiry alerts 2.Delayed approvals due to email overload 3.Manual reporting and document tracking 4.Poor transparency and audit readiness Which benefit does it provide? The system streamlines travel request management, reduces administrative burden, minimizes delays in approvals, ensures timely document renewals, and improves overall compliance tracking and employee experience. | Product What product is it? A digital travel and compliance platform with guided forms, document uploads, role-based dashboards, approval workflows, and expiry notifications. What makes it desirable and special? Its real-time alerts, integration with HRMS, mobile-friendly design, and role-based dashboards make it a practical and modern solution for travel and compliance management. Is it feasible to develop the product? Yes, it is feasible. The solution uses standard web technologies, Agile methodology, and cloud infrastructure already supported by the client. | Value How is the product going to benefit the company? It improves efficiency, reduces approval delays, lowers compliance risks, and ensures smoother audits by digitizing and automating the travel request lifecycle. What are the business goals? To implement the system within 3 months, reach 90% user adoption in 4 months, and achieve 80% user satisfaction, supporting the organization’s digital transformation efforts. What is the business model? This is an internal enterprise application intended to streamline company operations. Future potential: can be white-labeled and sold as SaaS to similar businesses in the future. Reduces approval time by 50%, improves audit readiness, saves admin effort, ensures document validity, and improves user satisfaction. |

Document 3: User Stories

| User Story No: 1 | Tasks: 4 | Priority: High |
| --- | --- | --- |
| As an Employee I want to submit travel requests online So that I can get approvals faster and track them easily |  |  |
| BV: 500 | CP: 05 |  |
| Acceptance Criteria: Request form includes destination, purpose, and dates Upload option for travel documents is available Request visible to manager and HR Email confirmation is sent upon submission |  |  |

| User Story No: 2 | Tasks: 4 | Priority: High |
| --- | --- | --- |
| As a Manager I want to approve or reject travel requests So that I can ensure policy compliance and control department budget |  |  |
| BV: 600 | CP: 08 |  |
| Acceptance Criteria: Manager dashboard displays pending requests Remarks are mandatory for rejection Status updates in real-time Requester receives approval/rejection notification |  |  |

| User Story No: 3 | Tasks: 3 | Priority: Medium |
| --- | --- | --- |
| As HR/Admin I want to get alerts before passport/visa expiry So that I can avoid last-minute renewal issues |  |  |
| BV: 550 | CP: 05 |  |
| Acceptance Criteria: Alerts triggered 30 days before expiry Email notification sent to employee and admin Status visible on HR dashboard |  |  |

| User Story No: 4 | Tasks: 3 | Priority: Medium |
| --- | --- | --- |
| As a Compliance Officer, I want to view audit logs of travel requests So that I can ensure audit preparedness |  |  |
| BV: 450 | CP: 08 |  |
| Acceptance Criteria: Each action is time-stamped and recorded Logs can be exported in standard formats Only authorized users can view logs |  |  |

| User Story No: 5 | Tasks: 3 | Priority: Low |
| --- | --- | --- |
| As an Employee I want to check the real-time status of my request So that I can follow up if needed |  |  |
| BV: 400 | CP: 03 |  |
| Acceptance Criteria: Status is shown on the employee dashboard Notifications sent on status updates Estimated approval time is shown |  |  |

| User Story No: 6 | Tasks: 4 | Priority: High |
| --- | --- | --- |
| As an Admin I want to upload and store travel documents So that I can access them quickly during audits |  |  |
| BV: 600 | CP: 13 |  |
| Acceptance Criteria: Uploads include metadata (expiry, employee name) System supports search and filters Access is role-based and secure |  |  |

| User Story No: 7 | Tasks: 3 | Priority: Medium |
| --- | --- | --- |
| As an Employee/Manager I want to use the platform on mobile So that I can submit or approve requests on the go |  |  |
| BV: 300 | CP: 08 |  |
| Acceptance Criteria: UI adapts to mobile screen sizes All key features work on mobile No layout/alignment issues |  |  |

| User Story No: 8 | Tasks: 3 | Priority: High |
| --- | --- | --- |
| As a Admin I want to define approval flows by roles So that I can reduce manual follow-ups and errors |  |  |
| BV: 550 | CP: 13 |  |
| Acceptance Criteria: Admin can configure approval logic Requests are auto-routed based on hierarchy Escalation is triggered after timeout |  |  |

Document 4: Agile PO Experience

As the Product Owner (PO) for the Travel and Compliance Hub project, I was responsible for defining the vision, managing the backlog, ensuring alignment with business goals, and delivering incremental value through Agile practices. My role required continuous collaboration between business stakeholders and the Scrum team, ensuring transparency, adaptability, and quality throughout the project lifecycle.

Responsibilities and Activities

1. Market Analysis

- Conducted research to understand the demand for automated travel and compliance systems.

- Analysed competitor products in the market and identified gaps in HRMS integration, real-time alerts, and document compliance features.

- Assessed organizational readiness for digital transformation in travel workflows.

2. Enterprise Analysis

- Performed a feasibility study to evaluate cost-benefit analysis of automating manual processes.

- Verified that the proposed solution aligns with enterprise goals such as reducing approval times, improving compliance, and enhancing transparency.

3. Product Vision and Roadmap

- Defined the product vision: “To build a centralized, cloud-based system to manage employee travel requests and compliance processes efficiently.”

- Developed a product roadmap including high-level epics:

  - Travel Request Management

  - Approval Workflow Automation

  - Expiry Alerts & Compliance Notifications

  - Secure Document Storage

  - Real-Time Dashboards

  - Audit Logs

  - Mobile Responsiveness

- Assigned timelines and mapped features across multiple sprints for iterative delivery.

4. Managing Product Features

- Collected requirements through stakeholder interviews and JAD sessions.

- Converted requirements into epics, user stories, and tasks.

- Used MoSCoW prioritization to classify features into Must-Have, Should-Have, Could-Have, and Won’t-Have categories.

- Evaluated ROI for each feature and prioritized accordingly.

5. Managing Product Backlog

- Created and maintained the product backlog in Jira.

- Broke down epics into user stories with BV (Business Value) and CP (Complexity Points) using Planning Poker and Fibonacci Series.

- Regularly performed backlog refinement sessions to clarify acceptance criteria and reprioritize based on stakeholder feedback.

6. Sprint Management

- Facilitated Sprint Planning Meetings to finalize user stories for each sprint and ensure proper estimation.

- Participated in Daily Scrum Meetings to monitor progress and address blockers.

- Conducted Sprint Review Meetings to demo completed features to stakeholders.

- Organized Sprint Retrospectives to identify improvements and implement them in subsequent sprints.

7. Collaboration and Communication

- Acted as the single point of contact between stakeholders and the Scrum team.

- Ensured all changes in requirements were communicated clearly and updated in the backlog.

- Maintained transparency on progress through Jira dashboards and reports.

8. Quality Assurance and Acceptance

- Defined acceptance criteria for each user story.

- Verified delivered features against acceptance criteria before marking them complete.

- Ensured the Definition of Done (DoD) was adhered to, including peer reviews, unit testing, and QA sign-off.

9. Risk and Dependency Management

- Identified risks such as data migration challenges, policy changes, and integration delays.

- Worked on mitigation strategies like early testing and stakeholder alignment meetings.

- Managed dependencies with HRMS and hosting vendors to ensure smooth integration.

Meetings and Agile Ceremonies Conducted

- Sprint Planning – Prioritized stories and assigned tasks.

- Daily Scrum – Monitored progress and resolved blockers.

- Sprint Review – Showcased completed functionality to stakeholders.

- Sprint Retrospective – Captured lessons learned and planned improvements.

- Backlog Refinement – Updated and clarified stories for upcoming sprints.

Learnings as PO

- Effective prioritization techniques like MoSCoW and MVP for maximum ROI.

- Importance of clear user stories with acceptance criteria and proper estimation.

- Handling scope changes and reprioritization without impacting sprint goals.

- Enhanced skills in stakeholder communication, risk management, and Agile ceremonies.

- Gained expertise in Jira for backlog management, sprint tracking, and burndown reporting.

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog:

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Travel request submission | 4 | High | 500 | 05 | Sprint 1 |
| 2 | Manager approval workflow | 4 | High | 600 | 08 | Sprint 1 |
| 3 | Document expiry alerts | 3 | Medium | 550 | 05 | Sprint 2 |
| 4 | Audit log tracking | 3 | Medium | 450 | 08 | Sprint 2 |
| 5 | Travel status tracking | 3 | Low | 400 | 03 | Sprint 3 |
| 6 | Document upload & storage | 4 | High | 600 | 13 | Sprint 3 |
| 7 | Mobile-friendly UI | 3 | Medium | 300 | 08 | Sprint 4 |
| 8 | Custom approval hierarchy | 3 | High | 550 | 13 | Sprint 4 |

Sprint Backlog (Sprint 1):

| User story ID | User story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| 1 | Travel request submission | Design UI, Develop backend, Enable upload, Email setup | Ajay Sharma, Priya Deshmukh | In Progress | 16 hrs |
| 2 | Manager approval workflow | Build dashboard, Approval logic, Notification, Testing | Rohit Verma, Rakesh Mehta | Not Started | 20 hrs |

Sprint Backlog (Sprint 2):

| User story ID | User story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| 3 | Document expiry alerts | Configure alerts, Cron job, Email template | Sneha Kulkarni | Not Started | 14 hrs |
| 4 | Audit log tracking | Create DB schema, Track actions, Export feature | Nikhil Bansode | Not Started | 16 hrs |

Sprint Burndown Chart -

Product Burndown Chart –

Document 6: Sprint Meetings

Meeting Type 1: Sprint Planning meeting

| Date | 01-06-2025 |
| --- | --- |
| Time | 10:00 AM – 12:30 PM |
| Location | World Foods LLP Conference Room |
| Prepared By | Kunal Kadambande (Product Owner) |
| Attendees | Scrum Master: Vickykumar Sancheti Product Owner: Kunal Kadambande Developers: Ajay Sharma, Priya Deshmukh, Rakesh Mehta, Sneha Kulkarni, Rohit Verma, Anjali Patil, Nikhil Bansode |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Sprint Goal Discussion | Scrum Master | 20 mins |
| Review Product Backlog | Product Owner | 30 mins |
| Select Stories for Sprint | Development Team | 30 mins |
| Task Breakdown | Developers + PO | 40 mins |
| Estimation & Assignment | Scrum Master | 30 mins |

Other Information: Sprint 1 will include user stories: Travel request submission, Manager approval.

| Observers | HR Stakeholder (Amit Chordia) |
| --- | --- |
| Resources | Jira board, Burndown templates, Laptop, Projector |
| Special Notes | Emphasis on delivering core travel request features in Sprint 1 |

Meeting Type 2: Sprint Review Meeting

| Date | 15-06-2025 |
| --- | --- |
| Time | 10:00 AM – 11:00 AM |
| Location | MS Teams |
| Prepared By | Vickykumar Sancheti |
| Attendees | Product Owner, Scrum Master, Development Team, Stakeholders |

| Sprint status | Sprint 1 completed successfully. |
| --- | --- |
| Things to Demo | 1.Travel Request Form (UI + Backend Integration) 2.Manager Approval Flow |
| Quick updates | Email notifications pending for next sprint. |
| What is next | Start working on Document Expiry Alerts and Audit Logs in Sprint 2. |

Meeting Type 3: Sprint retrospective meeting

| Date | 15-06-2025 |
| --- | --- |
| Time | 11:30 AM – 12:30 PM |
| Location | MS Teams |
| Prepared By | Kunal Kadambande |
| Attendees | Scrum Team |

| Agenda | What went well | What did not go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Review what went well and what did not | On-time delivery of planned user stories | Delay in email notification configuration | How can QA be involved earlier in development? | Jira board and Sprint 1 backlog |
| Define action items for improvement | Clear communication during daily stand-ups | Some tasks underestimated |  |  |

Meeting Type 4: Daily Stand-up Meeting

Week 1 (from 01-06-2025 to 07-06-2025)

| Question | Name/Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Dev 1 (Ajay) | UI Design | Form Layout | API Connect | Testing | Bug Fixes | NA | NA |
|  | Dev 2 (Priya) | DB Setup | Backend Dev | Data Binding | Integration | Unit Test | NA | NA |
|  | Dev 3 (Rohit) | Setup Env | Test Cases | QA Review | Testing | Retest | NA | NA |
| What will you do today? | Dev 1 | API Link | Validation | Error Fix | Integration | Deployment | NA | NA |
|  | Dev 2 | Validation | Logic Fix | Unit Tests | Email Logic | Bug Fix | NA | NA |
|  | Dev 3 | Smoke Test | Test Review | Execute Test | Defect Log | Retest | NA | NA |
| What (if any) is blocking you? | Dev 1 | None | None | Pending API | None | None | NA | NA |
|  | Dev 2 | None | DB Issue | None | None | None |  |  |
|  | Dev 3 | Env Delay | None | None | None | None | NA | NA |