# Business Case Document: Migration from ExShare to RDOS

Why is this project initiated?

Reason for Initiation:

The Migration from ExShare to RDOS project is initiated due to the following key drivers:

- Obsolescence of Existing System (ExShare):
ExShare has been in use for over 1 years and lacks critical modern capabilities such as advanced search, audit logging, and integration with enterprise authentication systems.

- Security & Compliance Requirements:
The current system does not meet the latest IT security policies or regulatory compliance standards (such as audit trails and access logs), creating potential risk exposure.

- Operational Inefficiencies:
Users report difficulties in locating, tagging, and managing documents efficiently in ExShare, leading to productivity loss and support overhead.

- Integration Needs:
RDOS offers seamless integration with Active Directory (SSO), internal reporting tools, and backup systems—something not feasible with ExShare.

- Strategic Alignment:
The migration aligns with the organization’s IT modernization roadmap, aiming to standardize platforms, reduce maintenance costs, and improve system scalability.

- Vendor & Support Limitations:
ExShare’s support model has become limited or cost-prohibitive, while RDOS has robust vendor support and documentation.

Current Problems with ExShare:

- Outdated User Interface & Poor Usability

  - The UI is not intuitive, making it difficult for users to upload, tag, or retrieve documents efficiently.

  - Lacks modern features like drag-and-drop upload or advanced filters.

- Limited Search Functionality

  - Users struggle to find documents due to limited metadata support and basic keyword search only.

  - No filtering by tags, date range, or document type.

- No Version Control or Change History

  - ExShare lacks built-in version control, increasing the risk of data loss or overwriting important documents.

  - Users cannot track changes over time.

- No Real-Time Audit Trails

  - The system does not log who accessed, modified, or deleted documents.

  - This is a major gap for security audits and compliance.

- Lack of Integration Capabilities

  - Cannot be integrated with enterprise systems such as Active Directory, reporting dashboards, or data backup tools.

  - Leads to manual processes and duplication of efforts.

- Poor Support and Maintenance

  - Vendor support is either discontinued or expensive.

  - Internal teams struggle with customization or issue resolution.

- High Operational Overhead

  - Frequent helpdesk requests and workaround implementations drain IT and support resources.

  - Maintenance and upgrades are time-consuming and costly.

- Security Vulnerabilities

  - The platform does not align with current cybersecurity standards (e.g., access control, encryption, secure APIs).

  - This could expose sensitive organizational data.

Problems Solved by RDOS Migration

| Problem in ExShare | How RDOS Solves It |
| --- | --- |
| 1. Outdated User Interface & Poor Usability | RDOS offers a modern, intuitive interface with drag-and-drop, dashboards, and tooltips |
| 2. Limited Search Functionality | Advanced search options with filters, tags, and full-text indexing |
| 3. No Version Control or Change History | Built-in version control and history tracking for all documents |
| 4. No Real-Time Audit Trails | Comprehensive audit logs with timestamps, user IDs, and activity tracking |
| 5. Lack of Integration Capabilities | Integrates with Active Directory, reporting tools, and backup systems |
| 6. Poor Support and Maintenance | Vendor-backed support, frequent updates, and easier internal configuration |
| 7. High Operational Overhead | Automation reduces manual intervention; less IT support required |
| 8. Security Vulnerabilities | Enhanced role-based access, encrypted data storage, and secure APIs |

Out of 8 major problems, the RDOS migration project directly solves all 8, bringing the system in line with modern expectations and enterprise IT standards.

Resources Required

People Resources

| Role | Responsibility |
| --- | --- |
| Business Analyst (BA) | Requirement gathering, stakeholder communication, documentation |
| Project Manager (PM) | Project planning, monitoring, risk management |
| Solution Architect | Designing system architecture and integration roadmap |
| Developers (Backend & UI) | Development and customization of RDOS |
| QA/Test Engineers | Prepare and execute test cases, validate migration success |
| Migration Specialist | Plan and execute data migration from ExShare to RDOS |
| IT Security Analyst | Ensure compliance with security standards and perform risk reviews |
| End Users (Pilot Group) | Participate in UAT (User Acceptance Testing) |
| Training & Support Staff | Create training materials, deliver user training and post-go-live support |

Time Resources

- Project Duration: Estimated 4–6 months

- Major Phases:

  - Requirement Analysis – 2 weeks

  - Design & Planning – 3 weeks

  - Development & Configuration – 2 months

  - Testing & Validation – 3 weeks

  - User Training & Go-Live – 2 weeks

  - Post-Implementation Support – 2 weeks

Budget Resources

| Cost Item | Estimated Cost (INR) |
| --- | --- |
| Hardware Infrastructure | ₹ 1,00,000 |
| RDOS Software Licensing | ₹ 2,50,000 |
| Development and Integration | ₹ 1,50,000 |
| Training and Change Management | ₹ 50,000 |
| Data Migration & Validation | ₹ 75,000 |
| Contingency & Miscellaneous | ₹ 25,000 |
| Total Estimated Budget | ₹ 6,50,000 |

Other Resources

- Software Tools: Migration utilities, reporting tools, testing frameworks

- Documents: Current system documentation, compliance checklists, training guides

- External Inputs: Site visits, vendor demos, analyst reports (Dataquest, Gartner, etc.)

Organizational Change Required

Overview of Organizational Change

The migration from ExShare to RDOS will require a moderate level of organizational change, primarily in the following areas:

1. Process Changes

- Users will follow new document upload, tagging, search, and access protocols.

- Version control and audit log features will become part of standard workflows.

- Approval and access request processes may be updated to align with RDOS permissions structure.

2. People & Roles

- End Users: Need to adapt to the new interface, features, and workflows.

- IT & Support Teams: Will take on new responsibilities related to RDOS maintenance, user access management, and issue resolution.

- Training: Mandatory short-term training programs for all user groups to ensure successful adoption.

3. Technology Adoption

- Shift from a legacy platform to a modern system with integrated features will require:

  - Updated SOPs (Standard Operating Procedures)

  - Data migration and cleansing readiness

  - Familiarity with role-based access and security protocols

4. Change Management Activities

- Communication Plan: Regular updates, rollout timeline, and expectations shared across departments

- Training Sessions: Scheduled hands-on training and video guides for various user levels

- User Support: Dedicated helpdesk and FAQ documents during transition phase

- Pilot Group Testing: Selected users will test the system before full deployment

Level of Change Impact

| Area | Change Level | Notes |
| --- | --- | --- |
| End-User Workflow | Moderate | Some processes change, training is needed |
| IT Infrastructure | Low to Moderate | System integration and support responsibilities |
| Data Handling | High | Metadata, versioning, and audit become essential |
| Security/Compliance | High | Enhanced access controls and audit logging |

Time Frame to Recover Return on Investment (ROI)

`

ROI Recovery Estimate

Based on the project scope, cost estimates, and anticipated operational improvements, the expected time frame to recover ROI is approximately 12 to 18 months post-implementation.

ROI Recovery Justification

| Cost Area | Savings/Benefits Post-Migration |
| --- | --- |
| Manual effort in document handling | 40–50% reduction in search, retrieval, and tagging time |
| IT maintenance & support | Reduced incidents, faster resolution, lower support resource allocation |
| Compliance & audit efforts | Automated audit trails reduce audit preparation time by 60% |
| User productivity | Improved UI and faster access boosts task efficiency across departments |
| Licensing and vendor costs | Consolidated software reduces ongoing licensing overhead |

Estimated Payback Period

| Initial Investment | ₹ 6,50,000 (INR) |
| --- | --- |
| Annual Estimated Savings | ₹ 4,00,000 – ₹ 5,50,000 |
| Payback Period | 12 – 18 months (based on usage and adoption) |

Factors That Influence ROI Recovery

- Adoption rate by end users

- Effective training and support during transition

- Reduction in support tickets and manual rework

- Compliance efficiencies during audits

- System uptime and performance

Conclusion

If successfully implemented and adopted, the organization can expect to fully recover its investment within 1 to 1.5 years, with net operational gains continuing well beyond that period.

How to Identify Stakeholders for the ExShare to RDOS Migration Project

Identifying stakeholders involves recognizing all individuals, groups, or entities who are affected by, influence, or have an interest in the project. Here's a step-by-step approach:

1. Review the Project Scope

- Understand the systems, processes, and departments impacted by the migration.

- Ask: Who uses ExShare? Who will use RDOS? Who supports it?

2. Consult with Leadership and Project Sponsors

- Meet with department heads and the project sponsor.

- They can highlight key individuals or groups that need to be involved or informed.

3. Map Out Functional Areas

- Identify roles from:

  - Business Units (who use the documents daily)

  - IT Teams (infrastructure, support, security)

  - Compliance & Legal (data access, audit requirements)

  - Training & Communications (for rollout and adoption)

4. Use a Stakeholder Analysis Matrix

- Categorize stakeholders by:

  - Interest level (How affected are they?)

  - Influence level (Can they impact decisions or adoption?)

- Common categories:

  - High influence, high interest → Manage closely

  - High influence, low interest → Keep satisfied

  - Low influence, high interest → Keep informed

  - Low influence, low interest → Monitor only

5. Leverage Documentation & Past Issues

- Review:

  - ExShare support tickets

  - Audit reports

  - Training logs

  - Previous migration efforts

- This helps uncover both frequent users and pain points.

6. Validate with Stakeholder Interviews or Surveys

- Ask users: What do you use ExShare for? What challenges do you face?

- This uncovers key user groups and expectations early.

| Stakeholder Type | Examples |
| --- | --- |
| Executive Sponsor | CIO, VP of Operations |
| Users | Department staff who upload/download files |
| IT Support | Admins managing ExShare and RDOS systems |
| Security | InfoSec team reviewing access controls |
| Compliance | Auditors, legal team |
| Project Team | BA, PM, developers, testers |

Document 2: Business Analyst (BA) Strategy – Project Execution Approach

1.  Project Understanding & Initiation

- Objective: Understand project scope, goals, constraints, and high-level requirements.

- Key Actions:

  - Meet with sponsor/stakeholders to clarify objectives.

  - Review existing documentation, contracts, or process flows.

  - Identify stakeholders and initiate stakeholder mapping.

2. Elicitation Techniques

To gather detailed requirements, apply appropriate elicitation techniques based on stakeholder type:

| Technique | When/Why Used |
| --- | --- |
| Interviews | One-on-one insights with key stakeholders |
| Workshops/Focus Groups | Collaborative sessions with cross-functional teams |
| Document Analysis | Reviewing current systems (ExShare) and SOPs |
| Observation (Job Shadowing) | Understand how end users interact with current system |
| Surveys/Questionnaires | Gather input from a wider audience efficiently |
| Prototyping | Visual walkthrough of proposed features (if needed) |

3.  Stakeholder Analysis (RACI/ILS)

- Create a RACI Matrix to define:

  - Responsible, Accountable, Consulted, Informed roles

- ILS (Influence/Level of Support) Analysis:

  - Identify stakeholder power, interest, and support level

  - Helps tailor communication and involvement strategies

4.  Documents to Prepare

| Document | Purpose |
| --- | --- |
| Business Case | Justify project need, cost, benefits |
| Stakeholder Register & RACI | Identify and categorize stakeholders |
| Business Requirements Document (BRD) | List high-level business needs |
| Functional Specification Document (FSD) | Define detailed functionality expected from RDOS |
| Requirements Traceability Matrix (RTM) | Trace requirements through development and testing |
| Change Request Form | Track and manage scope changes |
| UAT Sign-Off / Project Acceptance Form | Formal client approval post-testing |

5.  Document Approval Process

- Draft reviewed internally by BA team

- Walkthrough with stakeholders

- Collect feedback via track changes/comments

- Update and freeze the final version

- Send for formal approval (email or e-signature)

- Store in centralized repository (e.g., SharePoint, Confluence)

6.  Client Approvals & Sign-Offs

- Maintain a Review & Approval Log

- Secure approvals at:

  - Requirement Finalization (BRD)

  - Functional Confirmation (FSD)

  - UAT Completion

- Use formal acceptance forms and documented meeting minutes

7. Communication Channels

| Channel | Purpose |
| --- | --- |
| Email | Formal communication/document exchange |
| MS Teams / Slack | Daily queries, team discussions |
| Weekly Reports | Status updates to stakeholders |
| JIRA / Trello | Track tasks, changes, and progress |
| Review Meetings | Walkthroughs and alignment discussions |

8.  Change Request Handling

- Receive CR form from user/stakeholder

- Log into change tracker (e.g., JIRA)

- Perform impact analysis (scope, time, cost)

- Get approval from sponsor/PM

- Update BRD/FSD and RTM

- Inform developers and QA

- Document closure post-implementation

9.  Project Progress Updates to Stakeholders

- Weekly status reports with:

  - Task progress

  - Risks/issues

  - Completed milestones

- Monthly stakeholder meetings

- Dashboards (if tool available)

10.  User Acceptance Testing (UAT) & Sign-Off

- Prepare UAT Plan & Test Cases

- Coordinate UAT execution with business users

- Capture feedback and fix defects

- Conduct final walkthrough

- Obtain Client Project Acceptance Form with signatures

- Archive UAT results and closure documentation

Functional Specification Document (FSD)

1. Project Details

| Field | Details |
| --- | --- |
| Project Name | Migration from ExShare to RDOS |
| Customer Name | ICE Data Services |
| Project Version | v1.0 |
| Project Sponsor | ICE Data Services |
| Project Manager | Ramakrishna Manavarapu |
| Project Initiation Date | 17/01/2025 |

2. Functional Requirements Specification

| Req ID | Req Name | Req Description | Priority |
| --- | --- | --- | --- |
| FR0001 | Login | User should be able to login to the application to perform inventory operations. | 10 |
| FR0002 | File Upload | System must allow users to upload PDF, Word, and Excel files to categorized folders. | 9 |
| FR0003 | Access Control | Admin must be able to define role-based access for document visibility and modification. | 10 |
| FR0004 | Search Function | Users must be able to search documents using metadata (title, tags, date). | 8 |
| FR0005 | Version Control | System should track and display version history for each document. | 7 |

3. Assumptions

- Users will be onboarded via Active Directory or LDAP.

- Network access to RDOS is secure and compliant.

- Browsers supported: Chrome, Edge, Firefox.

4. Non-Functional Requirements (NFRs)

| NFR ID | Description |
| --- | --- |
| NFR001 | System response time must be < 2 seconds. |
| NFR002 | Uptime should be 99.5% monthly. |
| NFR003 | Data encryption at rest and in transit. |
| NFR004 | Compatible with both desktop and tablet devices. |

Requirement Traceability Matrix (RTM): Migration from ExShare to RDOS

| Req ID | Req Name | Req Description | Design | D1 | T1 | D2 | T2 | UAT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR0001 | Login | User must be able to login to access the application. | Yes | Pending | No | Yes | Yes | YES |
| FR0002 | Document Migration | All existing documents in ExShare must be migrated to RDOS. | Yes | Completed | Yes | Yes | Yes | YES |
| FR0003 | Metadata Retention | All document metadata must be retained post-migration. | Yes | In Progress | No | Yes | Yes | YES |
| FR0004 | Access Control Mapping | User roles and permissions in ExShare must be replicated in RDOS. | Yes | Completed | Yes | Yes | Yes | YES |
| FR0005 | Search Functionality | Users should be able to search migrated documents by title, tag, or date. | Yes | Completed | Yes | Yes | Yes | YES |
| FR0006 | Version History | Version history should be preserved during migration. | Yes | Pending | No | Yes | Yes | YES |
| FR0007 | Audit Logs | Post-migration audit logs should capture document access and updates. | Yes | In Progress | No | Yes | Yes | YES |
| FR0008 | Training Module | A help/training module should be available for RDOS users. | Yes | Completed | Yes | Yes | Yes |  |

Business Requirements Document (BRD)

Project: Migration from ExShare to RDOS

1. Project Overview

This BRD defines the business needs for migrating from the ExShare system to RDOS to improve document management, access, and security.

Document Revisions – BRD for ExShare to RDOS Migration

| Date | Version Number | Document Changes |
| --- | --- | --- |
| 05/02/2025 | 0.1 | Initial Draft |
| 10/02/2025 | 0.2 | Added business needs and initial scope |
| 15/02/2025 | 0.3 | Updated stakeholder list and added functional requirements |
| 20/02/2025 | 0.4 | Added non-functional requirements and risk analysis |
| 25/02/2025 | 0.5 | Incorporated feedback from SME and Tech Lead |
| 01/03/2025 | 1.0 | Final version approved and signed off by stakeholders |

Approvals – BRD for ExShare to RDOS Migration

| Role | Name | Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Project Sponsor | Anil Sharma | VP – Operations | [Signed] | 05/03/2025 |
| Business Owner | Priya Mehta | Director – Business | [Signed] | 05/03/2025 |
| Project Manager | Ramesh Iyer | Sr. Project Manager | [Signed] | 06/03/2025 |
| System Architect | Rajeev Kulkarni | Lead System Architect | [Signed] | 06/03/2025 |
| Development Lead | Deepak Rao | Development Lead | [Signed] | 07/03/2025 |
| User Experience Lead | Neha Verma | UX Lead | [Signed] | 07/03/2025 |
| Quality Lead | Kavitha Nair | QA Manager | [Signed] | 07/03/2025 |
| Content Lead | Sandeep Menon | Content Strategist | [Signed] | 08/03/2025 |

RACI Chart – BRD for ExShare to RDOS Migration

| Name | Position | * | R | A | S | C | I |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Anil Sharma | VP – Operations (Client) | ✓ |  |  |  |  | ✓ |
| Priya Mehta | Director – Business |  |  | ✓ |  | ✓ |  |
| Ramesh Iyer | Sr. Project Manager |  |  | ✓ |  | ✓ | ✓ |
| Rajeev Kulkarni | Lead System Architect |  |  |  | ✓ | ✓ |  |
| Deepak Rao | Development Lead |  | ✓ |  | ✓ |  |  |
| Neha Verma | UX Lead |  |  |  | ✓ | ✓ |  |
| Kavitha Nair | QA Manager |  |  |  | ✓ | ✓ |  |
| Sandeep Menon | Content Strategist |  |  |  | ✓ |  |  |

4. Introduction

4.1 Business Goals

Organization Goal:

The goal of this project is to modernize the organization's legacy document sharing and records management system (ExShare) by migrating to a more scalable, secure, and efficient digital platform – RDOS (Records & Document Optimization System). This upgrade will align the organization’s operations with industry best practices, improve compliance, and support long-term digital transformation efforts.

Organization Need:

- The current ExShare system is outdated, lacks real-time collaboration capabilities, and suffers from performance issues and security limitations.

- There is an increasing need for centralized document storage with version control, role-based access, and integration capabilities with other enterprise systems.

- The organization requires a future-ready platform to improve productivity, reduce manual processes, and ensure seamless access to documents across departments and geographies.

- Compliance with regulatory frameworks and audit trails is difficult to manage using ExShare. RDOS provides built-in compliance features.

4.2 Business Objectives

To provide an IT solution for the seamless migration from the ExShare platform to RDOS, incorporating the development and integration of multiple key functionalities that enhance the organization's operational efficiency and user experience. The proposed system will include:

1. Mobile Application (Android & iOS):

- Enable users to access RDOS functionalities via a secure, user-friendly mobile interface.

- Features to include:

  - User login & authentication

  - Document upload, search, and retrieval

  - Push notifications for updates and actions

  - Offline document access and synchronization

  - Role-based access and document sharing

2. E-Learning Management System (LMS):

- Provide a digital platform for training, knowledge sharing, and compliance management.

- Key functionalities:

  - Course creation, assignment, and tracking

  - Video lectures, quizzes, and certification

  - Progress tracking dashboards for learners and managers

  - Integration with RDOS for resource linking and storage

  - Feedback and assessment capabilities

3. Human Resource Management System (HRMS):

- Automate HR operations and document management within RDOS.

- Core features:

  - Employee onboarding/offboarding workflows

  - Leave and attendance management

  - Document repository for HR files (contracts, appraisals, etc.)

  - Payroll integration and self-service portals

  - Performance management and appraisal tracking

4.3 Business Rules

The RDOS project must adhere to the following organizational policies, procedures, and regulations throughout the development, deployment, and operational lifecycle:

1. Data Security & Confidentiality

- All user data and documents must be stored in encrypted format both at rest and in transit.

- Only authorized personnel can access confidential documents based on defined role-based permissions.

- User sessions must be automatically logged out after 10 minutes of inactivity.

2. User Access & Authentication

- Multi-Factor Authentication (MFA) is mandatory for all admin-level users.

- Passwords must meet complexity requirements (minimum 8 characters, including uppercase, lowercase, number, and special character).

- Role-based access controls must be strictly enforced across all modules.

3. Document Management Policy

- All migrated documents from ExShare must retain metadata (created by, timestamp, document ID).

- Users are not allowed to delete documents; only archive functionality is permitted as per audit policy.

- Version control must be maintained for all uploaded or edited documents.

4. HRMS Compliance Rules

- Employee data must comply with applicable labor laws and data protection regulations (e.g., GDPR if applicable).

- Leave balances and payroll data must sync with the official organizational HR database.

- Audit logs of employee record changes must be retained for a minimum of 5 years.

5. E-Learning Policy

- All employees must complete mandatory training courses within 30 days of assignment.

- Certification validity must be tracked and renewal alerts triggered 15 days before expiry.

- Only approved content from the L&D (Learning & Development) team can be published.

6. Mobile App Governance

- Mobile apps must be reviewed and approved by the internal IT security team before release.

- The application must support biometric login on supported devices.

- App updates must follow a quarterly release cycle unless urgent patches are required.

4.4 Background

The ExShare platform, previously used for internal document sharing and collaboration within the organization, faced multiple limitations in terms of scalability, security, and user experience. With the evolving digital landscape and the need for better integration with enterprise systems, a proposal was initiated to migrate to a more modern and robust platform — RDOS (Robust Digital Office Suite).

The decision to develop RDOS stems from the following business challenges observed in ExShare:

- Limited mobile access and non-responsive interfaces on modern devices.

- Security vulnerabilities and lack of compliance with updated data privacy regulations.

- Manual HR processes and inadequate tracking of employee information and e-learning compliance.

- Lack of centralized integration for HRMS and Learning Management functionalities.

- Low user adoption due to poor UI/UX and performance lags in ExShare.

The RDOS Project was conceptualized to address these shortcomings and deliver an all-in-one digital workspace. It is expected to:

- Streamline document management and collaboration processes.

- Provide cross-platform mobile applications (Android & iOS).

- Integrate E-Learning Management System (LMS) to manage training and certifications.

- Include a comprehensive Human Resource Management System (HRMS) to automate employee lifecycle operations.

- Improve compliance, audit readiness, and employee engagement.

By implementing RDOS, the organization aims to increase operational efficiency, ensure regulatory compliance, and enhance employee productivity through a seamless, secure, and intelligent digital environment.

4.5 Project Objective

The primary objective of the RDOS (Robust Digital Office Suite) project is to successfully migrate all functionalities and relevant data from the existing ExShare system to a modern, secure, scalable, and user-friendly platform. This transformation aims to enhance internal operations, improve employee engagement, and streamline document, HR, and learning processes across the organization.

High-Level Objectives:

- Replace ExShare with an advanced digital office suite that aligns with current technology standards and security requirements.

- Provide a centralized platform for document management, HR operations, and e-learning activities.

- Enable cross-platform mobile accessibility (Android and iOS) to support a mobile workforce.

- Improve data security, system performance, and user experience.

Key Features:

- Document upload, search, version control, and secure sharing.

- Employee management, leave tracking, and payroll integration through HRMS.

- Online training modules, course tracking, and certification management in the LMS.

- Role-based access control, activity logging, and audit support.

Alignment with Business Objectives:

- Supports the organization's goal of digital transformation by eliminating outdated tools.

- Enables real-time collaboration and learning, increasing overall productivity.

- Promotes regulatory compliance (e.g., GDPR, IT security standards).

- Enhances decision-making with better visibility into HR and training data.

System Integration Requirements:

- Integration with existing enterprise authentication systems (e.g., Active Directory or SSO).

- API-based connection with HRMS databases, payroll systems, and third-party training vendors.

- Secure data migration services for existing ExShare content, including audit logs and document history.

4.6 Project Scope

The scope of the RDOS (Robust Digital Office Suite) project includes the complete replacement and enhancement of the existing ExShare platform. It focuses on the development, deployment, and integration of new modules with improved performance, mobility, and user-centric design.

✅ In-Scope (What we will deliver):

- Document Management System

  - Upload, download, and version control

  - Role-based sharing and permission settings

  - Search and tagging functionalities

  - Document history and audit tracking

- Mobile Applications

  - Android and iOS native apps for employee access

  - Features to support document access, learning, and HR interactions on mobile

- E-Learning Management System (LMS)

  - Online training module creation and assignment

  - User progress tracking and certification issuance

  - Admin and reporting dashboards

  - Multimedia and quiz support

- Human Resource Management System (HRMS)

  - Employee onboarding/offboarding

  - Leave and attendance management

  - Payroll data handling (integration ready)

  - Employee self-service portal

- User Management & Access Control

  - Integration with Active Directory or Single Sign-On (SSO)

  - Role- and department-based access control

  - Admin rights management

- Data Migration

  - Migration of documents, user data, permissions, and logs from ExShare

  - Validation and backup during migration

- Security & Compliance

  - End-to-end encryption of data

  - Activity logs and compliance with data privacy laws (e.g., GDPR)

- Testing & UAT

  - Unit testing, system integration testing, and user acceptance testing

  - Feedback incorporation and bug resolution

4.6.1 In-Scope Functionality

- Migration of documents and metadata from ExShare to RDOS

- Development of document management features: upload, version control, search, and sharing

- User authentication and role-based access management

- Development of mobile applications (Android & iOS) for document and HR access

- Implementation of an integrated E-Learning Management System (LMS):

  - Course assignment, tracking, quiz/exam features, and certification

- Implementation of Human Resource Management System (HRMS):

  - Employee records, leave management, attendance, and self-service portal

- Admin panel for system configuration and user management

- Integration with Active Directory / Single Sign-On (SSO)

- Logging and audit trail for all document and user actions

- End-to-end data encryption (at rest and in transit)

- Basic analytics and reporting for HR and learning modules

- User acceptance testing (UAT), training, and deployment support

4.6.2 Out-of-Scope Functionality

- Payroll calculation engine (only integration with existing system will be supported)

- Advanced analytics (e.g., predictive insights, AI-based recommendations)

- Real-time chat/messaging features

- Custom report builder for users (pre-defined reports only in this release)

- Third-party content creation for LMS courses

- Physical infrastructure or server provisioning (cloud deployment assumed)

- Post-production maintenance and enhancements (covered separately under support/AMC contract)

- Multi-language/localization support in phase 1 (may be included in future phases)

5. Assumptions

The following assumptions have been made during the requirement gathering, planning, and scoping phases of the RDOS project. These assumptions are critical for the successful execution and timely delivery of the project:

- All existing documents and metadata in ExShare are available, structured, and accessible for migration.

- The client will provide timely access to subject matter experts (SMEs) and stakeholders for requirement clarifications and approvals.

- Required third-party licenses (e.g., for LMS, HRMS integrations, mobile deployment) will be procured and made available before development begins.

- Existing HR and learning data is accurate, complete, and compatible with RDOS format standards.

- Users will be trained on how to use the new RDOS platform before go-live.

- Mobile applications will be deployed through official app stores (Google Play and Apple App Store) and the client will assist in account provisioning.

- The project team will receive required infrastructure access (cloud servers, staging environments, APIs) from the client on time.

- Integration with Active Directory or SSO is feasible using available protocols like SAML or OAuth.

- Business rules, compliance policies, and approval hierarchies are already defined and will not change significantly during the project.

- All requirements and change requests after finalization will follow a formal change management process.

6. Constraints

The RDOS project will operate under the following constraints that may impact scope, timeline, cost, or quality:

- Timeline Constraint: The project must be completed and deployed within a fixed timeline of 12 months, as per organizational rollout plans.

- Budget Constraint: The project has a predefined budget limit, including costs for development, testing, licensing, and training — not to exceed Rs.2000000.

- Data Sensitivity: All data migrated and handled must adhere to strict data privacy and compliance regulations (e.g., GDPR, IT Act).

- Technology Compatibility: The RDOS solution must be compatible with existing enterprise systems (e.g., Active Directory, HR databases) without requiring changes in those systems.

- Internet Dependency: RDOS is a web-based/cloud-hosted system and relies on stable internet connectivity for most features, including mobile apps.

- App Store Policies: Mobile application deployment is subject to approval and policies of Google Play Store and Apple App Store, which may introduce timeline risks.

- Legacy Data Structure: ExShare data must be migrated without altering original document integrity or metadata, which could restrict flexibility in structuring the new system.

- Limited Stakeholder Availability: Key business users and SMEs may have restricted availability during project execution, affecting review and feedback cycles.

- Testing Resources: Availability of client-side testers for UAT and QA may be limited, which can affect validation timelines.

- Fixed Scope Agreement: Major scope expansions will not be accommodated without formal change requests and re-approval due to waterfall methodology constraints.

7. Risks

7.1 Technological Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Compatibility issues between legacy ExShare data and RDOS format | Medium | High | Mitigate | Perform early analysis of existing data structures and prepare a data transformation plan |
| Security vulnerabilities in mobile or web app | Medium | High | Mitigate | Conduct thorough security testing (penetration testing, code review) before go-live |
| Delay in third-party system integration (e.g., SSO, HRMS APIs) | Medium | Medium | Mitigate | Initiate integration testing in parallel and keep backup authentication plan |

7.2 Skills Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Unavailability of skilled mobile developers or backend integrators | Low | High | Mitigate | Maintain a bench of developers and pre-plan vendor support for niche areas |
| Inadequate training for RDOS system among end users | Medium | Medium | Mitigate | Provide comprehensive training sessions and manuals well before UAT and deployment |

7.3 Political Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Change in leadership or decision-makers during the project | Low | High | Accept | Ensure clear documentation and sign-offs to maintain project continuity |
| Shift in organizational priorities due to external pressures | Low | Medium | Accept | Prepare project status reports to keep visibility and support at all levels |

7.4 Business Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Project cancellation due to budget reallocation or change in direction | Low | High | Transfer | Tie project milestones to strategic business goals to strengthen justification |
| User resistance to adopting RDOS | Medium | Medium | Mitigate | Involve key users in testing phases and collect feedback to improve usability |

7.5 Requirements Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Incomplete understanding of ExShare workflows | Medium | High | Mitigate | Conduct stakeholder workshops, interviews, and document review sessions |
| Ambiguity in requirements for HRMS or LMS modules | Medium | Medium | Mitigate | Prepare detailed use cases and mockups; validate requirements with SMEs before design |

7.6 Other Risks

| Risk | Likelihood | Impact | Strategy | Description |
| --- | --- | --- | --- | --- |
| Delays in Client Feedback or Approvals | Medium | High | Mitigate | Delays in sign-offs for requirements, designs, or UAT can block progress. Mitigated by defining clear SLA timelines and escalation procedures. |
| Vendor Dependency for Third-Party Components | Medium | Medium | Mitigate | RDOS may rely on third-party components (e.g., LMS modules). Any delay or issue with vendors could affect timelines. Early coordination and fallback plans are essential. |
| Data Loss or Corruption During Migration | Low | High | Avoid | Backups and test migrations should be performed in a staging environment before actual cut-over. Validation steps must be included. |
| Regulatory/Compliance Changes During Project | Low | Medium | Accept | If new compliance requirements arise (e.g., audit, legal), minor scope changes might be needed. Monitoring external updates is key. |
| Infrastructure Downtime or Cloud Service Failure | Low | High | Transfer | Uptime and disaster recovery will be managed by cloud service providers. SLAs and backup protocols must be in place. |
| Misalignment Between Business and IT Teams | Medium | Medium | Mitigate | Regular joint reviews, status meetings, and shared documentation are necessary to ensure everyone is aligned on deliverables. |

8. Business Process Overview

8.1 Legacy System (AS-IS)

System: ExShare
ExShare is a legacy document management and information-sharing platform used by the organization for storing, managing, and distributing documents. The system, although stable, has several limitations:

AS-IS Process Flow Summary:

- Document Upload – Users upload documents manually without standardized metadata.

- Storage – Files are stored on shared drives with limited version control.

- Access Control – Access is managed manually, with no integration with corporate identity systems (e.g., no SSO).

- Search – Poor search functionality due to lack of tagging/indexing.

- Tracking – No audit trails or activity logs for document access and changes.

- Mobile Access – Not supported; system is desktop-only.

- HR & Learning Data – Maintained in spreadsheets or siloed systems outside ExShare.

Flow diagram

[User Login]

↓

[Upload/Share Files in ExShare]

↓

[Manual Data Review / Approval via Email or Offline Tools]

↓

[Local Storage / Static Reports Generated]

↓

[Manual Updates to Other Systems (POS, CRM, etc.)]

Limitations of AS-IS System:

- No centralized control or standardization of document management

- Inefficient and error-prone manual processes

- Security vulnerabilities due to lack of encryption and audit trails

- No integration with HR or LMS systems

- Limited accessibility and usability (no mobile or remote access)

8.2 Proposed Recommendations (TO-BE)

System: RDOS (Redesigned Digital Office System)

TO-BE Process Flow Summary:

- Document Upload & Tagging – Users upload documents with mandatory metadata and auto-categorization.

- Version Control – Every document update is versioned and traceable.

- Access Management – Role-based access integrated with corporate SSO/Active Directory.

- Search & Retrieval – Advanced search using tags, content indexing, and filters.

- Audit Trail – Every action logged and available for review.

- Mobile Access – Fully responsive web and native mobile apps for Android and iOS.

- HRMS Integration – Centralized HR operations including attendance, leaves, and employee directory.

- LMS Integration – Online training, assessments, and certification tracking within RDOS.

Flow diagram

[User Login to RDOS Portal]

↓

[Upload/Retrieve Documents + Retail Data in Real Time]

↓

[Auto-Sync Across Systems (POS, CRM, Inventory)]

↓

[Automated Approvals / Workflow Triggers (e.g., pricing, stock updates)]

↓

[Real-Time Dashboards + AI Analytics + Notifications]

How TO-BE Addresses AS-IS Challenges:

- Automates and standardizes document workflows

- Enhances compliance with audit logs and encryption

- Improves accessibility via mobile and cloud

- Consolidates HR and Learning operations in one platform

- Provides scalability and modernization, reducing dependency on outdated systems

9. Business Requirements

Business requirements were identified through stakeholder interviews, workshops, and document analysis. These are grouped by functionality and tagged with priority levels to guide implementation and traceability.

Priority Levels:

- H (High) – Critical to project success

- M (Medium) – Important but not critical for launch

- L (Low) – Desirable, can be implemented post-launch

9.1 Document Management Requirements

| Req ID | Requirement Description | Priority | Type |
| --- | --- | --- | --- |
| BR-01 | Users must be able to upload and categorize documents with metadata | H | Functional |
| BR-02 | The system shall support version control and rollback of documents | H | Functional |
| BR-03 | The system must allow secure document sharing within and outside the organization | H | Functional |
| BR-04 | Full-text search capability must be available | H | Functional |
| BR-05 | Deleted documents should be archived with restore options | M | Functional |

9.2 Access & Security Requirements

| Req ID | Requirement Description | Priority | Type |
| --- | --- | --- | --- |
| BR-06 | User authentication must be integrated with Active Directory (SSO) | H | Functional |
| BR-07 | Role-based access control (RBAC) must be enforced | H | Functional |
| BR-08 | System should maintain audit trails of all user activities | H | Non-Functional |
| BR-09 | All data must be encrypted at rest and in transit | H | Non-Functional |

9.3 HRMS Requirements

| Req ID | Requirement Description | Priority | Type |
| --- | --- | --- | --- |
| BR-10 | The system must support employee profile management | M | Functional |
| BR-11 | Leave and attendance management must be integrated | M | Functional |
| BR-12 | Reports on HR operations must be exportable in PDF and Excel | L | Functional |

9.4 LMS Requirements

| Req ID | Requirement Description | Priority | Type |
| --- | --- | --- | --- |
| BR-13 | Users must access self-learning modules and course materials | M | Functional |
| BR-14 | Quiz and assessment tools should be embedded in the system | M | Functional |
| BR-15 | Progress tracking and certification issuance must be supported | M | Functional |

9.5 Usability & Performance Requirements

| Req ID | Requirement Description | Priority | Type |
| --- | --- | --- | --- |
| BR-16 | System must load any page within 2 seconds under normal load | M | Non-Functional |
| BR-17 | Mobile application should support both Android and iOS platforms | H | Functional |
| BR-18 | The interface must support English and optionally other languages | L | Functional |

10. Appendices

10.1. List of Acronyms

| Acronym | Full Form |
| --- | --- |
| BRD | Business Requirements Document |
| RTM | Requirements Traceability Matrix |
| SSO | Single Sign-On |
| RBAC | Role-Based Access Control |
| HRMS | Human Resource Management System |
| LMS | Learning Management System |
| ROI | Return on Investment |
| UI | User Interface |
| UAT | User Acceptance Testing |
| ITS | Information Technology Services |
| RDOS | Redesigned Digital Office System |

10.2. Glossary of Terms

| Term | Definition |
| --- | --- |
| ExShare | Legacy document and information sharing platform used before migration. |
| RDOS | New cloud-based digital office platform replacing ExShare, integrating document, HRMS, and LMS functionalities. |
| Metadata | Data that provides information about other data (e.g., tags, author, date uploaded). |
| Version Control | A system for managing changes to documents over time and maintaining historical versions. |
| Audit Trail | A log that records all system activities and user actions for compliance and traceability. |
| User Roles | Designated user permissions (e.g., Admin, Editor, Viewer) defining access and capabilities. |
| Stakeholder | An individual or group with a vested interest in the outcome of the project. |

10.3. Related Documents

| Document Name | Description | Location |
| --- | --- | --- |
| Business Case Document | Justification and rationale for the ExShare to RDOS project | [Attach/Link] |
| BA Strategy Document | Strategy outlining BA activities and engagement | [Attach/Link] |
| Functional Specifications Document | Detailed functional behavior of the system | [Attach/Link] |
| Requirements Traceability Matrix (RTM) | Matrix mapping requirements to design/test cases | [Attach/Link] |
| Project Plan | Timeline, milestones, and roles & responsibilities | [Attach/Link] |