## Slide 1: Project Title: Insurance Finance Ledger Management Portal
Prepared By: Suman Samaiya

## Slide 2: Situations
The BPO company manages the backend finance operations for multiple insurance providers (Aviva, Allianz, AXA, NMU, Mitsui, etc.)
All Insurer statements are shared in Excel or PDF format by the Insurers.
The finance team manually enters, verifies, and compares the Insurer ledgers against the internal ledgers.
The process is:
Receive statements from insurance organizations.
Open and review Excel/PDFs.
Match insurance ID, insurance name, amounts paid, dues, taxes, and aged payments with BPO’s internal ledger.
Make the Monthly due payments.
Identify mismatches, prepare follow-ups, and request clarifications.
Problems:
The finance reconciliation process is completely manual, relying on Excel sheets and PDF statements sent by Insurers.
This creates multiple inefficiencies:
  High error risk : manual matching of insurance ID, paid amount, dues, and taxes often leads to mistakes.
  Delayed processing : overdue and aged payments are not flagged in real-time, causing delays in follow-ups.
  Poor traceability : documents are scattered across emails and folders, making it hard to track status.
  Scalability issue : as the number of insurance clients grows, manual Excel reconciliation cannot keep pace.
  Lack of visibility for stakeholders : managers don’t have dashboards or reports to monitor overdue payments or mismatches instantly.

## Slide 3: Opportunities
Automation of Ledger Reconciliation: Uploads from insurance partners can be automatically compared with the BPO’s internal records, reducing manual work and errors.
Real-time Visibility: Dashboards and reports will provide instant insights into overdue payments, aged dues, and mismatches.
Improved Efficiency: Reduces processing time, enabling finance teams to handle higher volumes without adding manpower.
Stronger Compliance & Audit Trail: Centralized storage of all statements ensures easy access for audits and regulatory checks.
Cost Savings: Less time spent on manual checking reduces operational costs.
Better Client Relationship: Faster reconciliation and timely follow-ups improve trust with insurance partners.
Scalability: A system-based approach can easily support more clients and larger volumes of transactions in the future.

## Slide 4: Purpose Statement (Goals):
Analyze and design an automated Insurance Finance Ledger Management Portal.
Enable insurance partner organizations to upload Insurer statements(ledger) directly into the system.
Validate and compare uploaded ledgers with the BPO’s internal ledger records.
Track payments efficiently and highlight mismatches or overdue amounts.
Ensure timely reconciliation of financial records across all insurance partners.
Improve document handling by centralizing statements and related records.
Reduce aging of unpaid dues through automated reminders and follow-up tracking.
Project Objectives:
Develop a secure portal for insurance companies to upload their payment ledgers (Excel/PDF).
Automate ledger comparison between organization-uploaded and internal BPO ledgers.
Highlight mismatches and overdue payments automatically.
Enable report generation and follow-up tracking for aged dues.
Improve document centralization and visibility for the finance team.

## Slide 5: Success Criteria
Reconciliation Accuracy
Ensure over 95% accuracy in statement uploads and mismatch flagging.
Enhance visibility
Highlight overdue and aged payments with real-time dashboards and alerts
Turn Around time
Reduce the average turnaround time for clearing payments to 10 days.
Operational Efficiency
Reduce overdue follow-ups by 30% within the first 3 months of deployment.
Information Accessibility & Transparency
Improve document accessibility and traceability for all stakeholders.
User Adoption & Training
Achieve 100% adoption among finance staff and at least 80% adoption among insurance partners within 2 months of go-live.
Processing Speed
System should process and validate uploaded statements within 2 minutes per file.
Scalability
System should support onboarding of 50+ insurance partners without performance degradation
Reduce processing time
Reduce processing time for reconciliation and follow-up activities by at least 30% within 3 months of implementation
Project delivery on Time and Budget:
The project is completed on agreed timeframe and Budget, meeting all the major deliverables

## Slide 6: Waterfall method
1. Requirement Gathering and Analysis
Collect detailed requirements from finance team and insurance partners.
Analyze current process (Excel/PDF uploads, manual matching, overdue follow-ups).
Document functional and non-functional requirements.
Define success factors such as reconciliation accuracy, TAT reduction, and error elimination.
Deliverable: Business Requirement Document (BRD)
2. System Design
Create the system architecture based on requirements.
Design the database schema for storing ledger and transaction data.
Prepare workflows for statement uploads, automated comparison, and mismatch flagging.
Define user interfaces for upload screens, reports, and dashboards.
Prepare system flow diagrams, use case diagrams, and activity diagrams.
Deliverable: System Design Document (SDD)

## Slide 7
3. Development
Develop modules for:
  Statement upload (Excel/PDF formats)
  Automated ledger comparison & mismatch detection
  Overdue follow-up reminders
  Reports & dashboards for stakeholders
  Backend development for reconciliation logic and automated notifications.
Deliverable: Fully coded and internally tested modules
4. Testing
Perform System Testing to validate overall functionality.
Conduct Integration Testing with insurance partner data.
Carry out User Acceptance Testing (UAT) with finance users.
Validate reconciliation accuracy, upload speed, and turnaround time reduction.
Deliverable: Tested system with UAT sign-off

## Slide 8
5. Deployment
Deploy the system in the production environment.
Migrate initial data (ledger formats and existing statements if required).
Go Live with the new Finance Ledger Management Portal.
Deliverable: Live system ready for end-user access
6. Training & Support
Train finance staff and insurance partners on system usage.
Provide user manuals and quick reference guides.
Establish technical support and issue resolution processes.
Deliverable: Trained users and established support process

## Slide 9
Resources for Insurance Finance Ledger Management Portal :
1. People
From Gallagher Shared Services
Business Stakeholders
Project team members from client’s finance team
From IT
Business Analyst: Gather requirements, document processes, and bridge between stakeholders and developers
Developers: Design, code, and implement system modules and integrations
Testers (QA): Prepare and execute test cases to ensure system accuracy and reliability.
Finance SMEs: Provide domain expertise, validate business rules, and support UAT.
Client Side: Approve scope, provide resources, and ensure final sign-off.
2. Timeline (6 Months Total)
Requirement Gathering & Analysis (1 Month)
System Design (1 Month)
Development (2 Months)
Testing (1 Month)
Deployment (1 month)

## Slide 10: 3. Budget
Detailed Budget Breakdown (within ₹25,00,000)
Development Cost: ₹8,00,000 – Application design, coding, integration, and testing.
Infrastructure Cost: ₹5,00,000 – Servers, storage, backup, and network setup.
Licensing Cost: ₹4,00,000 – Database, PDF/Excel parser, reporting, and security tools.
Training Cost: ₹2,00,000 – End-user and technical staff training, workshops, and manuals.
Support & Maintenance Cost: ₹3,00,000 – Post-go-live monitoring, issue resolution, and updates.
Services (Customization & Deployment): ₹3,00,000 – Implementation, migration, and go-live activities.
Total Estimated Budget: ₹25,00,000
4. Other Resources
Hardware
Servers (cloud/on-premise) for hosting the portal
Backup & disaster recovery systems
Secure storage for financial documents
Software & Tools
PDF/Excel parser for reading uploaded statements
Database (e.g., SQL Server, Oracle, or MySQL)
Reporting & dashboard tools
Development & testing tools (IDE, version control, bug tracking system)

## Slide 11
Network & Infrastructure
High-speed internet and VPN for secure data exchange
Load balancer for handling multiple insurance partners uploading simultaneously
Secure gateways for file uploads
Compliance & Documentation
Adherence to Insurance Regulatory Standards
Data privacy & security compliance (ISO/PCI, GDPR if international)
Audit trail documentation
Training & Knowledge Resources
Training materials (user manuals, quick guides, FAQs)
Workshops for finance staff and insurance partners
Knowledge base for troubleshooting common issues
Support Resources
Technical support team (post-go-live)
Issue tracking & ticketing system
Regular system maintenance schedules

## Slide 12
Risks
User Adoption Risk: Users may resist moving from Excel to a new portal.
Data Quality Risk: Incorrect or incomplete uploads can cause reconciliation issues.
Integration Risk: Different Excel/PDF formats from insurers may reduce auto-comparison accuracy.
Timeline Risk: Delays in one Waterfall phase can impact the overall schedule.
Cost Justification Risk: ROI from efficiency and accuracy may be hard to quantify initially.
Dependencies
Partner Data Dependency: Accurate and timely statement uploads from insurance organizations.
Infrastructure Dependency: Reliable servers, hosting, and network connectivity.
Compliance Dependency: Alignment with financial regulations and insurance audit standards.
Resource Dependency: Availability of developers, testers, and finance SMEs at critical phases.
Management Dependency: Active involvement of client representatives for approvals and sign-offs.

## Slide 13
Thank you