## Slide 1: FinnOne Loan Servicing application – ICICI Bank
Using the Waterfall Model
Prepared by: Pradnya Doiphode
Date: July 2025

## Slide 2: Situation/Problem/opportunity :
Situation
FinnOne is a comprehensive loan management solution used by ICICI Bank.
The goal is to digitise and streamline the loan servicing lifecycle.
Applying the Waterfall model ensures structured, sequential implementation.
Successful implementation leads to reduced turnaround time, better compliance, and enhanced customer satisfaction.
Problem:
Manual loan servicing processes were time-consuming and error-prone.
Increasing demand for faster and more accurate loan processing.
Opportunity :
FinnOne has been introduced to automate and manage loan servicing efficiently.
Aligns with ICICI Bank’s goal to digitize operations and improve service delivery.

## Slide 3: Purpose Statement (Goals):
The purpose of implementing the FinnOne application is to digitize and streamline the loan servicing process in ICICI Bank by automating key tasks such as loan disbursement, EMI tracking, payment collections, and customer communication. This helps in:
Improving operational efficiency and reducing manual effort.
Ensuring accuracy and compliance with regulatory requirements.
Speeding up loan lifecycle management, from approval to closure.
Enhancing customer experience through faster and more transparent service.
Reducing risks and delays by implementing a centralized, end-to-end loan management system.

## Slide 4: Project Objectives:
Project Objectives
Automate the Loan Servicing Process
Replace manual and semi-automated processes with a centralized loan management system.
Ensure Compliance and Accuracy
Adhere to RBI and internal audit guidelines through system-driven checks and validations.
Improve Operational Efficiency
Reduce turnaround time (TAT) for loan servicing activities such as disbursement, EMI management, and NOC issuance.
Enhance Customer Experience
Enable timely notifications, transparent tracking, and faster service resolution.
Implement a Structured, Risk-Minimized Development Approach
Follow the Waterfall model to clearly define requirements, minimize scope creep, and maintain control over the project lifecycle.
Facilitate Better Data Management and Reporting
Provide accurate, real-time data for internal MIS, compliance reporting, and decision-making.

## Slide 5: Success Criteria:
Deliverables:
Functional FinnOne loan servicing module.
User manuals and training guides.
Deployment and support plan.
Success Criteria:
Reduction in loan processing time by 30%.
Zero critical bugs post-deployment.
90% user adoption within first 3 months.

## Slide 6: Methods/Approach:
Requirement Gathering and Analysis
Collaborate with stakeholders (loan operations, IT, compliance) to capture all functional and technical requirements.
Document detailed system requirements and get sign-off.
System Design
Create a high-level and low-level design of the FinnOne application integration with ICICI Bank systems.
Define workflows, user roles, access controls, and interfaces.
Vendor Coordination and Customization
Work with the FinnOne vendor (e.g., Nucleus Software) for necessary customizations and configurations based on ICICI Bank’s needs.
Development and Configuration
Set up the application environment, integrate with core banking systems, and implement business logic as per requirements.

## Slide 7
Testing
Conduct system testing, integration testing, and user acceptance testing (UAT).
Ensure all modules like loan creation, EMI management, pre-closure, and reporting are thoroughly tested.
Training and Documentation
Prepare user manuals and conduct training sessions for end-users (branch staff, operations, customer support).
Create SOPs and internal help guides.
Deployment and Go-Live
Deploy the application in the production environment.
Ensure proper data migration from legacy systems (if any).
Monitor post-go-live performance.
Post-Implementation Support
Provide support for initial stabilization period.
Track issues, apply hotfixes/patches, and gather user feedback.

## Slide 8: Resources:
People :
BA, Developer, QA, Project Manager, Trainers.
Time
Estimated 6 months from start to go-live.
Budget
Software Licensing: ₹5,00,000
Training & Implementation: ₹3,00,000
Support & Maintenance: ₹2,00,000
Other –
third party software evaluation, site visits, Dataquest reports

## Slide 9: Risks and Dependencies :
1. Resistance to Change from End-Users
Staff who are comfortable with the existing manual or legacy system may resist adopting FinnOne.
Risk of low adoption if proper training and communication are not provided.
Mitigation: Conduct change management sessions and hands-on training workshops.
2. Delay in Requirement Finalization
Waterfall model relies on clear and complete requirements upfront.
Any delay or ambiguity in finalizing requirements can delay the overall timeline and affect downstream phases.
Mitigation: Engage all stakeholders early and sign off detailed requirements documents before moving to design.
3. Integration Complexity
FinnOne must integrate with multiple ICICI Bank systems: Core Banking, CRM, Payment Gateway, and Compliance systems.
Technical glitches or lack of documentation from existing systems may cause integration issues.
Mitigation: Allocate experienced IT resources and conduct integration testing in a controlled environment.
.

## Slide 10
4. Data Migration Challenges
Migrating data from legacy systems (if any) to FinnOne may result in data loss, inconsistency, or format issues.
Mitigation: Perform data validation, reconciliation, and dry runs before actual migration
5. Vendor Dependency
Project success depends on the responsiveness and support from the FinnOne vendor (e.g., Nucleus Software).
Any delay from their side in customization, deployment, or bug fixing can halt progress.
Mitigation: Set clear SLAs and regular checkpoints with the vendor team.
6. Budget Overruns
If the initial effort estimation or resource planning is inaccurate, the project may exceed budget limits.
Mitigation: Have a contingency budget and monitor costs regularly through a project manager.

## Slide 11
7. Post-Go-Live Support Issues
Even after successful deployment, system bugs or user errors may arise, impacting operations.
Mitigation: Keep a post-go-live support team ready for at least 30-60 days.
8. Regulatory Changes
Any change in RBI or internal policy during the project can impact application compliance requirements.
Mitigation: Maintain liaison with compliance/legal team throughout the development

## Slide 12: Conclusion :
FinnOne will bring efficiency, accuracy, and speed to ICICI Bank’s loan servicing.
The Waterfall approach ensures a clear, trackable path to implementation.
Structured project planning and stakeholder involvement are key to success.

## Slide 13
To Be Completed by Appropriate Manager :
Project Sponsor : Akshay Shinde
Project Manager : Nisha Patel
Business analyst : Pradnya Doiphode