## Slide 1: RP Applications Support
Prepared By – Uday Hadap
Date – 05/09/2025

## Slide 2: Agenda
Situation/Problem/Opportunity
Purpose Statement
Project Objectives
Success Criteria
Methods/Approach
Resources
Risks and Dependencies
Concluding Points

## Slide 3: Situation/Problem/Opportunity
Customer has ERP set up to support their spare parts business. The set up is divided into 3 applications ASW, B2B and B2C.
Each application has their own team to support the application.
Due to volatile market conditions, the requirements and their priority keeps on changing very frequently.
The communication across teams is poor and that leads to issues like not meeting target dates etc.
The business don’t have clear status about which team is working on which tickets/project, effort estimation and deployment date.
Since the resource utilization is poor, time taken to complete the ticket/project is high. Due to this the cost to support the application is going high.
Customer wants to set up a process to effectively handle these 3 teams, their tickets/projects and reduce the operating cost.

## Slide 4: Purpose Statement (Goals)
The purpose of this project is to analyze the current application support process and establish a new process that will cover following:
Streamline application support process
Give clear visibility to business about each application support activities.
Manage team efforts effectively and reduce the project support cost.

## Slide 5: Project Objectives:
Analyze the current application support process and identify the gaps.
Establish a good communication among 3 different teams. This is mainly required when the scope of ticket/project splits across the teams/applications.
Establish a process where business can easily change the requirements and their priorities.
Make effective use of the resources within each team and reduce the project support cost.
Make sure that the issues/blockers faced by teams are brought up and address quickly.
Implement a good ticket/project tracking system with all needed information. This will help business to know the status of any ticket/project at any point of time.

## Slide 6: Success Criteria:
Improved communication among 3 different teams.
The scope and priority of the requirements can be changed with minimum rework.
Each team has steady flow of work and working on tickets/projects as per priority given by business.
The issues/blockers faced by teams while working on ticket/projects are addressed quickly.
The cost of application support is reduced.
Business gets clarity about application support activities.

## Slide 7: Methods/Approach:
Agile methodology and Scrum framework will be used in the new process.
‘Scrum Team’ will be formed that will have:
    Product Owner
    Scrum Master
    Development Teams
    Business Owners
Product owner will create and maintain ‘Product Backlog’. This will have all the tickets/projects at one place. He will be conducting the ‘Product Backlog Refinement meeting’ with business at regular intervals to re-order the tickets/projects as per business priority.
For each ticket or project functionality, a ‘User Story’ will be created. Each user story will have following:
  Acceptance Criteria – Defined by business.
  Business Value (BV) – Business will define this.
  Complexity Points (CP) – Development team will define this.
Related user stories will be clubbed under ‘Epic’, which is set of related user stories.

## Slide 8: Methods/Approach: (Cont.…)
‘Sprint’ of 2 or 3 weeks will be defined. In each Sprint, development team will develop and deliver/deploy tickets or project components.
‘Sprint Planning’ meeting will be conducted, where team will look at the product backlog and decide which tickets/project components can be taken up in next sprint for development. This will be based on BV/CP and ‘Velocity of team’ i.e. how much they can deliver in single sprint.
The user stories, those are taken up by team for the next sprint, will be pulled into ‘Sprint Backlog’.
Scrum Master will conduct a daily team meeting called as ‘Daily Scrum meeting’ for around 15 min. In this meeting, team will discuss sprint progress, what they are planning to work on today and are there any issues (also called as ‘Impediments’) that they are facing. Scrum Master will address all the issues being faced by team.
At end of Sprint, ‘Sprint Review’ meeting will be conducted where team will demonstrate the work done in the Sprint to all stakeholders and gather their feedback.

## Slide 9: Methods/Approach: (Cont.…)
‘Sprint Retrospective’ meeting will also be conducted at the end of each Sprint, where team will discuss about things like how Sprint went, challenges faced, what went wrong, areas of improvements etc.
For each sprint, team will use DOR (Definition of Ready) and DOD (Definition of Done) checklists.
Once the Sprint planning is done and team is going to start the Sprint, the DOR checklist will be used to verify that all the things are complete to start the Sprint (like user stores are sorted, they are filled with BV and CP etc.).
After Sprint is complete and review meeting is done, the DOD checklist is used to verify that all the things related to Sprint are complete (like all user stories are completed, no open bugs, testing is done etc.).
To manage/track all the support work effectively, JIRA tracking tool will be used.

## Slide 10: Resources:
People:
  Scrum development team.
  Product Owner
  Scrum Master
  Business Owners
Time:
  This will be ongoing application support project on T&M basis
Budget:
  Billing will be done as per actual timesheets submitted by team.

## Slide 11: Risks and Dependencies:
Risks:
  Insufficient business involvement can be a risk, as it will result into Inadequate understanding of their needs/priorities.
  Incorrect priorities given by business for user stories will result into delay in delivery of priority requirements.
  Current application support teams may be hesitant for this new process.
Dependencies:
  Business will get involved closely with the team. So, they need to spend a dedicated time for the project.
  There will be dependency on external vendors or other internal teams, if and when needed.

## Slide 12: Concluding Points:
Implementation of Agile methodology and Scrum framework in the project will address all the current issues being faced by business.
It will also help business to reduce the application support cost.

## Slide 13: Thank You !!!