## Slide 1: Proposal
Project Title : Online Dairy Products Store
Prepared By : Varshini Thoudishetty
Date : 26/09/2025
Organization : DD Dairy Farm
Online Agriculture Products Store Project

## Slide 2: Executive Summary
Purpose
Facilitate remote customers to buy Milk, Paneer, Curd, Ghee and Cheese directly from manufacturers.
Success
Easy-to-use web/mobile platform, seamless order and delivery process, secure payments.
Value
DD Dairy Farm stands for quality, freshness, animal welfare, sustainability, and customer trust.

## Slide 3: Situation / Problem / Opportunity
Situation: Rising demand for fresh and hygienic milk products in both rural and urban areas.
Problem: Traditional dairy practices result in low productivity, inconsistent quality, and supply chain gaps.
Opportunity: By adopting modern dairy farming techniques, DD Dairy Farm can ensure high-quality products, expand market reach, and achieve sustainable profitability.

## Slide 4: Purpose Statement (Goals):
Dairy farming has been a traditional livelihood in rural India, but many small farmers face challenges like low milk yield, poor storage facilities, and lack of market access.
Consumers are increasingly demanding fresh, hygienic, and chemical-free milk products.
DD Dairy Farm is established to bridge this gap by introducing modern farming practices, ensuring quality production, and creating a sustainable supply chain.
The project aligns with broader goals of rural employment, community development, and food security while building a profitable business model.

## Slide 5: Project Objectives:
Adopt Modern Dairy Practices – Use mechanized milking, cooling, and hygienic storage methods.
High-Yield Cattle & Nutrition – Introduce well-bred buffaloes/cows and ensure balanced feed with veterinary care.
Value-Added Products – Produce curd, ghee, paneer, and other milk-based items to diversify income.
Efficient Supply Chain – Establish local collection, packaging, and doorstep delivery to urban and rural markets.
Sustainability Measures – Use cow dung for biogas/manure and implement water conservation practices.
Technology Integration – Implement digital tools for cattle health tracking, inventory, and customer orders.

## Slide 6: Project Deliverables
Well-Established Dairy Farm Infrastructure – Cattle sheds, storage facilities, and mechanized milking system.
Healthy & Productive Cattle Herd – High-yield cows/buffaloes with proper veterinary care.
Daily Fresh Milk Supply – Consistent delivery of hygienic milk to consumers.
Value-Added Products – Production of curd, ghee, paneer, and other dairy products.
Efficient Distribution Network – Local and urban supply chain for timely product delivery.
Sustainability Initiatives – Use of dung for manure/biogas and eco-friendly practices.
Employment Generation – Jobs for local community and training in modern dairy practices.

## Slide 7: Success Criteria
Daily Milk Production Targets Met – Achieve planned liters of milk per day from healthy cattle.
High Product Quality – Maintain hygienic, fresh, and chemical-free milk and dairy products.
Customer Satisfaction – Positive feedback, repeat buyers, and growing customer base.
Sustainability Goals – Effective use of dung for manure/biogas and eco-friendly farming practices.
Profitability – Steady increase in revenue and reduction in wastage.
Community Impact – Job creation and support for local farmers.
User Adoption: At least 80% of targeted customers can place and track orders successfully.

## Slide 8: Methods / Approach
Requirement gathering & stakeholder analysis
Solution design & prototyping
Development (web & mobile)
Testing & UAT
Deployment & Go Live
Post-launch support & maintenance

## Slide 9: Resources Required
People: Project Manager, BA, Developers, Testers, Network & DB Admin
Estimated budget: Rs. 15-20 Lakhs (initial phase)
Farm Staff – for managing cattle, milk production, and product quality.
Project Team – Business Analyst, Project Manager, IT developers, UI/UX designers, testers.
Delivery Staff / Logistics Partners – for order fulfillment.
Customer Support Team – to handle inquiries, complaints, and feedback.
Marketing Team – for promotions, campaigns, and customer engagement
Website & Mobile App Platform – e-commerce solution for customers to place orders.
Hosting & Cloud Infrastructure – to ensure scalability and uptime.
Payment Gateway Integration – secure transactions (UPI, cards, wallets).
Inventory Management System – to track milk and dairy product stock.
Logistics & Delivery Tracking System – real-time tracking of orders.
Data Security Tools – for cybersecurity and customer data protection

## Slide 10: Risks & Dependencies
Category | Risks | Dependencies
Operational | - Supply chain interruptions - Inventory spoilage - Order fulfillment errors - Staff shortage | - Reliable suppliers for feed & packaging - Skilled farm and delivery staff
Technical | - Website/app downtime - Payment gateway failures - Cybersecurity threats - Poor user experience | - Stable hosting & e-commerce platform - Integration with payment & logistics systems
Financial | - Fluctuating costs of feed & logistics - Low sales conversion - High operational costs | - Consistent revenue from online sales - Efficient cost management & budgeting
External / Regulatory | - Changes in food safety or e-commerce regulations - Natural disasters affecting livestock - Competition from other dairy stores | - Compliance with government regulations - Backup plans for natural disasters - Competitive pricing & marketing strategies

## Slide 11: Conclusion / Recommendation
Conclusion:
DD Dairy Farm Online Store connects farm-fresh dairy products directly to customers.
Enhances operational efficiency, market reach, and revenue consistency.
Proper risk management ensures reliability and trust.
Recommendations:
Invest in Technology: Secure, robust, and user-friendly online platform.
Strengthen Supply Chain: Reliable suppliers and cold chain logistics.
Focus on Quality & Compliance: Regular checks and regulatory adherence.
Implement Marketing Strategies: Social media, local campaigns, loyalty programs.
Monitor Performance: Track sales, customer behavior, and operational efficiency.

## Slide 12: Q&A
Contact details :8919988566
Open floor for discussion

## Slide 13
Thank You