## Slide 1: Project Title:LAS(Loan Automation System)
Prepared By Date:07-07-2025
A B Prem Kumar

## Slide 2: Overview:
Union Bank of India aims to automate its Loan Processing System through a web-based Loan Automation System (LAS), developed using the Waterfall methodology. This system addresses inefficiencies in the current manual processing of Retail and MSME loans

## Slide 3: Problem Statement
Manual loan processing by Credit Officers
Time-consuming calculations for eligibility and repayment
Manual preparation of Sanction Letters with EMI details
Manual documentation and Signature collection
Risk of Human errors and delays in Loan disbursal

## Slide 4: Solution
Develop LAS: a web-based application to automate Loan processing
Input Customer details (Name, Age, Income)
System calculates Loan eligibility and repayment period automatically
Auto-generates Sanction Letters with EMI and T&Cs
Auto-fills security documents for Signature

## Slide 5: Opportunity
Digital transformation in Banking
Improved customer experience through faster processing
Reduced workload on staff
Minimized errors and compliance risks
Positioning for future AI and Analytics Integration

## Slide 6: Purpose Statement (Goals)
To digitize and streamline the end-to-end Loan processing system
Improve operational efficiency
Reduce processing time and manual errors
Enhance Customer satisfaction and compliance

## Slide 7: Project Objectives
Develop a secure, scalable web application
Automate eligibility and repayment calculations
Generate and manage sanction and security documents digitally
Ensure smooth integration with internal Banking systems

## Slide 8: Success Criteria
100% automation of Loan eligibility and document generation
50% reduction in average processing time
High user adoption by Credit Officers
Accurate document outputs and compliance adherence
Positive feedback from Customers and Staff

## Slide 9: Methods / Approach
Development Methodology: Waterfall
Phases:
1. Requirement Gathering : Clear and well-defined.
Requirement elicitation from Credit Officers & IT
2. System Design (Architecture, UI/UX)
User-Centric Design: Involve Credit Officers and other Stakeholders
in the design process.
3. Implementation (Coding)
Technology : Java, Python, SQL databases
For APIs & Third-Party Integrations connect to credit bureaus like
Experian, CIBIL, Equifax for Credit Score and Finacle for CBS.
4.Testing: Comprehensive testing phases (Unit, Integration, User
Acceptance Testing)
Provide thorough training to all end-users.
5.Deployment :
Phased Rollout: Implement the system in stages, Retail loans
first then MSME.
6. Maintenance :Updates and Issue resolution

## Slide 10: Resources
People:
Client-Side:
Project Sponsor – 1 (Senior Management Representative)
Business Users – 4 (Retail Loans Officer, MSME Loans Officer, General Banking Officer, Credit Manager)
Bank IT Coordinator – 1 (For coordination with internal IT systems & security)
Compliance Officer – 1 (For legal, Documentation, and Audit Compliance)
IT SERVICE PROVIDER
Project Manager
Business Analysts - Requirement Phase
Developers - Development Phase
Test Engineers - Testing Phase
Credit Officers (SMEs)

## Slide 11
Time:
Total Duration: 12 Months
Sequential phase execution
Budget:
Estimated Budget of Rs.2.00 Crores for Development, Infrastructure, Licensing and Training.
Other:
Third-party software evaluation for document generation
Site visits to Branches for user feedback/workflow analysis
Reports from Dataquest and other analysts for insights into Loan automation trends and Regulatory compliance standards

## Slide 12: Risks and Dependencies
Risks:
Resistance to adopting digital systems
Data accuracy and migration risks
Integration challenges with Core Banking
Security vulnerabilities
Dependencies:
Timely access to CBS data
Involvement of Credit and Legal departments
Support from IT vendors and partners

## Slide 13: Approval & Acknowledgement
Role | Name | Signature | Date | Remarks / Approval Status
Project Sponsor | Pankaj Trivedi | Gpt | 07/07/2025 | Approved
Project Manager | Sam Vargheese | Psv | 07/07/2025 | Approved

## Slide 14: THANK YOU