Nurturing Process – Agile Deliverables –V2D2 August 2024

Agile Documents

Document 1: Definition of Done

Document 2- Product Vision

Document 3: User stories

Document 4: Agile PO Experience

Document 5: Product and sprint backlog and product and sprint burn down charts

Document 6: Sprint meetings

Answers:

Document 1: Definition of Done (DoD)

Project Name: CRM Salesforce for Banking

Prepared by: Lolabhattu Surya Lipkhitha

Date: 25/07/2025

Definition of Done Overview

The Definition of Done ensures that all work items (user stories, tasks, features) meet agreed quality and value standards before being considered “complete.” This aligns the development team, Product Owner, and stakeholders around clear expectations.

DoD Checklist – User Story Level

| Criteria Category | Definition/Activity |
| --- | --- |
| Functional Completion | • Code implemented for user story functionality • All acceptance criteria met |
| Testing | • Unit tests written and passed • Functional testing by QA completed • Feature tested on target devices/browsers |
| Design Approval | • UI/UX design reviewed and signed off by UX Designer |
| Code Quality | • Peer code review completed • Code refactored as per coding standards |
| Deployment | • Feature deployed to staging/test environment |
| Documentation | • Technical and user documentation updated |
| Product Validation | • Reviewed and approved by Product Owner • Linked tasks closed in Jira |
| Configuration | • Any new config/build changes documented |

DoD Checklist – Sprint Level

| Criteria Category | Definition/Activity |
| --- | --- |
| Sprint Planning | Sprint goals clearly defined and committed |
| Demo Readiness | All stories complete and demo-ready |
| Regression Testing | Completed for impacted features |
| Sprint Review | Conducted with stakeholders |
| Sprint Retrospective | Completed with documented improvement points |

DoD Checklist – Release Level

| Criteria Category | Definition/Activity |
| --- | --- |
| Integration | Successfully integrated with core banking APIs |
| UAT Completion | UAT conducted and signed-off by business users |
| Training | RM onboarding/training completed |
| Go-Live Readiness | Final deployment verified on production-like environment |
| Support Readiness | Post-release support plan and issue resolution process in place |

DoD Checklist for Each User Story

The following checklist represents the agreed-upon criteria that must be fulfilled before any user story is marked as “Done”

| S No | DoD Criteria | Status |
| --- | --- | --- |
| 1 | Produced code for all presumed functionalities of the user story | ☐ |
| 2 | Assumptions and conditions of the user story are met | ☐ |
| 3 | Project builds successfully without any errors | ☐ |
| 4 | Unit tests are written and all tests are passing | ☐ |
| 5 | Feature is deployed on a test environment identical to the production platform | ☐ |
| 6 | Tests passed on all devices/browsers listed in project assumptions | ☐ |
| 7 | UX designer has reviewed and approved the UI/UX design | ☐ |
| 8 | QA team has tested the feature and all reported issues are resolved | ☐ |
| 9 | Feature is validated against the defined acceptance criteria | ☐ |
| 10 | Feature has been reviewed and approved by the Product Owner | ☐ |
| 11 | Necessary refactoring has been completed to improve code quality | ☐ |
| 12 | All relevant configuration or build changes are documented | ☐ |
| 13 | Required documentation (user manuals, tech docs, etc.) is updated | ☐ |
| 14 | Peer code review has been completed and any suggested improvements are implemented | ☐ |

- This checklist is used by the Scrum Team during the Sprint Review and/or before a release deployment.

- A story is considered “Done” only when all items are checked.

- The checklist promotes transparency, shared accountability, and consistent delivery quality.

Document 2- Product Vision

| Scrum Project Name | CRM Salesforce for Banking |  |  |
| --- | --- | --- | --- |
| Venue | Conference Room / Virtual |  |  |
| Date : 25/07/2025 | Start time : 10:00 AM | End Time : 12:00 PM | Duration : 2 hours |  |
| Client | COEPD BANK ltd |  |  |
| Stakeholder list | Project Sponsor, Product Owner, Relationship Managers, IT Head |  |  |
| Scrum Team |  |  |  |
| Scrum Master | Varshini |  |  |
| Product Owner | Likhitha |  |  |
| Scrum Developer 1 | Sai |  |  |
| Scrum Developer 2 | Srija |  |  |
| Scrum Developer 3 | Praneetha |  |  |
| Scrum Developer 4 | Veera |  |  |
| Scrum Developer 5 | Aditya |  |  |

Vision

| Target Group | Needs | Product | Value |
| --- | --- | --- | --- |
| Relationship Managers (RMs) in the banking sector. Mid- to large-sized banks seeking better customer engagement. | RMs struggle to track calls, log remarks, and follow up with customers. Manual methods lead to missed leads and poor customer service. | A Salesforce-based CRM platform to manage RM portfolios, track customer interactions, and improve service delivery. Real-time, mobile-compatible, and integrated with core banking systems. | Increases lead conversions via SA/CA references. Reduces manual work by 50%. Boosts customer satisfaction and transparency. Aligns with business goals to enhance productivity and cross-selling. |

Document 3: User stories

EPIC 1: Portfolio Management

| User story No : US001 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO view my customer portfolio, SO THAT I can prepare before calls. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Customer list loads with names and engagement levels |  |  |  |

| User story No : US002 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO filter customers by account type, SO THAT I can prioritize follow-ups. |  |  |  |
| BV : 250 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Filter for SA/CA and engagement score |  |  |  |

| User story No : US003 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO search customers by name or ID, SO THAT I can access them faster. |  |  |  |
| BV : 200 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Search bar returns exact match with suggestions |  |  |  |

| User story No : US004 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO tag key customers, SO THAT I can track priority accounts. |  |  |  |
| BV : 280 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Add custom tags to profiles |  |  |  |

| User story No : US005 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO group customers by location, SO THAT I can plan in-person visits. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Grouping option by branch or region |  |  |  |

EPIC 2: Call Logging

| User story No : US006 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO log details of customer calls, SO THAT I can track conversations. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Mandatory remarks field and timestamp |  |  |  |

| User story No : US007 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO assign follow-up dates, SO THAT I never miss a callback. |  |  |  |
| BV : 250 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Follow-up calendar field available |  |  |  |

| User story No : US008 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO choose the purpose of the call, SO THAT call types are categorized. |  |  |  |
| BV : 220 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Options like Inquiry, Complaint, Lead |  |  |  |

| User story No : US009 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO attach documents during call logging, SO THAT records are complete. |  |  |  |
| BV : 280 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Attach PDF, image, or notes |  |  |  |

| User story No : US010 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO view past call logs, SO THAT I can check history before next calls. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA List of past calls with date and outcome |  |  |  |

EPIC 3: Reference Tracking

| User story No : US011 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO log SA/CA references, SO THAT I can generate leads. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Input for referred name, contact, and type |  |  |  |

| User story No : US012 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO track the status of each reference, SO THAT I know progress. |  |  |  |
| BV : 250 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA New, Contacted, Converted |  |  |  |

| User story No : US013 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO assign a reference to a team member, SO THAT they can follow up. |  |  |  |
| BV : 220 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Assignee field in form |  |  |  |

| User story No : US014 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Relationship Manager, I WANT TO view a report of my references, SO THAT I can monitor performance. |  |  |  |
| BV : 280 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Report by status and date |  |  |  |

| User story No : US015 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO view top-performing RMs by references, SO THAT I can reward achievements. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Dashboard view with RM-wise count |  |  |  |

EPIC 4: Reporting & Dashboard

| User story No : US016 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO view RM call stats, SO THAT I can evaluate productivity. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Daily, weekly, monthly call counts |  |  |  |

| User story No : US017 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO view conversion rates from references, SO THAT I can track lead success. |  |  |  |
| BV : 250 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Total vs. converted reference graph |  |  |  |

| User story No : US018 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO export reports, SO THAT I can share with stakeholders. |  |  |  |
| BV : 220 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Export as PDF/Excel |  |  |  |

| User story No : US019 | Task: 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO filter reports by date range, SO THAT I can analyze trends. |  |  |  |
| BV : 280 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Date filter with custom range option |  |  |  |

| User story No : US020 | Task: 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A Manager, I WANT TO view missed follow-ups, SO THAT I can coach RMs better. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA List of overdue actions |  |  |  |

Document 4: Agile PO Experience

Project Name: CRM Salesforce for Banking

Product Owner: Lolabhattu Surya Likhitha

Date: 25/07/2025

The Role of the Product Owner

As the Product Owner (PO) for the CRM Salesforce for Banking project, my role was central to the product’s success. I acted as a bridge between stakeholders and the development team, making sure the product vision remained aligned with business goals and market needs. I translated business requirements into user stories and collaborated closely with cross-functional teams through every sprint.

Responsibilities of a Product Owner (PO)

1. Market Analysis

- I analyzed the needs of relationship managers (RMs) in the banking sector who were manually managing customer portfolios.

- Through competitive analysis, I reviewed existing CRM solutions like Zoho and Microsoft Dynamics to identify Salesforce’s edge in integration, flexibility, and usability.

- I validated the market demand by engaging with the bank’s leadership team and conducting interviews with RMs and IT teams. This helped justify the investment and feature selection.

2. Enterprise Analysis

- I performed due diligence by identifying integration feasibility with the bank’s core systems (e.g., customer master database, telephony, lead tracking tools).

- Explored regulatory compliance and customer data privacy issues to ensure product readiness.

- I assessed the ROI potential by estimating time saved, lead conversion improvement, and operational efficiency.

3. Product Vision and Roadmap

- I crafted a clear product vision: “To enable seamless customer engagement and lead tracking for Relationship Managers using CRM Salesforce.”

- I structured a 12-week product roadmap divided into 6 sprints. Each sprint focused on delivering value incrementally:

  - Sprint 1–2: Portfolio view setup

  - Sprint 3–4: Call logging and follow-ups

  - Sprint 5–6: Lead tracking and reporting dashboards

  - Sprint 7: UAT and Go-Live

4. Managing Product Features

- I collaborated with stakeholders (Branch Managers, IT Heads, and RMs) to gather detailed functional needs.

- I prioritized Epics and features based on business urgency, effort estimates (CP), and business value (BV).

- I ensured that all features directly tied back to user goals and business objectives—such as tracking SA/CA references or improving RM productivity.

5. Managing Product Backlog

- I created and maintained the Product Backlog in Jira, updating it weekly after backlog grooming meetings.

- I ensured stories were well-defined and INVEST-compliant (Independent, Negotiable, Valuable, Estimable, Small, Testable).

- Based on changing stakeholder inputs and sprint reviews, I frequently reprioritized stories and epics.

6. Managing Overall Iteration Progress

- I conducted Sprint Planning meetings, where I presented top-priority stories and clarified doubts from developers and testers.

- I participated in Daily Scrum meetings to unblock the team and monitor progress.

- During Sprint Reviews, I demoed features to stakeholders and gathered feedback.

- In Sprint Retrospectives, I reviewed what went well and what could be improved alongside the Scrum Master and BA.

- I collaborated in backlog refinement meetings to keep the pipeline ready for upcoming sprints.

Key Learnings from this Project

- I learned how to write effective User Stories that included:

  - Story Number

  - Business Value (BV) & Complexity Points (CP)

  - Tasks

  - Acceptance Criteria

- I understood how to maintain transparency with stakeholders and adjust the product scope without derailing sprint commitments.

- I practiced using Agile estimation techniques, such as story pointing and relative sizing with the Scrum Team.

- I gained hands-on exposure to CRM Salesforce, Jira for backlog management, and Postman for API testing.

- I also improved my skills in conflict resolution, stakeholder communication, and collaborative sprint delivery.

Agile PO’s Strategic Contribution

In Scrum, the Product Owner is the voice of the customer. I served as a liaison across business, development, and testing teams, ensuring that the team delivered a product that was:

- Technically feasible

- Business relevant

- User-friendly

- Agile in adaptation

My role involved continuously communicating changes, addressing business needs, and converting them into technical requirements that could be executed in an iterative fashion.

Document 5: Product and Sprint Backlog – CRM Salesforce for Banking

| Product Backlog |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| US001 | View customer portfolio | Load customer data, design table | High | 300 | 2 | 1 |
| US002 | Log call remarks | Create input form, DB entry, test logging | High | 280 | 2 | 1 |
| US003 | Log SA/CA references | Reference form, status tracker | Medium | 250 | 2 | 2 |
| US004 | View RM performance reports | Reporting module, filter setup | Medium | 220 | 2 | 3 |
| US005 | Search customers | Search bar UI, DB query, result handling | High | 200 | 1 | 2 |
| US006 | Assign follow-up dates to calls | Calendar integration, validation | Medium | 260 | 2 | 1 |
| US007 | Categorize call types | Dropdown list, DB tagging | Medium | 240 | 1 | 1 |
| US008 | Attach documents to call log | File upload UI, DB linking | High | 280 | 2 | 1 |
| US009 | View past call logs | History UI, search past logs | Medium | 300 | 2 | 1 |
| US010 | Group customers by region | Region tags, grouping logic | Medium | 270 | 2 | 2 |
| US011 | Track reference status | Status field, update logic | Medium | 250 | 2 | 2 |
| US012 | Assign references | Assignee dropdown, role mapping | Low | 220 | 1 | 2 |
| US013 | Reference performance report | Dashboard chart, filters | Medium | 280 | 2 | 3 |
| US014 | Top RM by references | Count by RM, leaderboard view | High | 300 | 2 | 3 |
| US015 | Tag key customers | Custom tags, visual marker | Medium | 260 | 2 | 2 |
| US016 | Daily/weekly call stats | Call count logic, filter | High | 300 | 2 | 3 |
| US017 | Conversion report from references | Ratio chart, filter | Medium | 250 | 2 | 3 |
| US018 | Export reports | Export as PDF/Excel | Medium | 220 | 1 | 3 |
| US019 | Date filter for reports | Date picker, filter function | Medium | 280 | 2 | 3 |
| US020 | Missed follow-up list | Overdue query, alert highlight | High | 300 | 2 | 3 |

| Sprint Backlog |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| US001 | View customer portfolio | Load customer data, design table | Dev1 | To Do | 4 hrs |
| US002 | Log call remarks | Create input form, DB entry, test logging | Dev2 | In Progress | 6 hrs |
| US003 | Log SA/CA references | Reference form, status tracker | Dev3 | Completed | 8 hrs |
| US004 | View RM performance reports | Reporting module, filter setup | Dev4 | To Do | 4 hrs |
| US005 | Search customers | Search bar UI, DB query, result handling | Dev5 | In Progress | 6 hrs |
| US006 | Assign follow-up dates to calls | Calendar integration, validation | Dev1 | Completed | 8 hrs |
| US007 | Categorize call types | Dropdown list, DB tagging | Dev2 | To Do | 4 hrs |
| US008 | Attach documents to call log | File upload UI, DB linking | Dev3 | In Progress | 6 hrs |
| US009 | View past call logs | History UI, search past logs | Dev4 | Completed | 8 hrs |
| US010 | Group customers by region | Region tags, grouping logic | Dev5 | To Do | 4 hrs |
| US011 | Track reference status | Status field, update logic | Dev1 | In Progress | 6 hrs |
| US012 | Assign references | Assignee dropdown, role mapping | Dev2 | Completed | 8 hrs |
| US013 | Reference performance report | Dashboard chart, filters | Dev3 | To Do | 4 hrs |
| US014 | Top RM by references | Count by RM, leaderboard view | Dev4 | In Progress | 6 hrs |
| US015 | Tag key customers | Custom tags, visual marker | Dev5 | Completed | 8 hrs |
| US016 | Daily/weekly call stats | Call count logic, filter | Dev1 | To Do | 4 hrs |
| US017 | Conversion report from references | Ratio chart, filter | Dev2 | In Progress | 6 hrs |
| US018 | Export reports | Export as PDF/Excel | Dev3 | Completed | 8 hrs |
| US019 | Date filter for reports | Date picker, filter function | Dev4 | To Do | 4 hrs |
| US020 | Missed follow-up list | Overdue query, alert highlight | Dev5 | In Progress | 6 hrs |

Sprint Burn down charts:

Sprint  : Sprint 1|||| Estimation level : Story Point

Sprint  : Sprint 1|||| Estimation level : Work Item Count

Sprint  : Sprint 1|||| Estimation level : Time

Sprint  : Sprint 2|||| Estimation level : Story Points

Sprint  : Sprint 2|||| Estimation level : Work Item Counts

Sprint  : Sprint 2|||| Estimation level : Time

Sprint  : Sprint 3|||| Estimation level : Story Points

Sprint  : Sprint 3|||| Estimation level : Work Item Count

Sprint  : Sprint 3|||| Estimation level : Time

Sprint  : Sprint 4|||| Estimation level : Story points

Sprint  : Sprint 4|||| Estimation level : Work Item Count

Sprint  : Sprint 4|||| Estimation level : Time

Product Backlog:

Product Backlog Board:

Document 6: Sprint Meetings

Meeting Type 1: Sprint Planning Meeting

| Field | Details |
| --- | --- |
| Date | 5-Aug-25 |
| Time | 10:00 AM – 11:30 AM |
| Location | Conference Room B / MS Teams |
| Prepared By | Surya Likhitha (Business Analyst) |
| Attendees | Scrum Master, Product Owner, Development Team, QA, BA |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Review of Product Backlog | Product Owner | 20 mins |
| Sprint Goal Finalization | Scrum Master | 15 mins |
| Story Point Estimation (Planning Poker) | Scrum Team | 30 mins |
| Task Breakdown & Assignment | Development Team | 20 mins |
| Final Q&A / Clarifications | Entire Team | 5 mins |

Other Information

| Observers | Mr. Ravi (IT Head), Mr. Henry (Client Representative) |
| --- | --- |
| Resources | Jira board access, CRM Salesforce sandbox, sprint backlog |
| Special Notes | Sprint 1 to focus on Portfolio Viewing & Call Logging module |

Meeting Type 2: Sprint Review Meeting

| Field | Details |
| --- | --- |
| Date | 19- Aug- 2025 |
| Time | 11:00 AM – 12:00 PM |
| Location | MS Teams / Conference Room A |
| Prepared By | Surya Likhitha (Business Analyst) |
| Attendees | Product Owner, Scrum Master, Development Team, QA, Stakeholders |

Sprint Summary Table

| Sprint Status | Things to Demo | Quick Updates | What’s Next |
| --- | --- | --- | --- |
| Sprint 1 completed successfully; 6/7 stories done | 1. Portfolio view screen 2. Customer detail popup 3. Add remark functionality | Minor UI enhancements requested by POBug fixed in remarks auto-save | Begin Sprint 2:- Reference Tracking module- Call logging analytics |

Meeting Type 3: Sprint Retrospective Meeting

| Field | Details |
| --- | --- |
| Date | 21-Aug-25 |
| Time | 3:00 PM – 4:00 PM |
| Location | MS Teams / Agile War Room |
| Prepared By | Surya Likhitha (Business Analyst) |
| Attendees | Scrum Master, Product Owner, Dev Team, QA, Stakeholder Rep |

Agenda Table

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint 1 Review | Clear sprint goal and good collaboration across roles | Minor delays in UI integration due to late API responses | Can API dependencies be finalized earlier in Sprint 2? | Sprint Backlog Item #CRM-SP1-03 |
| Retrospective Feedback | Product Owner appreciated RM portfolio demo | Few bugs discovered late due to skipped mid-sprint QA reviews | Can we add a mid-sprint QA check going forward? | QA Bug Tracker Entry #BUG-122 |
| Planning Improvements | Estimations using Planning Poker were accurate and well-timed | No time buffer for last-minute change requests | Should we include buffer in sprint capacity planning? | Sprint Planning Doc – 05 Aug 2025 |

Meeting Type 4: Daily Stand-up meeting

| Date | 22-Aug-25 |
| --- | --- |
| Time | 10:00 AM – 10:15 AM |
| Location | MS Teams / Daily Scrum Channel |
| Prepared By | Surya Likhitha (Scrum Team Member) |
| Attendees | Scrum Master, PO, Dev Team, QA |

Team Member Updates Format

| Name | What I did yesterday | What I will do today | Blockers |
| --- | --- | --- | --- |
| Developer 1 | Completed Portfolio API integration | Start UI binding for Portfolio screen | Awaiting endpoint test access |
| Developer 2 | Created database schema for Call Log and Reference Data | Begin backend logic for saving remarks and references | Clarification needed on SA/CA flow |
| Developer 3 | Completed login and user authentication module | Integrate user session into dashboard access | Waiting for UI mockups confirmation |
| QA Analyst | Wrote test cases for Call Logging module | Begin functional testing | None |
| Product Owner | Reviewed Sprint 1 progress with stakeholders | Prepare demo notes for Sprint Review | Need final input on reference logic |
| BA (Likhitha) | Updated user stories and clarified acceptance criteria | Participate in sprint review prep | None |