## Slide 1: Project Title: DB TRACKER
Prepared By: SHRUTI PARASHAR Date: 15/06/2025

## Slide 2: Situation/Problem/Opportunity: <<
SITUATION:-
The DB TRAKER tool is use for sales department ,where the employee generate the lead in tablet and open the bank account(saving account).
This the semi online process, where the employee need to fill the physical form ,capture the picture in the tablet and send the same to branch sales manager
Manager will do the analysis of form and if there is any rejection it will resend to employee id tray or if there is no rejection bsm will forward the form to Mumbai team .
There is possibility Mumbai team can also identify the rejection resend to the bsm tray
Then BSM again resend the same form to employee for rework
And after solving all the rejection this process will repeat
The account will get activated and deposit the kyc cheque
This cheque will be credited in customer account in 3 working days

## Slide 3: Problem:-
This whole process is very time consuming
In this employee need to fill the physical form in which employee faced a lot of problem like overwriting, physical form lost, scratch, form destroy, share the customer personal details by mistake,
If there is rejection form customer side employee revisit the customer and resolve the issue , so it is very difficult to get the appointment from the customer again and again. Because of this reason customer could irate and do the complaint also cancel the account so there are possibility to loose the customers trust
To avoid this situation employee may do the duplicate signature of the customer which is against the process
Employee having a fear to loose the account and target will not completed
Also the process is very lengthy because if there is any special case we need to take a multiple approval and signature of reporting authority and every employee have there own work so it is difficult to take a follow up of RA and get the approval and physical signature ,some time it takes a 2 to 3 days
After get the approval the BSM do the analysis and send it to another tray ,but there are approximate 30 to 40 people send the form to bsm so it takes a time to do the proper analysis of every form
And after sending the form to another team for activation if that team pick any rejection it could heat the branch score so it is very difficult and time taking activity for emp and BSM as well
So this whole process is very time taking and in this the employee and customer both are irate and bank will loose the business and client

## Slide 4: Opportunity:-
After analyzing this whole the process we can do this process online
We can removed the physical form to avoid the overwriting, form lost , or form destroy
We can fill the online form through the biometric and get the aadhar card information if the aadhar number is fetch the details automatically
Also put the pan card number to check the pan number is correct and linked to NSDL site
So there is no spelling mistake system will catch the details according to there document
Signature can be online
Take the online picture of customer and also fetch the adhere card photo
Submit the form send directly to the online team and get activate account with in 3 to 4 hours
Deposit the cheque it will credited to customer account 2 working days
This process helps to complete the task with in time
Customer will satisfy and help to increase the business

## Slide 5: Goal:-
To do this whole process online
Account should get activated with 1 working day
Reduce the time and process
Avoid the physical storage because it is also a cost cutting process
It increase the transparency
It helps to do the customer satisfaction and build the trust and increase the business

## Slide 6: Project Objectives:
Simplification:- Reducing the complexity of a process
Optimization:-making a process more effective and efficient
Streamlining:- Making a process more efficient by removing unnecessary steps and delays
Easy of use and enhancement :- improving the user experience of a process to make it easier to use
It help into sales for potential customer lead conversion
If we shift all this process from offline to online we can focus on customer services
Release the employee workload

## Slide 7: Success Criteria:
Reduced the processing time:- online process is faster than offline process
Improve accuracy and reduced the human error
24/7 accessibility:- online process are available at any time from any location
Improved the user interface:-online process can more user friendly process
Reduced the labor cost:-online process can streamline the process and reduced the labor cost
Online process reduced the physical infrastructure
Real time tracing:- online process provide the real time tracking process
It maintain the clear communication and maintain the transpharancy
All the detail are maintain on record if there is any need of retrieve
It help in data security
Online process must follow the regulation and complinces so there is less chance of any fraude and fake account

## Slide 8: SMART:-
Specific :- Reduced the time and process , transparency, anytime anywhere access , fast process, streamline the process
MEASURABLE:- activate account with in 1 working day,24/7 access, only 2 employee handle process 1 sourced and 2nd activation ,budget, timeline is 1 year , kyc cheque clear in 2days
Achievable:- reduced the process, transparency , reduced the workload, focus on customer services , customer satisfaction
Relevant:- this implementation is very important for employee and customer both because this will save both time, it is beneficial for bank as well
Time bound:- this project should be completed with in 1 year

## Slide 9: Methods/Approach:
Form a cross-functional committee with members from IT, Operations, Compliance, and Customer Service
.
Conduct process mapping of the current offline activation workflow.
Identify pain points, compliance needs and customer expectations
Define functional and non-functional requirements for the online system:
Online form submission
Document upload and validation
eKYC integration (Aadhaar/PAN)
OTP/email verification
Backend core banking system integration
Data security and regulatory compliance

## Slide 10: Evaluate vendor responses based on
Technical capability
Experience in BFSI domain
Compliance readiness
Cost and implementation timeline

## Slide 11: Begin system development/customization:
API integration (UIDAI,NSDL OFFICIAL SITE)
Security feature (two-factor authentication)
Conduct rigorous testing:
Functional Testing
Security Testing
UAT (User Acceptance Testing)
Train Users:-
Create user manuals, SOPs, and training videos.
Give Helpdesk/Support system
Provide the vedio
Go Live:-
Make necessary improvements based on real-time feedback.
Monitor performance and collect early feedback

## Slide 12: Resources:
People:-
Project manager- Mayank paliwal
BA- Shruti parashar
Technical team
Developer team
Testing team
Stakeholder
Clients
TIME:- timeline is 1 year

## Slide 13: Budget
Custom Development cost:- salary for BA, developers salary , data base admin, project manager 6 to 10 lakh
Infrastructure cost:- office rent, servers, electricity, backup system, internet cost, - 1 lakh to 2 lakh
Training session cost :- internal training and customer care 50000 to 100000
Licensing Fees:- Annual or lifetime license 2 to 5 lakh
Maintenance cost and support cost:- post deployment support- 3 lakh /year
Requirment gathering and documentation -150000
Development team :- 3 to 4 lakh
Travel and accomodtaion – 10 to 20 k
Total budget:- Approximate 26 lakh
Other resources :-
SOFTWARE:- development tool like java ,data base tool, auto send email parsing tool, certificate design templet tool
HARDWARE :- Strong dedicated servers for support the application and backup

## Slide 14: Risk and Dependency:-
RISK
System Downtime:-During transition, unplanned downtime may impact account activations
Security and fraud risk increases in online systems
Technical downtime could affect access to the new system
Regulatory Non-compliance:- Failure to meet RBI/KYC regulations in online environment.
Accessibility Issues:-Not all users may have smartphones or internet access.
Identity Verification Errors:- Online KYC may fail due to poor photo quality or wrong documents.
Budget overruns
Vendor delay:- client may delay sending their data and details affecting the delaying in worksflow
While updating a software system could get hang
Contineous chaging in requirement on the basis of clients feed back or daily review of users

## Slide 15: Dependencies:-
Regulatory Approval :- Must follow the guidelines of RBI norms for digital account opening and activation
KYC integration:- link aadhar ,PAN, TO NSDL,UIDAI API’S for digital kyc verification
Vendor/tech partner:-dependencies on 3rd party software developers
Contingency plan:- back up manual or hybrid process incase of technical failure
Staff training:- proper training to handle the queries and backend operation
Customer awareness:-campaigns to educate the user how to activate the account online
Must follow RBI norms for digital account opening and activation.

## Slide 16: Summary
Current challenges:-
Use of physical forms leads to overwriting, loss, and destruction.
Manual steps create delays, rejections, and rework loops between Employee → BSM → Mumbai Team.
Employee may take unauthorized shortcuts (e.g., duplicating signatures) due to target pressure.
Frequent customer revisits lead to customer dissatisfaction and possible complaints.
Manual approval collection takes 2–3 days due to reporting authority unavailability.
Time-consuming process resulting in loss of business and trust.
Proposed Digital Solution:-
Replace physical forms with digital KYC forms on tablets.
Auto-fetch data using biometric Aadhaar authentication and PAN validation.
Integrate with UIDAI and NSDL APIs to auto-fill data and reduce errors.
Enable online photo capture and e-signature.
Automate approval flow via digital trays for BSM and backend teams.
Reduce activation cycle to 3–4 hours vs current 3–5 days.
Cheque deposit credited in 2 working days.

## Slide 17: Expected outcomes:-
Faster account activation → from 3–5 days to 3–4 hours
Improved accuracy, compliance, and data security
Enhanced employee productivity and customer experience
Reduced customer complaints, fraud, and manual effort
Higher branch score and business retention

## Slide 18: COMPLETED BY:- SHRUTI PARASHAR PROJECT SPONSER:-ICICI BANK LTD PROJECT MANAGER:-MAYANK PALIWAL
THANK YOU