## Slide 1: “Seat Booking- Copeland, Pune” Agile Project
Prepared by- Ruchita Pawar

## Slide 2
Situation: Current IP Environment
Copeland India Pvt. Ltd. (Pune branch) operates with approximately 350 employees, but has limited seating capacity of about 270–280 seats.
The company follows a hybrid working model, where employees attend office on flexible schedules.
Due to fluctuating attendance, seat allocation is currently managed manually by HR and team leads.
This manual process often leads to inefficient seat utilization and last-minute confusion on working days.

## Slide 3
Problems: Challenges Identified
Frequent seat shortages and double bookings occur when multiple employees plan to work onsite simultaneously.
HR and managers lack real-time visibility into seat availability and occupancy trends.
Employees experience uncertainty and frustration, impacting productivity and overall workplace satisfaction.
Manual coordination via emails or messages consumes time and causes errors.
There is no central system to manage bookings, approvals, and reporting efficiently.

## Slide 4
Opportunities: Areas for Improvement
Implementing a digital Seat Booking App can streamline the entire seat allocation process.
Enables employees to pre-book seats and receive timely manager approvals, ensuring smooth operations.
Provides data-driven insights on office utilization to HR and management for planning future workspace needs.
Enhances employee satisfaction and productivity by ensuring fair and transparent seat availability.
Supports Copeland’s digital transformation and hybrid work strategy, improving efficiency and collaboration.

## Slide 5
Purpose Statement: Project Summary
Develop a mobile/web-based Seat Booking App.
Employees request seats in advance.
Manager approval workflow ensures fairness.
Real-time visibility of available seats.
Notifications for booking confirmation.
Agile methodology for phased and iterative delivery.

## Slide 6
Project Objectives
Implement digital seat booking to replace manual process.
Ensure seamless manager approval workflow.
Provide transparency of seat availability.

## Slide 7
Success Criteria
Seat conflicts reduced to <5%.
Manager approval turnaround <24 hrs.
80% employee adoption in 3 months.
100% transparency in seat allocation.

## Slide 8
Methods / Approach – Scrum Model
Agile Methodology is a flexible and iterative approach to project management and software development that focuses on delivering value to the customer quickly and efficiently. Agile breaks project into small, manageable parts called “sprints”, usually lasting 2–4 weeks.
Requirement Gathering:
Conduct stakeholder interviews (HR, IT, Managers, Employees).
Used elicitation techniques like Focus Groups, Interview, Questionnaire.
Documented AS-IS process challenges and TO-BE needs.
Prepared and validated Business Requirements Document (BRD).
Requirement Traceability Matrix (RTM)
Design:
Created UI/UX wireframes for showing features.
Prepared Mock-ups using Balsamiq tool.
Design seat map layout.
Define workflows & created Use Case diagram & Activity Diagram to show the work flow of the process.

## Slide 9
Development:
Sprint-based development (App front-end, back-end, DB setup)
Build and integrate portal features
Integration of manager approval workflow
Develop HR/Admin dashboard
Testing:
Conducted System Testing to validate functionality of configured workflows.
Logged defects and coordinated with team for fixes.
Functional testing
Test Case Document.
Continuous feedback loop & enhancements
UAT:
UAT with HR & selected employees
Fix defects, improve UX based on feedback
Gathered feedback, documented issues, and supported defect resolution.
Final Approval before full deployment.
Obtained formal sign-off from stakeholders for go-live readiness.

## Slide 10
Resources
Role | Count | Involvement Period
Project Manager | 1 | Full Project (9 months)
Java Developers | 4 | Design to Testing
Database Admins | 2 | Design to testing
System Admins | 2 | Dev, Testing, UAT
QA Testers | 2 | Testing & UAT
Business Analyst | 1 | Entire lifecycle (9 months)

## Slide 11
Phase | Duration | Key Activities
Requirement Gathering | 1 month | Stakeholder Interviews, Documentation
Design | 1 month | Wireframes, mock-ups, prototype
Development | 4 months | Coding, DB Setup
Testing | 2 months | QA testing
UAT | 1 month | Feedback, Bug fixes, Approval
Total Duration: 9 Months
Total Budget: 500,000

## Slide 12
Other resources:
Hardware: Servers for hosting the Application and database
Software: Development & Testing tools
Network: Secure global access (VPN, high-speed internet)
People: BA, HR, IT, Database Admin
Training resources for employees to use application.

## Slide 13
Risks
Low adoption by employees.
Technical downtime / infra issues.
Manager approval delays.
Data privacy & security concerns.

## Slide 14
Dependencies
Availability of IT team & budget approvals.
HR & Manager collaboration.
Infrastructure readiness (servers, devices).

## Slide 15
Thank You!