Online Agriculture Products Store

Project Scope:

This project aims to develop a user-friendly web and mobile application that enables farmers in remote areas to conveniently purchase fertilizers, seeds, and pesticides directly from manufacturers. It will streamline product listings, facilitate secure transactions, browsing, delivery management to farmer locations and ensure doorstep delivery, bridging the gap between agricultural suppliers and rural farmers through digital access.

Question 1:

Identify Business Process Model for Online Agriculture Store – (Goal, Inputs, Resources, Outputs,

Activities, Value created to the end Customer)

Goal

To create a digital platform connecting remote farmers with agriculture product manufacturers, enabling easy access to fertilizers, seeds, and pesticides.

Inputs

- Product details from manufacturers (type, quantity, price)

- Farmer registrations, product requirements & delivery information

- Internet connectivity and mobile/desktop/web app access

Resources

Organizational Resources:

- SOONY Company (Project owner)

- APT IT SOLUTIONS (Implementation partner)

Human Resources: Stakeholders (Henry, Pandu, Dooku, Peter, Kevin, Ben)

- Project Sponsor: Mr. Henry

- Financial Head: Mr. Pandu

- Project Coordinator: Mr. Dooku

- Stakeholders / Domain Experts: Peter, Kevin, Ben (Farmers)

- Development Team (APT IT SOLUTIONS):

- Project Manager

- Business Analyst

- UI/UX Designers

- Frontend Developers

- Backend Developers

- Mobile App Developers

- QA/Testers

- DevOps Engineer

Financial Budget and Time Duration:

- Budget 2 Crores INR and                                                                                                                                                      18 months Duration under CSR initiative.

Key Outputs:

- Fully Functional Online Agriculture Product Platform

  - Web application

  - Mobile application (Android/iOS)

- Product Management System

  - Manufacturers can list fertilizers, seeds, and pesticides with details (price, quantity, usage, etc.)

- Farmer Interface

  - Farmers can browse, search, and purchase products

  - Easy registration and user-friendly navigation

- Order and Delivery Management System

  - Farmers can place orders

  - System tracks shipping and delivery to remote locations

- Secure Payment Gateway Integration

  - Digital payments for product purchases

- Communication Channel

  - Direct interaction between farmers and manufacturers (chat/support/helpdesk)

- Admin Dashboard

  - Managed by SOONY/Committee to oversee platform activity, approvals, reports, etc.

- Reports & Analytics

  - Data on farmer usage, product demand, order volume, delivery performance

- Overall Outcome:

An accessible, user-friendly online platform that empowers remote farmers to easily obtain essential agricultural inputs, leading to better crop production and improved livelihood --- while fulfilling SOONY's CSR goals.

Activities:

      - Collecting and uploading product data by manufacturers

      - Farmer registration and profile setup

      - Browsing and searching products

      - Adding items to cart (Add to Card Items) and placing orders

      - Payment processing and confirmation

      - Order fulfilment and delivery

      - Feedback and support

Values Created to the End User (Farmers)

- Easy access to quality agricultural products

- User friendly Saves time and travel costs

- Empowerment through direct communication with manufacturers

Question 2:

Mr Karthik is doing SWOT analysis before he accepts this project. What Aspects he Should consider as Strengths, as Weaknesses, as Opportunity and as Threats. answer to this question

| S - Strengths - Wide range of agricultural products - Convenience for farmers - Potential for vendor partnerships | W - Weaknesses - Initial development costs - Dependency on technology - Logistics and delivery challenges |
| --- | --- |
| O - Opportunities - Growing adoption of e-commerce - Expansion to new regions - Value-added services for farmers | T - Threats - Competition from existing platforms - Internet connectivity issues - Weather-related disruptions affecting supply |

Strength

- Backed by Mr. Henry, a successful businessman with financial strength and social commitment.

- Targets a real need for farmers in remote areas, improving their livelihood.

- Budget & Timeline: ₹2 Crores and 18 months duration under CSR initiative provide financial and planning clarity.

- Dedicated Stakeholders: Farmers (Peter, Kevin, Ben) directly involved for authentic requirements.

Weaknesses

- Digital Literacy Gap - Target users (farmers) may lack the technical skills to use the platform.

- Internet Accessibility - Remote villages may have poor or inconsistent internet connectivity. internet connectivity, device access

- Logistics Complexity - Delivering physical products to rural areas can be challenging and costly. Logistics and delivery hurdles for rural locations

Opportunities

- Possible collaboration with government schemes promoting digital agriculture. supporting agri-tech and rural development

- Expand services to include farming tools, machinery, or training modules

- Empower local entrepreneurs through logistics and last-mile delivery

- Collect valuable agricultural data for future innovations

Threats:

- Competition from existing e-commerce/agri-tech platforms

- Cybersecurity and data privacy risks

- Unpredictable farming seasons and market conditions affecting demand

Question 3:

Mr Karthik is trying to do feasibility study on doing this project in Technology (Java), Please help him with points (HW SW Trained Resources Budget Time frame) to consider in feasibility Study.

Feasibility Study for Online Agriculture Store (Java Technology)

| Hardware (HW): | - Web server (e.g., Apache Tomcat) with sufficient RAM & GPU - Secure hosting (e.g., cloud-server infrastructure like AWS, Azure, GCP) - Backup storage systems |
| --- | --- |
| Trained Resources: | - Java Development Kit (JDK 17+ preferred) - Java EE or Spring Boot framework for backend - Frontend: UI; MySQL/PostgreSQL - Tools: Eclipse/IntelliJ, Git, Jenkins, JIRA - API integration tools for payment and logistics services |
| Project Team: | - 1 Java Full-Stack Developer - 1 UI/UX Designer - 1 QA/Tester (Optional) - (Optional) Support Executive post-launch |
| Budget: | - Development cost for 6–8 months - Infrastructure cost (cloud server, bandwidth) - Licensing fees, if any - Marketing/promotion expenses |
| Time Frame: | - Total: 6–7 months from project start |

With proper planning in hardware, software, skilled team, budget control, and phased development, the project can be successfully completed within the 18-month CSR initiative timeframe.

- Skilled in full-stack development

- Ensure thorough testing and performance optimization

- Coordinate with stakeholders and vendors

- Licensing: Potential costs for enterprise software, security tools, or cloud services

- Training Costs: Upskilling staff, onboarding farmers or vendors

- Marketing & Outreach: Promoting platform among remote farmers

- Buffer Margin: Set aside 10–15% for contingency expenses

Question 4:

Mr Karthik must submit Gap Analysis to Mr Henry to convince to initiate this project. What points (compare AS-IS existing process with TO-BE future Process) to showcase in the GAP Analysis

GAP Analysis identifies critical challenges faced by remote farmers in accessing agricultural products and outlines how the proposed Online Agriculture Store application will bridge these gaps through technology, improving accessibility, efficiency, and transparency for both farmers and manufacturers.

Please find the below sheet to check AS-IS and TO-BE

https://docs.google.com/spreadsheets/d/16MltKmOq5GINXMvKt7bQoCAQLByxQ6KrUraQI3_L0bg/edit?gid=0#gid=0

Overall Gap Identified

A major disconnect exists between farmers’ needs and existing supply channels. This project bridges that gap by introducing convenience, transparency, and empowerment—digitally transforming rural agriculture procurement. The new system will empower farmers, increase efficiency, reduce costs, and improve agricultural productivity — strongly supporting the case for project initiation under the CSR initiative.

Question 5:

List down different risk factors that may be involved (BA Risks And process/Project Risks)

Below is a tailored list of Business Analysis (BA) Risks and Process/Project Risks specific to the online agriculture product store project described, building on the previous response and focusing on the context provided. The risks are organized to reflect the project’s unique challenges, stakeholders (Mr. Henry, Peter, Kevin, Ben, SOONY committee, APT IT Solutions team), and objectives (user-friendly platform for farmers and manufacturers). This list refines and prioritizes risks relevant to the project’s scope, budget (2 Crore INR), timeline (18 months), and CSR initiative.

Absolutely! Let’s break down the possible risks into two key areas relevant to your project role: Business Analyst (BA) Risks and Process/Project Delivery Risks. Understanding these early helps the team plan proactive mitigation strategies.

These are the effectively manage the risks identified for Mr. Henry’s online agriculture product store project, the following optional risk management suggestions are tailored to the context of developing a user-friendly web/mobile application for farmers and manufacturers.

Business Analysis (BA) Risks

These risks relate to the requirements elicitation, analysis, and management processes for the online agriculture product store.

# Incomplete Requirements:

## Risk: Missing key requirements due to limited engagement with diverse farmers or manufacturers, leading to an incomplete feature set.

## Context: Peter, Kevin, and Ben may represent specific farming needs (e.g., fertilizers, seeds, pesticides), but other farmers in different regions may have unique requirements (e.g., organic products, specific crop varieties).

## Impact: The platform may lack critical features, reducing its utility for a broader farmer base and failing Mr. Henry’s CSR goal.

## Mitigation: Conduct surveys and focus groups with a wider farmer demographic beyond Peter, Kevin, and Ben, and validate requirements with manufacturers for comprehensive product listings.

# Miscommunication with Stakeholders:

## Risk: Misinterpretation of requirements due to farmers’ limited technical knowledge or manufacturers’ complex demands.

## Context: Farmers may describe needs in non-technical terms (e.g., “easy to use”), while manufacturers may request advanced features (e.g., bulk uploads, analytics), leading to misaligned expectations.

## Impact: Features may not meet user needs, reducing platform adoption.

## Mitigation: Use visual aids (e.g., mockups, flowcharts) and iterative feedback sessions to clarify requirements with all stakeholders.

# Stakeholder Unavailability:

## Risk: Limited availability of farmers (Peter, Kevin, Ben) due to farming schedules or remote locations.

## Context: Their rural setting may limit access to meetings or internet-based communication, delaying requirements validation.

## Impact: Slowed requirements finalization, risking the 18-month timeline.

## Mitigation: Leverage asynchronous communication (e.g., email, recorded feedback) and involve Mr. Henry to coordinate with farmers.

# Scope Creep:

## Risk: Additional features (e.g., farmer training modules, real-time weather integration) requested by Mr. Henry or the SOONY committee mid-project.

## Context: Mr. Henry’s passion for helping farmers may lead to expanding the platform’s scope beyond core e-commerce functionality.

## Impact: Increased costs and delays, straining the 2 Crore INR budget and timeline.

## Mitigation: Define a clear scope with Mr. Henry, Mr. Pandu, and Mr. Dooku, and enforce a change control process for new feature requests.

# Inaccurate Assumptions:

## Risk: Assumptions about farmers’ digital literacy, device preferences (mobile vs. web), or internet access in remote areas.

## Context: The platform assumes internet connectivity, but rural farmers may have unreliable or no access, preferring mobile apps over web interfaces.

## Impact: Low adoption if the platform is inaccessible or too complex for farmers.

## Mitigation: Conduct user research to confirm farmers’ access to devices and internet, and prioritize a lightweight, mobile-first design.

# Conflicting Requirements:

## Risk: Farmers prioritizing simplicity (e.g., easy navigation) vs. manufacturers demanding complex features (e.g., detailed product customization).

## Context: Peter may want a simple product selection process, while manufacturers may push for advanced catalog management, creating tension.

## Impact: Delays in finalizing requirements and potential dissatisfaction among stakeholders.

## Mitigation: Facilitate joint workshops to prioritize features and balance usability with functionality, ensuring farmer needs take precedence.

# Lack of Stakeholder Alignment:

## Risk: Misalignment between the SOONY committee (Mr. Henry, Mr. Pandu, Mr. Dooku) and farmers on project priorities.

## Context: Mr. Pandu (Financial Head) may focus on cost control, while farmers prioritize free delivery or low-cost products.

## Impact: Conflicting priorities could delay decisions or compromise the platform’s effectiveness.

## Mitigation: Establish a stakeholder alignment matrix and hold regular reviews to ensure consensus on goals.

# Inadequate Documentation:

## Risk: Poorly documented requirements leading to misinterpretation by developers (Ms. Juhi, Mr. Teyson, Ms. Lucie, Mr. Tucker, Mr. Bravo).

## Context: Complex product details (e.g., fertilizer specifications, seed variants) require precise documentation to ensure accurate implementation.

## Impact: Rework or incorrect features, increasing costs and delays.

## Mitigation: Use standardized templates (e.g., user stories, process flows) and validate documentation with stakeholders and the development team.

# Insufficient Domain Knowledge:

## Risk: Limited understanding of agriculture-specific needs (e.g., seasonal seed requirements, pesticide regulations) by the BA.

## Context: The BA may not be familiar with agricultural product nuances or rural logistics challenges.

## Impact: Missed requirements or non-compliant features, such as ignoring pesticide safety standards.

## Mitigation: Collaborate with Peter, Kevin, Ben, and agricultural experts to gain domain knowledge and validate requirements.

# Change Resistance:

## Risk: Farmers resisting the platform due to unfamiliarity with digital tools or preference for local vendors.

## Context: Remote farmers may trust traditional procurement methods over an online system.

## Impact: Low platform adoption, undermining Mr. Henry’s CSR objective.

## Mitigation: Design a user-friendly interface with minimal learning curve and provide training or on boarding support for farmers.

# These risks relate to the management and execution of the project by APT IT Solutions.

# Schedule Delays:

## Risk: Delays in development, testing, or deployment due to technical challenges or dependencies.

## Context: The 18-month timeline may be ambitious for building a robust e-commerce platform with features like product listings, order processing, and delivery tracking.

## Impact: Missing the deadline could delay benefits to farmers and affect SOONY’s CSR initiative.

## Mitigation: Mr. Vandanam (Project Manager) should develop a detailed Gantt chart with milestones, monitored by Mr. Karthik (Delivery Head), and include buffer time for unforeseen issues.

# Budget Overruns:

## Risk: Costs exceeding the 2 Crore INR budget due to underestimation of development, infrastructure, or third-party integration costs.

## Context: Features like real-time delivery tracking or multi-language support may increase expenses.

## Impact: Financial strain on SOONY and APT IT Solutions, potentially compromising quality.

## Mitigation: Mr. Pandu and Mr. Vandanam should conduct regular budget reviews and prioritize essential features within the budget.

# Resource Constraints:

## Risk: Limited expertise or availability of the development team (Ms. Juhi, Mr. Teyson, Ms. Lucie, Mr. Tucker, Mr. Bravo) or infrastructure support (Mr. Mike, Mr. John).

## Context: The team may lack experience in agriculture-focused e-commerce or rural logistics integrations.

## Impact: Suboptimal platform performance or delays in tasks like database optimization.

## Mitigation: Assess team skills early, provide training if needed, and ensure Mr. Mike (Network Admin) and Mr. John (DB Admin) plan for scalable infrastructure.

# Poor Risk Management:

## Risk: Inadequate identification or mitigation of risks, such as technical or stakeholder issues.

## Context: Mr. Dooku (Project Coordinator) may not have a robust risk management plan, leading to reactive problem-solving.

## Impact: Unaddressed risks could escalate, causing delays or quality issues.

## Mitigation: Develop a risk register with input from the BA, Mr. Vandanam, and the team, reviewed regularly by Mr. Dooku.

# Scope Misalignment:

## Risk: The platform’s features may not align with Mr. Henry’s goal of empowering remote farmers.

## Context: Overemphasis on manufacturer features (e.g., advanced product management) could overshadow farmer usability.

## Impact: Failure to serve farmers effectively, reducing the platform’s CSR impact.

## Mitigation: Regularly validate deliverables with Mr. Henry and farmers to ensure alignment with project objectives.

# Technology Risks:

## Risk: Issues with platform scalability, security, or compatibility, especially for rural users with poor internet.

## Context: The platform must support low-bandwidth environments and ensure secure transactions.

## Impact: Downtime or poor performance could discourage farmer adoption.

## Mitigation: Mr. Mike and Mr. John should ensure robust network and database solutions, while developers prioritize lightweight, secure designs with offline capabilities.

# Team Collaboration Issues:

## Risk: Miscommunication or conflicts among developers, testers (Mr. Jason, Ms. Alekya), or other roles.

## Context: A large team working under a tight timeline may face coordination challenges.

## Impact: Delays in development or testing, leading to quality issues.

## Mitigation: Mr. Vandanam should implement agile methodologies (e.g., daily stand-ups, sprint reviews) to enhance collaboration.

# Vendor or Third-Party Risks:

## Risk: Delays or issues with third-party services, such as payment gateways or delivery providers.

## Context: Rural delivery logistics may be unreliable, and payment systems must support local methods (e.g., UPI, cash-on-delivery).

## Impact: Failed transactions or delivery delays could frustrate farmers.

## Mitigation: Select reliable vendors early, test integrations thoroughly, and plan for fall back options (e.g., manual payment processing).

# Regulatory/Compliance Risks:

## Risk: Non-compliance with agricultural regulations (e.g., pesticide certifications) or e-commerce laws (e.g., data privacy).

## Context: Pesticides and fertilizers require regulatory approvals, and farmer data must comply with India’s data protection laws.

## Impact: Legal penalties or platform restrictions could halt operations.

## Mitigation: Consult agricultural and legal experts to ensure compliance in product listings and data handling.

# Inadequate Testing:

## Risk: Insufficient testing by Mr. Jason and Ms. Alekya, missing critical bugs in user flows.

## Context: The platform must handle diverse scenarios (e.g., browsing, ordering, tracking) across web and mobile for users with varying technical skills.

## Impact: Bugs or usability issues could reduce farmer trust and adoption.

## Mitigation: Develop a comprehensive test plan covering functional, usability, and performance testing, with real-world farmer scenarios.

Question 6:

Perform stakeholder analysis (RACI Matrix) to find out the key stakeholders who can take Decisions and Who are the influencers

To perform a stakeholder analysis for Mr. Henry’s online agriculture product store project using a RACI Matrix, we will identify key stakeholders, their roles, and their influence in decision-making. The RACI Matrix categorizes stakeholders as Responsible (R), Accountable (A), Consulted (C), or Informed (I) for key project tasks or decisions. This analysis will help determine who can take decisions (typically Accountable or Responsible) and who are influencers (typically Consulted or with significant project impact). The matrix is tailored to the project context, involving the SOONY committee, APT IT SOLUTIONS team, and farmers as stakeholders.

Stakeholder Analysis Overview:

Project Context: Developing a user-friendly web/mobile application to connect farmers (e.g., Peter, Kevin, Ben) with manufacturers for purchasing fertilizers, seeds, and pesticides, with a budget of 2 Crore INR and an 18-month timeline.

Key Decisions: Requirements approval, budget allocation, technical architecture, user interface design, testing approval, and deployment.

Stakeholders: Identified from the project description, including SOONY committee members, APT IT SOLUTIONS team, and farmers.

RACI Definitions:

Responsible (R): Performs the task or makes the decision.

Accountable (A): Ultimately answerable for the task/decision; approves work.

Consulted (C): Provides input or expertise; influences decisions.

Informed (I): Kept updated but does not actively participate.

Key Stakeholders:

- Mr. Henry (SOONY, Project Sponsor): Initiator and primary funder; high decision-making authority.

- Mr. Pandu (SOONY, Financial Head): Oversees budget and financial decisions.

- Mr. Dooku (SOONY, Project Coordinator): Coordinates between SOONY and APT IT SOLUTIONS.

- Peter, Kevin, Ben (Farmers, Stakeholders): Represent end-users; provide requirements and feedback.

- Mr. Karthik (APT IT SOLUTIONS, Delivery Head): Oversees project delivery and team performance.

- Mr. Vandanam (APT IT SOLUTIONS, Project Manager): Manages day-to-day project execution.

- Ms. Juhi (APT IT SOLUTIONS, Senior Java Developer): Leads technical development.

- Mr. Teyson, Ms. Lucie, Mr. Tucker, Mr. Bravo (APT IT SOLUTIONS, Java Developers): Implement application features.

- Mr. Mike (APT IT SOLUTIONS, Network Admin): Manages network infrastructure and security.

- Mr. John (APT IT SOLUTIONS, DB Admin): Manages database systems.

- Mr. Jason, Ms. Alekya (APT IT SOLUTIONS, Testers): Ensure application quality.

- You (APT IT SOLUTIONS, Business Analyst): Elicits and documents requirements.

- Manufacturers (External Stakeholders): Provide product data and integration requirements.

Key Decision Areas:

Based on the project, the following key tasks/decisions are critical:

- Requirements Gathering and Approval: Defining and approving application features.

- Budget Allocation and Monitoring: Managing the 2 Crore INR budget.

- Technical Architecture Design: Designing the system (web/mobile, database, integrations).

- User Interface (UI) Design: Ensuring a user-friendly interface for farmers.

- Testing and Quality Assurance: Validating the application’s functionality.

- Deployment and Rollout: Launching the application for farmers and manufacturers.

Key Stakeholders and Their Roles

Decision-Makers (Accountable or Responsible)

Mr. Henry (SOONY, Project Sponsor):

Role: Accountable for budget allocation and deployment decisions, ensuring alignment with the CSR initiative.

Decision-Making Power: Approves major project milestones and budget; final authority on project vision.

Mr. Pandu (SOONY, Financial Head):

Role: Responsible for budget allocation and monitoring.

Decision-Making Power: Approves financial decisions and ensures the project stays within 2 Crore INR.

Mr. Dooku (SOONY, Project Coordinator):

Role: Consulted on most tasks; facilitates communication between SOONY and APT IT SOLUTIONS.

Decision-Making Power: Limited, but influences decisions through coordination and stakeholder alignment.

Mr. Karthik (APT IT SOLUTIONS, Delivery Head):

Role: Responsible for deployment and consulted on budget and architecture.

Decision-Making Power: Approves delivery timelines and resource allocation.

Mr. Vandanam (APT IT SOLUTIONS, Project Manager):

Role: Responsible for requirements, UI design, and deployment; consulted on budget and testing.

Decision-Making Power: Manages day-to-day decisions and project execution within the approved scope.

Ms. Juhi (Senior Java Developer):

Role: Accountable for technical architecture; responsible for UI design and development.

Decision-Making Power: Decides technical implementation details and leads development.

Mr. Jason, Ms. Alekya (Testers):

Role: Accountable for testing and quality assurance.

Decision-Making Power: Approve testing outcomes and ensure the application meets quality standards.

You (Business Analyst):

Role: Accountable for requirements gathering and UI design; responsible for testing input.

Decision-Making Power: Approves requirements and ensures stakeholder needs are met.

Peter, Kevin, Ben (Farmers, Stakeholders):

Role: Consulted on requirements and UI design; provide critical input as end-users.

Influence: Their feedback shapes the application’s usability and functionality, ensuring it meets farmers’ needs.

Impact: High, as their adoption is critical to project success.

Manufacturers (External Stakeholders):

Role: Consulted on requirements, architecture, and deployment for product integration.

Influence: Their input on product data formats and integration requirements shapes technical design.

Impact: High, as their participation drives the platform’s product catalog.

Mr. Dooku (SOONY, Project Coordinator):

Role: Consulted across most tasks.

Influence: Facilitates stakeholder alignment and influences decisions through communication with Mr. Henry.

Mr. Mike (Network Admin) and Mr. John (DB Admin):

Role: Responsible for architecture and deployment tasks.

Influence: Their expertise in network and database systems influences technical decisions.

Mr. Karthik (Delivery Head) and Mr. Vandanam (Project Manager):

Role: Involved in multiple tasks as Responsible or Consulted.

Influence: Their oversight ensures project alignment with timeline and budget, influencing strategic decisions.

Analysis Summary:

Primary Decision-Makers:

Mr. Henry: Final authority on budget and deployment.

Mr. Pandu: Financial decisions.

Mr. Karthik and Mr. Vandanam: Delivery and project execution.

Ms. Juhi: Technical architecture.

You (BA): Requirements and UI design.

Mr. Jason, Ms. Alekya: Testing approval.

Key Influencers:

Peter, Kevin, Ben: Shape user requirements and usability, critical for adoption.

Manufacturers: Influence product integration and catalog design.

Mr. Dooku: Bridges SOONY and APT IT SOLUTIONS, influencing stakeholder alignment.

Mr. Mike and Mr. John: Influence technical reliability and scalability.

Recommendations:

Engage Influencers Early: Conduct regular workshops with Peter, Kevin, Ben, and manufacturers to validate requirements and UI designs, leveraging their influence to ensure user adoption.

Clarify Decision Authority: Confirm with Mr. Henry and Mr. Pandu their approval roles to avoid delays in budget or deployment decisions.

Use RACI for Communication: Share the RACI Matrix with the team (via Jira or meetings) to clarify roles and streamline decision-making.

Monitor Influencer Feedback: Track input from farmers and manufacturers in the Risk Register to mitigate risks like misaligned requirements.

Escalate to Decision-Makers: Escalate critical issues (e.g., budget overruns) to Mr. Henry or Mr. Pandu as Accountable stakeholders.

Question 7:

Help Mr Karthik to prepare a business case document?

To assist Mr. Karthik, the Delivery Head at APT IT SOLUTIONS, in preparing a business case document for Mr. Henry’s online agriculture product store project, we need to create a clear and compelling document that justifies the project, outlines its objectives, benefits, costs, risks, and implementation approach. The business case will align with the project’s goal of developing a user-friendly web/mobile application to connect farmers (e.g., Peter, Kevin, Ben) with manufacturers for purchasing fertilizers, seeds, and pesticides, under a 2 Crore INR budget and 18-month timeline as part of SOONY’s CSR initiative. The document will be structured to address the needs of key stakeholders (Mr. Henry, Mr. Pandu, Mr. Dooku, farmers, and manufacturers) and provide a rationale for APT IT SOLUTIONS to execute the project.

# Business Case: Online Agriculture Product Store

## 1. Executive Summary

The online agriculture product store is a Corporate Social Responsibility (CSR) initiative by SOONY, led by Mr. Henry, to address the challenges faced by farmers in remote areas, such as Peter, Kevin, and Ben, in procuring essential agricultural inputs (fertilizers, seeds, pesticides). The proposed web and mobile application will connect farmers directly with manufacturers, enabling seamless browsing, purchasing, and delivery of products. APT IT SOLUTIONS has been contracted to develop this platform within a budget of 2 Crore INR and an 18-month timeline. The project aims to empower farmers, enhance agricultural productivity, and support rural economies while aligning with SOONY’s CSR objectives. This business case outlines the project’s objectives, benefits, costs, risks, and implementation strategy to justify its execution.

## 2. Background and Problem Statement

Farmers in remote areas, including SOONY’s stakeholders Peter, Kevin, and Ben, face significant challenges in accessing quality agricultural inputs:

- Procurement Difficulties: Limited access to fertilizers (Peter), seeds (Kevin), and pesticides (Ben) due to geographic isolation and unreliable supply chains.

- Lack of Direct Access: Farmers rely on intermediaries, leading to higher costs and delays.

- Digital Divide: Many farmers have limited digital literacy, necessitating a user-friendly platform.
SOONY aims to address these issues by funding a digital platform that connects farmers directly with manufacturers, reducing costs, improving access, and fostering rural development.

## 3. Project Objectives

- Facilitate Access: Enable farmers to browse and purchase fertilizers, seeds, and pesticides from anywhere via a web/mobile application.

- Ensure Usability: Develop a user-friendly interface tailored to farmers with limited digital literacy.

- Enable Direct Communication: Allow manufacturers to list products and interact directly with farmers, streamlining the supply chain.

- Support CSR Goals: Enhance agricultural productivity and rural livelihoods, aligning with SOONY’s CSR initiative.

- Deliver Within Constraints: Complete the project within 18 months and a 2 Crore INR budget.

## 4. Benefits

### 4.1 Tangible Benefits

- Cost Savings for Farmers: Direct purchasing reduces intermediary costs by an estimated 10-20% per transaction.

- Increased Productivity: Improved access to quality inputs can boost crop yields by 15-25% (based on industry benchmarks).

- Revenue for Manufacturers: Direct access to a broader farmer base increases sales opportunities.

- Economic Impact: Supports rural economies by empowering farmers and creating a scalable platform for agricultural commerce.

### 4.2 Intangible Benefits

- Farmer Empowerment: Enhances farmers’ ability to make informed purchasing decisions.

- Community Impact: Aligns with SOONY’s CSR mission, improving brand reputation and stakeholder trust.

- Scalability: The platform can expand to include additional products (e.g., farming tools) or regions.

## 5. Options Analysis

### Option 1: Develop Web and Mobile Application (Recommended)

- Description: Build a custom web and mobile platform with features for product browsing, purchasing, and delivery tracking.

- Pros: Tailored to farmers’ needs, scalable, supports both web and mobile access.

- Cons: Higher initial cost and development time; requires ongoing maintenance.

- Cost: 2 Crore INR.

- Timeline: 18 months.

### Option 2: Use an Existing E-Commerce Platform

- Description: Customize an off-the-shelf e-commerce solution (e.g., Shopify) for agricultural products.

- Pros: Lower initial development cost (~1 Crore INR), faster deployment (9-12 months).

- Cons: Limited customization for farmers’ unique needs, potential dependency on third-party providers.

- Cost: ~1 Crore INR.

- Timeline: 9-12 months.

### Option 3: Do Nothing

- Description: Maintain the status quo, relying on traditional supply chains.

- Pros: No immediate cost or effort.

- Cons: Fails to address farmers’ challenges, misses CSR objectives, no economic or social impact.

- Cost: 0 INR.

- Timeline: N/A.

Recommendation: Option 1 is recommended as it provides a tailored, scalable solution that meets stakeholder needs and aligns with SOONY’s CSR goals, despite higher initial costs.

## 6. Cost-Benefit Analysis

### 6.1 Estimated Costs

- Development Costs: 1.2 Crore INR (development team salaries, tools, cloud infrastructure).

- Testing and Quality Assurance: 0.3 Crore INR (testing resources, user acceptance testing with farmers).

- Training and Outreach: 0.2 Crore INR (farmer training programs, user guides).

- Maintenance (Year 1): 0.2 Crore INR (server hosting, updates).

- Contingency (10%): 0.1 Crore INR.

- Total: 2 Crore INR.

### 6.2 Expected Benefits (5-Year Horizon)

- Farmer Savings: Estimated 5,000 farmers saving 10,000 INR annually = 5 Crore INR.

- Manufacturer Revenue: 10 manufacturers gaining 50 Lakh INR annually = 5 Crore INR.

- Social Impact: Improved livelihoods for 5,000+ farmers, supporting rural development.

- ROI: Positive return within 3 years, driven by social and economic benefits.

## 7. Risks and Mitigation

The following key risks, identified through stakeholder analysis and risk management, will be tracked in a Risk Register:

| Risk ID | Risk Category | Description | Likelihood | Impact | Mitigation Plan | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | BA | Limited digital literacy of farmers | High | High | Conduct training sessions and design intuitive UI by Month 3 | BA |
| R2 | Project | Dependency on external logistics partners | High | High | Contract multiple providers with SLAs by Month 4 | Project Manager (Mr. Vandanam) |
| R3 | BA | Conflicting requirements from farmers/manufacturers | Medium | Medium | Facilitate joint workshops by Month 2 | BA |
| R4 | Project | Scalability challenges | Medium | High | Use scalable cloud architecture; load test by Month 8 | Senior Java Developer (Ms. Juhi) |

Mitigation Strategy: Regular stakeholder engagement, iterative testing, and robust project management by Mr. Vandanam will minimize risks.

## 8. Implementation Approach

- Phase 1: Requirements and Design (Months 1-4)

  - Led by BA, engage Peter, Kevin, Ben, and manufacturers to finalize requirements.

  - Design UI and technical architecture (Ms. Juhi, Mr. Mike, Mr. John).

- Phase 2: Development (Months 5-12)

  - Develop web/mobile app (Ms. Juhi, Mr. Teyson, Ms. Lucie, Mr. Tucker, Mr. Bravo).

  - Integrate manufacturer APIs and logistics systems.

- Phase 3: Testing and Training (Months 13-16)

  - Conduct testing (Mr. Jason, Ms. Alekya) and user acceptance testing with farmers.

  - Train farmers on app usage (BA, Peter, Kevin, Ben).

- Phase 4: Deployment and Rollout (Months 17-18)

  - Launch platform and monitor initial usage (Mr. Karthik, Mr. Vandanam).

  - Provide ongoing support and updates.

## 9. Stakeholder Roles (RACI Matrix Summary)

- Decision-Makers: Mr. Henry (approves budget/deployment), Mr. Pandu (financial oversight), Mr. Karthik (delivery), BA (requirements), Ms. Juhi (architecture).

- Influencers: Peter, Kevin, Ben (user feedback), manufacturers (product integration), Mr. Dooku (coordination).

- Full RACI Matrix: Available separately, detailing Responsible, Accountable, Consulted, and Informed roles for key tasks.

## 10. Recommendation

APT IT SOLUTIONS recommends proceeding with the development of the online agriculture product store (Option 1) to deliver a tailored, scalable platform that addresses farmers’ challenges and aligns with SOONY’s CSR objectives. The project’s benefits (cost savings, productivity gains, social impact) outweigh the costs, and risks can be managed through proactive mitigation. Approval from Mr. Henry and Mr. Pandu is requested to initiate the project within the 2 Crore INR budget and 18-month timeline.

## 11. Next Steps

- Approval: Seek approval from Mr. Henry and Mr. Pandu by [insert date].

- Kickoff: Schedule project kickoff with SOONY committee and APT IT SOLUTIONS team by [insert date].

- Requirements Workshops: Begin stakeholder engagement with farmers and manufacturers by Month 1.

Question 8:

To assist Mr. Karthik in explaining the Software Development Life Cycle (SDLC) methodologies to the SOONY committee (Mr. Henry, Mr. Pandu, Mr. Dooku) for the online agriculture product store project, I’ll provide a clear and concise overview of the four SDLC methodologies mentioned—Sequential, Iterative, Evolutionary, and Agile—tailored to the project context. The explanation will clarify each methodology, its suitability for the project (developing a user-friendly web/mobile application for farmers and manufacturers within a 2 Crore INR budget and 18-month timeline), and recommendations to guide the committee’s decision. The goal is to help stakeholders understand the approaches and select the most appropriate one for the project.

Overview of SDLC:

The Software Development Life Cycle (SDLC) is a structured process for planning, designing, developing, testing, and deploying software. It ensures the project meets stakeholder needs (e.g., farmers like Peter, Kevin, Ben, and manufacturers) while staying within scope, budget, and timeline. The four methodologies—Sequential, Iterative, Evolutionary, and Agile—differ in how they manage phases, adaptability, and stakeholder involvement.

  - Sequential Methodology (Waterfall):

Description:
The Sequential methodology, often called Waterfall, follows a linear, step-by-step process where each phase (requirements, design, development, testing, deployment) is completed before moving to the next. There is no overlap or revisiting of phases.

Key Characteristics:

- Phases: Requirements → System Design → Implementation → Testing → Deployment → Maintenance.

- Stakeholder Involvement: Stakeholders (e.g., Peter, Kevin, Ben) provide requirements upfront; limited involvement during development.

- Change Management: Changes to requirements are difficult once the project begins.

- Deliverables: A complete application is delivered at the end of the 18-month timeline.

Pros:

- Clear structure and milestones, easy to manage for Mr. Vandanam (Project Manager).

- Well-suited for projects with stable, well-defined requirements.

- Predictable budget and timeline, aligning with Mr. Pandu’s financial oversight.

Cons:

- Inflexible to changes, risky if farmers’ needs evolve (e.g., new features requested by Ben).

- Limited stakeholder feedback during development, which may lead to misalignment with farmers’ digital literacy needs.

- Late testing may uncover issues (e.g., UI complexity) too late to fix within budget.

Suitability for the Project:

- Low Suitability: The project involves users (farmers) with limited digital literacy and evolving needs, requiring frequent feedback. The Waterfall’s rigidity may lead to misaligned deliverables, especially given the 18-month timeline and diverse stakeholders (farmers, manufacturers).

2. Iterative Methodology

Description:
The Iterative methodology breaks the project into smaller cycles (iterations), each producing a partial, functional version of the application. Each iteration includes planning, design, development, and testing, allowing for incremental improvements.

Key Characteristics:

- Phases: Repeated cycles of requirements, design, development, testing, and review.

- Stakeholder Involvement: Farmers and manufacturers provide feedback after each iteration (e.g., every 2-3 months).

- Change Management: Flexible to incorporate changes based on feedback.

- Deliverables: Incremental versions (e.g., a basic product catalog first, then payment features).

Pros:

- Early feedback from Peter, Kevin, Ben ensures the UI is user-friendly.

- Allows adjustments to requirements, reducing risks like conflicting farmer-manufacturer needs.

- Early testing (by Mr. Jason, Ms. Alekya) catches issues sooner.

Cons:

- Requires more planning and coordination by Mr. Vandanam, increasing management effort.

- Budget and timeline may be harder to predict, concerning Mr. Pandu.

- Risk of scope creep if stakeholders request excessive changes.

Suitability for the Project:

- Moderate Suitability: Iterative development suits the project’s need for stakeholder feedback (farmers, manufacturers) and adaptability to digital literacy challenges. However, managing multiple iterations within 18 months may challenge the team’s coordination.

3. Evolutionary Methodology:

Description:
The Evolutionary methodology builds a prototype or minimum viable product (MVP) early, which is refined through multiple versions based on stakeholder feedback. It evolves into the final product over time.

Key Characteristics:

- Phases: Develop prototype → Gather feedback → Refine → Repeat until final product.

- Stakeholder Involvement: Heavy involvement from farmers and manufacturers to test and refine prototypes.

- Change Management: Highly flexible, incorporating feedback at each stage.

- Deliverables: Evolving prototypes, with the final product delivered by Month 18.

Pros:

- Prototypes allow farmers to test usability early, addressing digital literacy risks.

- Reduces risk of misaligned requirements by validating with Peter, Kevin, Ben, and manufacturers.

- Supports complex features (e.g., logistics integration) through iterative refinement.

Cons:

- Higher initial effort for prototyping, potentially straining the 2 Crore INR budget.

- Requires significant stakeholder time, which may be challenging for busy farmers.

- Timeline may extend if refinements take longer than planned.

Suitability for the Project:

- High Suitability: The Evolutionary approach is ideal for a project with diverse stakeholders and uncertain requirements (e.g., farmers’ UI needs, manufacturer integrations). Prototypes can ensure the app is intuitive and functional, aligning with SOONY’s CSR goals.

4. Agile Methodology

Description:
Agile is a flexible, collaborative approach that delivers small, functional increments (sprints) every 2-4 weeks. It emphasizes continuous stakeholder feedback, adaptability, and teamwork, often using frameworks like Scrum or Kanban.

Key Characteristics:

- Phases: Short sprints involving planning, development, testing, and review.

- Stakeholder Involvement: Continuous engagement with farmers, manufacturers, and the SOONY committee.

- Change Management: Highly adaptable to changing requirements.

- Deliverables: Frequent releases of usable features (e.g., product browsing in Sprint 1, payments in Sprint 2).

Pros:

- Maximizes feedback from Peter, Kevin, Ben, ensuring a farmer-friendly app.

- Mitigates risks like conflicting requirements through regular stakeholder reviews.

- Enables early delivery of critical features, enhancing user adoption.

Cons:

- Requires strong team collaboration (Ms. Juhi, Mr. Teyson, testers, etc.), which may challenge coordination.

- Budget oversight (Mr. Pandu) may be complex due to evolving scope.

- Demands active stakeholder involvement, potentially straining farmers’ availability.

Suitability for the Project:

- High Suitability: Agile’s flexibility and frequent feedback align well with the project’s need to address farmers’ digital literacy and manufacturer integration challenges. It supports rapid adaptation within the 18-month timeline and ensures stakeholder satisfaction.

| Methodology | Flexibility | Stakeholder Involvement | Risk Management | Suitability for Project | Challenges |
| --- | --- | --- | --- | --- | --- |
| Sequential (Waterfall) | Low | Low (upfront only) | Low (late feedback) | Low | Inflexible to changes |
| Iterative | Medium | Medium (per iteration) | Medium (early testing) | Moderate | Coordination effort |
| Evolutionary | High | High (prototype feedback) | High (iterative refinement) | High | Prototyping costs |
| Agile | High | High (continuous) | High (frequent reviews) | High | Team/stakeholder coordination |

Recommendation

Recommended Methodology: Agile

- Rationale: Agile is the best fit for the online agriculture product store project due to:

Stakeholder Needs: Farmers (Peter, Kevin, Ben) have limited digital literacy, requiring frequent feedback to ensure a user-friendly interface. Agile’s sprints allow continuous validation.

Complex Requirements: Integrating manufacturer data and logistics systems may evolve, and Agile’s flexibility accommodates changes.

Risk Mitigation: Frequent testing and stakeholder reviews reduce risks like misaligned requirements or scalability issues.

Timeline and Budget: Agile’s incremental deliveries ensure usable features within 18 months, with budget oversight managed through sprint planning.

Implementation Approach:

Use Scrum with 2-3 week sprints, led by Mr. Vandanam (Project Manager).

Assign you (BA) to gather requirements in early sprints, consulting farmers and manufacturers.

Involve Ms. Juhi (Senior Java Developer) for technical leadership and Mr. Jason/Ms. Alekya for testing each sprint.

Hold sprint reviews with Mr. Henry, Mr. Pandu, and Mr. Dooku to align with CSR goals.

Mitigating Challenges:

Stakeholder Availability: Offer asynchronous feedback options (e.g., video demos) for farmers.

Budget Control: Monitor costs per sprint with Mr. Pandu, using a Risk Register to track overspending.

Team Coordination: Use Jira for task tracking and daily stand-ups to align the team (Ms. Juhi, Mr. Mike, etc.).

Alternative: If Agile’s intensity is a concern (e.g., stakeholder availability), the Evolutionary methodology is a strong alternative, using prototypes to validate requirements while requiring less frequent stakeholder engagement.

Next Steps:

- Present Recommendation: Mr. Karthik to present Agile as the preferred methodology, highlighting its alignment with stakeholder needs and risk mitigation.

- Plan First Sprint: You (BA) to initiate requirements workshops with Peter, Kevin, Ben, and manufacturers by Month 1.

- Set Up Tools: Mr. Vandanam to configure Jira for sprint tracking and Risk Register integration.

- Seek Approval: Obtain Mr. Henry’s approval to adopt Agile, confirming the 18-month timeline and budget.

Question: 10

Write down the differences between waterfall model and V model?

The Waterfall Model and V Model are both linear SDLC methodologies, but they differ significantly in their approach to testing, flexibility, and stakeholder involvement. Below is a detailed comparison across key dimensions, with examples relevant to the agriculture product store project.

| Aspect | Waterfall Model | V Model (Verification and Validation Model) |
| --- | --- | --- |
| Definition | Waterfall is simpler and suitable for smaller, fixed-scope projects. - A linear, sequential methodology where each phase (requirements, design, implementation, testing, deployment) is completed before moving to the next, with no overlap. | V-Model is preferred when quality assurance is critical, and you want testing to be tightly integrated with development. - An extension of Waterfall, where each development phase is paired with a corresponding testing phase, forming a “V” shape to emphasize verification (building the product right) and validation (building the right product). |
| Structure | Sequential phases: 1. Requirements 2. System Design 3. Implementation 4. Testing 5. Deployment 6. Maintenance Example: Requirements are gathered from farmers (Peter, Kevin, Ben) upfront, and testing occurs only after development by Ms. Juhi’s team. | Sequential phases with parallel testing: - Development: Requirements → System Design → Detailed Design → Implementation - Testing: Unit Testing ↔ Detailed Design, Integration Testing ↔ System Design, System Testing ↔ Requirements, Acceptance Testing ↔ Requirements Example: Requirements for the product catalog are tested via acceptance testing by farmers at the end, with unit tests planned during design. |
| Testing Approach | 1.Testing is conducted in a single phase after implementation, at the end of the project. Example: Mr. Jason and Ms. Alekya test the entire app (e.g., UI, payments) in Month 16, after development is complete. 2.Testing is carried out after the development is completed | 1.Testing is planned and aligned with each development phase, starting early with test case design. Example: Test cases for the product catalog are created during requirements (Month and executed during unit testing (Month 10), ensuring early quality checks. 2. Testing is carried out at right from the beginning at each phase of the application |
| Flexibility | Low flexibility; changes to requirements (e.g., new UI features requested by Ben) are difficult and costly after the requirements phase. Example: If farmers request a multilingual UI mid-project, it requires significant rework, risking budget overruns. | Low flexibility; similar to Waterfall, changes are costly after requirements are set, but early test planning may catch issues sooner. Example: A change in manufacturer API requirements after design disrupts both development and testing plans, increasing costs. |
| Stakeholder Involvement | Limited to the requirements phase (upfront) and post-deployment feedback. Example: Peter, Kevin, Ben provide input in Month 1, with no further involvement until the app is delivered in Month 18. | Limited to requirements and acceptance testing phases, with stakeholders involved at the start and end. Example: Farmers validate requirements in Month 1 and test the app’s usability in Month 17 during acceptance testing. |
| Risk Management | High risk of late issue detection due to testing at the end. Example: If the app’s UI is not farmer-friendly, this is only discovered in Month 16, requiring costly fixes that may exceed the 2 Crore INR budget. | Lower risk due to early test planning and alignment with development phases. Example: Test cases for logistics integration are defined early, reducing the risk of late defects in Month 15. |
| Complexity | Simple to manage, with clear, sequential milestones. Example: Mr. Vandanam can easily track progress as each phase completes, aligning with Mr. Pandu’s budget oversight. | More complex due to parallel test planning and execution. Example: Mr. Jason and Ms. Alekya must create test plans during requirements, increasing coordination effort for Mr. Vandanam. |
| Quality Assurance | Quality is assessed late, increasing the chance of defects. Example: A bug in the payment system is only found during final testing, delaying deployment. | Strong focus on quality, with tests defined for each phase, ensuring early defect detection. Example: Unit tests for the product catalog catch errors during development, improving reliability. |
| Cost and Time Implications | Predictable costs and timeline if requirements are stable, but rework can be expensive. Example: Fixed budget of 2 Crore INR is easier to manage, but late changes could require additional funds. | Higher initial planning costs due to test case development, but fewer late-stage rework costs. Example: Early test planning may use 10% of the budget upfront but saves on rework by catching issues early. |
| Suitability for Project | Low suitability: The project’s need for frequent feedback (due to farmers’ digital literacy) and evolving requirements (e.g., manufacturer integrations) makes Waterfall’s rigidity a poor fit. Late testing risks misaligned deliverables. | Moderate suitability: The V Model’s testing focus ensures reliability, but its linear nature limits feedback and adaptability, risking usability issues for farmers and late changes from manufacturers. |
| Error Detection | Errors are usually found late in the lifecycle during the testing phase. | Errors are usually found late in the lifecycle during the testing phase. |
| Focus | Emphasis on development process. | Emphasis on development process. |
| Maintenance | Comes after deployment. | Comes after deployment, but with fewer issues if V-model is followed well. |
| Suitable For | Projects with well-defined, stable requirements | Projects where quality and testing are top priorities |
| Quality Assurance | Limited; quality is assessed late, increasing defect risks. Example: A payment system bug found in Month 16 delays deployment. Critical Focus: Early test planning ensures high quality, reducing defects. Example: Unit tests catch catalog errors during development, improving reliability. | Critical Focus: Early test planning ensures high quality, reducing defects. Example: Unit tests catch catalog errors during development, improving reliability. |

Question 11:

As a BA, state your reason for choosing one model for this project

As a Business Analyst (BA) for the Online Agriculture Product Store project, I recommend choosing the V-Model (Verification and Validation Model) as the most suitable SDLC model. Here's the justification:

High Emphasis on Quality and Testing

- The application will be used by farmers in rural and remote areas who rely heavily on the platform for their livelihood.

- Early testing and validation at every stage in the V-Model ensure a stable, bug-free, and user-friendly application, minimizing risk of failure after release.

Clear and Stable Requirements

- The project scope (facilitating online purchase of fertilizers, seeds, and pesticides) is well-defined by stakeholders like Mr. Henry, Mr. Pandu, Mr. Dooku, and the farmer representatives.

- V-Model works best when requirements are fixed early and unlikely to change frequently.

Strict Budget and Timeline

- The project has a fixed budget (₹2 Crores) and timeline (18 months).

- V-Model ensures strict phase-by-phase execution with predefined deliverables, helping manage cost and time efficiently.

Early Risk Mitigation

- With validation activities running in parallel to development, defects and mismatches between requirements and implementation are caught early—saving time and money.

Stakeholder Confidence

- V-Model provides visibility at every phase, allowing the committee (Mr. Henry, Mr. Pandu, Mr. Dooku) to review and validate deliverables continuously—building trust and reducing surprises.

Conclusion:

The V-Model is the best fit for this project due to its focus on early validation, structured phases, and quality assurance. It ensures the development team can deliver a reliable, farmer-friendly product within budget and on time, while meeting all stakeholder expectations.

Question 13:

Fixed Bid and Billing (Time and Materials, or T&M) are two common contract types used in project engagements, each with distinct approaches to scope, cost, and risk management. Below is a detailed comparison, followed by their relevance to the agriculture product store project.

| Aspect | Fixed Bid | Billing (Time and Materials) |
| --- | --- | --- |
| Definition | A contract where the service provider (APT IT SOLUTIONS) agrees to deliver a defined scope of work for a fixed price and timeline, regardless of the actual effort required. | A contract where the client (SOONY) pays for the actual time and resources expended by the service provider, typically based on hourly or daily rates. |
| Scope | Clearly defined and fixed upfront, with detailed requirements and deliverables. Example: The agriculture store app must include product browsing, payment, and delivery tracking, finalized in the Requirements Gathering (RG) phase of the V Model. | Flexible, allowing scope changes as the project progresses. Example: Farmers may request a multilingual UI during User Acceptance Testing (UAT), and the scope adjusts accordingly. |
| Cost | Fixed cost, agreed upon before the project starts. Example: APT IT SOLUTIONS commits to delivering the app for 2 Crore INR, covering all V Model phases (RG, RA, Design, D1-T1, D2-T2, D3-T3, D4-T4, UAT). | Variable cost, based on hours worked and resources used. Example: SOONY pays for actual hours spent by you (BA), Ms. Juhi, Mr. John, etc., which may exceed or fall below 2 Crore INR depending on effort. |
| Timeline | Fixed timeline, with strict deadlines for deliverables. Example: The app must be delivered by January 20, 2027, per the 18-month timeline, with milestones like T3 (System Testing) by August 29, 2026. | Flexible timeline, adjusting based on project needs and changes. Example: If UAT reveals usability issues, additional weeks may be added, extending beyond 18 months. |
| Risk Allocation | Risk lies primarily with the service provider (APT IT SOLUTIONS), who must absorb cost or time overruns. Example: If integration testing (T2) delays due to manufacturer API issues, APT IT SOLUTIONS covers the extra effort within the 2 Crore INR budget. | Risk lies primarily with the client (SOONY), who pays for additional time or resources. Example: If farmers request new features during UAT, SOONY pays for extra development hours, potentially exceeding 2 Crore INR. |
| Change Management | Changes are difficult and require formal change requests, often increasing costs or delaying the timeline. Example: Adding a pest identification feature after Requirements Analysis (RA) requires a contract amendment, approved by Mr. Henry and Mr. Pandu. | Changes are easily accommodated, with costs and timeline adjusted based on effort. Example: Adding a multilingual UI during D3 (Detailed Design 3) is billed based on additional hours by Java Developers. |
| Stakeholder Involvement | Limited to key milestones (e.g., RG, UAT), with less frequent interaction during development. Example: Farmers (Peter, Kevin, Ben) provide input in RG and UAT, with minimal involvement during Design or T1-T4 phases. | Continuous involvement, as scope evolves with stakeholder feedback. Example: Farmers and manufacturers can provide feedback throughout the V Model phases, adjusting features dynamically. |
| Quality Control | Quality is ensured within the fixed scope, but changes may compromise quality if not planned. Example: The V Model’s testing phases (T1-T4, UAT) ensure quality, but late changes may strain resources. | Quality can be enhanced through iterative feedback, but depends on client budget. Example: Continuous farmer feedback during T3 (System Testing) improves UI, but increases costs. |
| Payment Structure | Payments are milestone-based or lump-sum. Example: SOONY pays 50 Lakh INR after RG, 50 Lakh after Design, 50 Lakh after T3, and 50 Lakh after UAT. | Payments are periodic (e.g., monthly) based on hours logged. Example: SOONY pays monthly invoices for hours worked by Ms. Juhi, Mr. Mike, etc., based on timesheets. |
| Suitability for Project | Suitable for projects with well-defined requirements and low likelihood of change. Project Fit: Moderate, as the V Model’s structured phases align with Fixed Bid’s predictability, but evolving farmer needs (e.g., digital literacy) risk costly change requests. | Suitable for projects with uncertain or evolving requirements. Project Fit: High, as farmers’ usability needs and manufacturer integrations may change, but SOONY’s 2 Crore INR budget cap favors Fixed Bid. |

Question 14:

Business Analyst Timesheets for Online Agriculture Product Store Project

The following timesheets detail the Business Analyst’s (BA) activities and hours across the V Model SDLC phases for the online agriculture product store project. The project runs from July 20, 2025, to January 20, 2027 (18 months), using a Fixed Bid contract with a 2 Crore INR budget. The BA’s role focuses on requirements, stakeholder engagement, design support, testing assistance, and user acceptance.

1. Design Phase Timesheet (RG, RA, Design, D1, D2, D3, D4)

Duration: July 20, 2025 – September 26, 2026 (60 weeks, covering RG, RA, Design, D1, D2, D3, D4)
Role: Accountable for RG and RA; Consulted for Design, D1, D2, D3, D4
Description: The BA leads requirements gathering and analysis, facilitates stakeholder alignment, and supports system and detailed design by reviewing specifications to ensure alignment with farmer and manufacturer needs.

| Date Range | Task | Description | Hours |
| --- | --- | --- | --- |
| Jul 20, 2025 – Sep 13, 2025 (8 weeks) | Requirements Gathering (RG) | Conduct workshops with farmers (Peter, Kevin, Ben) and manufacturers to elicit requirements (e.g., product catalog, payment system). Document user stories and use cases. | 240 (30 hr/wk) |
| Sep 14, 2025 – Oct 25, 2025 (6 weeks) | Requirements Analysis (RA) | Analyze requirements, create requirement specification documents, validate with SOONY committee (Mr. Henry, Mr. Pandu, Mr. Dooku). Identify risks (e.g., digital literacy). | 180 (30 hr/wk) |
| Oct 26, 2025 – Dec 20, 2025 (8 weeks) | System Design | Review high-level architecture (e.g., web/mobile structure, APIs) with Ms. Juhi, Mr. John (DB), and Mr. Mike (NW). Ensure farmer-friendly UI requirements are included. | 80 (10 hr/wk) |
| Dec 21, 2025 – Jan 31, 2026 (6 weeks) | Detailed Design 1 (D1) | Support design of core features (e.g., product browsing). Review design documents for alignment with requirements. | 60 (10 hr/wk) |
| Mar 1, 2026 – Apr 11, 2026 (6 weeks) | Detailed Design 2 (D2) | Support design of integration features (e.g., manufacturer APIs, payments). Provide input on stakeholder needs. | 60 (10 hr/wk) |
| May 24, 2026 – Jul 4, 2026 (6 weeks) | Detailed Design 3 (D3) | Support design of system-wide features (e.g., delivery tracking, UI). Validate design against user needs. | 60 (10 hr/wk) |
| Aug 30, 2026 – Sep 26, 2026 (4 weeks) | Detailed Design 4 (D4) | Support final design for deployment (e.g., security, scalability). Review for stakeholder alignment. | 40 (10 hr/wk) |
| Total Hours |  |  | 720 |

Notes: High effort in RG and RA due to stakeholder engagement. Reduced hours in design phases (D1-D4) as BA is Consulted, focusing on reviews rather than leading tasks.

2. Development Phase Timesheet (Implementation within D1, D2, D3, D4)

Duration: December 21, 2025 – September 26, 2026 (40 weeks, overlapping with D1, D2, D3, D4 implementation)
Role: Consulted (support developers during implementation)
Description: The BA supports Java Developers (Ms. Juhi, Mr. Teyson, Ms. Lucie, Mr. Tucker, Mr. Bravo) by clarifying requirements, resolving stakeholder queries, and ensuring implementation aligns with requirements.

| Date Range | Task | Description | Hours |
| --- | --- | --- | --- |
| Dec 21, 2025 – Jan 31, 2026 (6 weeks) | Support D1 Implementation | Clarify requirements for core features (e.g., product browsing). Address developer queries. | 48 (8 hr/wk) |
| Mar 1, 2026 – Apr 11, 2026 (6 weeks) | Support D2 Implementation | Support integration feature development (e.g., APIs, payments). Resolve manufacturer queries. | 48 (8 hr/wk) |
| May 24, 2026 – Jul 4, 2026 (6 weeks) | Support D3 Implementation | Support system feature development (e.g., delivery tracking). Ensure farmer usability. | 48 (8 hr/wk) |
| Aug 30, 2026 – Sep 26, 2026 (4 weeks) | Support D4 Implementation | Support deployment preparation (e.g., security features). Verify requirement adherence. | 32 (8 hr/wk) |
| Total Hours |  |  | 176 |

Notes: BA effort is lower during development, focusing on clarification and support, as Java Developers lead implementation.

3. Testing Phase Timesheet (T1, T2, T3, T4)

Duration: February 1, 2026 – October 24, 2026 (38 weeks, covering T1, T2, T3, T4)
Role: Informed for T1, T2, T3; Consulted for T4
Description: The BA supports testers (Mr. Jason, Ms. Alekya) by reviewing test cases, providing requirement clarification, and assisting in internal acceptance testing (T4) to ensure alignment with stakeholder needs.

| Date Range | Task | Description | Hours |
| --- | --- | --- | --- |
| Feb 1, 2026 – Feb 28, 2026 (4 weeks) | Support T1 (Unit Testing) | Review unit test cases for core features (e.g., product catalog). Provide clarification as needed. | 20 (5 hr/wk) |
| Apr 12, 2026 – May 23, 2026 (6 weeks) | Support T2 (Integration Testing) | Review integration test cases (e.g., API-payment integration). Clarify requirements. | 30 (5 hr/wk) |
| Jul 5, 2026 – Aug 29, 2026 (8 weeks) | Support T3 (System Testing) | Review system test cases (e.g., end-to-end functionality). Ensure farmer requirements are met. | 40 (5 hr/wk) |
| Sep 27, 2026 – Oct 24, 2026 (4 weeks) | Support T4 (Acceptance Testing) | Assist in internal acceptance testing. Validate against requirements with Mr. Vandanam. | 80 (20 hr/wk) |
| Total Hours |  |  | 170 |

Notes: BA involvement is minimal in T1-T3 (Informed), focusing on review, but higher in T4 (Consulted) due to validation responsibilities.

4. UAT Phase Timesheet

Duration: October 25, 2026 – December 5, 2026 (6 weeks)
Role: Accountable
Description: The BA leads User Acceptance Testing, coordinating with farmers (Peter, Kevin, Ben) and manufacturers to validate the app’s usability and functionality, addressing issues and ensuring CSR alignment.

| Date Range | Task | Description | Hours |
| --- | --- | --- | --- |
| Oct 25, 2026 – Dec 5, 2026 (6 weeks) | Lead UAT | Plan and conduct UAT sessions with farmers and manufacturers. Document feedback (e.g., UI usability). Coordinate fixes with Java Developers and Testers. | 180 (30 hr/wk) |
| Total Hours |  |  | 180 |

Notes: High BA effort due to accountability for ensuring stakeholder satisfaction, mitigating risks like limited digital literacy.

5. Deployment and Implementation Phase Timesheet

Duration: December 6, 2026 – January 2, 2027 (4 weeks)
Role: Support (Consulted)
Description: The BA supports deployment by ensuring stakeholder readiness (e.g., farmer training) and verifying that the deployed app meets requirements.

| Date Range | Task | Description | Hours |
| --- | --- | --- | --- |
| Dec 6, 2026 – Jan 2, 2027 (4 weeks) | Support Deployment | Train farmers on app usage. Verify deployment aligns with requirements. Address stakeholder queries. | 80 (20 hr/wk) |
| Total Hours |  |  | 80 |

Notes: Moderate BA effort to support training and deployment, ensuring farmer adoption.

Total BA Hours Across SDLC

- Design: 720 hours

- Development: 176 hours

- Testing: 170 hours

- UAT: 180 hours

- Deployment: 80 hours

- Total: 1,326 hours (approx. 33 weeks at 40 hr/wk, spread over 70 weeks, leaving capacity for other tasks or contingency).

Question 9:

They discussed models in SDLC like waterfall RUP Spiral and Scrum . You put forth your understanding on these models When the APT IT SOLUTIONS company got the project to make this online agriculture product store, there is a difference of opinion between a couple of SMEs and the project team regarding which methodology would be more suitable for this project. SMEs are stressing on using the V model and the project team is leaning more onto the side of waterfall model. As a business analyst, which methodology do you think would be better for this project?

Solution:

To address your query, I’ll first provide a concise overview of the Software Development Life Cycle (SDLC) models mentioned—Waterfall, Rational Unified Process (RUP), Spiral, and Scrum—based on my understanding. Then, I’ll analyze the suitability of the V Model versus the Waterfall Model for APT IT Solutions’ online agriculture product store project, considering the perspectives of the Subject Matter Experts (SMEs) and the project team, and provide a recommendation as a business analyst.

Understanding SDLC Models

- Waterfall Model:

  - Overview: A linear, sequential approach where each phase (e.g., Requirements, Design, Implementation, Testing, Deployment, Maintenance) is completed before moving to the next. No overlap or iteration between phases.

  - Strengths: Simple, well-defined stages, easy to manage, suitable for projects with stable, well-understood requirements.

  - Weaknesses: Inflexible to changes, late testing (issues discovered late), not ideal for complex or evolving projects.

  - Use Case: Best for projects with fixed requirements and minimal expected changes, such as regulatory or straightforward systems.

- Rational Unified Process (RUP):

  - Overview: An iterative framework dividing the project into four phases: Inception (define scope), Elaboration (plan and design), Construction (build and test), and Transition (deploy and maintain). It emphasizes iterative development and risk management.

  - Strengths: Flexible, supports iterative refinement, manages risks early, accommodates changes.

  - Weaknesses: Complex to implement, requires experienced teams, can be resource-intensive.

  - Use Case: Suitable for large, complex projects with evolving requirements and high risks.

Spiral Model:

- Overview: Combines iterative development with risk analysis. The project progresses through repeated cycles (spirals), each including planning, risk assessment, prototyping, and evaluation.

- Strengths: Strong risk management, supports prototyping, adaptable to changing requirements.

- Weaknesses: Costly, time-consuming, requires expertise in risk assessment.

- Use Case: Ideal for high-risk, innovative projects with unclear or evolving requirements, such as research-driven or experimental systems.

Scrum:

- Overview: An agile framework using short iterations (sprints, typically 2–4 weeks) to deliver incremental product features. It involves roles (e.g., Product Owner, Scrum Master, Team), ceremonies (e.g., sprint planning, daily stand-ups), and artifacts (e.g., product backlog).

- Strengths: Highly flexible, promotes collaboration, delivers working software frequently, adapts to changes.

- Weaknesses: Requires disciplined teams, can lead to scope creep, less focus on documentation.

- Use Case: Best for dynamic projects with evolving requirements, such as web or mobile applications.

Analysis: V Model vs. Waterfall for the Online Agriculture Product Store

Project Context:

- The project involves developing an online agriculture product store, likely including features like product listings, e-commerce functionality (cart, payments), user accounts, and possibly inventory or supply chain integration.

- SMEs advocate for the V Model, while the project team prefers the Waterfall Model.

- As a business analyst, I need to evaluate which methodology better suits the project’s needs, considering factors like requirements stability, complexity, stakeholder involvement, and delivery timelines.

V Model:

Description: An extension of the Waterfall Model, the V Model maps each development phase (e.g., Requirements, Design, Development) to a corresponding testing phase (e.g., Unit Testing, Integration Testing, User Acceptance Testing). It emphasizes verification and validation at each stage.

Pros:

Rigorous Testing: Each development phase has a paired testing phase, ensuring issues are caught early (e.g., requirements validated during acceptance testing).

Structured: Like Waterfall, it’s sequential and disciplined, suitable for projects needing clear documentation and traceability, which may be important for an agriculture store with regulatory or compliance needs (e.g., payment security, data privacy).

Predictable: Well-defined phases align with fixed budgets and timelines, which may appeal to stakeholders like SMEs who value control.

Cons:

Limited Flexibility: Changes to requirements after the initial phase are difficult, which could be problematic if the agriculture store’s features (e.g., user interface, integrations) evolve during development.

Late Delivery: The full product is delivered only at the end, delaying feedback from end-users (e.g., farmers, buyers).

Suitability: Ideal if the project has well-defined, stable requirements and requires high reliability (e.g., secure transactions, compliance with agricultural regulations).

Waterfall Model:

- Description: A linear, sequential approach with no iteration. Phases (Requirements, Design, Implementation, Testing, Deployment) are completed one after another.

- Pros:

Simplicity: Easy to understand and manage, which may align with the project team’s preference for a straightforward approach.

Clear Milestones: Well-suited for projects with fixed scope and predictable deliverables, potentially fitting an agriculture store with standard e-commerce features.

Cost Control: Fixed phases help in budgeting, which may be a priority for APT IT Solutions.

- Cons:

No Early Testing: Testing occurs only after implementation, risking late discovery of defects, which could be costly for an online store with complex integrations (e.g., payment gateways, inventory systems).

Inflexible: Changes in requirements (e.g., new user features or market demands) are hard to accommodate, which could be a drawback if the agriculture market demands evolve.

Suitability: Best for projects with clear, unchanging requirements and low complexity, but less ideal if the store requires iterative feedback or has potential for scope changes.

Project Considerations:

- Requirements Stability: An online agriculture product store likely has some standard e-commerce features (product catalog, checkout, user accounts), but requirements may evolve based on user feedback (e.g., farmers wanting specific features like bulk ordering or seasonal promotions) or market trends (e.g., adding mobile app support).

- Complexity: The project may involve integrations (e.g., payment gateways, inventory systems, logistics for agricultural products), increasing complexity and the need for robust testing.

- Stakeholder Needs: SMEs’ preference for the V Model suggests a focus on quality and reliability, possibly due to regulatory or operational concerns in agriculture (e.g., accurate product data, secure transactions). The project team’s preference for Waterfall indicates a desire for simplicity and predictability.

- Timeline and Budget: Both models support fixed schedules, but the V Model’s early testing may reduce rework costs compared to Waterfall’s late testing.

Recommendation as a Business Analyst

Recommended Methodology: V Model

Rationale:

- Enhanced Quality through Early Testing: The V Model’s strength lies in its paired testing phases, ensuring that requirements, design, and code are validated at each step. For an online agriculture product store, this is critical to avoid costly errors in features like payment processing, inventory tracking, or user experience, which could affect farmers and buyers.

- Alignment with SME Priorities: The SMEs’ emphasis on the V Model suggests they prioritize reliability and compliance, which aligns with the potential need for regulatory adherence (e.g., data privacy, secure transactions) in an agriculture e-commerce platform.

- Moderate Complexity Handling: While the project may have some standard e-commerce features, integrations (e.g., supply chain, payment systems) and potential customizations (e.g., agricultural product-specific features) increase complexity. The V Model’s structured approach with early validation is better suited than Waterfall’s late testing, which risks discovering issues too late.

- Balancing Team Concerns: The project team’s preference for Waterfall likely stems from its simplicity. The V Model, while slightly more complex, retains a sequential structure they’re familiar with, making it a feasible compromise that addresses both quality (SME concern) and manageability (team concern).

- Risk Mitigation: The V Model reduces risks by catching defects early, which is crucial for a customer-facing platform where errors (e.g., incorrect pricing, failed transactions) could harm user trust and business reputation.

Conclusion:

As a business analyst, I recommend the V Model for APT IT Solutions’ online agriculture product store project. It balances the SMEs’ focus on quality and reliability with the project team’s need for a structured, predictable process. Its early testing ensures robust deliverables, critical for a customer-facing e-commerce platform, while its sequential nature aligns with the team’s comfort with Waterfall. To enhance success, the team should prioritize early stakeholder engagement and prototyping to minimize the V Model’s inflexibility risks.

Question 12:

The Committee of Mr. Henry, Mr Pandu, and Mr Dooku discussed with Mr Karthik and finalised on the V Model approach (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) Mr Vandanam is mapped as a PM to this project. He studies this Project and Prepares a Gantt chart with V Model (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) as development process and the Resources are PM, BA, Java Developers, testers, DB Admin, NW Admin.

A Gantt Chart is a visual project management tool used to plan, schedule, and track tasks over time. It is especially useful in software development, construction, marketing campaigns, and other projects where time and task coordination are crucial.

A Gantt chart is a project management tool that visually represents a project’s tasks, their durations, and their sequence over a timeline. It uses horizontal bars to show when each task starts and ends, making it easy to track progress, dependencies, and resource allocation.

In the context of your previous query about the V Model project managed by Mr. Vandanam, I provided a Gantt chart using a Chart.js bar chart to illustrate the timeline of tasks (Requirements Gathering, Requirements Analysis, Design, Development phases D1–D4, Testing phases T1–T4, and User Acceptance Testing) starting from January 1, 2026. Each task was represented as a bar, with lengths corresponding to estimated durations (e.g., RG: 2 weeks, D1: 4 weeks) and assigned resources (PM, BA, Java Developers, Testers, DB Admin, NW Admin). The chart showed the sequential nature of the V Model, where development phases are followed by corresponding testing phases, spanning 34 weeks.

Benefits of a Gantt Chart:

Shows start and end dates for each task.

Helps identify overlapping tasks and manage dependencies.

Clearly displays project timelines and progress.

Keeps all stakeholders aligned on deliverables and schedule.

Useful for tracking delays or overruns.

Gantt Chart Table – V-Model SDLC Approach

| Phase | Start Date | End Date | Duration | Responsible Resource(s) |
| --- | --- | --- | --- | --- |
| RG - Requirement Gathering | Aug 1, 2025 | Aug 10, 2025 | 10 days | BA, PM |
| RA - Requirement Analysis | Aug 11, 2025 | Aug 20, 2025 | 10 days | BA, PM |
| Design | Aug 21, 2025 | Aug 30, 2025 | 10 days | BA, Java Developers |
| D1 - Development Phase 1 | Sep 1, 2025 | Sep 10, 2025 | 10 days | Java Developers |
| T1 - Testing Phase 1 | Sep 11, 2025 | Sep 15, 2025 | 5 days | Testers |
| D2 - Development Phase 2 | Sep 16, 2025 | Sep 25, 2025 | 10 days | Java Developers |
| T2 - Testing Phase 2 | Sep 26, 2025 | Sep 30, 2025 | 5 days | Testers |
| D3 - Development Phase 3 | Oct 1, 2025 | Oct 10, 2025 | 10 days | Java Developers |
| T3 - Testing Phase 3 | Oct 11, 2025 | Oct 15, 2025 | 5 days | Testers |
| D4 - Development Phase 4 | Oct 16, 2025 | Oct 25, 2025 | 10 days | Java Developers |
| T4 - Testing Phase 4 | Oct 26, 2025 | Oct 31, 2025 | 5 days | Testers |
| UAT - User Acceptance Testing | Nov 1, 2025 | Nov 10, 2025 | 10 days | BA, PM, Testers |
| Database Setup | Sep 1, 2025 | Sep 10, 2025 | 10 days | DB Admin |
| Network Configuration | Sep 1, 2025 | Sep 5, 2025 | 5 days | NW Admin |
| Project Oversight & PM | Aug 1, 2025 | Nov 10, 2025 | Full Duration | PM |