## Slide 1: CRM Enhancement Project Proposal
Prepared by: Susmita Devi
Date: 5/07/2025

## Slide 2: Situation
RMs use CRM to handle lead generation, KYC uploads, account opening, and service requests.
Initial training is provided, but RMs often face difficulties during live CRM usage.
Common issues include forgetting steps, misinterpreting fields, or system navigation errors.
RMs frequently depend on peers for help, leading to wasted hours and work delays.
Once an escalation is raised, there is limited visibility on its status or ownership.
Customer feedback is collected externally (email/SMS) and not visible to RMs inside CRM.
No structured notification system exists to remind RMs of pending tasks or follow-ups.
These gaps impact service quality, TAT, client communication, and overall CRM usability.

## Slide 3: Problem
RMs lack real-time support while performing CRM tasks, leading to operational delays.
Over-reliance on peers during working hours slows down task completion.
No visibility into the progress of raised escalations creates confusion and missed SLAs.
CRM does not offer a built-in feedback loop, so client sentiments remain hidden.
Missed follow-ups and deadlines occur due to absence of intelligent reminders or alerts.
Client trust and satisfaction drop when service delays or repeated issues go unaddressed.
These challenges lead to inefficiencies, errors, and inconsistent service quality across teams.

## Slide 4: Opportunity
Introduce an in-app Chabot to guide RMs in real-time, reducing dependency on peers.
Build an escalation tracking dashboard to provide visibility and accountability across teams.
Integrate a feedback loop to capture client experience immediately after key actions.
Implement a smart notification engine to remind RMs of pending tasks, follow-ups, and SLA deadlines.
Enhance overall user experience and process efficiency within the CRM.
Enable RMs to provide more proactive and consistent service, improving customer satisfaction.
Empower team leads and supervisors with data-driven insights on performance and resolution gaps.

## Slide 5: Purpose Statement (Goals)
To enhance CRM usability and efficiency for Relationship Managers through real-time support, tracking, and automation. Improve customer experience with timely follow-ups, feedback capture, and escalation transparency. Deliver business value through faster service, better compliance, and increased RM productivity.

## Slide 6: Project Objective
Improve Relationship Manager (RM) efficiency by enabling real-time, in-app support and reducing peer dependency.
Build an interactive chatbot/help overlay to guide RMs during critical CRM workflows like lead input, KYC submission, and account opening.
Increase transparency and ownership in issue resolution through an integrated escalation tracker dashboard with SLA indicators and role-based access.
Strengthen customer satisfaction by implementing a feedback loop that captures sentiment after key RM-client interactions.
Ensure timely follow-ups and task closures by introducing a smart notification and reminder engine with configurable alerts.
Deliver all features incrementally as MVPs through Agile sprints, allowing early user validation and minimizing delivery risk.
Track and measure outcomes post-implementation through KPIs such as SLA adherence, task completion rates, RM adoption, and feedback response scores.

## Slide 7: Success Criteria
RMs are able to complete CRM tasks independently with reduced peer dependency, improving productivity.
Escalation handling time is reduced due to real-time visibility and SLA tracking.
Follow-ups and task deadlines are met consistently through smart notifications and reminder triggers.
At least 50% of clients respond to feedback prompts, helping identify dissatisfaction early.
New RMs require less time to become proficient in CRM operations due to in-app support.
Target improvements in key metrics:
+10% increase in SLA adherence
+15% reduction in task delays
+3-point growth in Net Promoter Score (NPS)
Features are successfully implemented using Agile methodology, with iterative delivery and continuous stakeholder input.

## Slide 8: Methods
Agile method- reason for choosing it.
The project involves multiple small enhancements-best suited for phased, iterative development.
The end users and stakeholders could validate each features quickly, allowing room for course correction.
Agile-scrum allows flexibility in prioritizing feature based on urgency and impact(eg. Chatbot before dashboard)
Support collaborations between cross-functional teams-business tech QA and end users.

## Slide 9: Approaches
Conduct stakeholder meetings to identify current pain points in CRM and gathered requirements
Created product backlog representing all CRM enhancement features, applied MOSCOW framework to prioritize them.
Identified and documented MVP.
Created clear user stories with acceptance criteria, ensuring alignment with both business goal and development needs.
Supported development team in estimating efforts using story points assigned business value to help prioritize high-impact story.
Conducted and participated in sprint planning daily standups, sprint reviews and retrospectives.
Collaborate with UI/UX and development teams to prototype solutions.
Tracked progress, via sprint burn downtime, discussed blockers and ensured sprint goals stay on track.
Conducted UAT or demoed features to stakeholders, business team after each sprint.
Supported in delivering working features

## Slide 10: Resources
Recourses- stakeholders, developers, UI/UX team, product owner, database support, compliance team
Time: 6-8 weeks, 4 sprint, 4 months
Budget: 25 lakhs
Tools: Business Analysis tools- JIRA/Trello , Draw.io, power BI, CRM dashboard. Development tools- React/Angular front end- For building interactive components like Chatbot UI, escalation dashboard, JAVA/.NET, APIs.

## Slide 11: Risks
CRM is tightly integrated with legacy systems; changes may impact stability
End-users (RMs, Ops staff) may resist changes to familiar workflows.
Risk of integration issues or unintended disruption to existing workflows while implementing new features (e.g., overlays, dashboards).
Improvements like feedback loops may not show immediate ROI, affecting management buy-in

## Slide 12: Dependencies
Technical dependency on internal IT teams and CRM vendors may delay sprints
Regulatory compliance needs to be considered in all workflow modifications

## Slide 13: Project Governance
Project Sponsor: [ Endrew Jacob]
Project Manager: [ Harish Balli]