CAPSTONE PREP – 2

QUESTION – 1

WRITE AGILE MANIFESTO

-AGILE MANIFESTO

Four main values –

- Individuals and interactions over process and tools

- Working software over comprehensive documentation

- Customer collaboration over contract negotiation

- Responding to change over following plan.

Twelve principles of Agile software –

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile process harness change for the customer’s competitive advantage.

- Deliver working software frequently , from a couple of weeks to a couple of months with preference to the shorter timescale.

- Business people and developers must work together daily through out the project.

- Build projects around motivated individuals. Give them  the environment and support they need, and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.

- Working software is the primary measure of progress.

- Agile process promote sustainable development. The sponsors, developers and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

(10)Simplicity …the art of maximizing the amount of work not done ..is essential.

(11) The best architectures, requirements and designs emerge from self organizing                 teams

(12) At regular intervals, the team reflects on how to become more effective, then tunes and adjust its behaviour accordingly.

QUESTION-2

Write minimum 40 user stories and their Acceptance criteria along with their BV and CP ?

| User Story NO: 1 | Tasks: 2 |  | Priority: high |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO REGISTER AN ACCOUNT WITH MY EMAIL ID AND PASSWORD SO THAT I CAN SAVE MY ORDER HISTORY |  |  |  |
| BV: 500 |  | CP:04 |  |
| Acceptance Criteria : Registration screen Text boxes for email id and password Click on Register button Send registered successfully notification to customer |  |  |  |

| User Story NO: 2 | Tasks:2 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO LOGIN AND OUT OF MY ACCOUNT SO THAT I CAN SECURELY ACCESS MY INFORMATION |  |  |  |
| BV: 400 |  | CP:03 |  |
| Acceptance Criteria : Click on login button Click on logout button Get to enter credentials screen after logout. |  |  |  |

| User Story NO: 3 | Tasks:2 |  | Priority: High |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO BROWSE THE RESTAUARNTS SO THAT I CAN EASILY FIND THE KIND OF FOOD I AM LOOKING FOR |  |  |  |
| BV: 300 |  | CP: 03 |  |
| Acceptance Criteria : System should display the list of restaurants. User should able to sort the restaurants. |  |  |  |

| User Story NO: 4 | Tasks: 2 |  | Priority: |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW RESTAURANT MENU WITH PRICES WITH DESCRIPTIONS SO THAT I CAN MAKE INFORMATED DECISION ABOUT MY ORDER |  |  |  |
| BV: 300 |  | CP:02 |  |
| Acceptance Criteria : System should display the menu and description of restaurant User can able to select the item from menu |  |  |  |

| User Story NO:05 | Tasks:02 |  | Priority: high |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO ADD MY ADDRESS SO THAT I CAN GET MY ORDER TO MY ADDRESS |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Text box to enter the address Business rules. within the 4 km radius |  |  |  |

| User Story NO:06 | Tasks:2 |  | Priority: High |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SELECT PAYMENT MODE SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |  |
| BV: 500 |  | CP:04 |  |
| Acceptance Criteria : Display payment modes Radio buttons for payment modes Payment submit button, payment successful notification Business Rule: can select only one payment mode . |  |  |  |

| User Story NO:07 | Tasks:02 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SEE HIGH QUALITY PHOTOS OF DISHES SO THAT I CAN VISUALIZE WHAT I AM ORDERING |  |  |  |
| BV: 300 |  | CP:02 |  |
| Acceptance Criteria : DISPLAY THE DISHES IMAGES ZOOM OPTION FOR IMAGES |  |  |  |

| User Story NO:08 | Tasks:02 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO TRACK THE ORDER SO THAT I CAN KNOW WHERE THE DELVERY BOY IS |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Display the tracking id and link By clicking on link display the delivery boy status. |  |  |  |

| User Story NO:09 | Tasks:02 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW MY PAST ORDER HISTORY SO THAT I CAN REORDER MY FAVORITE MEALS |  |  |  |
| BV: 200 |  | CP:02 |  |
| Acceptance Criteria : Click on history Display the order list of past dates |  |  |  |

| User Story NO: 10 | Tasks: 02 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO TRACK THE REAL TIME STATUS OF MY ORDER SO THAT I KNOW WHEN TO EXPECT MY FOOD |  |  |  |
| BV: 300 |  | CP:03 |  |
| Acceptance Criteria : Click on order status button Show order status as order places, preparing, out for delivery. |  |  |  |

| User Story NO:11 | Tasks:02 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO RECIVE NOTIFICATIONS FOR ORDER UPADTES SO THAT IAM ALWAYS INFORMED |  |  |  |
| BV: 300 |  | CP:04 |  |
| Acceptance Criteria : Click on notification button show notifications to customer |  |  |  |

| User Story NO:12 | Tasks:02 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO CONTACT CUSTOMER CARE OF APPLICATION SO THAT I CAN GET HELP WITH ANY ISSUES |  |  |  |
| BV: 500 |  | CP:04 |  |
| Acceptance Criteria : Display help option on screen Click on contact us button Clear the issue . |  |  |  |

| User Story NO: 13 | Tasks:02 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO RATE AND REVIEW RESTAURANT AND DELIVERY DRIVERS SO THAT I CAN GICE FEEDBACK AND HELP OTHER USERS |  |  |  |
| BV: 300 |  | CP:04 |  |
| Acceptance Criteria : Display rating and review option on screen Text box for rating Click on submit button Rating gets uploaded |  |  |  |

| User Story NO: 14 | Tasks:02 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO ADD, EDIT AND REMOVE MENU ITEMS SO THAT I CAN KEEP MY OFFERINGS UP TO DATE |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Click on add button, edit button and remove items System should able to perform activities |  |  |  |

| User Story NO:15 | Tasks:3 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW ORDES SO THAT I CAN VIEW THE LIST OF ORDERS |  |  |  |
| BV: 400 |  | CP:03 |  |
| Acceptance Criteria : View orders Display the list of orders in the tabular form |  |  |  |

| User Story NO:16 | Tasks:03 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO UPLOAD HIGH QUALITY IMAGES OF DISHES SO THAT CUSTOMERS CAN SEE WHAT THEY ARE ORDERING |  |  |  |
| BV: 300 |  | CP:04 |  |
| Acceptance Criteria : Can able to upload hd images Display the images of dishes |  |  |  |

| User Story NO:17 | Tasks:03 |  | Priority:medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO MARK ITEMS AS OUT OF STOCK SO THAT CUSTOMER DON’T ORDER UNAVAILABLE DISHES |  |  |  |
| BV: 200 |  | CP:02 |  |
| Acceptance Criteria : Click on update item status Select available or not available Shoe status on display |  |  |  |

| User Story NO:18 | Tasks:03 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PROVIDE TIME SLOTS SO THAT CUSTOMER CAN CHECK OPENINGS AND CLOSING HOURS OF RESTAURANT |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Click on restaurant dashboard Add from time to time Click submit button |  |  |  |

| User Story NO:19 | Tasks:3 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTURANT OWNER I WANT TO KNOW FEEDBACK FROM CUSTOMERS SO THAT I CAN IMPROVE MY SERVICES |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Click on ratings Display ratings and reviews uploaded by customers |  |  |  |

| User Story NO:20 | Tasks:03 |  | Priority:Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO RECIVE INSTANT NOTIFICATIONS FOR NEW ORDERS SO THAT I CAN START PREPARE THE ORDER |  |  |  |
| BV: 500 |  | CP:05 |  |
| Acceptance Criteria : Click on new order button Display the new order Click on accept button |  |  |  |

| User Story NO:21 | Tasks:02 |  | Priority:medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO ACCEPT OR REJECT ORDERS SO THAT I CAN MANAGE MY CAPACITY |  |  |  |
| BV: 300 |  | CP:03 |  |
| Acceptance Criteria : Display on view orders Select accept or reject option Click submit |  |  |  |

| User Story NO:22 | Tasks:03 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PRINT ORDER RECEIPTS SO THAT I CAN KEEP PHYSICAL RECORDS |  |  |  |
| BV: 400 |  | CP:05 |  |
| Acceptance Criteria : Display order accepted Click on print option Take the print |  |  |  |

| User Story NO:23 | Tasks:03 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW MY ORDER HISTORY AND SALES REPORT SO THAT I CAN TRACK MY PERFORMANCE |  |  |  |
| BV: |  | CP: |  |
| Acceptance Criteria : Click on sold items Display the sold item list with prices |  |  |  |

| User Story NO: 24 | Tasks: 03 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO COMMUNICATE WITH CUSTOMERS SO THAT I CAN RESLOVE PROBLEMS EASILY |  |  |  |
| BV: 200 |  | CP:02 |  |
| Acceptance Criteria : Click on customer complains Display notifications list from the customers |  |  |  |

| User Story NO:25 | Tasks:03 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO OFFER DISCOUNTS AND COUPONS SO THAT I CAN GET MORE SALE |  |  |  |
| BV: 400 |  | CP: 04 |  |
| Acceptance Criteria : Click on upload Select discounts or coupons and upload in application. Display coupons and discounts to customers |  |  |  |

| User Story NO:26 | Tasks:4 |  | Priority: high |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REGISTER IN SCRUM FOOD APPLICATION SO THAT I CAN DELIVER ORDERS |  |  |  |
| BV: 500 |  | CP:02 |  |
| Acceptance Criteria : Register screen Text box for user name and password ,mobile number, bike RC , Bike images etc.. Verification Click on register button Send successful notification to user |  |  |  |

| User Story NO: 27 | Tasks:04 |  | Priority:High |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN APPLICATION BY USER NAME AND PASSWORD SO THAT I CAN DELIVER MY ORDERS |  |  |  |
| BV: 300 |  | CP:02 |  |
| Acceptance Criteria : Click on login button Text box for user name and password Show login successful in display |  |  |  |

| User Story NO:28 | Tasks:04 |  | Priority: High |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO RECIVE NOTIFICATIONS FOR DELIVERY REQUEST SO THAT I CAN ACCEPT THEM |  |  |  |
| BV: 500 |  | CP:04 |  |
| Acceptance Criteria : Show the notifications in app Select accept or reject button Display Accepted successfully |  |  |  |

| User Story NO:29 | Tasks:4 |  | Priority:High |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VEIW PICK UP LOCATION AND DELIVERY LOCATION ON A MAP SO THAT I CAN PLAN MY ROUTE |  |  |  |
| BV: 500 |  | CP:05 |  |
| Acceptance Criteria : Click on view location Display route on map Click on start option in map for route. |  |  |  |

| User Story NO:30 | Tasks:04 |  | Priority:Medium |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW CUSTOMER DELIVERY INSTEUCTIONS SO THAT I CAN DELIVER ACCORDING TO THEIR OPTIONS |  |  |  |
| BV: 400 |  | CP:03 |  |
| Acceptance Criteria : Click on customer instructions Display the selected option 1: GIVE NEAR DOOR STEP, 2 HANDOVER IT TO WATCH MAN etc.. Click on Deliver successful button |  |  |  |

| User Story NO:31 | Tasks:04 |  | Priority: Medium |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO CONTACT THE CUSTOMER FOR ANY ISSUES WITH DELIVERY SO THAT I CAN RESLOVE THEM |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Display the customer contact option Select call or chat option Communicate with them . |  |  |  |

| User Story NO:32 | Tasks:4 |  | Priority: medium |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO MARK AN ORDER AS DELIVERED WITH PROOF BY IMAGE SO THAT THERE IS A RECORD |  |  |  |
| BV: 300 |  | CP:3 |  |
| Acceptance Criteria : Click on upload delivery items image Click image and upload Click on delivery completed |  |  |  |

| User Story NO:33 | Tasks:4 |  | Priority:high |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VEIW THE PAYMENT MODE SO THAT I CAN COLLECT MONEY IF IT IS COD |  |  |  |
| BV: 500 |  | CP:5 |  |
| Acceptance Criteria : Click on payment option If it is COD collect the money . |  |  |  |

| User Story NO:34 | Tasks:4 |  | Priority: hidh |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW FEEDBACK SO THAT I CAN IMPROVE MY PERFORMANCE ACCORDINLLY |  |  |  |
| BV: 400 |  | CP:04 |  |
| Acceptance Criteria : Click on my rating option Display the customer rating on delivery driver |  |  |  |

| User Story NO:35 | Tasks:4 |  | Priority:medium |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW MY EARNINGS FOR EACH DELIVERY SO THAT I CAN TRACK MY INCOME |  |  |  |
| BV: 400 |  | CP:03 |  |
| Acceptance Criteria : Click on my trips Display the successfully delivered items with earnings |  |  |  |

| User Story NO:36 | Tasks:5 |  | Priority:high |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VEIW THE RESTAURANT SO THAT I CAN APPROVE RESTAURANT REGISTRATION |  |  |  |
| BV: 500 |  | CP:04 |  |
| Acceptance Criteria : Click on restaurant list option. Display the restaurant list ,verify restaurant ,approve button , reject button Notification to restaurant. |  |  |  |

| User Story NO: 37 | Tasks:05 |  | Priority:medium |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO MONITOR AVERAGE DELIVERY TIMES AND DELAYS IN MY REGION SO THAT I CAN TAKE CORRECTIVE ACTIONS FOR BETTER SERVICE QUALITY |  |  |  |
| BV: 300 |  | CP:02 |  |
| Acceptance Criteria : Tracking orders button Display delivery time and delays with location Display the customers feedbacks |  |  |  |

| User Story NO:38 | Tasks:5 |  | Priority:m |
| --- | --- | --- | --- |
| AS A BUSSINESS OWNER I WANT TO VIEW RESTAURANT REVENUE REPORT SO THAT I CAN VIEW THE RESTAURANT’S REVENUE |  |  |  |
| BV: 300 |  | CP:2 |  |
| Acceptance Criteria : Reports button Display revenue reports in options Select revenue report in list Download report in excel |  |  |  |

| User Story NO: 39 | Tasks:5 |  | Priority:m |
| --- | --- | --- | --- |
| AS A BUSSINESS OWNER I WANT TO TRACK CUSTOMER RATINGS AND REVIEWS SO THAT I CAN IDENTIFY SERVICE ISSUES . |  |  |  |
| BV: 300 |  | CP:4 |  |
| Acceptance Criteria : Click on customer feedback Display review and ratings |  |  |  |

| User Story NO:40 | Tasks:2 |  | Priority:m |
| --- | --- | --- | --- |
| AS AN BUSSINESS OWNER I WANT TO OFFER DISCOUNTS AND COUPONS SO THAT I CAN ATTRACT NEW CUSTOMERS |  |  |  |
| BV: 400 |  | CP:03 |  |
| Acceptance Criteria : Create discounts and coupons Release option Approve coupons and discounts. |  |  |  |

Question – 3

WHAT IS EPIC ? WRITE 2 EPICS

An epic is a set of related user stories they can also consider a really big user story in another words its like a large body of work that can be broke down into smaller , manageable user stories .

It represents a significant feature ,functionality or business goal that usually takes multiple sprints to complete.

SCRUM FOODS

(1)

The epic is scrum foods a food delivery applications will charge of this epic and this application should ensure that all the user stories should complete to satisfy the customers and the user stories include from the customer side is

. User should register by the email id and password and he should get logged in by entering the credentials

. user should browse the restaurant and select the specific dishes from the restaurant

. He should able to see the high quality images so that he can visualize what he wants to order

. He should able to contact the restaurant and the delivery boy about the order he placed.

. he should have many option for the payment by debit cards,credit cards , COD options to make the payments in the applications

. He need option like review and ratings in the application so that he can give the feedback and help the other customers

(2) Epic of an scrum foods from the application side

.Scrum food application wants to provide fast , reliable online food delivery application targeting customer of all age group offering any time service

. customers and delivery boy should able to contact the restaurant for ant issues

.Every individual how participate in the application should registered in the application

. application should show the performance of the delivery boy and restaurant what types of service the are performing to satisfying the customer

.Communication between the customer,restaurant and delivery boy should be happened by the application.

.Payment options should be display to the delivery rider so that he can collect the payment and update in the application

.Every one hoe got registered in the application should get satisfied by the performance of the application

Question -4

WHAT IS THE DIFFERENCE BETWEEN BV AND CP?

| BUSINESS VALUE | COMPLEXITY POINTS |
| --- | --- |
| - Measures the benefit or impact a feature brings to the business or end user - It is seen by the customer and stakeholder perspective - It helps to prioritize work based on the impact - This is estimated by the scrum currency notes for (ex-Rs 10,20,50,100,500,1000) - Higher value items are usually prioritized first. - Based on customer impact, revenue potential, cost savings. | - It estimates the efforts ,difficulty or time required to implement the feature. - It is seen by the development team’s perspective. - It Helps plan and estimate workload and team capacity. - This is estimated by scrum developer by using poker cards with values 1,2,3,5,8,13,20.40..Big - It Help determine if a high-value item is worth the effort - It is Based on technical difficulty, unknowns, risks, and effort. |

QUESTION – 5

EXPLAIN ABOUT SPRINT ?

. A sprint is a scrum based agile methodology concept similar to an iteration and it is a timeboxed to deliver a specific set of user stories and produce working features within a set of time period .

. During the sprint planning the business customer or the product owner specifies the user story priority and the development team commits to the scope for a given sprint.

. During a print , user stories can be removed from the sprint scope but new stories can’t be added . this allows project team to focus on the goals of the sprint and deliver rapidly.

. A sprint is short,fixed period of time usually 1 to 4 weeks where the software development team willwork to complete a specific set of tasks .

. Its like a focused work cycle with the clear goal.

. in anther words a sprint is like a mini project inside a bigger project ,the team picks few important things to build like creating the feature,fixing bugs,testing something etc..

And they commit to finishing those tasks within the sprint’s timeframe

. At the end of the sprint , the team shows what they have completed and gets the feedback and then plans to the next sprint

. in this way progress is made step by step and the product keeps improving .

KEY POINTS

- TIME BOXED : Has a set of duration (e.g. 2 weeks )

- GOAL ORIENTED : Focuses on delivery something valuable and usable

- TEAM COMMITMENT : Every one will agrees on what will be delivered during the sprint

- CONTINUOUS FEEDBACK: Ends with a review to gather feedback and improve

Question – 6

Explain product backlog and sprint backlog ?

PRODUCT BACKLOG

The product backlog is a master list of everything that needs to be done for a product.it is includes all the features, improvements, bugs fixes, technical tasks  and ideas its like any work that could add value to the product.

KEY POINTS  :

- Owned and maintained by the product owner

- Continuously updated as new ideas or requirements come in.

- Items are typically written as user stories

- Prioritized based on business value and urgency

- Not every thing in the product backlog will be done only the most valuable items rise to the top

SPRINT BACKLOG –

The sprint backlog is a subset of the product back log. it includes the specific items the team commits to delivering in the current sprin , its like sprint backlog is a smaller list taken from the product backlog,

The team will plan to finish the task during the current sprint usually (1to 2 weeks)

Its like saying : From the big to-do list , here is what we are focusing on right now .

The team chooses these items during the sprint planning meeting and breaks them down into smaller tasks so they know what exactly needs to be done .

KEY POINTS :

- Created during sprint planning

- Owned by the development team

- Contains selected product back log items and plan for complete them

- Can include tasks that break user stories into manageable steps

- Changes during the sprint are discouraged unless absolutely necessary

Question – 7

What is impediments log? write 2 impediments.

An impediments log is a list of problems or blockers that are slowing down or stopping the team from getting there work done

These type of problems are called impediments and they can be anything like technical issue , missing information, unclear requirements , delays from other teams or even broken tools .

The scrum master or team lead usually keeps track of the issues In the log and work to get them resolved as quickly as possible .

- A description of the problem, the date it was identified and who reported it is included in an impediments log

Impediment #1 - DESCRIPTION: The payment gateway integration is failing in the staging environment due to missing API keys - Impact : Blocks testing and deployment of the new “ADD TO CART & PAY” feature. - Raised by: Developer - STATUS: Open - ACTION: Waiting for API credentials from the payment provider, scrum master following up with the vendor - OWNER: Scrum master

IMPEDIMENT #2 - DESCRIPTION: Restaurant owner have not provided updated menus , which are required for the dynamic pricing feature. - IMPACT: User story for “MENU & PRICE UPDATES” cannot be started. - RAISED BY : Product owner - STATUS: In progress - ACTION: Reminder sent to restaurants . sales team asked to escalate to key accounts - OWNER: Product owner

Question – 8

Explain velocity of the team?

Velocity is measured as how much work a team can finish in  a sprint ,it helps the team to understand their speed and capacity over time.

. It is usually measured in the story points .

. It helps to plan future sprints more accurately

. It shows how the team is progressing over time

. It helps in predicting delivery timelines .

As per my assumption

13 story points in sprint 1

14 story points in sprint 2

15 story points in sprint 3

So the average velocity is about 13.6 points per sprint .

Question-9

Draw a sprint burn charts and product burnt down charts

Sprint 1

LOGIN

Sprint 1 BURNDOWN CHART

Sprint burndown chart -

Sprint 2

TRACKING-

BURNUP CHART

Sprint burndown chart

QUESTION – 10

Explain about Product Grooming?

Product grooming in scrum is a key ongoing activity that ensures the product backlog is well organized, clear and prioritized so the team can efficiently plan and deliver work in upcoming springs

Product grooming is the process of

- Reviewing items in the product backlog

- Clarifying requirements or user stories

- Breaking down large items into smaller, actionable tasks like epics into stories

- Prioritizing based on value,risk and dependencies

- Estimating efforts

- Ensuring readiness of item for future sprint planning

The benefits of product grooming is keeping the backlog clean and actionable, it prevents last minute confusion during sprint planning, it improves team alignment and shared understanding, it leads to better sprint forecasts and delivery predictability.

QUESTION 11

Explain role of the scrum master and product owner

SCRUM MASTER-

The scrum master is responsible for ensuring that the scrum process is understood and followed, he is like servant leader who helps the team to work efficiently by removing the obstacles and fostering a productive environment

KEY REPONSIBILITIES :

- He will facilitate scrum process by

. Sprint planning

. Daily scrum meeting (stand up meeting)

. Sprint review

. Sprint Retrospective meeting

- Remove impediments

Helps resolve blockers or issues that slows down project

- Coach the team

.Teach scrum principles

.Guide the team towards self-organization and continuous improvement

- Shield the team

.  Protect team from outside interruptions or distractions

- Work with product owner

.  Help to manage the backlog

.  Ensure backlog items are clear and ready for sprint planning

- Foster collaboration

. encourage healthy communication between team members and stakeholders

PRODUCT OWNER

The product owner is responsible for maximizing the value of the product by managing the product backlog , he acts as a bridge between the business needs and the development team.

Key responsibilities

- Define and prioritize work

. create and maintain the product backlog

. prioritize items basd on the business value , risk and need.

- Clarify requirements

.   provide clear and detailed user stories or backlog items

.   Be available to answers team questions

- Represents stakeholders

. Acts as the voice of the customers

. gather feedback and requirements from stakeholders and also consider stake holders interest.

- Accept work

.  accept or reject completed stories in sprint review

. Continue or discontinue the development.

.whether to ship the product or not.

- Set product vision

. define goals and long term strategy for the product.

QUESTION – 12

Explain all meetings conducted in the scrum project

-Sprint planning meeting

This happens at the beginning of the each sprint and team decides on what they will deliver in this sprint ( sprint goal) and how will we do the work ( plan the tasks)

The output of the meeting is sprint goal and sprint backlog items and plan.

The participants are Scrum master , Product owner, Development team

-DAILY SCRUM MEETING (STAND-UP)

This happens daily usually at the same time and place to inspect progress and team activities

The participants are scrum master, product owner, development team.

The team will just answer this three questions

- What did you do today ?

- What will you do tomorrow?

- Is there any impediments that slowing or stopping you ?

SPRINT REVIEW MEETING-

This meeting happens at the end of the sprint

The participants are scrum team , product owner , scrum master , development team and key stakehoders

In this meeting the team will demo the completed stories to product owner and get it cleared.

SPRINT RETROSPECTIVE MEETING

This meeting happens after the sprint review meeting and before the next sprint planning meeting

This participate in this meeting are only the scrum team

This is to reflect on the sprint nad identify improvements for the next sprint

In this the team will answers this three questions

- What went well in the sprint?

- What did not go well?

- What are the required areas of improvements in next sprint?

QUESTION – 13

Explain sprint size and scrum size?

- Sprint size

The sprint size refers to the duration of the sprint that is how long each iteration lasts

The duration of the sprint would be for

.1week, 2 weeks the most common, 3 week and maximum 4 weeks not more than that allowed in scrum

The duration of the sprint size is decided by Team maturity and experience, project complexity and risk and stake holders availability.

- Scrum size

The scrum size is refers to the size of the scrum team, project resources are grouped as the scrum teams. which is made up of:

. Product owner

. Scrum master

. Developers (development team)

Each team size will on average be 7-8 members . if team is larger than 10, scrum recommends splitting into multiple scrum teams each working on the same product but focus different areas.

The reason why the scrum team size been smaller is easy communication and  quicker decision.

QUESTION – 14

EXPLAIN DOR AND DOD?

In the scrum the DOR stand for Definition of Ready and DOD stands for Definition of Done are important agreements that ensure clarity and quality during the product development process.

- Definition of Ready

It is a check list or a set of criteria that a product backlog item like user story or tasks must meet before the development team can work on it , like is this work item is ready to be picked up in the sprint.

Example –

. The story is clearly defined and understood by the team

. It has acceptance criteria

. Dependencies are  identified and resolved

. No blockers

- Definition of done

It is a shared understanding of what it means for work to be complete like can we say this is 100 percent done and potentially shippable

Example –

. Documentation is completed

. Code is unit tested

. Bug free

. Feature is functionally tested

Question – 15

- Explain Prioritization techniques and MVP?

In the scrum the prioritization  techniques helps the product owner and it is used in business analysis and software development to reach a common understanding with the stake holders on the importance they place on the delivery of each requirement also known as MOSCOW prioritization or MOSCOW analysis

The Moscow stands for must, should, could and would

- Must have this requirement to meet the business needs.

- Should have this requirement if possible, but project success does not rely on it.

- Could have this requirement if it does not affect anything else in the project

- Would like to have this requirement later, but it wont be delivered this time.

MVP

The MVP stands for Minimum Viable Product  in the scrum it is s smallest possible version od a product that :

. Delivers enough value to early adopters

. Can be shipped at the end of one or few sprints

. Allows the team to validates assumptions with real feedback

The MVP will aligned with the product goal and it is delivered and reviewed through sprint reviews

QUESTION 16

Difference between product owner and business analyst ?

The difference between the product owner and business analyst

| PRODUCT OWNER | BUSINESS ANALYST |
| --- | --- |
| - Owns the product vision and the product backlog - Official role in scrum - He prioritize the backlog - He will accept or reject work - He is like driver of car | - Gathers, analyses and documents the business requirements - Not an official role but he can work within - He will gather the requirements - He will translate needs into user stories - He is like navigator |

Question – 17

Prepare a sample resume of 3years experience of product owner ?

RESUME

Name       : RALLABANDI PRADEEP CHARY

Phone       : 9963501487

Email       : rallabandipradeep004@gmail.com

Location: Hyderabad, India.

Professional summary

Results – driven owner with 3 years of experience driving product strategy and development in Agile environments, Skilled in defining product roadmaps, gathering the user requirements, prioritizing features and collaborating with cross functional teams to deliver high impact digital solutions. Proven success in launching scalable products that improve customer experience and meet business goals.

Core Competences

. Product  Road mapping & Strategy

. Agile & Scrum Methodology

. User Story Writing

. Stake holder Communication

. Sprint Planning & Review

. Data -Driven Decision Making.

Professional Experience

Associate Product owner

X4Z Technology Pvt. Ltd – Hyderabad, India

June 2022 – Present

Domain: E- commerce

. Assisted the senior PO in managing the backlog of a high-traffic e-commerce web application

. Coordinated with cross-functional teams to refine requirements and ensure timely feature delivery.

. Wrote detailed user stories and acceptance criteria , supporting multiple product releases.

. Supported UAT efforts and ensured alignment between development output and stakeholder expectations

Education

Bachelor of Commerce (B.Com)- computers

Osmania university Hyderabad.

Graduated – 2020

Certifications:

Certified Scrum Product Owner (CSPO)- Scrum Alliance .

Tools & Technologies

Microsoft excel, JIRA, Powe Bi, Tableau, SQL (basic).

Languages

English (Fluent)

Telugu (Native)

Hindi (Conversational)

Declaration

I here by declare that the information mentioned above is true to the best of my knowledge

Place: Hyderabad

Date:

(R. PRADEEP CHARY)