## Slide 1: NEXUS DRIVE IFTIKHAAR ALI S D
25-09-2025

## Slide 2: SITUATION
XYMA Analytics currently operates with departments using separate, specialized software for their core functions.
Key teams including HR, Finance, Electronics, µTMapS, PoRTS and Software are working in disconnected digital environments.
Communication and fulfillment of inter-departmental requirements rely on manual processes and multiple channels.
The organization lacks a unified platform, creating a complex and fragmented technological landscape.

## Slide 3: PROBLEM
The existing fragmented system creates significant operational inefficiencies and data redundancy across the company.
Information silos between departments lead to poor communication, collaboration breakdowns, and process delays.
Managing numerous software licenses and vendor dependencies results in increased operational costs and complexity.
There is a lack of real-time, centralized visibility into critical cross-departmental workflows like approvals and inventory.

## Slide 4: OPPORTUNITY
Develop a single, integrated platform to unify all core business functions and serve as a central communication bridge.
Streamline key business processes by automating tasks such as leave requests, payroll, reimbursements, and purchase orders.
Achieve significant long-term cost savings by consolidating software licenses and reducing IT maintenance overhead.
Establish a single source of truth for company-wide data, enabling improved visibility and more strategic decision-making.

## Slide 5: PURPOSE STATEMENT
To streamline business operations by consolidating disparate software systems into a single, unified platform.
To enhance inter-departmental communication and collaboration by creating a centralized hub for all workflows and requests.
To reduce operational costs associated with managing multiple software licenses and dependencies.
To improve data accuracy and accessibility by establishing a single source of truth for key business functions.
To increase operational efficiency by automating processes such as leave requests, reimbursements, and purchase orders.

## Slide 6: PROJECT OBJECTIVES
To design and deploy a single, integrated software platform that consolidates core functions from HR, Finance, and Technical departments.
To integrate specific modules for attendance, payroll, leave requests, reimbursements, purchase orders, and inventory tracking.
To automate and streamline key cross-departmental workflows, including all approval processes for requests and expenses.
To establish a centralized database that provides a single source of truth for all operational data, enabling real-time reporting and enhanced decision-making.

## Slide 7: SUCCESS CRITERIA
Unified Platform Adoption – At least 95% of departments actively using the new platform within 3 months of go-live.
Process Automation – 90% of leave, payroll, reimbursements, and purchase requests processed automatically with minimal manual effort.
Cost Savings – Achieve at least 20–25% reduction in IT/software license and maintenance costs within the first year.
Data Accuracy & Visibility – Ensure 98% accuracy of centralized data with real-time reporting available to all stakeholders.
Faster Approvals & Collaboration – Reduce approval cycle times by 40–50% compared to current manual processes.
System Uptime & Reliability – Maintain 99.5% uptime for the platform to ensure smooth daily operations.

## Slide 8: METHODS AND APPROACHES
1. Requirements Gathering (1 Month)
Stakeholder analysis is based on RASCI Matrix
Conducting workshops, interviews, and meetings with departmental heads from HR, Finance, and technical teams
Wireframe was made to get more specific requirement
Prioritize requirement – Moscow
Estimated Cost: ₹5,00,000
Key Documents: Business Requirement Document (BRD).
2. Requirements Analysis (1 Month)
Visually mapped all departmental processes using UML diagrams.
Detailed functional needs and set technical specifications with architects.
Requirements were compiled into a single SRS document as the official guide.
A Requirement Traceability Matrix (RTM) was created to track every requirement from start to finish.
Estimated Cost: ₹5,00,000
Key Documents: Functional Requirements Specification (FRS), Supplementary Support Document (SSD), Software Requirements Specification (SRS), Requirement Traceability Matrix (RTM)

## Slide 9: METHODS AND APPROACHES
3. Design (2.5 Month).
Create detailed UI/UX wireframes with all features.
Define the integration strategy for connecting the various modules (HR, Finance, etc.).
Estimated Cost: ₹15,00,000
Key Documents: High-Level Design Document (HDD), Application Design Document (ADD).
4. Development (3.5 Months)
Frontend: Develop the user-facing dashboards and forms.
Backend: Build the core logic for all business processes.
Integration: Connect the different modules to ensure seamless data flow.
Estimated Cost: ₹40,00,000
Key Documents: Functional and Non-functional Requirement Document
5. Testing (2 Months)
Perform comprehensive system and integration testing to ensure the platform is stable and works as intended.
Identify, document, and track software defects and bugs for resolution.
Conduct regression testing to ensure that new code has not negatively impacted existing features.
Estimated Cost: ₹15,00,000
Key Documents: Test Cases Document

## Slide 10: METHODS AND APPROACHES
6. User Acceptance Testing (UAT) (1 Month)
Selected group of end-users were allowed to test the software in a "real-world" environment to validate that it meets their business needs.
Gathered feedback on usability, functionality, and overall user experience.
Obtained formal sign-off from stakeholders, giving final approval for deployment.
Estimated Cost: ₹10,00,000
Key Documents: Sign-off Document.
7. Deployment & Training (1 Months)
Deploy the application to the live server.
Conduct training sessions for all employees and provide initial post-launch support.
Estimated Cost: ₹10,00,000
Key Documents: Deployment Plan, User Guides.
Total Estimated Budget: ₹1,00,00,000

## Slide 11: RESOURCES
Total Duration: 1 Year
Total Budget: ₹1,00,00,000
PHASE | DURATION | KEY ACTIVITIES | ESTIMATION COST
Requirements Gathering | 1 Month | Workshops with XYMA teams to define needs. | ₹5,00,000
Requirements Analysis | 1 Month | Analyze data and create workflow diagrams & SRS. | ₹5,00,000
Design | 2.5 Months | Architect platform, design database & UI/UX. | ₹15,00,000
Development | 3.5 Months | Build modules, APIs, and database. | ₹40,00,000
Testing | 2 Months | System QA, integration & regression testing. | ₹15,00,000
User Acceptance Testing | 1 Months | Departmental validation, feedback & approval. | ₹10,00,000
Deployment & Training | 1 Months | Go-live, data migration, and user training. | ₹10,00,000

## Slide 12: RISK AND DEPENDENCIES
Requirement Changes: Any changes in requirements during later phases can cause rework, delays, and increased costs due to the sequential nature of the Waterfall model.
Inter-departmental Coordination: Timely availability of inputs and approvals from all departments is critical; delays may impact project progress and phase transitions.
Technology & Integration Risks: Integration with existing or third-party systems may encounter unforeseen technical challenges or compatibility issues.
Resource Availability: Project milestones depend on the consistent availability of key personnel (development, testing, client reviewers); unexpected resource constraints can affect timelines.

## Slide 13: TECHNOLOGIES
Modern object-oriented programming languages for backend logic (example: Java, Python).
Web frameworks to streamline API development and server-side processing (example: Django, Spring Boot).
Contemporary JavaScript frameworks for building interactive front-end user interfaces (example: React.js, Angular).
Combination of relational and NoSQL databases for flexible and scalable data management (example: MySQL, Cassandra).
Messaging and streaming platforms to enable efficient data integration across modules (example: Apache Kafka).
Secure authentication mechanisms such as token-based or OAuth systems.
Leading cloud service providers for hosting and scalability (example: AWS, Azure, Google Cloud).
API-based integration with third-party and internal applications as needed.

## Slide 14: THANK YOU