Question 1 – write Agile Manifesto

Answer:

The Agile Manifesto was created in 2001 by a group of software practitioners to improve software development practices. It is based on four core values and twelve guiding principles.

#### Four Core Values of Agile

- Individuals and interactions over processes and tools

- Working software over comprehensive documentation

- Customer collaboration over contract negotiation

- Responding to change over following a plan

#### Twelve Principles of Agile

- Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference for the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.

- The most efficient and effective method of conveying information is face-to-face conversation.

- Working software is the primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

- Simplicity—the art of maximizing the amount of work not done—is essential.

- The best architectures, requirements, and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

Question 2 – User Stories- Acceptance Criteria-BV-CP –

| User Story No. 1 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REGISTER IN SCRUM FOODS SO THAT I CAN DELIVER FOODS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Registration Screen Textboxes for User name, Password, Location, Mobile number, Captcha. Click on Registration Button Send Successful Registration notification |  |  |  |

| User Story No. 2 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN IN SCRUM FOODS SO THAT I CAN DELIVER FOODS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Login Screen Textboxes for Username & Password entry, Forgot password option. Click on Login Button Send Successful Login notification |  |  |  |

| User Story No. 3 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO BROWSE ACTIVE ORDERS IN SCRUM FOODS SO THAT I CAN SELECT FOOD ORDERS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Display active order request Textboxes to Browse for available orders. Click to view order status. |  |  |  |

| User Story No. 4 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW ACTIVE ORDER DETAILS IN SCRUM FOODS SO THAT I CAN ACCEPT ORDERS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Display active order details Textboxes to View details option for delivery location, Display for checking delivery fees with the order. Click on View Order Location and Price Button Display all order details |  |  |  |

| User Story No. 5 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO CLAIM ORDERS IN SCRUM FOODS SO THAT I CAN DELIVER FOODS |  |  |  |
| BV : 50 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Claim your desired order delivery Textboxes or button to claim the order Click on Claim Button Send Successful Accepted notification |  |  |  |

| User Story No. 6 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO CHECK ORDER PAYMENT STATUS IN SCRUM FOODS SO THAT I CAN CHECK PAYMENT FOR FOODS IS COMPLETED |  |  |  |
| BV : 20 |  | CP : 04 |  |
| ACCEPTANCE CRITERIA Order Payment status check Textboxes to display payment status paid or unpaid, For unpaid Accept Cash or UPI option. Click on Mark Payment Button Send Successfully Delivered notification |  |  |  |

| User Story No. 7 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW DELIVERIES REPORT AND REVENUE GENERATED IN SCRUM FOODS SO THAT I CAN CHECK FOODS DELIVERY REVENUE |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Deliveries report and revenue generated Button to generate report and view report. Click to download receipt Send list of orders and fees generated |  |  |  |

| User Story No. 8 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGOUT IN SCRUM FOODS SO THAT I CAN LOGOUTAFTER DELIVERING FOODS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Logout Screen Textboxes to Logout from application. Click on Logout Button Send Successful logout notification |  |  |  |

| User Story No. 9 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A RESTURANT I WANT TO REGISTER IN SCRUM FOODS SO THAT I CAN PREPARE AND DELIVER FOODS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Registration Screen Textboxes for User name, Password, Location, Mobile number, Captcha. Click on Registration Button Send Successful Registration notification |  |  |  |

| User Story No. 10 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A RESTURANT I WANT TO LOGIN IN SCRUM FOODS SO THAT I CAN PREPARE AND DELIVER FOODS |  |  |  |
| BV : 500 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Login Screen Textboxes for Username & Password entry, Forgot password option. Click on Login Button Send Successful Login notification |  |  |  |

| User Story No. 11 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A RESTURANT I WANT TO VIEW ORDERS IN SCRUM FOODS SO THAT I CAN PREPARE AND DELIVER FOODS |  |  |  |
| BV : 100 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA View Order screen Textboxes to view order and accept order Click on View order Button Send list of order notification |  |  |  |

| User Story No. 12 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A RESTURANT I WANT TO DELIVERY BOY VERIFICATION IN SCRUM FOODS SO THAT I CAN VERIFY FOOD DELIVERY BOYS |  |  |  |
| BV : 100 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Delivery boy verification screen Textboxes to Check delivery boy is verified or not, Button to view details, Button to view rating and Unique ID. Click on Verify Button Send the verified as delivery partner notification |  |  |  |

| User Story No. 13 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A RESTURANT I WANT TO DELIVERY BOY VERIFICATION IN SCRUM FOODS SO THAT I CAN VERIFY FOOD DELIVERY BOYS |  |  |  |
| BV : 100 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Delivery boy verification screen Textboxes to Check delivery boy is verified or not, Button to view details, Button to view rating and Unique ID. Click on Verify Button Send the verified as delivery partner notification |  |  |  |

| User Story No. 14 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO REGISTER ON THE SCRUM FOODS APP SO THAT I CAN PLACE FOOD ORDERS |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Registration form must validate name, email, phone number, and password. User receives confirmation upon successful registration. |  |  |  |

| User Story No. 15 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO LOG IN TO MY ACCOUNT SO I CAN ACCESS MY PROFILE AND ORDER FOOD |  |  |  |
| BV : 100 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Login screen accepts email and password, verifies credentials, and redirects to dashboard. Invalid inputs must return error messages. |  |  |  |

| User Story No. 16 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SEARCH RESTAURANTS SO I CAN CHOOSE FROM VARIOUS FOOD OPTIONS. |  |  |  |
| BV : 90 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA A functional search bar allows searching by name, location, or cuisine. Results display relevant restaurants with thumbnails. |  |  |  |

| User Story No. 17 | Tasks : 2 |  | Priority : Low |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW A RESTAURANT'S MENU SO THAT I CAN DECIDE WHAT TO ORDER |  |  |  |
| BV : 90 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Menu displays all food items with names, prices, images, and descriptions. Each item should be selectable for the cart. |  |  |  |

| User Story No. 18 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO TRACK MY ORDER SO THAT I CAN KNOW ITS CURRENT STATUS. |  |  |  |
| BV : 100 |  | CP : 03 |  |
| ACCEPTANCE CRITERIA Real-time tracking shows order status (Placed, Accepted, Out for delivery, Delivered). Updates automatically based on delivery boy actions. |  |  |  |

| User Story No. 19 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO PROVIDE FEEDBACK AND RATING AFTER DELIVERY. |  |  |  |
| BV : 80 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Feedback screen appears after order is marked as delivered. Allows star rating and optional comment. |  |  |  |

| User Story No. 20 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT I WANT TO VIEW INCOMING ORDERS SO I CAN PREPARE AND DISPATCH THEM. |  |  |  |
| BV : 100 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Order list displays items, quantity, customer name, and status. Option to mark as “Accepted” or “Ready for pickup”. |  |  |  |

| User Story No. 21 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A RESTAURANT I WANT TO SEE CUSTOMER FEEDBACK ON MY FOOD |  |  |  |
| BV : 80 |  | CP : 01 |  |
| ACCEPTANCE CRITERIA Feedback tab lists reviews with ratings and comments. Sort or filter by rating or date. |  |  |  |

| User Story No. 22 | Tasks : 2 |  | Priority : Low |
| --- | --- | --- | --- |
| AS A RESTAURANT I WANT TO VIEW MY REVENUE SO THAT I CAN TRACK SALES FROM THE PLATFORM |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Summary page shows total earnings, commission, and number of orders. Supports daily, weekly, and monthly filters |  |  |  |

| User Story No. 23 | Tasks : 2 |  | Priority : Low |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO APPROVE OR REJECT DELIVERY BOY REGISTRATIONS IN MY REGION. |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Show pending applications with all documents. Admin can approve/reject with comments. System sends notification to applicant. |  |  |  |

| User Story No. 24 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO SUSPEND DELIVERY BOYS WHO VIOLATE POLICIES |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Button to suspend/unblock delivery boys with reason logging. Status updates reflect instantly. |  |  |  |

| User Story No. 25 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO VIEW COMPLAINTS FROM USERS IN MY REGION |  |  |  |
| BV : 80 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Display list of issues submitted by customers, delivery boys, and restaurants. Filter by type and date |  |  |  |

| User Story No. 26 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO ASSIGN UNRESOLVED ISSUES TO APPROPRIATE TEAMS |  |  |  |
| BV : 85 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Assign button with dropdown to route issue to support, tech, or escalation teams. Issue status changes to "Assigned". |  |  |  |

| User Story No. 27 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO HANDLE ISSUES RAISED BY CUSTOMERS AND DELIVERY BOYS IN MY REGION SO THAT I CAN ENSURE SATISFACTION. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA View all open/closed issues Assign issue to responsible team Change status to “In Progress” or “Resolved” |  |  |  |

| User Story No. 28 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO LOG IN TO THE ADMIN PANEL SO THAT I CAN MANAGE THE SYSTEM. |  |  |  |
| BV : 300 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Login screen with secure authentication Redirect to admin dashboard Forgot Password option |  |  |  |

| User Story No. 29 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO MANAGE REGIONAL ADMINS SO THAT I CAN CONTROL ACCESS. |  |  |  |
| BV : 350 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA View list of Regional Admins Add/Edit/Delete admins Activate/Deactivate accounts |  |  |  |

| User Story No. 30 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO TRACK OVERALL REVENUE AND SYSTEM USAGE METRICS SO THAT I CAN REPORT TO STAKEHOLDERS. |  |  |  |
| BV : 350 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Dashboard with KPIs: Revenue, Active Users, Orders Filter by region or time Exportable reports |  |  |  |
| User Story No. 31 | Tasks : 2 |  | Priority : Highest |
| AS A BUSINESS OWNER I WANT TO LOG IN SECURELY TO MANAGE BUSINESS FINANCES |  |  |  |
| BV : 350 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Secure login ensures data protection for sensitive financial data. Email/password login 2FA (optional) Dashboard access |  |  |  |

| User Story No. 32 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW TOTAL REVENUE GENERATED PER REGION |  |  |  |
| BV : 150 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Revenue breakdown by region Filter by date Export to PDF/Excel |  |  |  |

| User Story No. 33 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO UPDATE OR PROCESS PAYMENTS TO RESTAURANTS AND DELIVERY BOYS |  |  |  |
| BV : 350 |  | CP : 03 |  |
| ACCEPTANCE CRITERIA Revenue breakdown by region Filter by date Export to PDF/Excel |  |  |  |

| User Story No. 34 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW PLATFORM-WIDE ISSUE TRENDS OVER TIME. |  |  |  |
| BV : 100 |  | CP : 03 |  |
| ACCEPTANCE CRITERIA Line chart or table of issues over time Filter by region/type View average resolution time |  |  |  |

| User Story No. 35 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO LOG OUT SECURELY FROM THE PORTAL. |  |  |  |
| BV : 200 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Logout button Clear session Redirect to login |  |  |  |

| User Story No. 36 | Tasks : 2 |  | Priority : Medium |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO RECEIVE MONTHLY PERFORMANCE SUMMARIES VIA EMAIL. |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Enable email summary setting Choose preferred day of month Auto-send reports |  |  |  |

| User Story No. 37 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO ADD INTERNAL NOTES TO DELIVERY BOY PROFILES SO I CAN TRACK PERFORMANCE HISTORY. |  |  |  |
| BV : 100 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA “Add Note” button on delivery boy profile Save timestamped notes Editable by Regional Admin only |  |  |  |

| User Story No. 38 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO DEFINE ISSUE RESOLUTION SLAS FOR DIFFERENT ROLES. |  |  |  |
| BV : 150 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Define SLAs (e.g., 24h for support) Assign SLA by issue type Highlight overdue issues |  |  |  |

| User Story No. 39 | Tasks : 2 |  | Priority : Highest |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN, I WANT TO DEACTIVATE USER ACCOUNTS THAT VIOLATE PLATFORM POLICIES. |  |  |  |
| BV : 150 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA “Deactivate” option for user accounts Log reason for deactivation Notify affected user via email |  |  |  |

| User Story No. 40 | Tasks : 2 |  | Priority : Low |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO ASSIGN SPECIAL BONUSES TO TOP-PERFORMING REGIONS. |  |  |  |
| BV : 150 |  | CP : 02 |  |
| ACCEPTANCE CRITERIA Identify top regions by revenue/ratings Input bonus amount and confirm Track bonus history per region |  |  |  |

Question 3– What is epic? Write 2 epics

Answers:

An Epic in Agile and Scrum is a large body of work that can be broken down into smaller, manageable user stories. It represents a significant feature or requirement that cannot be completed in a single sprint due to its size and complexity. Epics often span multiple sprints and help in organizing and prioritizing the product backlog at a high level.

Epics are useful for tracking progress on broader goals and ensure alignment with the product vision.

Epic 1: Customer Ordering Process

This epic includes all the functionalities related to how a customer places an order on the Scrum Foods app.

Related User Stories:

As a customer, I want to register so that I can use the app.

As a customer, I want to add my address so that my food can be delivered.

As a customer, I want to search and view restaurants and their menu.

As a customer, I want to make payment through different payment modes.

As a customer, I want to track my order in real-time.

Epic 2: Delivery Management System

This epic includes all functionalities that enable delivery boys to manage and fulfill orders effectively.

Related User Stories:

As a delivery boy, I want to register so that I can start delivering.

As a delivery boy, I want to view and accept orders.

As a delivery boy, I want to update delivery status.

As a customer, I want to view the contact number of the delivery boy.

As a delivery boy, I want to view my earnings and delivery report.

Question 4 –What is the difference between BV and CP ?

Answer :

| Sr.No | Business Value (BV) | Complexity Points (CP) |
| --- | --- | --- |
| 1 | Indicates the importance of a feature to business | Indicates the effort/complexity to develop a feature |
| 2 | Estimated by Stakeholders / Product Owner | Estimated by Scrum Developers |
| 3 | Measured using Scrum currency notes (₹1000, ₹500, ₹100, etc.) | Measured using Poker Cards (1, 2, 3, 5, 8, etc.) |
| 4 | Helps in prioritizing features based on value | Helps in planning the sprint workload |
| 5 | Represents the business impact | Represents the technical effort required |

Question 5 – Explain about Sprint?

Answer:

A Sprint is a fixed time-boxed period in Agile Scrum during which the Scrum Team works to complete a set of Product Backlog Items (PBIs). It is the core unit of development in Scrum where planning, execution, review, and reflection happen. Sprint is subset of product backlog on user stories.

There are 4 types of Sprint meetings that are carried out :

1) Sprint Planning meeting:

Purpose: To plan what work will be done during the upcoming sprint.

Participants: Product Owner, Scrum Master, Scrum Developers.

The Product Owner presents prioritized Product Backlog Items (PBIs).

The Scrum Team selects the items they can complete based on their capacity and velocity.

Tasks are broken down, and the Sprint Goal is defined.

Output:

A clear Sprint Backlog with selected User Stories and assigned tasks.

2. Daily Scrum (Daily Stand-Up) :

Purpose:

To synchronize the team and ensure progress is on track.

Duration:

15 minutes (max).

Participants:

Scrum Developers (Product Owner and Scrum Master may attend but don’t participate unless they are also developers).

Output:
Daily visibility into the team’s progress and any potential risks.

3. Sprint Review Meeting:

Purpose: To demonstrate the work completed during the sprint and gather feedback.

Participants:

Scrum Developers, Product Owner, Scrum Master, Stakeholders, Clients, 3rd Party Reviewers.

What happens:

Completed User Stories are demonstrated.

Stakeholders provide feedback.

Team discusses what is done and not done.

Discusses the velocity and burn-down charts.

Output:

Approval or suggestions for improvement, and clarity on what will go into future sprints.

4. Sprint Retrospective Meeting

Answer:

Purpose:To reflect on the sprint process and identify improvements.

Participants:

Only Scrum Developers (Scrum Master facilitates).

What happens:

Discuss what went well, what didn’t, and what can be improved.

Actionable items are listed to implement in the next sprint.

Output:

Continuous improvement of team performance and sprint process.

Question 6 – Explain Product backlog and sprint back log

Answer:

Product Backlog:

The Product Backlog is a comprehensive, prioritized list of all the features, enhancements, bug fixes, technical work and knowledge acquisition required in the product. It is owned and managed by the Product Owner. Items in the backlog are referred to as Product Backlog Items (PBIs). These include user stories, epics, and tasks. PBIs are prioritized based on business value (BV), customer needs, and urgency.

The Product Backlog acts as the single source of requirements for any changes to be made to the product.

Example from Scrum Foods Project:

User stories like:

"As a customer, I want to add my address..."

"As a restaurant owner, I want to view orders..."

These would be added to the Product Backlog and prioritized by business value.

Sprint Backlog:

The Sprint Backlog is a subset of the Product Backlog, containing only the user stories that the team commits to deliver in a specific Sprint (typically 2 weeks). It is created during the Sprint Planning Meeting by the Scrum Team. Each item in the Sprint Backlog is broken down into tasks which can be completed by developers in a single day (Scrum).

It also includes any technical work or improvements the team needs to make during the sprint.

Question 7 – What is impediments log? Write 2 impediments

Answer:

An Impediments Log is a documented list of all the challenges, blockers, or issues faced by the Scrum Team during a Sprint. These impediments prevent the team from making progress on their tasks effectively and need to be tracked and resolved to maintain productivity and Sprint goals.

It is generally maintained by the Scrum Master. It helps identify recurring issues, aids in retrospective discussions, and ensures that no blocker goes unnoticed.

Purpose of Impediments Log:

Ensures transparency of challenges.

Helps prioritize and resolve blockers quickly.

Improves team performance and sprint predictability.

Encourages a culture of continuous improvement.

Two Sample Impediments:

Impediment 1 – Technical Issue:

Description: Developer is unable to integrate payment gateway due to lack of documentation.

Impact: Delay in implementing "Select Payment Mode" user story.

Resolution: Product Owner coordinated with vendor to get documentation and support.

Impediment 2 – Resource Unavailability:

Description: One developer is on unexpected leave, affecting the completion of two tasks.

Impact: Risk of missing Sprint goal.

Resolution: Scrum Master reallocated tasks among available team members.

Question 8 – Explain Velocity of the Team

Answer:

Velocity is the measure of the amount of work a Scrum Team can complete during a single Sprint. It is usually calculated by summing up the total number of Complexity Points (CP) (also known as Story Points) for all the completed user stories in that Sprint.

Importance of Velocity :

Helps in predicting future sprint capacity.

Assists Product Owners in release planning.

Tracks the progress and performance of the team over time.

Enables realistic Sprint planning.

Example from Scrum Foods Project:

In Sprint 1, the team completed 10 user stories.

The total CP (Complexity Points) delivered = 20.

So, the Team Velocity = 20 CP per Sprint.

Question 9 – Draw Sprint Burn Charts n Product Burn Down Charts

Answer:

Sprint Burn Charts - A Sprint Burn Chart is a visual tool used in Agile project management to track progress within a sprint. It helps teams understand how much work remains and whether they are on track to meet their sprint goals.

Types of Sprint Burn Charts –

1. Sprint Burn Down Chart - Tracks the remaining work overtime during a sprint. Shows a downward slope as tasks are completed. Key goal is to ensure the team is completing tasks at a pace to finish the sprint on time.

2. Sprint Burn Up Chart - Tracks the completed work overtime during a sprint. Shows an upward slope as more tasks are completed. Key goal is to monitor progress toward the sprint's total scope.

Product Burn Down Chart - A Product Burn Down Chart is a visual tool used in Agile project management to track the progress of a project toward completing all the work (usually in the form of user stories or tasks) in the product backlog. It helps teams and stakeholders monitor the remaining work overtime, providing a clear picture of whether the project is on track to meet its deadlines and goals.

Question 10 – Explain about Product Grooming

Answer:

Product Grooming is a collaborative activity where the Product Owner and Scrum Team review, refine and prioritize items in the Product Backlog to ensure they are ready for upcoming Sprints.

Purpose of Product Grooming:

- To break down large epics into smaller, actionable user stories.

- To clarify requirements, acceptance criteria, and business rules.

- To estimate complexity points (CP) and assign business value (BV).

- To ensure that the top-priority user stories are clear, concise, and ready to be picked for the next Sprint.

- To prioritize backlog items based on urgency and customer value.

Question 11 – Explain the roles of Scrum Master and Product Owner

Answer:

Scrum Master:

The Scrum Master is a servant leader and facilitator for the Scrum Team. They ensure that the Scrum framework is properly followed and help remove obstacles that may hinder the team’s progress.

Key Responsibilities:

Facilitates Scrum events – Daily Stand-ups, Sprint Planning, Review, and Retrospective.

Removes impediments – Helps resolve blockers that prevent the team from progressing.

Coaches the team – Guides the team on Agile and Scrum principles.

Protects the team – Shields the team from external interruptions.

Tracks progress – Uses burn down charts, velocity reports, and WIP boards.

Product Owner :

The Product Owner (PO) is responsible for maximizing the value of the product resulting from the work of the Scrum Team. They manage the Product Backlog and are the voice of the customer.

Key Responsibilities:

Defines and prioritizes the Product Backlog – Based on business value.

Writes clear user stories – With proper acceptance criteria, BV, and CP.

Engages stakeholders – Gathers feedback and aligns team goals with business needs.

Accepts/rejects work – Evaluates if the work meets the Definition of Done.

Makes fast decisions – Ensures the team is not blocked by unclear requirements.

Question 12 – Explain all Meetings Conducted in Scrum Project

Answer:

1. Sprint Planning Meeting

Purpose: To plan the work to be done in the upcoming Sprint.

Participants:

Product Owner

Scrum Master

Scrum Developers

Activities:

Product Owner presents prioritized Product Backlog Items (PBIs).

Developers discuss feasibility and capacity.

Team selects which user stories to commit to in the Sprint.

Stories are moved to the Sprint Backlog, and tasks are created.

2. Daily Scrum (Daily Stand-Up Meeting)

Purpose: To inspect progress and plan for the next 24 hours.

Duration:

15 minutes (usually)

Participants:

Scrum Developers (Mandatory)

Scrum Master (Optional/Facilitator)

Product Owner (Optional Listener)

Each Developer answers 3 questions:

What did I do yesterday?

What will I do today?

Any blockers (impediments)?

3. Sprint Review Meeting

Purpose: To inspect the product increment and get stakeholder feedback.

Participants:

Scrum Team (PO, SM, Developers)

Stakeholders (Client, Business Owner, 3rd Party Reviewers)

Activities:

Demonstration of completed user stories.

Feedback and suggestions are gathered.

Discussion of what was done vs. what was planned.

4. Sprint Retrospective Meeting

Purpose: To reflect on the Sprint and improve processes for the next one.

Participants:

Scrum Developers

Scrum Master

Activities:

What went well?

What didn’t go well?

What can be improved?

5. Product Backlog Grooming (Refinement) Meeting

Purpose: To keep the Product Backlog clean, prioritized, and development-ready.

Participants:

Product Owner (Leads the meeting)

Scrum Developers

Scrum Master (Facilitator)

Activities:

Clarifying user stories

Adding acceptance criteria

Estimating CP and assigning BV

Re-prioritizing stories based on value or urgency

Question 13 – Explain Sprint Size and Scrum Size

Answer:

Sprint Size:

A Sprint is a time-boxed iteration in Scrum where a usable, potentially shippable product increment is developed.

Standard Duration:

In the Scrum Foods project, the Sprint Size is 2 weeks (10 working days).

Purpose:

To give the team enough time to plan, build, test, and deliver a set of user stories.

Scrum Size:

A Scrum refers to a single day of work within a Sprint. It represents the smallest time-boxed planning unit in Scrum.

Standard Duration:

In this project, Scrum Size is 1 day.

Purpose:

Allows the team to focus on short-term goals and track daily progress. Each Scrum ends with a Daily Stand-up Meeting.

Question 14 – Explain DOR and DOD

Answer:

DOR (Definition of Ready): DOR means that a User Story is fully prepared and ready to be picked up by the development team in a Sprint.

Why it is created: To avoid confusion, delays, or missing information during development.

Criteria for DOR:

User Story is clearly written and understood.

Acceptance Criteria is defined.

Business Value (BV) and Complexity Points (CP) are estimated.

Dependencies are identified and resolved.

Approved by the Product Owner.

DOD (Definition of Done) : DOD means that the User Story is fully developed, tested, reviewed, and accepted — and can be considered “done”.

Purpose: To maintain quality and ensure consistency across all work.

Criteria for DOD:

Code is complete and reviewed.

Unit & integration tests are passed.

Feature is deployed in test/staging environment.

Product Owner has reviewed and accepted the story.

Documentation is updated (if required).

Question 15 – Explain Prioritization Techniques and MVP

Answer:

Prioritization is the process of deciding which features or user stories to implement first, based on business goals, value, risk, and customer needs. It helps the Product Owner and team focus on delivering the most valuable work first.

Common Prioritization Techniques:

- MoSCoW Method

M – Must Have

S – Should Have

C – Could Have

W – Won’t Have (this time)

- Business Value and Complexity Points (BV/CP)

Choose stories with high BV and low CP for higher ROI.

Scrum Foods used this model during grooming to prioritize 10 MVP stories.

MVP – Minimum Viable Product

MVP is the smallest version of a product that delivers enough value to customers and allows early   feedback.

Purpose:

Test assumptions quickly.

Reduce time to market.

Gather user feedback for improvement.

Avoid over-engineering.

Question 16 – Difference between Business Analyst n Product Owner

Answer:

| Aspect | Business Analyst (BA) | Product Owner (PO) |
| --- | --- | --- |
| Primary Role | Acts as a bridge between business stakeholders and the technical team. | Owns the product backlog and ensures the team builds the right product. |
| Responsibilities | - Gathers and analyzes business requirements- Prepares BRDs, FRDs, Use Cases- Facilitates communication among stakeholders | - Prioritizes backlog items- Writes user stories- Accepts or rejects completed work |
| Decision-Making Authority | Limited decision-making; provides inputs and insights to support decisions. | Has the final say on product features and backlog priorities. |
| Customer Interaction | Works closely with customers to understand their needs and document them. | Constantly communicates with customers to shape the product vision. |
| Position in Agile Team | May or may not be part of the Scrum team (depends on organization). | Core member of the Scrum team; a key stakeholder in agile projects. |
| Ownership | Owns documentation and requirement clarity. | Owns the product vision and backlog. |
| Focus | Focuses on requirements and analysis. | Focuses on product value and delivery. |

Question 17 – Prepare a sample Resume of 3yrs exp Product Owner

Answer:

PROFESSIONAL SUMMARY

Certified and experienced Product Owner with 3+ years of experience in Agile-Scrum environments, managing product backlogs, prioritizing user stories, and delivering high-value increments. Adept at stakeholder communication, requirement gathering, sprint planning, and maximizing business value through data-driven decision-making. Domain expertise in food delivery platforms and e-commerce.

KEY SKILLS

- Agile & Scrum Frameworks

- Product Backlog Management

- Sprint Planning & Review

- User Stories & Acceptance Criteria

- Stakeholder Management

- Jira, Trello, Confluence

- MVP & Prioritization Techniques (MoSCoW, Kano, etc.)

- Business Value (BV) & Complexity Points (CP) Estimation

- Product Roadmaps & Vision

- Excellent Communication & Documentation

CERTIFICATIONS

Certified Scrum Product Owner (CSPO) – Scrum Alliance

Agile Business Analyst – COEPD

PROFESSIONAL EXPERIENCE

Product Owner

COEPD IT Solutions, Hyderabad

Aug 2022 – Present

Project: Scrum Foods – Online Food Delivery App

- Acted as the Product Owner for “Scrum Foods” agile team of 8 developers.

- Created and prioritized product backlog with over 40 user stories aligned to business goals.

- Defined acceptance criteria, Business Value (BV), and Complexity Points (CP) for each story.

- Led sprint planning, sprint reviews, and product grooming sessions.

- Interacted with stakeholders including business owners, restaurant partners, delivery personnel, and customers to refine features.

- Coordinated with Scrum Master and Developers to remove impediments and ensure product delivery.

- Ensured product increments were delivered every sprint with validated business value.

- Participated in product strategy meetings and contributed to long-term vision planning.

EDUCATION

Bachelor of Technology in Computer Science

Osmania University, Hyderabad

Graduated: 2021

PROJECT HIGHLIGHTS

- Scrum Foods App: Implemented features like real-time delivery tracking, restaurant registration, payment gateways, and chat support.

- Prioritized MVP features for initial release based on customer feedback and business needs.

- Achieved 90% stakeholder satisfaction during UAT cycles.