# AGILE – DELIVERABLES

Document 1: Definition of Done

As per Agile Extension to the BABOK Guide v2, the Definition of Done (DoD) is shared agreement within the Scrum Team about the list of criteria must be completed before a backlog item such as user stories, sprint or release is considered as “done”.

This ensures transparency, alignment and consistent quality across all deliverables of the e-Treasury Bill Automation project.

Checklist for DoD

- User Story Level

- Acceptance criteria of the user stories are fully met.

- Business rules (e.g., approval hierarchy, fund availability validation) implemented and verified.

- Code is written, reviewed and integrated without errors.

- Unit tests are created with minimum coverage agreed say about 80%

- QA has tested the feature and all critical defects are resolved.

- Feature works across required browsers/devices (portal access for DDOs, Treasury Officers)

- Feature reviewed and accepted by the Product Owner.

- Relevant configuration details and database changes documented.

- Sprint Level

- All committed user stories in the sprint backlog meet the Definition of Done.

- End-to-end functionality demonstrated successfully in the Sprint Review (e.g., bill submission to approval flow).

- Regression Testing performed to ensure existing features are not broken.

- Updated sprint documentation using JIRA.

- Code deployed to a test environment identical to production to test the functionalities.

- Release Level

- All prioritization features for the release are completed and meet quality standards.

- System integration with banks and external services tested and verified.]

- Security compliance checks (SSL certificates, access control, audit trail) completed.

- Performance testing is passed (e.g., bill processing time within acceptable limits)

- Training materials and user documentation prepared for Drawing and Disbursing Officers (DDOs), Treasury Officers (TOs), and Vendors.

- Release signed off by Product Owner and key stakeholders (Finance Department).

Document 2: Product Vision

The product vision for the e-Treasury Bill Automation System is to digitize the entire treasury bill lifecycle covering submission, verification, approval and disbursement into a seamless, transparent and efficient process. It aims to reduce delays, minimize manual errors and provide real-time tracking for all stakeholders. By integrating with banks and enabling digital records, the system strengthens financial governance, ensures timely payments and improves service delivery for government departments and vendors.

| Scrum Project Name: | e-Treasury Bill Automation System |
| --- | --- |
| Venue: | Finance Department – Treasury Office, Kolkata |
| Date: | 01-09-2025 |
| Start Time: | 10:00AM |
| End Time: | 12:00 PM |
| Duration: | 2 Hours |
| Client: | West Bengal Finance Department |
| Stakeholder List: | - Treasury Officers (TOs) - Drawing & Disbursing Officers (DDOs) - Finance Department Officials - Vendors/Suppliers - Banks - Audit & Compliance Department |
|  | Scrum Team |
| Scrum Master: | Ms Saakshi Dugar |
| Product Owner: | Ms Sunita Acharya |
| Scrum Developer 1: | Mr Rahul Bose |
| Scrum Developer 2: | Mr Yug Mishra |
| Scrum Developer 3: | Mr Mayukh Bose |
| Scrum Developer 4: | Ms Sameera Reddy |
| Scrum Developer 5: | Mr Karthik |

| Vision: To digitize and streamline the treasury bill submission and validation process, ensuring faster approvals, improved transparency and reduced manual effort for stakeholders. |  |  |  |
| --- | --- | --- | --- |
| Target Group | Needs | Product | Value |
| Market segment: Government finance departments, treasury offices and public sector organisations. Target users and customers: - Treasury Officers - Drawing & Disbursing Officers (DDOs) - Finance Department Officials - Vendors/Suppliers - Banks - Audit & Compliance Department | Problem solved: Manual bill submission is time consuming, error-prone and lacks transparency. Benefit Provided: - It speeds up bill submission & validation. - Reduces errors with automated checks. - Provides tracking, transparency and audit trails. | What is it: A digital treasury bill submission & validation system accessible via web. Desirable and Special: - Real time bill validation. - Secure document upload. - Transparency on rejection/resubmission workflow - Easy tracking of status by users Feasibility: Yes, can be developed using Agile approach with manageable sprints and modular features. | Company Benefit: - Reduces operational costs & paperwork. - Enhances efficiency of financial operation. - Improves service delivery to departments. Business Goals: - Faster treasury operations. - 100% transparency and accountability. - Adoption of digital processes in governance. Business model: Internal implementation for government use, with potential extension as a scalable product for other finance departments. |

Document 3: User Stories

| User Story No: US1 | Tasks: Submit a treasury bill online |  | Priority: Highest |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to submit bills digitally So that I can avoid manual paperwork and speed up processing. |  |  |  |
| BV: 10 |  | CP: 5 |  |
| Acceptance Criteria: - System allows uploading of bill details and supporting document - Bill submission generates a unique reference ID - Confirmation message sent to DDO |  |  |  |

| User Story No: US2 | Tasks: Validate bill details automatically |  | Priority: Highest |
| --- | --- | --- | --- |
| Value Statement: As a treasury officer, I want the system to validate mandatory fields So that I can reduce errors in bill submissions. |  |  |  |
| BV: 8 |  | CP: 3 |  |
| Acceptance Criteria: - System highlights missing or invalid fields. - Bills with missing info cannot be submitted. - Validation report is shown instantly. |  |  |  |

| User Story No: US3 | Tasks: Approve bills online |  | Priority: Highest |
| --- | --- | --- | --- |
| Value Statement: As a treasury officer, I want to approve bills digitally So that I can eliminate manual approval delays. |  |  |  |
| BV: 10 |  | CP: 5 |  |
| Acceptance Criteria: - Officer can review bill details and attachments online. - Approval/Rejection is logged with timestamp. - Notification sent to DDO. |  |  |  |

| User Story No: US4 | Tasks: Track bill status in real-time |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a vendor, I want to check the real-time status of my bill so that I know when payment will be received. |  |  |  |
| BV: 7 |  | CP: 3 |  |
| Acceptance Criteria: - Status updates reflect submission, approval, processing and payment. - Vendors can log in with bill ID |  |  |  |

| User Story No: US5 | Tasks: Receive notification on updates |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want email/SMS notification on bill status so that I stay informed about approvals or rejections |  |  |  |
| BV: 6 |  | CP: 3 |  |
| Acceptance Criteria: - Notification triggered on submission, approval, rejection and payment. - Notification content includes bill ID and next steps. |  |  |  |

| User Story No: US6 | Tasks: Upload supporting documents securely |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to attach scanned bills and invoices so that treasury officers can verify records digitally. |  |  |  |
| BV: 6 |  | CP: 3 |  |
| Acceptance Criteria: - System supports PDF/JPEG uploads. - Files are encrypted and stored securely. - Upload confirmation is displayed. |  |  |  |

| User Story No: US7 | Tasks: Reject bills with remarks |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a treasury officer, I want to reject bill with comments So that DDOs can correct and resubmit quickly |  |  |  |
| BV: 5 |  | CP: 3 |  |
| Acceptance Criteria: - Rejection must include remarks. - Rejected bills return to DOO’s dashboard |  |  |  |

| User Story No: US8 | Tasks: Digital signature/approval |  | Priority: Highest |
| --- | --- | --- | --- |
| Value Statement: As a treasury officer, I want to sign bills digitally So that the process remains complaint and paperless |  |  |  |
| BV: 7 |  | CP: 5 |  |
| Acceptance Criteria: - Bills can be digitally signed with secure certificates. - System verifies authenticity of the signature. |  |  |  |

| User Story No: US9 | Tasks: Integration with banks for disbursement |  | Priority: Highest |
| --- | --- | --- | --- |
| Value Statement: As a vendor, I want my payment processed directly via bank integration So that I receive funds quickly. |  |  |  |
| BV: 9 |  | CP: 8 |  |
| Acceptance Criteria: - Approved bills trigger fund disbursement. - Payment confirmation available in system. |  |  |  |

| User Story No: US10 | Tasks: Audit trail for all transactions |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As an auditor, I want a digital log of all bill actions So that I can verify compliance. |  |  |  |
| BV: 5 |  | CP: 5 |  |
| Acceptance Criteria: - Every action logged with user, date and time. - Logs cannot be modified. |  |  |  |

| User Story No: US11 | Tasks: Dashboard for DDOs |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want dashboard view of all bills So that I can track pending, approval and rejected submission. |  |  |  |
| BV: 5 |  | CP: 5 |  |
| Acceptance Criteria: - Dashboard displays bill summary and status. - Can filter by date, status and amount. |  |  |  |

| User Story No: US12 | Tasks: Dashboard for Treasury Officers |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a treasury officer, I want a consolidated dashboard So that I can prioritize pending bills. |  |  |  |
| BV: 4 |  | CP: 5 |  |
| Acceptance Criteria: - Pending bills shown with priority indicators. - Officers can filter and sort. |  |  |  |

| User Story No: US13 | Tasks: Search functionality |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a user, I want to search bills by ID, date or department so that I can find records easily. |  |  |  |
| BV: 2 |  | CP: 2 |  |
| Acceptance Criteria: - Search supports multiple parameters. - Results display bill details and status. |  |  |  |

| User Story No: US14 | Tasks: Generate reports |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a finance officer, I want to generate monthly reports So that I can review fund utilization. |  |  |  |
| BV: 3 |  | CP: 3 |  |
| Acceptance Criteria: - Reports available in PDF/Excel formats. - Reports include bill counts, amounts and statuses. |  |  |  |

| User Story No: US15 | Tasks: Role-based access |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As an admin, I want to assign role-based access so that data remains secure |  |  |  |
| BV: 3 |  | CP: 5 |  |
| Acceptance Criteria: - Roles include DDO, Treasury Officer, Vendor, Admin. - Users only access their permitted features. |  |  |  |

| User Story No: US16 | Tasks: Mobile access |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to access the system on mobile So that I can track bills anytime |  |  |  |
| BV: 2 |  | CP: 3 |  |
| Acceptance Criteria: - Mobile-responsive interface. - Notification available on mobile. |  |  |  |

| User Story No: US17 | Tasks: Bills history tracking |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to view the history of each bill So that I can understand its journey. |  |  |  |
| BV: 2 |  | CP: 2 |  |
| Acceptance Criteria: - Timeline view of each bill’s status changes. - Remarks and approval visible. |  |  |  |

| User Story No: US18 | Tasks: Secure login with 2FA |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a user, I want to secure login with 2FA so that my account remains safe. |  |  |  |
| BV: 3 |  | CP: 3 |  |
| Acceptance Criteria: - Login requires password + OTP - OTP delivered via email/SMS |  |  |  |

| User Story No: US19 | Tasks: Bulk bill upload |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to upload multiple bills at once So that I save time |  |  |  |
| BV: 2 |  | CP: 3 |  |
| Acceptance Criteria: - System accepts bulk uploads in Excel/PDF. - Errors highlighted per record. |  |  |  |

| User Story No: US20 | Tasks: SLA compliance alerts |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a finance officer, I want alerts for SLA breaches so that I can act quickly |  |  |  |
| BV: 2 |  | CP: 3 |  |
| Acceptance Criteria: - Alerts triggered when processing exceed SLA. - Escalation sent to higher authorities. |  |  |  |

| User Story No: US21 | Tasks: Bill submission |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a DDO, I want to resubmit rejected bills easily So that I don’t start from scratch. |  |  |  |
| BV: 2 |  | CP: 2 |  |
| Acceptance Criteria: - Rejected bills allow edits and resubmission. - Old remarks retained for reference. |  |  |  |

| User Story No: US22 | Tasks: Vendor portal access |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a vendor, I want portal access So that I can track my payment status. |  |  |  |
| BV: 2 |  | CP: 2 |  |
| Acceptance Criteria: - Vendors log in with unique credentials - Dashboard shows pending and paid bills. |  |  |  |

| User Story No: US23 | Tasks: Configurable workflows |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As an admin, I want configurable approval workflows So that the system adapts to departmental needs. |  |  |  |
| BV: 1 |  | CP: 2 |  |
| Acceptance Criteria: - Workflows can be set by department or bill type. - Changes logged in system |  |  |  |

| User Story No: US24 | Tasks: Payment confirmation to vendors |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a vendor, I want payment confirmation notifications So that I know funds are credited. |  |  |  |
| BV: 2 |  | CP: 2 |  |
| Acceptance Criteria: - Notifications triggered after successful disbursement. - Includes transaction ID and date. |  |  |  |

| User Story No: US25 | Tasks: Archival of old bills |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As a finance officer, I want old bills archived digitally So that I can free system storage and maintain compliance. |  |  |  |
| BV: 1 |  | CP: 2 |  |
| Acceptance Criteria: - Bills older than 5 years moved to archive. - Archived bills retrievable when needed. |  |  |  |

Document 4: Agile Product Owner Experience

Project: e-Treasury Bill Automation System

Role of the Product Owner
The Product Owner in this project acted as the bridge between stakeholders (DDOs, Treasury Officers, Finance Department, Vendors) and the Scrum Team. With knowledge of government financial workflows treasury operations, the PO ensured that the product vision was aligned with stakeholder needs and regulatory compliance.

Responsibilities of the Product Owner in the Project

- Market / Domain Analysis

- Analysed the existing treasury process (manual + limited digitization)

- Assessed the demand for automation to reduce turnaround time, errors and inefficiencies.

- Studied similar e-governance financial systems for reference.

- Enterprise Analysis

- Conducted due diligence on opportunities to enhance transparency in government payments.

- Ensured the solution aligned with government digital initiatives and compliance standards.

- Product Vision and Roadmap

- Defined the vision by digitizing the treasury bill lifecycle for faster, transparent and accountable processing.

- Created a roadmap that included high-level featured like bill submission, approval workflows, bank integration, real-time tracking and dashboards.

- Managing Product Features

- Collected requirements from stakeholders (DDOs, Treasury Officers, Finance Department, Vendors).

- Prioritizes features based on critically, ROI and stakeholder need.

- Balanced between compliance requirements and user convenience.

- Managing Product Backlog

- Maintained and refined the product backlog in JIRA.

- Prioritized epics and user stories using Business Value (BV) via $100 technique and Complexity Points (CP) via Planning Poker.

- Re-prioritized backlog items as per changing stakeholder inputs.

- Managing Iteration Progress

- Facilitated sprint planning, ensuring the team icked the right stories aligned with sprint goals.

- Participated in daily scrums, monitoring progress and removing blockers with the Scrum Master.

- Conducted sprint reviews with stakeholders to demo increments and capture feedback.

- Engaged in retrospectives with BA and team to improve delivery.

Meetings Handled by the PO

- Sprint Planning

- Daily Scrum

- Sprint Review

- Sprint Retrospective

- Backlog Refinement

User Story Management

- Created and refined user stories including:

- Stories

- Tasks

- Priority

- Acceptance Criteria

- BV & CP values.

Key Learning as PO from this Project

- How to align a vision with evolving government financial requirements.

- Importance of stakeholder collaboration to prioritize value-driven features.

- Practical experience with Agile ceremonies and backlog management in JIRA.

- Balancing compliance-driven needs with user friendly design.

- Delivery working increments of automation that improved transparency and efficiency.

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US1 | As a DDO, I want to submit bills digitally So that I can avoid manual paperwork and speed up processing | Submit a treasury bill online | Highest | 10 | 5 | Sprint 1 |
| US2 | As a treasury officer, I want the system to validate mandatory fields So that I can reduce errors in bill submissions. | Validate bill details automatically | Highest | 8 | 3 | Sprint 1 |
| US3 | As a treasury officer, I want to approve bills digitally So that I can eliminate manual approval delays. | Approve bills online | Highest | 10 | 5 | Sprint 2 |
| US4 | As a vendor, I want to check the real-time status of my bill so that I know when payment will be received | Track bill status in real-time | High | 7 | 3 | Sprint 3 |
| US5 | As a DDO, I want email/SMS notification on bill status so that I stay informed about approvals or rejections | Receive notification on updates | High | 6 | 3 | Sprint 2 |
| US6 | As a DDO, I want to attach scanned bills and invoices so that treasury officers can verify records digitally | Upload supporting documents securely | High | 6 | 3 | Sprint 1 |
| US7 | As a treasury officer, I want to reject bill with comments So that DDOs can correct and resubmit quickly | Reject bills with remarks | High | 5 | 3 | Sprint 1 |
| US8 | As a treasury officer, I want to sign bills digitally So that the process remains complaint and paperless | Digital signature/approval | Highest | 7 | 5 | Sprint 2 |
| US9 | As a vendor, I want my payment processed directly via bank integration So that I receive funds quickly | Integration with banks for disbursement | Highest | 9 | 8 | Sprint 3 |
| US10 | As an auditor, I want a digital log of all bill actions So that I can verify compliance | Audit trail for all transactions | High | 5 | 5 | Sprint 4 |
| US11 | As a DDO, I want dashboard view of all bills So that I can track pending, approval and rejected submission | Dashboard for DDOs | High | 5 | 5 | Sprint 2 |
| US12 | As a treasury officer, I want a consolidated dashboard So that I can prioritize pending bills | Dashboard for Treasury Officers | High | 4 | 5 | Sprint 2 |
| US13 | As a user, I want to search bills by ID, date or department so that I can find records easily | Search functionality | Medium | 2 | 2 | Sprint 4 |
| US14 | As a finance officer, I want to generate monthly reports So that I can review fund utilization | Generate reports | Medium | 3 | 3 | Sprint 4 |
| US15 | As an admin, I want to assign role-based access so that data remains secure | Role-based access | High | 3 | 5 | Sprint 4 |
| US16 | As a DDO, I want to access the system on mobile So that I can track bills anytime | Mobile access | Medium | 2 | 3 | Sprint 3 |
| US17 | As a DDO, I want to view the history of each bill So that I can understand its journey | Bills history tracking | Medium | 2 | 2 | Sprint 4 |
| US18 | As a user, I want to secure login with 2FA so that my account remains safe | Secure login with 2FA | High | 3 | 3 | Sprint 4 |
| US19 | As a DDO, I want to upload multiple bills at once So that I save time | Bulk bill upload | Medium | 2 | 3 | Sprint 4 |
| US20 | As a finance officer, I want alerts for SLA breaches so that I can act quickly | SLA compliance alerts | Medium | 2 | 3 | Sprint 4 |
| US21 | As a DDO, I want to resubmit rejected bills easily So that I don’t start from scratch | Bill submission | Medium | 2 | 2 | Sprint 1 |
| US22 | As a vendor, I want portal access So that I can track my payment status | Vendor portal access | Medium | 2 | 2 | Sprint 3 |
| US23 | As an admin, I want configurable approval workflows So that the system adapts to departmental needs | Configurable workflows | Low | 1 | 2 | Sprint 4 |
| US24 | As a vendor, I want payment confirmation notifications So that I know funds are credited | Payment confirmation to vendors | Medium | 2 | 2 | Sprint 3 |
| US25 | As a finance officer, I want old bills archived digitally So that I can free system storage and maintain compliance | Archival of old bills | Low | 1 | 2 | Sprint 4 |

Sprint Backlog

Sprint 1

| User story ID | User story | Tasks | Owner | Status | Estimated Effort (CP) |
| --- | --- | --- | --- | --- | --- |
| US1 | As a DDO, I want to submit bills digitally So that I can avoid manual paperwork and speed up processing | Submit a treasury bill online | Mr Karthik | Done | 5 |
| US2 | As a treasury officer, I want the system to validate mandatory fields So that I can reduce errors in bill submissions. | Validate bill details automatically | Mr Rahul Bose | Done | 3 |
| US3 | As a DDO, I want to attach scanned bills and invoices so that treasury officers can verify records digitally | Upload supporting documents securely | Mr Karthik | Done | 3 |
| US4 | As a treasury officer, I want to reject bill with comments So that DDOs can correct and resubmit quickly | Reject bills with remarks | Mr Rahul Bose | Done | 3 |
| US5 | As a DDO, I want to resubmit rejected bills easily So that I don’t start from scratch | Bill submission | Mr Karthik | Done | 2 |

Sprint Burn Up Chart

Sprint Burn Down Chart

Document 6: Sprint Meetings

Meeting Type 1: Sprint Planning Meeting

| Date | 04-09-2025 |
| --- | --- |
| Time | 10:00AM – 12:00PM |
| Location | Zoom Meeting |
| Prepared By | Business Analyst |
| Attendees | Product Owner, Scrum Master, Developers, Testers, Business Analyst |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Product Backlog Review | Product Owner | 20 min |
| Prioritisation & Sprint Goal | Product Owner & Scrum Master | 30 min |
| User Story Breakdown (US1, US2, US6, US7, US21) | Developers & BA | 40 min |
| Task Estimation | Development Team | 20 min |
| Sprint Commitment & DoD | Scrum Master | 10 min |

Other Information

| Observers | Treasury Officers (Domain SME) |
| --- | --- |
| Resources | JIRA, Product Vision Document, DoD checklist |
| Special Notes | Sprint duration = 2 weeks |

Meeting Type 2: Sprint review meeting

| Date | 18-09-2025 |
| --- | --- |
| Time | 10:00 AM-12:00 PM |
| Location | Zoom Meeting |
| Prepared By | Scrum Master |
| Attendees | Scrum Team, Stakeholders (TO, DDO, Finance Officer) |

| Sprint Status | Things to demo | Quick Updates | What’s next |
| --- | --- | --- | --- |
| 5 User stories completed | - Online Bill submission (US1) - Auto validation of Bills (US2) - Upload of Supporting Documents (US6) - Rejection workflow with remarks (US7) - Resubmission of rejected Bill (US21) | Resubmission of rejected bills (US21) partially done, will be carried over to sprint 2 | Start Sprint 2 (Approval Workflow, Notifications, Audit Trail) |

Metting Type 3: Sprint retrospective meeting

| Date | 18-09-2025 |
| --- | --- |
| Time | 4:00 PM-5:00 PM |
| Location | Zoom Meeting |
| Prepared By | Scrum Master |
| Attendees | Product Owner, BA, Scrum Master, Development Team |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint Retrospective | Online Bill Submission (US1) and Auto Validation (US2) completed successfully | Resubmission of rejected bills (US21) not fully completed, carried forward | How can we better estimate effort for complex stories? | Sprint 1 backlog items |
|  | Supporting Documents uploaded (US6) and rejection workflow (US7) demo went well. | Burn down chart was regular (worked bunched at start, slow later) | Can we spread tasks more evenly across sprint days? | Sprint burndown chart |
|  | Team collaboration and communication were strong. | Testing started late, causing last-minute pressure | Should QA be involved earlier during development? | QA notes and testing logs |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week “1” (from 04-09-2025) |
| --- | --- | --- |

|  |  | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Mr Karthik (Developer) Ms Sameera Reddy (QA) | Set up DB schema (US1) Prepared Test (US2) | Developed API for bill submission (US1) Ran field validation (US2) | Integrated with UI (US1) Reported 3 bugs (US2) | Peer code review (US1) Re-tested fixes (US2) | Marked US1 as Done Closed US2 |
| What will you do today? | Mr Rahul Bose (Developer) Ms Sunita Acharya (Product Onwer) | Start upload UI. Clarified acceptance criteria with DDO | Add file encryption. Collected feedback from TO. | Integrated with backend. Updated JIRA backlog | Test Upload with sample files. Prepared sprint report | Deliver feature for QA. Ready for Sprint |
| What is blocking your progress? | Mr Karthik (Developer) | Waiting for rejection workflow (US21) | Dependency on US7 completion | Working on bug fixes. | Dependencies clarified | Start implementation. |