Document 2- Product Vision

Answer-

| Scrum Project Name: | Swift Cart – A Modern E-Commerce Platform |  |  |
| --- | --- | --- | --- |
| Venue | Bangalore |  |  |
| Date: 12-Aug-2024 | Start Time: 10:00 AM | End time: 12:30 | Duration: 2.5 years |
| Client | Swift Cart Retail Ltd. |  |  |
| Stakeholder list | End Customers Vendors/Sellers Warehouse Managers Logistics Providers Customer Support Team Marketing Team Product Management Team |  |  |
| Scrum Team |  |  |  |
| Scrum Master: | Sonal Pattaniak |  |  |
| Product Owner: | Priya Verma |  |  |
| Scrum Developer 1: | Asutosh rana |  |  |
| Scrum Developer 2: | Prateek .M |  |  |
| Scrum Developer 3: | Naresh panda |  |  |
| Scrum Developer 4: | Amit raj |  |  |
| Scrum Developer 5: | Sekhar Tripathi |  |  |

Vision

To develop a scalable, secure, and intuitive E-Commerce platform that provides a seamless online shopping experience to customers while enabling vendors to manage their products, inventory, and orders efficiently.

Target Group

Which market segment does the product address?
Online retail market segment – including fashion, electronics, home goods, personal care, and more.

Who are the target users and customers?

- Online shoppers across India

- Individual and business vendors looking to sell their products

- Logistics and delivery partners

- Internal support and fulfillment teams

Needs

What problem does the product solve?

- Reduces friction in online shopping and product discovery

- Enables sellers to manage catalog and inventory in real time

- Streamlines order tracking, returns, and customer service

Which benefit does it provide?

- One-stop platform for a wide variety of products

- Competitive pricing and faster delivery options

- Simplified vendor onboarding and management tools

Product

What product is it?
A web and mobile e-Commerce platform with admin dashboards, seller panels, customer portals, and integrated payment and delivery modules.

What makes it desirable and special?

- User-centric design with personalized recommendations

- Multi-vendor support

- Integrated logistics and real-time tracking

- Discounts, loyalty programs, and secure payments

Is it feasible to develop the product?
Yes, with the current tech stack (React.js, Node.js, MongoDB, Stripe/Paytm integration) and sprint planning, the MVP can be delivered within 3-4 sprints.

Value

How is the product going to benefit the company?

- Opens a new sales channel with a broad customer base

- Builds a competitive edge through data-driven promotions

- Reduces dependency on physical stores and expands market reach

What are the business goals?

- 10,000 user registrations in the first quarter

- 100+ vendor onboardings in 6 months

- Generate ₹50 lakh in gross merchandise value in the first year

What is the business model?

- Commission per transaction (3–5%)

- Subscription plans for premium seller tools

- Advertisement revenue from featured product listings

Document 3: User stories

Answer-

| User Story No: 01 | Tasks: Design registration and login page. Implement OTP verification. Configure user authentication. | Priority: High |
| --- | --- | --- |
| Value statement: As a customer, I want to register and log in securely, so that I can access my account and shop safely. |  |  |
| Bv: 13 | CP: 05 |  |
| Acceptance criteria: Registration via email/phone is successful OTP verification is mandatory Secure login and logout flow Error messages for invalid credentials |  |  |

| User Story No: 02 | Tasks: Create product catalog view Add category/brand/price filters Develop search and sort functionality | Priority: High |
| --- | --- | --- |
| Value Statement: As a customer, I want to browse and search products, so that I can find items easily. |  |  |
| Bv: 21 | CP: 08 |  |
| Acceptance criteria: Product listing is responsive Filters and sort options work Search returns relevant results |  |  |

| User Story No: 03 | Tasks: Create detailed product page Include product description, price, and reviews | Priority: High |
| --- | --- | --- |
| Value Statement: As a customer, I want to view product details, so that I can make an informed purchase. |  |  |
| Bv: 13 | CP: 05 |  |
| Acceptance criteria: Product info, price, ratings, and images are visible “Add to Cart” and “Buy Now” buttons present Shipping and stock info displayed |  |  |

| User Story No: 04 | Tasks: Develop cart management (add, remove, update quantity) Show real-time price and summary | Priority: High |
| --- | --- | --- |
| Value Statement: As a customer, I want to manage my shopping cart, so that I can review products before buying. |  |  |
| Bv: 21 | CP: 08 |  |
| Acceptance criteria: Cart shows all added items with quantity Price updates automatically Items can be removed or updated |  |  |

| User Story No: 05 | Tasks: Build multi-step checkout Add address, payment, and confirmation flows | Priority: High |
| --- | --- | --- |
| Value Statement: As a customer, I want to place an order easily, so that I can purchase products securely. |  |  |
| Bv: 21 | CP: 13 |  |
| Acceptance Criteria: Valid address required Multiple payment options available Confirmation page shown after order placed |  |  |

| User Story No: 06 | Tasks: Develop seller dashboard Enable product upload with price, image, stock | Priority: Medium |
| --- | --- | --- |
| Value Statement: As a vendor, I want to list my products, so that I can sell on the platform |  |  |
| Bv: 13 | CP: 08 |  |
| Acceptance Criteria: Seller login and dashboard accessible Product listing form with validations Admin approval required for listings |  |  |

| User Story No: 07 | Tasks: Enable order tracking Integrate shipment status updates | Priority: Medium |
| --- | --- | --- |
| Value Statement: As a customer, I want to track my order, so that I can stay informed about delivery. |  |  |
| Bv: 08 | CP: 05 |  |
| Acceptance Criteria: Tracking shows real-time status Status includes Processing, Shipped, Delivered Notifications sent at each update |  |  |

| User Story No: 08 | Tasks: Create review and rating system Moderate reviews before publishing | Priority: Low |
| --- | --- | --- |
| Value Statement: As a customer, I want to read and submit reviews, so that I can make better buying decisions. |  |  |
| Bv: 08 | CP: 03 |  |
| Acceptance Criteria: Customers can post reviews after delivery Reviews include text and star ratings Admin approval before display |  |  |

Document 5: Product and sprint backlog and product and sprint burndown charts

Answer-   Product Backlog

| User Story ID | User Story (Summary) | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US-01 | User Registration & Login | UI, OTP auth, error handling | High | 13 | 5 | Sprint 1 |
| US-02 | Browse & Search Products | Catalog, filter, search | High | 21 | 8 | Sprint 1 |
| US-03 | Product Detail View | Images, price, description | High | 13 | 5 | Sprint 1 |
| US-04 | Add/Remove Items to Cart | Cart logic, quantity updates | High | 21 | 8 | Sprint 2 |
| US-05 | Checkout Process | Address, payment, confirmation | High | 21 | 13 | Sprint 2 |
| US-06 | Vendor Product Listing Dashboard | Seller portal, product form, admin approval | Medium | 13 | 8 | Sprint 3 |
| US-07 | Order Tracking | Order status, shipment updates | Medium | 8 | 5 | Sprint 3 |
| US-08 | Product Reviews | Ratings, moderation | Low | 8 | 3 | Sprint 3 |

Sprint Backlog – Sprint 1

| User Story ID | User Story (Summary) | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-01 | Registration & Login | Auth logic, OTP, UI validation | Developer 1 | In Progress | 5 SP |
| US-02 | Product Browse & Search | Catalog, filter, search | Developer 2 | Not Started | 8 SP |
| US-03 | Product Detail Page | Detail layout, data binding | Developer 3 | In Progress | 5 SP |
| US-04 | Cart Functionality | Add/remove items, quantity updates | Developer 1 | Not Started | 8 SP |
| US-05 | Checkout Flow | Address, payment gateway, confirmation | Developer 2 | Not Started | 13 SP |

Product burndown chart

I included a Release Burndown Chart instead of a Product Burndown because it shows progress across multiple sprints toward our final deliverable. It helped us track how much work remains for the release goal, not just individual sprint progress. This gives better visibility to stakeholders about overall delivery status

Sprint burndown

A Sprint Burndown Chart is a visual tool in Agile Scrum used to track the amount of work remaining in a sprint on a daily basis. It helps the team and stakeholders see whether the sprint is on track to meet its goal.

Document 6: Sprint meetings

Answer-   Meeting Type 1: Sprint Planning meeting

| Date | 01-06-2025 |
| --- | --- |
| Time | 10:00 AM to 10:30 AM |
| Location | Zoom Meeting |
| Prepared by | Sonal, Business Analyst |
| Attendees | Mr. Rajesh Kumar – Product Owner Ms. Priya Sharma – Scrum Master Devendra Jain – Developer 1 Neha Joshi – Developer 2 Akash Mehta – Developer 3 |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Sprint goal overview | Product owner | 15 Mins |
| Review of product backlog | Scrum master | 25 Mins |
| User Story Discussion | BA/ Developer | 25 Mins |
| Estimation and Capacity Plan | Scrum Master | 15 Mins |
| Sprint Commitment | Entire Team | 10 Mins |

Other Information

| Observers | None for this session |
| --- | --- |
| Recourses | JIRA Board, Sprint Backlog Sheet, Velocity Charts |
| Special notes | Devendra will handle UI stories; Neha will work on API integration |

Meeting Type 2: Sprint review meeting

| Date | 15-06-25 |
| --- | --- |
| Time | 4:00 PM to :00 PM |
| Location | Zoom meeting Room |
| Prepared by | Priya Sharma (Scrum Master) |
| Attendees | Product Owner, Business Analyst Scrum Master, Developers Key Stakeholders (Mr. Arvind Rao – Marketing Head, Ms. Sneha Kapoor – QA Lead) |

| Sprint Status | Things To Demo | Quick updates | What’s Next |
| --- | --- | --- | --- |
| 8 out of 9 committed stories completed successfully. 1 story deferred due to API dependency | User Registration Form UI (Devendra) Notification Service Integration (Neha) Task Dashboard Filters (Akash) | Minor design alignment issue resolved No critical bugs found during QA testing | Remaining story moved to next sprint Next sprint will focus on reporting module and analytics dashboard |

Meeting Type 3: Sprint retrospective meeting

| Date | 16-06-2025 |
| --- | --- |
| Time | 10:00 AM to 11:00 AM |
| Location | Microsoft teams |
| Prepared by | Priya Sharma (Scrum Master) |
| Attendees | Scrum Master, Product Owner, All Developers, BA |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Review of sprint performance | Team communication was effective | Delay in 3rd party API delivery | Can we plan better for external dependencies? | Previous sprint retrospective notes, updated velocity chart |
| Capture lessons learned | Sprint goals met on time | Some confusion around story acceptance criteria | Should we include PO in user story walkthroughs? |  |
| Improvement planning | Testing completed within timeline |  |  |  |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week “X” (from dd-mm-yyyy to dd-mm-yyyy) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| What did you do yesterday? | Developer 1. Developer 2. Developer 3 | Completed login UI. | Unit test login page. | Worked on registration. | Fixed CSS issues. | Code review. | - | - |
|  |  | Integrated email API. | Set up DB schema. | Wrote API tests. | Fixed validation bugs. | QA support |  |  |
|  |  | Designed dashboard UI | Created filter logic | Connected backend. | Sprint testing | Worked on bug fixes |  |  |
| What will you do today | Developer 1. Developer 2. Developer 3 | Peer Review | Start registration form | Test registration | Update form logic | Merge PR |  |  |
|  |  | Start OTP logic | Work on email triggers | QA testing | Assist UI dev | Final integration |  |  |
|  |  | Start analytics UI | Create graph module | Backend logic | Fix reported bugs | Final UI tweaks |  |  |
| What (if any) is blocking your progress | Developer 1. Developer 2. Developer 3 | None | None | API delay | None | None |  |  |
|  |  | Waiting for test data | None | None | API response delay | API response delay |  |  |
|  |  | None | None | None | None | None |  |  |