## Slide 1: CRM Application
Prepared By : -Bhumika Sahu
Date– 04/07/2025

## Slide 2: Situation
Sales officers currently collect customer information using manual paper forms during field visits or at the point of contact. These forms are later submitted to the backend operations team, who manually input the customer details into the CRM system. This process is linear, non-automated, and dependent on human data entry.

## Slide 3: Problem
Manual Data Entry: The reliance on paper forms and manual entry leads to data entry errors, delays, and inconsistencies in customer records.
Inefficiency: Time is wasted transferring physical forms and waiting for backend processing, causing slow response times to customer inquiries or service requests.
Lack of Real-Time Access: Sales officers and management cannot track or access real-time customer data, leading to poor decision-making and missed follow-ups.
Data Security Risks: Paper forms are vulnerable to loss or unauthorized access, compromising customer confidentiality.
Scalability Issues: As customer volume grows, this manual process cannot scale efficiently, leading to operational bottlenecks.

## Slide 4: Opportunity
Process Automation: Implementing a CRM application with direct data entry capabilities (mobile or tablet-based) for sales officers can eliminate manual steps and reduce errors.
Real-Time Data Capture: Enabling digital form submissions can provide instant updates to the CRM system, improving responsiveness.
Improved Customer Experience: Faster onboarding and accurate data entry lead to better customer service and satisfaction.
Data Analytics & Reporting: Accurate and timely data improves analytics, reporting, and decision-making.
Cost and Time Efficiency: Reduces administrative overhead and speeds up sales and service cycles.

## Slide 5: Purpose Statement (Goals):
The purpose of this project is to digitize and streamline the customer data capture process within the CRM system by eliminating the existing manual and paper-based data entry workflow. The project aims to:
Enhance Data Accuracy Eliminate manual entry errors by enabling real-time digital data collection by sales officers through a mobile-enabled CRM interface.
Improve Operational Efficiency Reduce processing time and dependency on backend teams by automating the customer information entry process.
Enable Real-Time Data Access Provide instant access to updated customer records for all relevant stakeholders, enhancing collaboration and follow-ups.
Strengthen Data Security and Compliance Replace paper forms with secure digital data capture to minimize the risk of data loss, breaches, and non-compliance with data protection standards.
Support Scalability and Growth Build a scalable CRM infrastructure that can accommodate increased customer volume without additional manual overhead.
Improve Customer Experience Accelerate the customer onboarding process and improve response times, resulting in higher satisfaction and retention.

## Slide 6: Project Objectives:
Digitize Customer Data Collection Develop a digital form interface within the CRM system for sales officers to input customer information directly from the field, using tablets or mobile devices.
Eliminate Manual Data Entry Remove the need for the backend team to re-enter customer data from paper forms, thereby reducing redundancy and human errors.
Ensure Real-Time Synchronization Implement a system that syncs customer data instantly to the central CRM database, ensuring up-to-date information is always available.
Improve Data Quality and Integrity Introduce mandatory fields, validation checks, and dropdowns in digital forms to ensure standardized and accurate data entry.
Enhance Reporting and Monitoring Capabilities Enable dashboards and automated reports to track customer onboarding, sales performance, and data quality metrics.
Improve Turnaround Time (TAT) Reduce the average time from data collection to system entry by at least 50%, improving responsiveness across departments.
Increase System Adoption by Sales Team Conduct user training and provide a user-friendly interface to ensure at least 90% adoption of the new CRM data entry process by sales staff.
Ensure Data Security and Compliance Implement secure authentication, role-based access, and encrypted data transmission to protect sensitive customer information.
Support Scalability for Future Expansion Design the solution to accommodate future enhancements, such as integration with marketing automation or customer support tools.

## Slide 7: Success Criteria:
The success of this CRM project will be measured by the following key criteria:
100% Digital Data Collection All sales officers are using the CRM system to collect and submit customer information digitally, with no reliance on paper forms.
Reduction in Data Entry Errors by at least 80% Accuracy of customer data improves significantly due to real-time validation and elimination of manual re-entry by backend staff.
Decrease in Turnaround Time by 50% or More Time taken from customer interaction to data availability in CRM is reduced by half, improving operational responsiveness.
Real-Time Data Availability Customer data entered by sales officers becomes immediately visible to backend and management teams within the CRM system.
User Adoption Rate of 90% or Higher At least 90% of sales officers and backend staff actively use the new system without reverting to old manual processes.
System Uptime and Performance The CRM application maintains 99% uptime and responds efficiently during peak data entry periods.
Compliance and Data Security Achieved All customer data is handled according to organizational security policies and regulatory compliance standards (e.g., GDPR, data privacy norms).
Positive Stakeholder Feedback Sales officers and backend teams report improved ease of use, reduced workload, and higher productivity.
Management Reporting Enabled Managers can generate accurate and timely reports (e.g., customer onboarding stats, lead status, etc.) through CRM dashboards.
Project Delivered Within Timeline and Budget The CRM system enhancements are completed as per the waterfall plan milestones, without significant overruns.

## Slide 8: Methods/Approach:
This project will follow the Waterfall model, a linear and sequential approach to system development. Each phase will be
completed in full before proceeding to the next.
1. Requirements Gathering
Conduct interviews and workshops with sales officers, backend teams, and CRM users.
Document current process flows, pain points, and data fields captured on paper forms.
Create a detailed Business Requirement Document (BRD) and get stakeholder approval.
2. System Design
Prepare a Functional Requirement Specification (FRS) and Technical Design Document (TDD) based on the BRD.
Design UI wireframes for the digital data entry form.
Define system architecture, database schema, and validation rules.
3. Development
CRM development team builds the digital data entry module.
Integration with the existing CRM backend is implemented.
Frontend interfaces are made mobile/tablet responsive for sales officers.
4. Testing
Perform Unit Testing, System Testing, and Integration Testing.
Conduct User Acceptance Testing (UAT) with a pilot group of sales officers and backend staff.
Capture feedback and fix any defects before full deployment.
5. Deployment
Deploy the solution in the production environment.
Ensure necessary infrastructure, security, and data migration (if applicable) are in place.
6. Training and Support
Conduct training sessions for sales and backend teams.
Provide user manuals and quick reference guides.
Set up a helpdesk or support system for initial post-implementation issues.
7. Maintenance
Monitor system performance and user feedback.
Roll out any minor enhancements or bug fixes.
Plan for future upgrades or additional features.

## Slide 9: Resources:
This section outlines the human, technical, and financial resources required for successful project execution.
1. Human Resources
Role | Responsibility
Project Manager | Oversees project planning, execution, timelines, and communication.
Business Analyst | Gathers requirements, prepares BRD/FRD, and supports testing and stakeholder review.
CRM Developer(s) | Designs and develops the digital form and CRM enhancements.
UI/UX Designer | Designs user-friendly mobile/tablet interface for sales officers.
Database Administrator | Manages CRM database design, performance, and security.
QA/Test Engineer | Prepares and executes test cases, ensures system is bug-free and functional.
Sales Officers (Pilot Group) | Participate in UAT and provide feedback for improvements.
Trainer/Support Staff | Delivers training and provides ongoing user support post-deployment.

## Slide 10
2. Technical Resources
CRM Software Platform (existing or new module development)
Mobile/Tablets for Sales Officers (if not already provided)
Development Tools (IDE, version control, code repository)
Testing Tools (manual testing templates or automated test scripts)
Project Management Tool (e.g., MS Project, Jira, Trello)
Training Materials (user manuals, video guides, FAQ documents)
Cloud Storage/Servers (if CRM is hosted externally)
3. Financial Resources
Development Costs (internal or outsourced CRM developers)
Licensing Fees (if CRM tools/modules require licenses)
Hardware Purchase (mobile devices for field sales staff, if required)
Training Costs (materials, trainers, or sessions)
Contingency Budget (10-15% buffer for unexpected costs)

## Slide 11: Risks:
Risk | Description | Impact | Mitigation Strategy
1. Low User Adoption | Sales officers may resist the change from paper forms to digital entry. | High | Conduct training sessions, involve users in UAT, and provide user-friendly UI.
2. Data Loss or Corruption | Data may be lost during transition from paper to digital or due to system failure. | High | Implement data backup, proper testing, and rollback mechanisms.
3. Integration Challenges | Integrating the new module with existing CRM may cause technical issues. | Medium | Ensure early collaboration between developers and system architects.
4. Delays in Requirement Finalization | Stakeholders may take time to agree on requirements. | Medium | Set clear deadlines and conduct structured requirement-gathering workshops.
5. Inadequate Testing Time | Rushed timelines might limit thorough testing. | High | Allocate proper time in the project plan for multiple test cycles and bug fixing.
6. Device/Connectivity Issues in Field | Sales officers may face problems with internet or devices while entering data. | Medium | Enable offline data entry options and provide tech support.
7. Budget Overrun | Additional features or delays could increase costs. | Medium | Monitor budget regularly and maintain a contingency reserve.

## Slide 12: Dependencies :
Dependency | Description
1. Stakeholder Availability | Timely input and approval from business stakeholders are crucial, especially during requirements and UAT phases.
2. CRM Platform Stability | The existing CRM infrastructure must support integration with the new module.
3. IT Infrastructure Readiness | Mobile devices and secure network access must be in place for field sales usage.
4. Training Completion | Users must complete training before system go-live to ensure adoption and proper use.
5. Data Migration Accuracy | Any migration of legacy data or partial digitization must be validated and complete before deployment.

## Slide 13: To Be Completed by Appropriate Manager
Project Sponsor : - Rajat Rathi
Project Manager - Saurabh Singh