AGILE DELIVERABLES

Documented by B.Vaishnavi

Date : 06-SEP-2025

Agile Documents –

Document 1: Definition of Done

Definition of Done (DoD) for the Content Integrity Initiative (Single Review Tool - SRT):

As per Agile practices, the DoD defines the conditions that must be met for a user story or feature to be marked as complete. It ensures clarity, shared understanding, and delivery of quality.

Checklist for DoD:

Governance Features – Review checklists and approval workflows are fully functional, tested, and linked to roles (Creator, Reviewer, Publisher, Compliance).

Automated Integrity Checks – Keyword, metadata, and copyright validations run automatically and block non-compliant content.

Audit Trail & Version Control – All edits, reviews, and approvals logged with timestamps; side-by-side comparison available.

Dashboards & Alerts – SLA dashboards and overdue alerts display correct metrics with no missing data.

Compliance Workflow – High-risk posts (finance, healthcare, political) are routed through compliance officers before approval.

Document 2- Product Vision

| Scrum Project | Content Integrity Initiative – Single Review Tool (SRT) |
| --- | --- |
| Venue: | Online – Microsoft Teams |
| Date: | 05-September-2025 |
| Start time: | 10:00 AM |
| End time: | 12:00 PM |
| Duration: | 2 Hours |
| Client: | Content Operations & Compliance Department |
| Stakeholder list: | Moderators, Compliance Officers, Product Managers, Legal Team, Development Team |
| Scrum Role | Name |
| Scrum Master: | Roshan |
| Product Owner: | Vaishnavi |
| Scrum Developer 1: | Kiran Reddy (Frontend – ReactJS) |
| Scrum Developer 2: | Srija (Backend – Node.js/Java) |
| Scrum Developer 3: | Vardhan (AI/ML – Python) |
| Scrum Developer 4: | Sreemanthi (UI/UX Designer |
| Scrum Developer 5: | Arun (QA Engineer) |

### Vision

To build a smart and scalable content moderation platform that uses AI/ML to automatically detect harmful or non-compliant content, provides a centralized dashboard for moderators, and ensures transparency, compliance, and faster decision-making.

| Target group | Needs | Product | Value |
| --- | --- | --- | --- |
| Marketing teams publishing across Meta, Facebook, Instagram. - Compliance officers ensuring regulatory adherence. - Content creators & social media managers. | - Ensures content complies with brand guidelines, legal, and compliance rules. - Solves delays caused by manual review bottlenecks. - Prevents reputational risks from non-compliant or misleading posts. | A Single Review Tool (SRT) with built-in content integrity features. - Automated checks for banned keywords, metadata completeness, and copyright usage. - Version control, audit trails, and compliance workflows. - Feasible using existing SRT with added features (low incremental cost). | Reduces compliance risks and potential legal penalties. - Builds trust in the company’s digital presence. - Improves speed-to-market by reducing approval delays. - Business Goals: brand protection, faster publishing, cost reduction in manual reviews. - Business Model: Internal adoption for compliance efficiency; potential SaaS offering in future. |

Document 3 UserStories

# User Stories - Content Integrity Initiative (SRT)

| User story No: US-01 | Tasks: Implement review checklist functionality | Priority: High |
| --- | --- | --- |
| Value statement: As a Reviewer, I want to follow a standardized review checklist so that I can ensure content meets brand and compliance requirements. |  |  |
| BV: 500 | CP: 5 | Acceptance criteria: - Checklist is mandatory before approval - Reviewer cannot approve content without completing checklist - Checklist includes brand, metadata, and banned keywords |

| User story No: US-02 | Tasks: Configure workflow for multiple reviewer approvals | Priority: High |
| --- | --- | --- |
| Value statement: As a Publisher, I want mandatory multi-level approvals before publishing so that content integrity is not compromised. |  |  |
| BV: 500 | CP: 8 | Acceptance criteria: - At least 2 reviewers must approve content - System prevents publishing until all approvals completed - Approval sequence logged in audit trail |

| User story No: US-03 | Tasks: Set SLA timers for review turnaround | Priority: Medium |
| --- | --- | --- |
| Value statement: As a Marketing Manager, I want SLAs for reviews so that campaign timelines are not delayed. |  |  |
| BV: 200 | CP: 3 | Acceptance criteria: - SLA values configurable (e.g., 48 hours) - Alerts triggered when SLA is breached - Reports show SLA compliance rates |

| User story No: US-04 | Tasks: Develop automated banned keyword detection | Priority: High |
| --- | --- | --- |
| Value statement: As a Reviewer, I want the system to automatically flag banned keywords so that I don’t miss policy violations. |  |  |
| BV: 500 | CP: 8 | Acceptance criteria: - Banned keyword list configurable by Admin - Keywords highlighted in content for review - Reviewer alerted before content approval |

| User story No: US-05 | Tasks: Add metadata completeness validation | Priority: High |
| --- | --- | --- |
| Value statement: As a Content Creator, I want the system to validate metadata so that posts comply with publishing standards. |  |  |
| BV: 500 | CP: 5 | Acceptance criteria: - Missing hashtags flagged - Alt text required for images - Broken or missing links detected |

| User story No: US-06 | Tasks: Integrate copyright/media validation | Priority: Medium |
| --- | --- | --- |
| Value statement: As a Compliance Officer, I want copyright validation so that unauthorized media is not published. |  |  |
| BV: 200 | CP: 3 | Acceptance criteria: - System flags duplicate/unlicensed images - Requires proof of licensing before publishing - Blocked content logged in audit trail |

| User story No: US-07 | Tasks: Enable side-by-side post comparison | Priority: Medium |
| --- | --- | --- |
| Value statement: As a Reviewer, I want to compare post versions so that I can validate changes after feedback. |  |  |
| BV: 200 | CP: 2 | Acceptance criteria: - System stores all post versions - Changes highlighted automatically - Reviewer can approve/reject updated version |

| User story No: US-08 | Tasks: Create audit trail for all reviews and approvals | Priority: High |
| --- | --- | --- |
| Value statement: As an Admin, I want a complete audit trail so that accountability is maintained. |  |  |
| BV: 500 | CP: 5 | Acceptance criteria: - Logs all actions (submitted, edited, approved, rejected) - Includes timestamp and user ID - Audit logs exportable for compliance |

| User story No: US-09 | Tasks: Develop review status dashboard | Priority: High |
| --- | --- | --- |
| Value statement: As a Marketing Manager, I want a dashboard showing review status so that I can track campaign readiness. |  |  |
| BV: 500 | CP: 5 | Acceptance criteria: - Dashboard displays content by status (Draft, In Review, Approved, Rejected) - Filters by platform (Meta, FB, Instagram) - Exportable reports available |

| User story No: US-10 | Tasks: Configure overdue review alerts | Priority: Medium |
| --- | --- | --- |
| Value statement: As a Reviewer, I want overdue content flagged so that I can prioritize urgent reviews. |  |  |
| BV: 200 | CP: 3 | Acceptance criteria: - Alerts triggered when SLA breached - Notifications via email/in-app - Escalation to manager if not reviewed |

| User story No: US-11 | Tasks: Implement escalation workflow for high-risk content | Priority: Medium |
| --- | --- | --- |
| Value statement: As a Compliance Officer, I want high-risk content auto-escalated so that I can review before publishing. |  |  |
| BV: 200 | CP: 3 | Acceptance criteria: - High-risk categories configurable (finance, healthcare, political ads) - Posts auto-routed to compliance officer - Content blocked until compliance approval complete |

| User story No: US-12 | Tasks: Generate compliance performance reports | Priority: Low |
| --- | --- | --- |
| Value statement: As a Stakeholder, I want compliance reports so that I can measure integrity performance. |  |  |
| BV: 50 | CP: 1 | Acceptance criteria: - Monthly report shows rejection rates and SLA compliance - Exportable in PDF/Excel - Comparisons available across campaigns |

Document 4: Agile PO Experience

As the Product Owner, my responsibilities in the Content Integrity Initiative (SRT Project):

### Responsibilities:

- Market Analysis: Researched the demand for automated content moderation tools and identified that existing solutions lacked real-time AI detection, centralized dashboards, and audit trails.

- Enterprise Analysis: Analyzed compliance risks and opportunities, especially the need for transparent decision logs to satisfy regulators.

- Product Vision & Roadmap: Created a vision to deliver an AI-powered, compliance-ready content review platform. Designed a roadmap of six sprints, each delivering usable increments like flagging, dashboards, policy tagging, and reporting.

- Managing Features: Collected stakeholder inputs from moderators, compliance officers, and legal teams. Prioritized epics and user stories based on urgency, ROI, and regulatory deadlines.

- Backlog Management: Maintained product backlog in Jira, continuously refined user stories with acceptance criteria, and adjusted priorities after sprint reviews.

- Iteration Progress: Regularly reviewed sprint burndown charts, monitored progress, and worked with Scrum Master and BA to resolve blockers quickly.

### Lessons Learned:

- Actively participated in sprint planning, daily scrums, reviews, and retrospectives, gaining practical experience in Agile ceremonies.

- Learned how user stories evolve through collaboration, especially for modules like AI flagging and compliance dashboards.

- Improved skills in writing user stories with Business Value (BV) and Complexity Points (CP).

- Understood the importance of stakeholder communication to align business goals with technical implementation.

- Practiced balancing regulatory compliance vs. development capacity, ensuring critical features were prioritized early.

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US001 | As a Reviewer, I want to follow a standardized review checklist so that I can ensure content meets brand and compliance requirements. | Implement review checklist functionality | High | 500 | 5 | 1 |
| US002 | As a Publisher, I want mandatory multi-level approvals before publishing so that content integrity is not compromised | Configure workflow for multiple reviewer approvals | High | 500 | 8 | 1 |
| US003 | As a Marketing Manager, I want SLAs for reviews so that campaign timelines are not delayed. | Set SLA timers for review turnaround | Medium | 200 | 3 | 1 |
| US004 | As a Reviewer, I want the system to automatically flag banned keywords so that I don’t miss policy violations | Develop automated banned keyword detection | High | 500 | 5 | 1 |
| US005 | As a Content Creator, I want the system to validate metadata so that posts comply with publishing standards | Add metadata completeness validation | High | 500 | 5 | 2 |
| US006 | As a Compliance Officer, I want copyright validation so that unauthorized media is not published. | Integrate copyright/media validation | Medium | 200 | 3 | 2 |
| US007 | As a Reviewer, I want to compare post versions so that I can validate changes after feedback. | Enable side-by-side post comparison | Medium | 200 | 3 | 2 |
| US008 | As an Admin, I want a complete audit trail so that accountability is maintained. | Create audit trail for all reviews and approvals | High | 500 | 5 | 2 |
| US009 | As a Marketing Manager, I want a dashboard showing review status so that I can track campaign readiness. | Develop review status dashboard | High | 500 | 5 | 3 |
| US010 | As a Reviewer, I want overdue content flagged so that I can prioritize urgent reviews | Configure overdue review alerts | Medium | 200 | 3 | 3 |
| US011 | As a Compliance Officer, I want high-risk content auto-escalated so that I can review before publishing. | Implement escalation workflow for high-risk content | Medium | 200 | 3 | 3 |
| US012 | As a Stakeholder, I want compliance reports so that I can measure integrity performance | Generate compliance performance reports | Low | 50 | 1 | 3 |

Sprint Backlog

| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US001 | As a Reviewer, I want the system to automatically flag banned keywords so that I don’t miss policy violations | Develop automated banned keyword detection | Developer 1 &2 | Review | 12 hours |
| US002 | As a Reviewer, I want to compare post versions so that I can validate changes after feedback. | Enable side-by-side post comparison | Developer 1,2 & 3 | Done | 22 hours |
| US003 | As a Content Creator, I want the system to validate metadata so that posts comply with publishing standards | Add metadata completeness validation | Developer 3 & 1 | IN progress | 16 hours |
| US004 | As a Compliance Officer, I want copyright validation so that unauthorized media is not published. | Integrate copyright/media validation | Developer 2 & 3 | Done | 16 hours |

Burnup chart

Burndown chart

Document 6: Sprint meetings

Meeting Type 1: Sprint Planning meeting

| Date | 01-July-2025 |
| --- | --- |
| Time | 9:00 AM – 11:00 AM |
| Location | Online (Teams) |
| Prepared By | Scrum Master |
| Attendees | Product Owner, Scrum Master, Dev Team |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Discuss Sprint 1 scope | Product OWNER | 2 weeks |
| Story estimation & BV/CP assignment | BA | 45mins |

Other Information

| Observers | Stakeholders |
| --- | --- |
| Resources | JIIRA board , Backlog |
| Special Notes | Focus on content integrity features |

Meeting Type 2: Sprint review meeting

| Date | 10-July-2025 |
| --- | --- |
| Time | 4:00 PM |
| Location | Teams |
| Prepared By | Scrum Master |
| Attendees | PO , BA , QA, SM,COMPLAINCE MANAGER |

| Sprint status | Things to demo | Quick updates | What’s next |
| --- | --- | --- | --- |
| 100% DCS UI/Backend completed | Doubt input, mentor dashboard | Completed – engine flags disallowed words, tested with sample data. Metadata validation (hashtags, alt text, captions) working. Copyright check integration pending. | Timesheet & Job Portal in Sprint 2 |

Meeting Type 3: Sprint retrospective meeting

| Date | 23-Sep-2025 |
| --- | --- |
| Time | 10:00 AM – 11:00 AM |
| Location | Online (MS Teams) |
| Prepared By | Scrum Master / BA |
| Attendees | Scrum Team (PO, SM, Dev, QA), Compliance Officer |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint Goal Review | Integrity checks completed on time | Testing delays due to lack of test data | Can compliance provide datasets earlier? | Sprint Board |
| Collaboration | Dev & Compliance worked closely | Daily standup attendance low | How to ensure better engagement? | Jira |
| Technical Setup | Keyword detection engine integrated | Metadata rules not fully configured | Should we prioritize rules configuration next sprint? | User Stories |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week “1” (from 01-07-2025 to 15-07-2025) Monday; Tuesday; Wednesday; Thursday; Friday; Saturday; Sunday. |
| --- | --- | --- |
| What did you do yesterday? | Developer 1. Developer 2. Developer 3.. | Set up keyword rules engine; Integrated banned keyword list; Tested keyword detection with sample data; Fixed false positives in keyword detection; Prepared demo for PO; -; -. Created metadata validation rules; Implemented alt text validation; Tested metadata completeness for 10 sample posts; Debugged hashtag validation logic; Completed unit tests; -; -. Designed audit trail schema; Built version history storage; Implemented side-by-side comparison prototype; Integrated audit logging; Ran QA on audit logs; -; -. |
| What will you do today? | Developer 1. Developer 2. Developer 3.. | Integrate keyword rules with review workflow; Improve flagged word highlighting; Work with QA to refine validation; Update documentation; Demo in sprint review; -; -. Enhance metadata checks with broken link detection; Add mandatory caption validation; Support QA in testing; Document metadata module; Sprint review demo; -; -. Complete version comparison UI; Test audit trail export; Finalize API integration with dashboard; Prepare sprint review materials; Demo version control feature; -; -. |
| What (if any) is blocking your progress? | Developer 1. Developer 2. Developer 3.. | None; Waiting for compliance team to finalize banned keyword list.; -; -; -; -; -. Delay in getting accessibility guidelines from compliance officer; -; -; -; -; -; -. Need test data for old post versions to validate audit trail; -; -; -; -; -; -. |