# AGILE DOCUMENTS

Agile Documents -

Document 1: Definition of Done Document 2- Product Vision Document 3: User stories Document 4: Agile PO Experience

Document 5: Product and sprint backlog and product and sprint burndown charts Document 6: Sprint meetings

Document 1 Definition of done

For User Stories:

- All acceptance criteria defined for the story are met.

- All assumptions or clarifications raised in refinement are addressed.

- Code is written and committed to the source repository.

- Code passes peer code review.

- Unit test cases are written with minimum 80% coverage.

- Code is deployed in the staging/test environment

- Feature is tested thoroughly by QA and validated against test cases.

- All critical and major bugs are resolved.

- Documentation (technical/functional) is updated as required.

- Product Owner has reviewed and signed off the story.

For Sprint Delivery:

- All user stories in the sprint backlog meet their DoD.

- Regression testing completed on integrated modules.

- A working, potentially shippable product increment is ready.

- Sprint Review conducted with stakeholders.

- Feedback captured for upcoming sprints.

For Release Delivery:

- Final UAT (User Acceptance Testing) passed.

- Deployment plan finalized and approved.

- Production build tested and stable.

- Release notes prepared and shared with relevant teams.

- Training (if required) is conducted for HR or end users.

- Go-live checklist approved.

Document 2- Product Vision

| Scrum Project Name: | Human Resource Management System HRMS |  |  |
| --- | --- | --- | --- |
| Venue: | Conference Hall C |  |  |
| Date:04th June 2025 | Start time: 11:30 am | End time: 1: 00 pm | Duration: 1 hour 30 min |
| Client: | Internal HR Department | Senior Management |  |
| Stakeholder list: | - HR Manager - Talent Acquisition Lead - Recruiters - Payroll Specialist - Hr Admin, Hr Associate - Finance Head |  |  |
| Scrum Team |  |  |  |
| Scrum Master: | Pankaj Maghade |  |  |
| Product owner: | Ruchika Hiwarale |  |  |
| Scrum Developer 1: | Priya Shinde |  |  |
| Scrum Developer 2: | Mandeep Saini |  |  |
| Scrum Developer 3: | Sandra Dsouza |  |  |
| Scrum Developer 4: | Ritesh Singh |  |  |
| Scrum Developer 5: | Vrushabh Moon |  |  |

| Vision: To build a centralized, digital, and secure Human Resource Management System that simplifies, automates, and streamlines HR operations such as leave, attendance, recruitment, payroll, and training while enhancing transparency, improve efficiency and employee satisfaction. |  |  |  |
| --- | --- | --- | --- |
| Target group Market Segment: Internal enterprise users within the organization Target Users and Customers: - HR professionals - Recruiters - Employees (HR department) - Managers | Needs Problem that product solves : Manual handling of records in Excel sheets is error-prone and inefficient. Lack of centralized system results in delays in decision-making. Difficult to track employee information and manage training or leaves effectively Difficulty in tracking Recruitment process Benefit that product provide : - Centralized storage of employee records - Streamlined recruitment through ATS - Automated leave and attendance tracking - Quick generation of payroll and salary slips - Simplified training assignment and tracking | Product A web-based HRMS solution with integrated modules for Leave & Attendance, ATS, Payroll, and Training & Development. What Makes It Desirable and Special? - Role-based access (HR, Employee, Recruiter) - Real-time dashboards - Document upload and management (e.g., offer letters, ID proofs) - Secure login and data protection - User-friendly UI and mobile compatibility Is It Feasible to Develop the Product? Yes, using modern web technologies, an agile approach, and iterative feedback from HR stakeholders. | Value Reduces HR workload through automation. Enhances employee satisfaction with self-service access. Improves compliance, record accuracy, and decision-making speed. Saves time and cost spent on manual processes. What are the business goals? Business Goal : Digital transformation of HR processes Improve operational efficiency and data accuracy Ensure compliance and audit readiness Provide transparency and access to HR data across departments Business Model : The HRMS is designed as an internal enterprise application to streamline and automate HR operations within the organization. It follows an in-house deployment model where the system is accessed only by authorized HR personnel and employees through secure login credentials. The system is not intended for commercial sale, but is developed to improve internal efficiency, employee experience, and data accuracy. |

Document 3: User stories

| User story No: 1 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| As an HR, I want to add new employees to the system so that their records are maintained. |  |  |  |
| BV: 100 |  | CP: 3 |  |
| Acceptance criteria: - Admin can input employee name, ID, and contact details - System stores and displays entered employee information - New employee appears in the employee list |  |  |  |

| User story No: 2 | Tasks: 2 |  | Priority: Medium |
| --- | --- | --- | --- |
| As an HR, I want to edit employee information so that changes are reflected correctly. |  |  |  |
| BV: 100 |  | CP: 2 |  |
| Acceptance criteria: - Admin can select and edit employee records - Updated data is visible in profile and reports |  |  |  |

| User story No: 3 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| As an Employee, I want to mark employee attendance so that daily records are maintained. |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance criteria: - Employee can mark Present/Absent - Records are saved date-wise - Daily attendance visible in reports |  |  |  |

| User story No: 4 | Tasks: 4 |  | Priority:High |
| --- | --- | --- | --- |
| As an HR, I want to generate salary slips monthly for payroll records. |  |  |  |
| BV:200 |  | CP:5 |  |
| Acceptance criteria : - Salary components calculated - PDF of payslip downloadable - Salary details match with policies |  |  |  |

| User story No:5 | Tasks:2 |  | Priority: High |
| --- | --- | --- | --- |
| As an employee, I want to log in securely so that I can access my HRMS account. |  |  |  |
| BV: 100 |  | CP:2 |  |
| Acceptance criteria: - Login screen prompts for valid username and password - System authenticates credentials and grants access only to valid users - Error message is shown for invalid login attempts - Password reset option is available for forgotten credentials |  |  |  |

| User story No:6 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| As an employee, I want to apply for leave through the HRMS portal so that I can officially request time off and ensure proper approval from my manager. |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance criteria: - Employee can select leave type, dates, and reason from the leave application form - Leave balance is auto-checked before submission - Leave request is routed to the manager for approval and status is updated in real-time |  |  |  |

| User story No: 7 | Tasks:2 |  | Priority: Medium |
| --- | --- | --- | --- |
| As an employee, I want to track the status of my leave request in the HRMS so that I know whether it has been approved, rejected, or is still pending. |  |  |  |
| BV: 50 |  | CP: 2 |  |
| Acceptance criteria: - Employee can view the real-time status of all leave requests (Pending, Approved, Rejected) - Status updates are reflected automatically after manager action - Notifications are sent for status changes |  |  |  |

| User story No: 8 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| As an HR, I want to search employee records by name or employee ID so that I can quickly access specific employee information without manually browsing the entire list. |  |  |  |
| BV: 100 |  | CP: 2 |  |
| Acceptance criteria: - HR can enter name or ID in a search bar to retrieve employee details - Matching records are displayed instantly with key info (Name, ID, Department, Role) - Search supports partial matches and auto-suggestions |  |  |  |

| User story No: 9 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| As an HR, I want to track the recruitment status through the ATS module so that I can manage candidate records and stay updated on each stage of the hiring process. |  |  |  |
| BV: 100 |  | CP: 4 |  |
| Acceptance criteria: - HR can view all candidates by job title and application stage - Status like Applied, Shortlisted, Interviewed, Selected, Rejected should be visible - Filters should be available for sorting by date, job role, or status |  |  |  |

| User story No: 10 | Tasks: 3 |  | Priority:High |
| --- | --- | --- | --- |
| As an HR, I want to store employee-related documents such as offer letters, ID proofs, and certificates so that all records are securely maintained and easily accessible when needed. |  |  |  |
| BV: 100 |  | CP: 4 |  |
| Acceptance criteria: - HR can upload and categorize documents under each employee profile - Allowed file types include PDF, JPG, DOCX - Documents are securely stored and viewable/downloadable by authorized users only |  |  |  |

| User story No: 11 | Tasks:3 |  | Priority:Medium |
| --- | --- | --- | --- |
| As an HR, I want to generate monthly attendance reports for all employees so that I can track attendance trends, identify irregularities, and ensure accurate payroll processing. |  |  |  |
| BV: 50 |  | CP: 4 |  |
| Acceptance criteria: - HR can select a specific month to generate the report - Report includes Present, Absent, Leave, and Holiday counts for each employee - Report is exportable in PDF and Excel formats |  |  |  |

| User story No: 12 | Tasks: 4 |  | Priority:High |
| --- | --- | --- | --- |
| As an HR, I want to process employee payroll at the end of each month so that salary, tax deductions, and benefits are accurately calculated and disbursed on time. |  |  |  |
| BV:200 |  | CP: 5 |  |
| Acceptance criteria: - System fetches attendance, leave, and tax data for salary calculation - HR can preview and validate payroll before finalizing - Salary slips are auto-generated for each employee - Final payroll file is downloadable for bank disbursement |  |  |  |

| User story No : 13 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| As an HR, I want to assign training programs to employees based on their roles or skill gaps so that they can enhance their capabilities and stay aligned with organizational goals. |  |  |  |
| BV: 50 |  | CP: 3 |  |
| Acceptance criteria: - HR can select employees and assign specific training sessions - Assigned training is visible in the employee's profile/dashboard - Notification is sent to employees with training details and schedule |  |  |  |

| User story No: 14 | Tasks:2 |  | Priority: Medium |
| --- | --- | --- | --- |
| As an employee, I want to access my assigned training schedule through the system so that I can view upcoming sessions and attend them on time. |  |  |  |
| BV: 50 |  | CP:2 |  |
| Acceptance criteria: - Employee can log in and view a calendar/list of assigned training programs - Each training entry includes title, date, time, trainer name, and location/link - System sends reminders or notifications before scheduled sessions |  |  |  |

| User story No: 15 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| As an employee, I want to download my monthly pay slip from the HRMS portal so that I can keep a record of my earnings, deductions, and net pay for personal and official use. |  |  |  |
| BV: 100 |  | CP: 3 |  |
| Acceptance criteria: - Employee can select the desired month and view the corresponding pay slip - Pay slip is downloadable in PDF format with company branding - All relevant salary details (basic, HRA, deductions, net pay) are clearly shown |  |  |  |

| User story No: 16 | Tasks:3 |  | Priority:High |
| --- | --- | --- | --- |
| As an HR, I want to add new job openings to the ATS module so that position is visible in ATS and can assign this position to recruiter |  |  |  |
| BV: 200 |  | CP:3 |  |
| Acceptance criteria: - HR can enter job title, description, location, and required skills - Job openings are listed in the career/ATS section for internal or external applicants - HR can set application deadlines and view number of applicants per position |  |  |  |

| User story No: 17 | Tasks:2 |  | Priority:High |
| --- | --- | --- | --- |
| As an HR, I want to assign open job positions to specific recruiters in ATS so that they can take ownership of the hiring process for each role. |  |  |  |
| BV: 100 |  | CP: 3 |  |
| Acceptance criteria: - HR can select a job opening and assign it to one or more recruiters - Assigned recruiters receive a notification and can view/manage the job listing in their dashboard - The system logs the assignment history for tracking responsibility |  |  |  |

| User story No: 18 | Tasks:3 |  | Priority:High |
| --- | --- | --- | --- |
| As an employee, I want to view the list of job openings assigned to me so that I can focus on managing the hiring process for those positions. |  |  |  |
| BV: 100 |  | CP:3 |  |
| Acceptance criteria: - Recruiter can see all assigned job openings in their dashboard - Job details such as title, location, and application deadlines are displayed - Ability to filter and sort job openings by status or date |  |  |  |

| User story No: 19 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| As an Employee, I want to update the status of candidate applications so that all stakeholders are informed about the progress of the recruitment process. |  |  |  |
| BV: 100 |  | CP:3 |  |
| Acceptance criteria: - Recruiter can change candidate status (e.g., Applied, Shortlisted, Interview Scheduled, Rejected, Hired) - Status changes trigger automated notifications to candidates and HR - Historical status changes are recorded for audit purposes |  |  |  |

| User story No: 20 | Tasks:2 |  | Priority: Low |
| --- | --- | --- | --- |
| As an employee, I want to generate reports on recruitment activities so that I can analyze hiring trends and improve processes. |  |  |  |
| BV: 50 |  | CP:2 |  |
| Acceptance criteria: - Reports include metrics such as number of applications, interviews, and hires per job opening - Reports can be exported in PDF or Excel formats - Reports are filterable by date range and job position |  |  |  |

Document 4: Agile PO Experience

As the Product Owner, I served as the bridge between the business stakeholders and the development team, ensuring the final product delivers value to the organization. I was involved in strategic planning, requirement gathering, backlog grooming, prioritization, and validation of delivered features. I was responsible for defining and delivering a solution that aligns with both organizational goals and end-user needs. My role centered on bringing clarity, value, and vision to the product, while ensuring iterative and incremental delivery through Agile principles.

As the Product Owner, I began by:

Market & Enterprise Analysis

- Conducted a detailed analysis of the current HR practices, which were being managed manually using spreadsheets.

- Identified key pain points such as errors in payroll, lack of transparency in leave management, and poor tracking of training and recruitment status.

- Analyzed availability of similar HRMS solutions in the market and identified gaps where our system could offer a competitive edge.

Created Product Vision & Roadmap

- Created a clear product vision to build an efficient, user-friendly, and centralized HRMS that digitizes all core HR functions.

- Developed a product roadmap broken into phases such as Leave & Attendance, ATS, Training & Development, and Payroll Management, with timelines for MVP and progressive enhancements.

Managing Product Features

- Prioritized modules and features based on ROI, urgency, and end-user feedback.

- Facilitated discussions with stakeholders including HR managers and IT teams to understand expectations and align the product scope.

- Managed the feature backlog by categorizing and refining epics into meaningful user stories.

Managing the Product Backlog

- Maintained a well-organized and continuously prioritized backlog, based on business value (BV) and complexity points (CP).

- Regularly conducted backlog refinement sessions to reprioritize tasks based on sprint reviews, team capacity, and stakeholder feedback.

Managing Iteration Progress

- Led sprint planning meetings by collaborating with the Scrum Team to select high-priority backlog items.

- Conducted daily stand-ups, monitored progress, resolved blockers, and ensured alignment with sprint goals.

- Participated in sprint reviews to gather feedback from stakeholders and used insights in sprint retrospectives to improve team performance and delivery quality.

From this project I have learned how to handle sprint meetings such as

  Sprint Planning: Broke down product backlog into actionable tasks aligned with sprint capacity.

  Daily Scrum: Ensured team synchronization, early issue identification, and progress monitoring.

  Sprint Review: Presented completed user stories to stakeholders and gathered actionable feedback.

  Sprint Retrospective: Reflected on the sprint process and implemented improvements.

  Backlog Refinement: Prioritized features based on changing needs and feedback loops.

Gained expertise in creating detailed user stories that included:

- Story Number & Tasks

- Priority Levels (High/Medium/Low)

- Acceptance Criteria

- Business Value (BV) and Complexity Points (CP)

Example:

User Story No: 13

Tasks: 2
Priority: HIGH
As an employee,
I want to download my monthly pay slip from the HRMS portal
so that I can keep a record of my earnings, deductions, and net pay for personal and official use.
BV: 90  CP: 2

Acceptance Criteria:

- Employee can select the desired month and view the corresponding pay slip

- Pay slip is downloadable in PDF format with company branding

- All relevant salary details (basic, HRA, deductions, net pay) are clearly shown

Document 5: Product and sprint backlog and product and sprint burndown charts

Product backlog: A prioritized list of all features, enhancements, bug fixes, and tasks needed for the product.

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | As an HR, I want to add new employees to the system so that their records are maintained. |  | High | 10 | 3 | Sprint 1 |
| US02 | As an HR, I want to edit employee information so that changes are reflected correctly. |  | Medium | 8 | 2 | Sprint 1 |
| US03 | As an HR, I want to track the recruitment status through the ATS module so that I can manage candidate records and stay updated on each stage of the hiring process. |  | High | 9 | 4 | Sprint 2 |
| US04 | As an employee, I want to view the list of job openings assigned to me so that I can focus on managing the hiring process for those positions. |  | Medium | 8 | 3 | Sprint 2 |
| US05 | As an employee, I want to generate reports on recruitment activities so that I can analyze hiring trends and improve processes. |  | Low | 6 | 2 | Sprint 2 |
| US06 | As an HR, I want to assign open job positions to specific recruiters in ATS so that they can take ownership of the hiring process for each role. |  | High | 8 | 3 | Sprint 2 |
| US07 | As an HR, I want to store employee-related documents such as offer letters, ID proofs, and certificates so that all records are securely maintained and easily accessible when needed. |  | High | 9 | 4 | Sprint 1 |

Sprint backlog: A subset of the product backlog items selected for a specific sprint, plus a plan for delivering them.

| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US03 | As an HR, I want to track recruitment status through the ATS module | Create recruitment dashboard UI | Mandeep Saini | To Do | 4 |
|  |  | Backend logic for status tracking | Vrushubh Moon | To Do | 5 |
|  |  | Testing and stakeholder review | Shruti Desai | To Do | 3 |
| US04 | As an employee, I want to view the list of job openings assigned to me | UI to list assigned jobs | Ritesh Singh | To Do | 3 |
|  |  | Role-based filtering | Vrushabh Moon | To Do | 3 |
|  |  | Test case writing | Shruti Desai | To Do | 2 |
| US05 | As an employee, I want to generate reports on recruitment activities | UI for report generation | Ritesh singh | To Do | 2 |
|  |  | Generate reports in PDF/Excel | Sandra Dsouz | To Do | 4 |
|  |  | Add date range and filters | Vrushabh Moon | To Do | 2 |
| US06 | As an HR, I want to assign open job positions to specific recruiters in ATS | UI for recruiter assignment | Ritesh Singh | To Do | 3 |
|  |  | Assign role mapping in DB | Sandra Dsouza | To Do | 3 |
|  |  | Testing | Mandeep saini | To Do | 2 |

Sprint burndown  Chart

Document 6: Sprint meetings

Meeting Type 1: Sprint Planning meeting

| Date | 5th June 2025 |
| --- | --- |
| Time | 11:00 am to 12:00pm |
| Location | Microsoft Teams |
| Prepared By | Scrum Master - Pankaj Maghade |
| Attendees | Product owner, Developers, Scrum Master, QA |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Overview of Sprint Goals | Product Owner | 10 min |
| Review of Backlog & Prioritization | Scrum master | 15 min |
| Task Breakdown and Estimation | Developer team | 30 min |
| Risk Identification | QA Lead | 10 min |

Other Information

| Observers | None |
| --- | --- |
| Resources | HRMS Product Backlog, Jira, Sprint Board |
| Special Notes | Focus on completing Leave & Attendance Module |

Meeting Type 2: Sprint review meeting

| Date | 15th June 2025 |
| --- | --- |
| Time | 4:00 pm to 5:00pm |
| Location | Microsoft Teams |
| Prepared By | Scrum Master -Pankaj Maghade |
| Attendees | Product owner, HR stakeholders, Scrum team |

| Sprint status | Things to demo | Quick updates | What’s next |
| --- | --- | --- | --- |
| Sprint 1 completed successfully. | Leave request flow, Leave status page | Minor bugs fixed on mobile UI. | Start ATS Module in Sprint 2. |
| 7/8 stories delivered, 1 moved to next sprint | Login & password reset Admin panel UI | Feedback gathered from HR on usability. | Update backlog based on feedback. |
| Testing completed and passed. | Leave reports for admin | All code merged and deployed to staging. | Sprint Retrospective scheduled tomorrow. |

Meeting Type 3: Sprint retrospective meeting

| Date | 15th June 2025 |  |
| --- | --- | --- |
| Time | 5:00 pm to 6:00pm |  |
| Location | Microsoft Teams |  |
| Prepared By | Scrum Master - Pankaj Maghade |  |
| Attendees | Product owner, QA, Scrum team |  |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
|  | Leave Management Module delivered successfully | Minor delays in frontend integration for report UI | Can we split frontend/backend tasks more clearly in next sprint? | Sprint 1 User Stories & Burndown |
|  | Daily stand-ups helped in identifying blockers early | Limited test data during early QA testing | Should we add mock data earlier in development? | Jira Sprint Board |
|  | Team collaboration and code review practices improved productivity | Lack of clarity in acceptance criteria for some user stories | Can we involve QA earlier in user story review? | QA Logs & Feedback Notes |

Meeting Type 4: Daily Stand-up meeting

| Question | Mandeep Saini |  |  | Week “X” (25th May 2025 to 5th June 2025) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| What did you do yesterday? |  | Developer 1 |  | Built login Designed DB Created mockups | Integrated API API setup Resolved issue | Fixed bugs Role Mang UI Leave module | Wrote Unit test Code cleanup UX review | Deployed build Test case writing Report export Feature |  |  |
|  |  | Developer 2 |  |  |  |  |  |  |  |  |
|  |  | Developer 3 |  |  |  |  |  |  |  |  |
| What will you do today? |  | Developer 1 |  | Complete login test Write API docs Work on dashboard | Review backend code Finish role module Validate UI | Refactor login page Backend bug fixes Connect API to frontend | Assist QA Performance testing UI feedback updates | Plan next module Documentation Final push to staging |  |  |
|  |  | Developer 2 |  |  |  |  |  |  |  |  |
|  |  | Developer 3 |  |  |  |  |  |  |  |  |
| What (if any) is blocking your progress? |  | Developer 1 |  | None None Incomplete API | Backend delay Environment setup issue None | None None None | None Waiting for review Minor merge conflict | None None None |  |  |
|  |  | Developer 2 |  |  |  |  |  |  |  |  |
|  |  | Developer 3 |  |  |  |  |  |  |  |  |