Capstone Project 2 – Agile – Scrum

Scrum Food (Foods Delivery Application)

Question 01 – Write Agile Manifesto.

Answer:  The following are the four main values and twelve principles of the Agile Manifesto.

Four main values:

- Individuals and interactions over processes and tools.

- Working software over comprehensive documentation.

- Customer collaboration over contract negotiation.

- Responding to change over following a plan.

Twelve principles of Agile:

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build project around motivated individuals. Give them the environment and support they need and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face to face conversation.

- Working software is the primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers and user should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhance agility.

- Simplicity – the art of maximizing the amount of work not done – is essential.

- The best architectures, requirements and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

Question 02 – User stories – Acceptance Criteria-BV-CP

Write minimum 40 User stories and their Acceptance Criteria along with their BV and CP

Answer:

| User Story No.: 1 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REGISTER IN SCRUM FOODS SO THAT I CAN DELIVER ORDERS |  |  |  |
| BV: 500 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Registration Screen Text Boxes for User Name, Password, Nation ID, Mobile No., Email Address Click on Register Button Send Successfully Notification to the user |  |  |  |

| User Story No.: 2 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW ORDERS SO THAT I CAN VIEW THE LIST OF ORDERS |  |  |  |
| BV: 500 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA View Order, Display list of orders in the tabular form |  |  |  |

| User Story No.: 3 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO ADD THE ADDRESS SO THAT I CAN GET THE ORDER TO MY ADDRESS |  |  |  |
| BV: 500 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Text box to enter Business rules: Within the radius of 5 km |  |  |  |

| User Story No.: 4 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SELECT THE PAYMENT MODE SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |  |
| BV: 500 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Display payment modes, radio buttons to select payment modes, payments button Business rule: Can select only one payment mode |  |  |  |

| User Story No.: 5 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW THE RESTAURANTS SO THAT I CAN APPROVE THEIR REGISTRATION |  |  |  |
| BV: 500 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA List of restaurant, select restaurants, verify restaurants details, approve button, reject button, notification to the restaurant. |  |  |  |

| User Story No.: 6 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE PRICE SO THAT I CAN ORDER THE FOOD |  |  |  |
| BV: 50 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA - Display price in the list of menu items |  |  |  |

| User Story No.: 7 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE CONTACT NO. OF THE DELIVERY BOY SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |  |
| BV: 50 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA - Display delivery boy mobile number - Display delivery boy name in tracking field - Display delivery boy picture |  |  |  |

| User Story No.: 8 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PROVIDE TIME SLOT SO THAT CUSTOMER CAN CHECK OPENING AND CLOSING HOURS |  |  |  |
| BV: 100 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA - Click on restaurant dashboard - Add from time to time - Click on submit - Display updated successfully |  |  |  |

| User Story No.: 9 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW RESTAURANT REVENUE REPORT SO THAT I CAN VIEW THE RESTAURANT’S REVENUE |  |  |  |
| BV: 200 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Select Reports Select Revenue Reports Select to and from date Select Region (can select all) Generate reports Download report in Excel |  |  |  |

| User Story No.: 10 | Tasks: 3 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A REG ADMIN I WANT TO MANAGE REGIONAL RESTAURANTS SO THAT, I CAN TRACK THE PERFORMANCE OF REGIONAL RESTAURANT |  |  |  |
| BV: 200 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Click on performance of restaurants Select from date to date Click on generate report which incluses restaurants ID, Name, Revenue Click on download report should be in Excel |  |  |  |

| User Story No.: 11 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A ADMIN I WANT TO SEE THE REGIONAL REVENUE REPORTS, SO THAT, I CAN VIEW THE REGIONAL PERFORMANCE |  |  |  |
| BV: 100 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Select regional dropdown View performance of each rest of that region in tabular form which includes rest name, revenue, generated Download in Excel or PDF |  |  |  |

| User Story No.: 12 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO CHAT WITH THE REG ADMIN SO THAT I CAN REQUEST FOR REFUND |  |  |  |
| BV: 200 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA - BR-All mandatory - Text box fields - Display order ID - Text box, for description - Submit button - Generate issue ID - Display successful |  |  |  |

| User Story No.: 13 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO LOGIN SO THAT I CAN ACCESS MY ACCOUNT SECURELY |  |  |  |
| BV: 500 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Login screen Enter valid username and password Click on login Redirect to dashboard to if valid, error if invalid |  |  |  |

| User Story No.: 14 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SEARCH FOR RESTAURANTS SO THAT I CAN FIND MY FAVOURITE FOOD OPTIONS |  |  |  |
| BV: 450 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Search bar Filter by location, cuisine and ratings Display matching result in list view |  |  |  |

| User Story No.: 15 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW RESTAURANT MENU SO THAT I CAN SELECT ITEMS TO ORDER |  |  |  |
| BV: 300 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Display menu category-wise Show price and availability Option to add to cart |  |  |  |

| User Story No.: 16 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW MY ORDER HISTORY SO THAT I CAN TRACK PAST PURCHASES |  |  |  |
| BV: 250 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Display order list with date and amount Include status (Delivered, Cancelled, etc.) Option to reorder |  |  |  |

| User Story No.: 17 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO CANCEL AN ORDER SO THAT I CAN AVOID UNWANTED DELIVERY |  |  |  |
| BV: 350 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Show cancel button Ask reason for cancellation Update status and notify restaurant |  |  |  |

| User Story No.: 18 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO GIVE FEEDBACK AFTER DELIVERY SO THAT I CAN SHARE MY EXPERIENCE |  |  |  |
| BV: 200 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Show feedback form after order completion Star rating (1 to 5) Optional comment box Submit button with confirmation |  |  |  |

| User Story No.: 19 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SAVE MULTIPLE DELIVERY ADDRESSES SO THAT I CAN ORDER TO DIFFERENT LOCATIONS |  |  |  |
| BV: 250 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Option to add, edit and delete addresses Set default address Use saved addresses during checkout |  |  |  |

| User Story No.: 20 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW MY UPCOMING DELIVERIES SO THAT I CAN PLAN MY ROUTE |  |  |  |
| BV: 400 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA List of assigned orders Show pickup and drop locations Delivery time estimates |  |  |  |

| User Story No.: 21 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO UPDATE ORDER STATUS SO THAT CUSTOMER CAN TRACK DELIVERY IN REAL TIME |  |  |  |
| BV: 450 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Buttons: Pickup/On the way/ Delivery Real time update to customer app Timestamp record |  |  |  |

| User Story No.: 22 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO VIEW MY WEEKLY EARNINGS SO THAT I CAN TRACK MY INCOME |  |  |  |
| BV: 300 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Dashboard showing daily and weekly income Date filter Download as PDF or Excel |  |  |  |

| User Story No.: 23 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO ADD OR REMOVE MENU ITEMS SO THAT I CAN KEEP MY MENU UPDATED |  |  |  |
| BV: 400 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Menu dashboard for add/edit/delete Input fields: item name, price, image, category Save and confirmation message |  |  |  |

| User Story No.: 24 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO SET IETM AVAILABILITY STATUS SO THAT CUSTOMERS SEE ONLY AVAILABLE ITEMS |  |  |  |
| BV: 250 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Toggle for available/Not available Immediate reflection on customer app Message for items marked as unavailable |  |  |  |

| User Story No.: 25 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO TRACK ACTIVE ORDERS SO THAT I CAN PREPARE FOOD ON TIME |  |  |  |
| BV: 350 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Active order list Show order time, item, customer name Status tracking and delivery boy details |  |  |  |

| User Story No.: 26 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO MANAGE CUSTOMER COMPLAINTS SO THAT I CAN IMPROVE USER EXPERIENCE |  |  |  |
| BV: 500 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Complaint dashboard Assign to support team Mark resolve, notify customer |  |  |  |

| User Story No.: 27 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW PLATFORM-WIDE STATISTICS SO THAT I CAN MONITOR PERFORMANCE |  |  |  |
| BV: 200 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Show user count, orders per day, revenue summary Date filter Export report option |  |  |  |

| User Story No.: 28 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO APPROVE NEW DELIVERY BOY REGISTRATIONS SO THAT ONLY VERIFIED USERS CAN ACCESS THE SYSTEM |  |  |  |
| BV: 300 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA List of pending delivery boy requests View ID proof and contact details Approve/Reject buttons with confirmation |  |  |  |

| User Story No.: 29 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO GET DELIVERY TIME ESTIMATE SO THAT I KNOW WHEN MY ORDER WILL ARRIVE |  |  |  |
| BV: 350 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Show estimated time after placing order Auto-update based on distance and traffic Display on tracking page |  |  |  |

| User Story No.: 30 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO CHAT WITH CUSTOMER SO THAT I CAN HANDLE SPECIAL REQUESTS |  |  |  |
| BV: 400 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Live chat window Order ID linked to chat Option to close chat after delivery |  |  |  |

| User Story No.: 31 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REPORT AN ISSUE DURING DELIVERY SO THAT ADMIN CAN HELP ME RESOLVE IT |  |  |  |
| BV: 250 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Issue from with dropdown reasons Text box for explanation Submit and generate ticket ID |  |  |  |

| User Story No.: 32 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO SEE REFUND STATUS REPORT SO THAT I CAN ENSURE TIMELY REFUNDS TO CUSTOMERS |  |  |  |
| BV: 300 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA List of refund requests Status: Pending/Approved/Processed Download report as Excel or PDF |  |  |  |

| User Story No.: 33 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO GET ORDER CONFIRMATION VIA SMS/EMAIL SO THAT I AM SURE MY ORDER PLACED |  |  |  |
| BV: 400 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Send confirmation after payment Include order ID, estimated time and item list Available in both SMS and Email |  |  |  |

| User Story No.: 34 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SAVE MY FAVOURITE RESTAURANTS SO THAT I CAN ORDER FASTER NEXT TIME |  |  |  |
| BV: 250 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA “Add to favorite” button. View list under favorites section Remove from list option |  |  |  |

| User Story No.: 35 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO SEE DAILY SALES REPORT SO THAT I CAN ANALYZE MY PERFORMANCE |  |  |  |
| BV: 350 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Sales report by day/date Includes total orders, revenue, cancelled orders Export to Excel to PDF |  |  |  |

| User Story No.: 36 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO MARK MY SELF AS OFFLINE SO THAT I CAN TAKE BREAK WHEN NEEDED |  |  |  |
| BV: 150 |  | CP: 1 |  |
| ACCEPTANCE CRITERIA Toggle button for Online/Offline Show status to admin Restrict new order assignment when offline |  |  |  |

| User Story No.: 37 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW MOST ACTIVE DELIVERY BOY SO THAT I CAN REWARD THEM |  |  |  |
| BV: 300 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA List of delivery boys by number of orders delivered Filter by region and date Export data to Excel |  |  |  |

| User Story No.: 38 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO APPLY DISCOUNT COUPONS DURING PAYMENT SO THAT I CAN SAVE MONEY ON MY ORDER |  |  |  |
| BV: 400 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Enter coupon code field Validate coupon Apply discount to total amount Show final payable amount |  |  |  |

| User Story No.: 39 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO MONITOR CUSTOMER RATINGS FOR RESTAURANTS SO THAT I CAN TAKE ACTION IF NEEDED |  |  |  |
| BV: 300 |  | CP: 2 |  |
| ACCEPTANCE CRITERIA Rating overview per restaurant Average score and recent feedback View by week/month |  |  |  |

| User Story No.: 40 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW PLATFORM REVENUE REPORT SO THAT I CAN MAKE STRATEGIC DECISIONS |  |  |  |
| BV: 500 |  | CP: 3 |  |
| ACCEPTANCE CRITERIA Filter by day/week/month Region-wise revenue breakdown Download complete report as Excel |  |  |  |

Question 3 – What is Epic? Write 2 Epics.

Business Value and Complexity Points

Answer: An epic is a large user story or a collection of related user stories that represents the significant feature or functionality. Epics are high level, often spanning multiple sprint or iterations and they provide a way to organize and prioritize work in product backlog.

Epic 01 – Customer order management system

Description: This epic includes all activities performed by a customer, from registration to receiving the order and giving feedback.

Acceptance Criteria:

  - Customer registration & login

  - Searching for restaurants

  - Viewing menu items and prices

  - Adding items to cart

  - Applying discount coupons

  - Selecting delivery address

  - Placing the order

  - Tracking order status in real-time

  - Giving ratings & feedback

  - Viewing order history and reordering

Business Value (BV): 1000

Complexity Points (CP): 13

Epic 02 – Restaurant Operations Panel

Description: This epic covers the entire backend process for restaurant partners using the system. It helps them manage their operations efficiently.

Acceptance Criteria:

- Restaurant registration and login

- Uploading and editing menu items

- Setting availability time slots

- Accepting and tracking orders

- Viewing customer feedback

- Generating daily/weekly sales reports

- Managing item availability

- Chatting with customers for special instructions

Business Value (BV): 800

Complexity Points (CP): 10

Question 4 – What is the difference between BV and CP?

Answer:

Business Value (BV):

- BV is used to measure how important a user story or feature is from the business or customer point of view.

- It helps the Product Owner and stakeholders decide which features should be developed first.

- BV is estimated by the Product Owner or Client during backlog grooming.

- The values are assigned using a currency-like scale, for example: 1000, 500, 100, 50, etc.

- Higher BV means that the feature will bring more benefit to the customer or improve the product value.

Complexity Point (CP):

- CP measures the technical difficulty or effort needed to complete a user story.

- It is estimated by the Scrum Developers, using techniques like Planning Poker.

- CP shows how much time, resources, or logic is involved in developing that feature.

- It is represented using story point values such as 1, 2, 3, 5, 8, 13, etc.

- Higher CP means the story is more complex and may take more time to develop.

Question 5 – Explain about Sprint.

Answer:

A Sprint is a scrum based agile methodology concept that is similar to iteration. A sprint is time boxed to deliver a specific set of user stories and produce working feature within a set time period. During sprint planning, the business customer or product owner specifies the user story priority, and the development team commits to the scope for the given sprint. During a sprint, user stories can be removed from the sprint scope, but new stories cannot be added, this allows project team to focus on the goals of the sprint and deliver rapidly.

Key Points of Sprint:

- Time-boxed Duration:
A Sprint has a fixed time frame, usually between 1 to 4 weeks, where the team works without interruptions.

- Defined Goal:
Each sprint starts with a clear goal or Sprint Objective that guides the team’s work and focus.

- Sprint Planning:
A planning meeting at the start of the sprint where the team selects which user stories to work on based on priority and capacity.

- Daily Stand-up Meetings:
Every day, the team meets for 15 minutes to discuss what they did yesterday, what they’ll do today, and any blockers.

- Development and Testing:
During the sprint, the team performs both coding and testing to ensure the functionality is ready to deliver.

- Incremental Delivery:
The goal of each sprint is to produce a working product increment that can be shown to stakeholders.

- Sprint Review and Retrospective:

- In Sprint Review, the team presents the completed work to the Product Owner and stakeholders.

- In Retrospective, the team reflects on what went well and what to improve next time.

- Backlog Refinement:
The Product Backlog is regularly updated and refined during the sprint to prepare for future planning.

Question 6 – Explain Product backlog and Sprint backlog

Answer:

### 1. Product Backlog:

- The Product Backlog is a complete list of everything that needs to be developed in the product.

- It includes all features, enhancements, bug fixes, and technical improvements required by the product.

- It is created and maintained by the Product Owner, who constantly prioritizes the items based on business value.

- It is a live document, which means it is continuously updated throughout the project as new ideas and requirements come in.

- The items in the product backlog are called Product Backlog Items (PBIs), and these can be in the form of epics, features, or user stories.

- The team refers to this backlog during every Sprint Planning meeting to select which items they will work on.

### 2. Sprint Backlog:

- The Sprint Backlog is a subset of the product backlog, which includes only the user stories and tasks selected for the current sprint.

- It is created during the Sprint Planning meeting, where the Scrum Team decides what they can complete in the upcoming sprint (1–4 weeks).

- It includes the selected user stories + their breakdown into technical tasks.

- The Scrum Team (mainly developers) owns and manages the Sprint Backlog.

- Once the Sprint begins, the sprint backlog becomes fixed, and the team works to complete it without major changes.

- The Sprint Backlog helps the team stay focused and track progress daily through the Daily Scrum.

Question 7 – What is impediments log? Write 2 impediments.

Answer: An impediments log also known as an issue log or obstacle log, is a document or tool used in Agile software development to track and manage obstacle, bottlenecks or any factors that impede the progress of a project or team.

- To identify and prioritize problems impacting the team’s productivity.

- To provide visibility into unresolved issue.

- To ensure a structured approach to problem solving.

Sample of Impediments

1. Network Connectivity Issue
Due to slow internet in the development environment, the team faced interruptions while accessing the central code repository.

- Impact:
Developers were unable to push or pull code in time, affecting collaborative work and delaying integration testing.

- Resolution Plan:
The IT support team was informed immediately, and a backup high-speed connection was arranged to maintain smooth workflow.

2. Unavailable Product Owner during Sprint
The Product Owner was unavailable for three days during the sprint due to emergency leave.

- Impact:
Team could not get quick clarifications on user stories, leading to confusion in requirement understanding and slow progress.

- Resolution Plan:
A backup business analyst was assigned temporarily to help the team, and open points were noted for the PO to review after return.

Question 8 – Explain velocity of the team.

Answer: Velocity refers to the measure of the amount of work a development team can complete during a sprint. It helps the team and the Product Owner in estimating how much work can be delivered in future sprints.

The calculation of velocity is done by the development team because they are responsible for estimating the effort required to complete each user story or backlog item.

- Story Point Estimation:
Each user story is assigned story points based on its size and complexity.

- Tracking Completed Work:
Only the user stories that are fully completed (as per Definition of Done) are counted in velocity.

- Summing Story Points:
Add the story points of all completed user stories in the sprint.

- Average Velocity:
Take the average of story points completed over multiple sprints to plan future sprints.

Question 9 – Draw Sprint Burn Charts n Product Burn Down Charts.

Answer:

Sprint Burn down Chart

Question 10 - Explain about Product Grooming.

Answer:

- Product grooming, also known as backlog grooming or refinement, is an important activity in Agile software development. It involves reviewing, prioritizing, and refining the items in the product backlog.

- The main goal of product grooming is to ensure that the backlog is well-prepared, clearly organized, and ready for implementation in upcoming sprints.

- It is typically a collaborative effort involving the Product Owner, Development Team, and other relevant stakeholders.

Key point for conducted:

- Setting the context

- Backlog review

- Prioritization

- Refinement and Estimation

- Dependency Analysis

- Acceptance Criteria

- Backlog grooming meetings

Question 11 - Explain the roles of Scrum Master and Product Owner.

Answer:

Scrum Master: The Scrum Master is a servant leader responsible for facilitating the Scrum process and ensuring that the team follows Agile principles and practices effectively. In our project, the Scrum Master acted as a coach and mentor for the development team. He conducted daily stand-up meetings, removed impediments, and ensured smooth coordination between the Scrum Developers and stakeholders. He also ensured that Scrum ceremonies like Sprint Planning, Sprint Review, and Sprint Retrospective were conducted effectively.

Product Owner: As the Product Owner, I was responsible for maximizing the value delivered by the Scrum Team. I maintained and prioritized the Product Backlog, clearly defined user stories with BV (Business Value) and CP (Complexity Point), and ensured they were ready for upcoming sprints. I worked closely with stakeholders to understand their needs and converted them into valuable backlog items. I was actively involved in grooming sessions, sprint reviews, and provided feedback on product increments.

Question 12 – Explain all meetings conducted in scrum project.

Answer:

Sprint planning meeting: The first important meeting is the Sprint Planning Meeting, which is conducted at the beginning of every sprint. During this meeting, the team selects user stories from the product backlog and decides what they can deliver in the current sprint. A sprint goal is defined, and the team prepares a sprint backlog based on this discussion.

Daily Scrum: The second meeting is the Daily Scrum, also known as the daily stand-up. This is a short 15-minute meeting conducted every day during the sprint. Each team member shares what they did yesterday, what they plan to do today, and if they are facing any blockers. This meeting keeps the team in sync and helps identify issues early.

Sprint review: At the end of the sprint, the Sprint Review meeting is held. In this meeting, the team demonstrates the work they have completed to the stakeholders. It helps gather feedback from the Product Owner and other stakeholders so that changes can be made in the future based on user expectations.

Sprint Retrospective: After the sprint review, the team conducts a Sprint Retrospective. This is an internal meeting where the Scrum Team reflects on the sprint and discusses what went well, what didn’t go well, and how things can be improved in the next sprint. This meeting supports continuous improvement within the team.

Optional or As-Needed Meetings in Scrum

Backlog Grooming (Refinement): This meeting involves the Product Owner and the Development Team. Its purpose is to review, refine, and estimate the items in the Product Backlog. It ensures that the backlog is clean, clear, and prioritized for upcoming sprints. These sessions improve planning and reduce last-minute confusion during Sprint Planning.

Release Planning: This meeting is usually conducted at the start of a new project or before a major release. It involves the Product Owner, Scrum Master, Development Team, and sometimes stakeholders. The goal is to define the high-level scope, timeline, key deliverables, and business goals for the product or release.

Ad hoc Meetings: These are unscheduled or informal meetings that are arranged as needed. They may be used to resolve specific impediments, discuss urgent technical issues, or conduct extra planning or review sessions. These meetings provide flexibility and allow the team to respond quickly to changing project needs.

Question 13 – Explain Sprint Size and Scrum Size

Answer:

Sprint Size: In Scrum, Sprint Size refers to the duration or time frame of each sprint. A sprint is a fixed-length iteration in which a specific set of user stories or tasks are completed. The ideal sprint size depends on the nature and complexity of the project, but it is commonly between 1 to 4 weeks, with 2 weeks being the most widely used. A consistent sprint size helps the team plan work effectively, measure velocity, and deliver small, workable increments of the product regularly. In our project, we followed a sprint size of 2 weeks, allowing us to deliver features quickly and incorporate feedback without delays.

Scrum Size: Scrum Size refers to the number of members in the Scrum Team. According to Scrum guidelines, the ideal Scrum Team size is usually between 5 to 9 members, including the Product Owner, Scrum Master, and Development Team. This size ensures that the team is small enough to stay agile but large enough to complete the required work during a sprint. In our project, we followed this guideline and maintained a balanced team structure that encouraged collaboration, quick decision-making and smooth task division.

Question 14 – Explain DOR and DOD

Answer:

Definition of Ready (DoR):

The Definition of Ready (DoR) defines the criteria that a user story must fulfil before it is included in a sprint. It ensures that the team has enough clarity to start work without delay or confusion.

- The user story has a clear and concise description, including expected functionality or behaviour.

- Acceptance criteria are properly defined and agreed upon by the Product Owner and Development Team.

- Any necessary designs, wireframes, or reference documents are available.

- The user story is appropriately sized or estimated in story points or other effort units.

- All external dependencies or resources required are identified and accessible.

- The team has enough information to understand the story and begin development confidently.

Definition of Done (DoD)

The Definition of Done (DoD) defines the completion criteria for a user story or any backlog item. It ensures that the work meets all quality, testing, and documentation standards before it is considered “done” and ready for release. It brings clarity and a common understanding within the team regarding when a story can be closed.

- The code for the user story is implemented, reviewed, and merged into the main codebase.

- Automated tests are created and passed, ensuring the functionality works correctly and does not introduce regressions.

- The user story is tested and validated against the acceptance criteria.

- The UI/UX aspects of the user story are implemented and reviewed.

- The story is properly documented, including relevant instructions, guides, or release notes.

- The Product Owner has reviewed and accepted the user story as meeting all expected requirements.

Question 15 - Explain Prioritization Techniques and MVP

Answer:

Prioritization techniques help the Product Owner and Business Analyst decide which user stories or features should be taken up first based on business value, customer need, time constraints, or dependencies. These techniques ensure that the team works on the most valuable items first.

### MoSCoW Technique

This is one of the most popular methods. Requirements are divided into 4 categories:

- Must Have – Essential features without which the product won’t function

- Should Have – Important features but not absolutely critical

- Could Have – Nice to have features, implemented if time allows

- Won’t Have (for now) – Lowest priority, can be skipped for the current release

100-Dollar Technique:
In this method, each stakeholder is given 100 imaginary dollars. They “spend” their dollars on the features they consider most important.
The features with the highest total dollars receive the highest priority.

MVP (Minimum Viable Product): Minimum Viable Product is the first usable version of a product that includes only the most essential features. It is released early to gather feedback, reduce development cost, and test product-market fit with real users.

### Key Characteristics of MVP:

- It has just enough features to be usable by early customers

- Helps in validating assumptions before full-scale development

- Reduces the risk of building unwanted or unnecessary features

- Provides a base to collect feedback and improve in future iterations

- Speeds up the release and saves time and cost

### Purpose of MVP:

- To launch early and get real-world data

- To test the core functionality of the product

- To decide whether to continue, pivot, or stop development

- To involve customers in shaping the final product

Question 16 – Difference between Business Analyst n Product Owner

Answer:

### Business Analyst (BA):

- Collects and analyzes business requirements by closely interacting with clients and domain stakeholders.

- Prepares detailed documents like BRD, SRS, use cases, and flow diagrams for development reference.

- Acts as a communication bridge between business teams and technical development teams throughout the project.

- Suggests optimal business solutions based on requirement analysis, but doesn't own product-level decisions.

- Focuses on understanding current business processes and analyzing the impact of proposed system changes.

### Product Owner (PO):

- Owns the product backlog and decides which features are built and released in each sprint.

- Represents customer needs and ensures that the team delivers features that bring business value.

- Has authority to prioritize backlog items and approve or reject stories during sprint review.

- Communicates the product vision clearly and keeps the development team aligned with business goals.

- Balances business expectations with technical feasibility while making sprint-level and release decisions.

Question 17 - Prepare a sample Resume of 3yrs exp. Product Owner

Answer:

CHETAN AMBADKAR BUSINESS ANALYST ### PROFESSIONAL SUMMARY: Product Owner with 3 years of experience working in Agile-Scrum environments. Skilled in managing product backlogs, defining sprint goals, writing user stories, and delivering MVPs aligned with business goals. Proven ability to collaborate with cross-functional teams, gather requirements, and prioritize features based on customer value. ### WORK EXPERIENCE: Product Owner COEPD IT Solutions Pvt. Ltd., Pune July 2022 – Aug 2025 - Managed product backlog and conducted backlog grooming sessions with cross-functional teams. - Prioritized features based on business value, customer needs, and technical dependencies. - Coordinated with Scrum Master and team for sprint planning, stand-ups, and retrospectives. - Delivered MVP for a mobile-based food ordering application within 3 sprints. - Ensured all user stories had proper DoR and DoD and maintained stakeholder engagement. CERTIFICATION: - International Institute of Business Analyst (IIBA) CONTACT Email: Chetaanambadkar15@gmail.com Mob. No.: 7066660659 Address: Amravati, Maharashtra EDUCATION Bachelor of Engineering in Mechanical Engineering (2017-2020) G.H.Raisoni Collage of Engineering, Amravati. (SGBAU) SKILLS - Stakeholder Communication - Sprint Planning and Review - Agile-Scrum Framework - User Story Writing & Grooming - MoSCoW & Prioritization - JIRA