## Slide 1: Digital and Supply Chain Enablement
By Sramana Bhattacharya
02/07/2025

## Slide 2: Project Background
The Food Industry Company is an established player in several international markets, offering a diverse range of high-quality food products. With a growing global demand and proven success in existing territories, the company has set its sights on expanding into a new international market. This expansion will include the full portfolio of existing products. However, it also requires the creation of country-specific websites and mobile applications, as well as the development of a localized supply chain to source raw materials directly from the new country.

## Slide 3: Situation:
The Food Industry Company has built a strong presence across several international markets by delivering high-quality, ready-to-consume food products through well-established B2C digital and physical channels. Unlike past expansions, this entry will involve a hybrid strategy that includes digital enablement (new websites and mobile apps tailored for the local audience) and localization of the supply chain. All existing products will be offered in the new market, but raw materials will be sourced domestically within the target country. These materials will be processed into semi-finished and finished goods through newly established local operations. This expansion requires rapid adaptation to the new market's consumer behavior, regulatory requirements, technological infrastructure, and procurement ecosystem. An Agile approach has been chosen to ensure flexibility, speed of execution, and iterative feedback from local stakeholders during the rollout.

## Slide 4: Problem:
Entering a new market poses challenges including:
Building new digital platforms (website and mobile app) tailored to the local market.
Procuring raw materials within the target country and transforming them into semi-finished and finished goods.
Localizing B2C services while maintaining the quality and brand image of the company.
Implementing new operational workflows in an unfamiliar environment.

## Slide 5: Opportunity:
This market expansion provides the company with a strategic opportunity to:
Grow revenue by accessing a new and potentially large B2C customer base that aligns with the company’s product portfolio and health-conscious offerings.
Leverage Agile methodologies to implement a flexible and iterative approach for building digital and operational systems tailored to the local market.
Enhance brand equity by reinforcing the company’s global image as a responsive, locally engaged, and customer-first food provider.
Develop sustainable supply chains by sourcing raw materials locally, reducing logistics costs, and aligning with eco-conscious consumer expectations.
Create reusable infrastructure for future expansions by refining a scalable model for digital platforms, supply operations, and regulatory onboarding.

## Slide 6: Purpose Statement (GOALS):
The purpose of this project is to thoroughly analyze the market-specific business, technical, and operational requirements needed to successfully enter the new country, and to implement a scalable, Agile-driven solution that supports rapid development, local adaptation, and continuous improvement. This project aims to:
Enable a smooth market entry by building fully localized digital platforms that reflect the company’s core brand while meeting the expectations of local B2C customers.
Establish a cost-effective and compliant supply chain by identifying, sourcing, and managing local raw materials to produce semi-finished and finished goods.
Integrate customer-facing digital systems with backend operations, ensuring seamless order processing, inventory tracking, and customer support.

## Slide 7: Project Objectives:
Solution Selection: Identify suitable technologies, platforms, and vendors based on design criteria, functional specifications, and compliance requirements.
Solution Prototyping & Testing: Build MVPs (Minimum Viable Products) for the website and mobile app, supply chain workflows, and local fulfillment processes.
Agile Execution: Conduct iterative sprints to validate design, incorporate feedback, and continuously deliver working increments.
Go-to-Market Readiness: Ensure all customer-facing digital systems are functional, secure & localized; supply chain is tested and operational; and support systems are in place.

## Slide 8: Success Criteria:
Digital Platform Launch
Fully functional, user-friendly website and mobile application tailored to the new country’s language, regulatory standards, and user preferences.
Seamless integration with local payment gateways, logistics providers, and customer support systems.
Launch of digital platforms completed within the planned Agile timeline (e.g., within 4 sprints or 8 weeks).
Operational Readiness
Local sourcing, warehousing, and production workflows fully set up, tested, and capable of handling at least 1,000 customer orders/month.
The End-to-end supply chain visibility achieved through system integrations with procurement, inventory, and order tracking modules.
All operational processes comply with local food safety, packaging, and labor laws.

## Slide 9: Success Criteria:
Agile Delivery Milestones
Completion of key project sprints including backlog grooming, sprint planning, development, testing, and review cycles, with over 90% of user stories completed on time.
Successful MVP (Minimum Viable Product) demonstration to stakeholders by the mid-point of the timeline.
Incorporation of real-time feedback and iterative improvements through sprint retrospectives and customer testing.
User and Customer Satisfaction
Minimum 90% satisfaction rate in internal user training surveys post-Go Live.
Positive customer feedback in the first 60 days, measured through reviews, NPS (Net Promoter Score), and user engagement metrics.
Low rate of critical support tickets (<5%) in the first 30 days post-launch.

## Slide 10: Success Criteria:
Scalability and Future Readiness
Designed digital and operational systems are scalable and replicable for entry into at least two additional markets with minimal customization.
All code, documentation, supply chain models, and vendor contracts structured for reuse and localization in future projects.
Knowledge transfer and handover completed with internal teams trained to independently operate and maintain the system.
Compliances and Risk Management
All legal, regulatory, and tax compliance requirements in the new country are thoroughly documented, approved, and adhered to before launch.
Risk mitigation strategies established and validated for critical business areas including procurement delays, vendor failure, or digital downtime.
Successful completion of internal audits or compliance checks prior to system Go Live with zero major non-conformities reported.

## Slide 11: Methods/approach:
Define Business and Technical Requirements
Conduct collaborative discovery sessions with marketing, operations, procurement, IT, and legal teams.
Identify country-specific business rules, regulatory constraints, and customer behavior expectations.
Create user personas and customer journeys to guide digital experience design.
Develop a detailed product backlog capturing user stories and acceptance criteria.

## Slide 12: Methods/approach:
Vendor Evaluation and Selection
Initiate a formal RFP (Request for Proposal) process to invite qualified vendors (for app development, logistics, procurement).
Organize vendor demonstrations to assess technical fit, experience, scalability, and local knowledge.
Score and shortlist vendors using a weighted decision matrix based on cost, capability, compliance, and cultural fit.
Finalize contracts with selected vendors and define SLAs (Service Level Agreements).

## Slide 13: Methods/approach:
Agile Development and Prototyping
Set up Agile teams with defined roles: Product Owner, Scrum Master, Developers, Testers, UX Designers.
Execute 2-week sprint cycles to iteratively build, test, and refine features for the website, app, and backend systems.
Develop and test MVPs for both digital and operational processes.
Conduct sprint reviews and retrospectives with key stakeholders for feedback and continuous improvement.

## Slide 14: Methods/approach:
User Training and Change Management
Design and deliver training programs for internal users, logistics staff, customer support agents, and regional partners.
Provide hands-on workshops, e-learning modules, and SOPs for new systems and workflows.
Develop a communication and change management plan to manage transition from existing to new processes.
Establish feedback loops from early users to drive post-launch improvements.

## Slide 15: Methods/approach:
Operational Setup and Support Process Design
Finalize local raw material sourcing, warehousing, and production partnerships.
Map and automate supply chain workflows from procurement to order delivery.
Implement support infrastructure: helpdesk, ticketing system, escalation matrix, and maintenance schedule.
Set up data dashboards and reporting mechanisms to monitor performance and compliance.

## Slide 16: Methods/approach:
Go-Live and Post-Launch Monitoring
Execute a phased Go-Live strategy with controlled rollout to selected regions or customer segments.
Monitor real-time KPIs such as order volumes, app downloads, conversion rates, and system uptime.
Capture customer feedback using in-app surveys, support interactions, and usage analytics.
Address any critical issues in a stabilization sprint post-launch.
Conduct a post-implementation review to capture lessons learned and identify reusable assets for future rollouts.

## Slide 17: Resources:
People:
Project Manager
Product Owner
Scrum Master
Agile Development Team
UX/UI Designer
Procurement & Supply Chain Specialist
QA/Test Engineers
Local Market Analysts

## Slide 18: Resources:
Time:
Phase | Activities | Estimated Duration
Discovery & Requirements | Stakeholder workshops, requirement gathering, persona creation, backlog setup | Weeks 1–4
Vendor Evaluation & Selection | RFPs, demos, evaluations, finalization of contracts and SLAs | Weeks 3–6
Agile Development & Prototyping | MVP design and development, iterative sprints, testing | Weeks 5–16
User Training & Change Management | Develop training content, conduct workshops, change readiness checks | Weeks 13–18
Operational Setup & Support Design | Set up supply chain, logistics, support processes, dashboard integration | Weeks 14–20
Go-Live & Stabilization | Soft launch, monitor KPIs, stabilize systems, collect feedback | Weeks 21–24

## Slide 19: Resources:
Time:
Sprint Structure
Sprint Length: 2 weeks
Number of Sprints: 6 Agile Sprints
Sprints 1–3: Core MVP (UI, product listing, cart, local sourcing setup)
Sprints 4–5: Integrations (payments, logistics, analytics, support)
Sprint 6: Final refinements, UAT, pre-Go-Live checklist

## Slide 20: Resources:
Time:
Sprint Structure
Key Milestones
Week 4: Product backlog finalized
Week 6: Vendors selected and onboarded
Week 10: MVP ready for internal demo
Week 18: Training completed
Week 21: Go-Live
Week 24: Project closure and lessons learned workshop

## Slide 21: Resources:
Budget:
Cost Category | Description | Estimated Cost
Software Development | Agile-based development of localized website and mobile application (iOS/Android), backend systems | ₹25,00,000
Third-Party Licenses | CMS, payment gateway integrations, cloud services (e.g., AWS, Firebase) | ₹5,00,000
Vendor Services | External vendors for app development, logistics integration, UI/UX design | ₹10,00,000
Infrastructure & Hosting | Cloud infrastructure setup, storage, databases, performance monitoring tools | ₹3,00,000
Procurement Setup Costs | Local sourcing network setup, vendor onboarding, supplier contracts | ₹4,00,000

## Slide 22: Resources:
Budget:
Cost Category | Description | Estimated Cost
Training & Change Management | Training programs, documentation, workshops, onboarding internal teams | ₹2,00,000
Marketing & Localization | Content localization, SEO, initial digital marketing campaigns in the new region | ₹6,00,000
Compliance & Legal | Local legal consultancy, licensing, and food safety regulatory compliance | ₹2,00,000
Travel & Site Visits | Vendor site audits, local office setup inspections, supply chain evaluation | ₹2,00,000
Contingency Reserve | Buffer for unforeseen costs (approx. 10% of total budget) | ₹6,00,000

## Slide 23: Risks:
User Resistance to Change: Employees, vendors, or partners may resist adopting new digital systems or operational processes due to familiarity with existing tools and workflows in other countries.
Regulatory Compliance Delays: Navigating local food safety regulations, digital commerce laws, and taxation rules may take longer than expected, potentially delaying product launch.
Localization Challenges: Inaccurate translation, cultural mismatches, or overlooked local nuances in the app, website, or marketing could negatively affect customer experience.
Integration Failures: Technical integration between new digital systems and existing platforms (ERP, logistics, CRM) may result in data sync issues, order delays, or system downtime.

## Slide 24: Risks:
Vendor Underperformance: Local vendors (for raw materials, packaging, or delivery) may not meet quality standards, delivery schedules, or cost expectations, affecting product availability.
Cost Overruns: The project may exceed its allocated budget due to unexpected costs in technology, compliance, or logistics, especially during initial market adaptation.
Data Privacy & Security Breaches: Inadequate implementation of data protection protocols could lead to non-compliance with local laws and compromise user trust.
Limited Visibility into Local Market: Lack of real-time, accurate market data could lead to poor decisions regarding product demand, pricing, or marketing campaigns.

## Slide 25: Dependencies:
Timely Vendor Selection and Onboarding: The project’s progress relies heavily on the timely selection and contract finalization with local development, logistics, and supply vendors.
Availability of Skilled Local Resources: Successful setup of localized operations depends on the availability of trained personnel for warehousing, delivery, and customer support in the target country.
Third-Party Tool Integration: Core functionalities such as payment processing, supply chain tracking, and CRM require seamless integration with third-party tools and platforms.

## Slide 26: Dependencies:
Internal Resource Allocation: The success of Agile sprints and overall coordination depends on the availability of internal team members (developers, product owners, testers) from both IT and business departments.
Legal and Regulatory Approval: The Go Live date and operational rollout are dependent on securing required licenses, food safety approvals, and digital compliance certifications.
IT Infrastructure Readiness: Hosting environments, staging servers, and production configurations must be ready and tested prior to deployment of any digital systems.

## Slide 27: Thank you
Sramana Bhattacharya
02/07/2025
sramanabhattacharya337@gmail.com