## Slide 1: Proposal
Project Title : Online Dairy Products Store
Prepared By : Varshini Thoudishetty
Date : 26/09/2025
Organization : DD Dairy Farm
Online Agriculture Products Store Project

## Slide 2: Executive Summary
Purpose
Facilitate remote customers to buy Milk, Paneer, Curd, Ghee and Cheese directly from manufacturers.
Success
Easy-to-use web/mobile platform, seamless order and delivery process, secure payments.
Value
DD Dairy Farm stands for quality, freshness, animal welfare, sustainability, and customer trust.

## Slide 3: Situation / Problem / Opportunity
Situation: Rising demand for fresh and hygienic milk products in both rural and urban areas.
Problem: Traditional dairy practices result in low productivity, inconsistent quality, and supply chain gaps.
Opportunity: By adopting modern dairy farming techniques, DD Dairy Farm can ensure high-quality products, expand market reach, and achieve sustainable profitability.

## Slide 4: Purpose Statement (Goals):
Dairy farming has been a traditional livelihood in rural India, but many small farmers face challenges like low milk yield, poor storage facilities, and lack of market access.
Consumers are increasingly demanding fresh, hygienic, and chemical-free milk products.
DD Dairy Farm is established to bridge this gap by introducing modern farming practices, ensuring quality production, and creating a sustainable supply chain.
The project aligns with broader goals of rural employment, community development, and food security while building a profitable business model.

## Slide 5: Project Objectives:
Adopt Modern Dairy Practices – Use mechanized milking, cooling, and hygienic storage methods.
High-Yield Cattle & Nutrition – Introduce well-bred buffaloes/cows and ensure balanced feed with veterinary care.
Value-Added Products – Produce curd, ghee, paneer, and other milk-based items to diversify income.
Efficient Supply Chain – Establish local collection, packaging, and doorstep delivery to urban and rural markets.
Sustainability Measures – Use cow dung for biogas/manure and implement water conservation practices.
Technology Integration – Implement digital tools for cattle health tracking, inventory, and customer orders.

## Slide 6: Project Deliverables
Well-Established Dairy Farm Infrastructure – Cattle sheds, storage facilities, and mechanized milking system.
Healthy & Productive Cattle Herd – High-yield cows/buffaloes with proper veterinary care.
Daily Fresh Milk Supply – Consistent delivery of hygienic milk to consumers.
Value-Added Products – Production of curd, ghee, paneer, and other dairy products.
Efficient Distribution Network – Local and urban supply chain for timely product delivery.
Sustainability Initiatives – Use of dung for manure/biogas and eco-friendly practices.
Employment Generation – Jobs for local community and training in modern dairy practices.

## Slide 7: Success Criteria
Daily Milk Production Targets Met – Achieve planned liters of milk per day from healthy cattle.
High Product Quality – Maintain hygienic, fresh, and chemical-free milk and dairy products.
Customer Satisfaction – Positive feedback, repeat buyers, and growing customer base.
Sustainability Goals – Effective use of dung for manure/biogas and eco-friendly farming practices.
Profitability – Steady increase in revenue and reduction in wastage.
Community Impact – Job creation and support for local farmers.

## Slide 8: Methods / Approach
1. Animal Rearing
Selection of high-yield, disease-resistant buffalo breeds
Balanced nutrition: fodder, grains, and mineral supplements
Routine veterinary check-ups and vaccinations
2. Milking & Milk Handling
Hygienic manual or machine milking techniques
Immediate cooling and proper storage of milk
Regular testing for milk quality (fat content, bacterial count)
3. Farm Management
Maintain detailed records of health, breeding, and milk yield
Breeding through natural or artificial insemination
Efficient waste management: converting dung into fertilizer or biogas
4. Technological Approaches
Use of farm management software for tracking data
IoT devices to monitor animal health and milk production
5. Sustainability Practices
Organic feed practices
Water conservation and recycling
Energy efficiency via solar panels or biogas systems

## Slide 9: Resources Required
Resource Type | Examples / Details
Human Resources | Farm Manager, Workers, Veterinarian, Nutritionist, Admin/Accounts Staff
Physical Resources | Land, Animal Housing, Milking & Feeding Equipment, Storage Facilities, Vehicles
Animal Resources | Buffalos, Cows, Goats, Breeding Stock, Replacement Animals
Financial Resources | Capital Investment, Operating Expenses (feed, wages, electricity), Contingency Fund
Technological Resources | Farm Management Software, Milking & Cooling Technology, Feed & Waste Management Tools
Natural Resources | Water, Fodder/Grass, Sunlight, Air
Knowledge & Training Resources | Training Programs, Best Practice Guides, Consultancy Services

## Slide 10: Risks & Dependencies
Category | Risks | Dependencies
Operational | - Supply chain interruptions - Inventory spoilage - Order fulfillment errors - Staff shortage | - Reliable suppliers for feed & packaging - Skilled farm and delivery staff
Technical | - Website/app downtime - Payment gateway failures - Cybersecurity threats - Poor user experience | - Stable hosting & e-commerce platform - Integration with payment & logistics systems
Financial | - Fluctuating costs of feed & logistics - Low sales conversion - High operational costs | - Consistent revenue from online sales - Efficient cost management & budgeting
External / Regulatory | - Changes in food safety or e-commerce regulations - Natural disasters affecting livestock - Competition from other dairy stores | - Compliance with government regulations - Backup plans for natural disasters - Competitive pricing & marketing strategies

## Slide 11: Conclusion / Recommendation
Conclusion:
DD Dairy Farm Online Store connects farm-fresh dairy products directly to customers.
Enhances operational efficiency, market reach, and revenue consistency.
Proper risk management ensures reliability and trust.
Recommendations:
Invest in Technology: Secure, robust, and user-friendly online platform.
Strengthen Supply Chain: Reliable suppliers and cold chain logistics.
Focus on Quality & Compliance: Regular checks and regulatory adherence.
Implement Marketing Strategies: Social media, local campaigns, loyalty programs.
Monitor Performance: Track sales, customer behavior, and operational efficiency.

## Slide 12: Q&A
Contact details :8919988566
Open floor for discussion

## Slide 13
Thank You