## Slide 1: LMS Module for Online Learning
By Samuel John
Date: 24th September 2025

## Slide 2: SITUATION:
During the Covid-19 pandemic, schools were forced to shut down physical classrooms due to government regulations.
The Sun School had no digital platform for conducting live online classes, though it was already using MyClassboard for ERP and finance modules.
Students from Grade 1 to Grade 10 needed an effective way to continue their education remotely.

## Slide 3: SITUATION:
The school management decided to leverage the existing MyClassboard ecosystem to build a secure LMS module for live online classes and assessments by integrating Zoom or Microsoft Teams to conduct online sessions seamlessly.
Secure role-based access had to be provided for students, teachers, academic coordinators, and admins.
Attendance and academic performance needed to be tracked digitally and reported in real time.

## Slide 4: PROBLEM:
Disruption of learning due to the sudden closure of physical classrooms. And No existing platform to manage live online teaching, scheduling, and student engagement.
Loss of revenue because parents were reluctant to pay fees without visible academic progress.
Data security concerns, as using open platforms directly could allow outsiders to join sessions.
Teachers and students had varying levels of technical expertise, making adoption of new systems challenging.

## Slide 5: OPPORTUNITY:
Build a custom LMS module integrated with the existing MyClassboard ERP, creating a one-stop solution for the school.
Enable seamless live classes with Zoom/Teams integration while maintaining data privacy and security.
Provide role-based dashboards for students, teachers, academic coordinators, and administrators.
Automate attendance tracking and generate real-time reports for decision-making. Introduce online tests and performance tracking, ensuring continuous academic assessment.

## Slide 6: OPPORTUNITY:
Improve parent trust and fee collection by demonstrating structured and consistent online learning.
Strengthen The Sun School’s digital transformation roadmap, positioning it for future blended learning models.
Build a scalable solution that MyClassboard can later offer to other schools, opening new revenue streams.

## Slide 7: PURPOSE STATEMENT:
The primary purpose of this project is to design and implement a comprehensive Learning Management System (LMS) module within the existing MyClassboard platform to ensure uninterrupted education for students of The Sun School during the Covid-19 pandemic and beyond. This initiative aims to bridge the gap created by the closure of physical classrooms, enable secure and efficient online learning, and maintain academic continuity while also supporting the school’s operational and financial stability.

## Slide 8: PROJECT OBJECTIVES:
Create a robust and user-friendly Learning Management System (LMS) within the existing MyClassboard platform to conduct live online classes securely. And enable students from Grade 1 to Grade 10 to continue their education seamlessly during pandemic disruptions or other emergencies.
Provide separate login portals for students, teachers, academic coordinators, and administrators to ensure data privacy and controlled access.

## Slide 9: PROJECT OBJECTIVES:
Build a centralized scheduling module to assign teachers to specific classes and sections while preventing time overlaps and resource conflicts.
Embed Zoom and Microsoft Teams within the LMS so teachers and students can access live sessions directly through the application without external links.
Implement an automated attendance capture mechanism for each session, with reporting available by class, section, teacher, and subject.

## Slide 10: PROJECT OBJECTIVES:
Create analytical dashboards to give coordinators and administrators insights into attendance, class participation, and academic performance.
Offer visibility into student learning progress to parents, improving trust and ensuring steady fee collection.
Build the LMS as a scalable solution that can support blended learning models and be extended to other schools partnered with MyClassboard.

## Slide 11: SUCCESS CRITERIA:
Successful implementation of separate logins for students, teachers, academic coordinators, and administrators, ensuring data privacy and preventing unauthorized access.
100% of planned live classes for Grades 1–10 are conductedwithout technical interruptions or scheduling conflicts.
The scheduling system accurately maps teachers to subjects,sections, and time slots, with no overlaps or double bookings.

## Slide 12: SUCCESS CRITERIA
Zoom and Microsoft Teams are fully integrated into the LMS, allowing teachers and students to join sessions directly through the portal without external links.
Attendance for each class session is captured automatically and accurately, with real-time reports. Coordinators, Teachers and administrators can generate detailed attendance, performance, and usage reports by class, section, teacher, and subject.
At least 90% of students and teachers actively use the platform within the first three months of deployment.

## Slide 13: SUCCESS CRITERIA
Parents report increased satisfaction and trust, resulting in a measurable improvement in fee collection rates.
The solution is scalable to accommodate future hybrid/blended learning models and can be extended to other schools using MyClassboard.
Post-implementation, there are no critical technical issues or downtime exceeding agreed service levels.

## Slide 14: METHODS & APPROACHES
Waterfall Methodology is used to develop this module. Each phase will be completed sequentially, with clear deliverables before moving to the next phase. This ensures proper planning, documentation, and controlled execution.
Project team has aligned to work for this project which has 9-10 members including Developers, Testers, PM, DB Admin, NW Admin.
Requirements Gathering & Analysis: Where the elicitation techniques like brainstorming, requirements workshop, JAD Session have been applied with school management, academic coordinators, teachers, and MyClassboard team and prepared BRD and RTM.
System Design: Convert business requirements into technical design specifications. Plan integration with Zoom and Microsoft Teams APIs. Will define DB structure for Classes, Sections, Schedules, Attendance records and Student Performance data. And will prepare System Design Document (SDD).

## Slide 15: METHODS & APPROACHES
Development: Set up the Development environment using MyClassboard's existing infrastructure and develop core modules like User Management, Class Scheduling, Video Conferencing Integration (Zoom API's into the LMS), Attendance Automation, Analytics Dashboards. And conduct Unit Testing to validate functionality of each component.
Testing: Will conduct different types of testing like Integration testing, System Testing, UAT, to ensure that system meets requirements with no defects before deployment. And then we get UAT sign-off document confirming the system is ready for deployment.
Deployment: Will Deploy the LMS module to live the production environment and migrate student & teacher data from existing ERP to LMS. Will generate and distribute secure login credentials for all users and conduct training sessions for teachers, coordinators and admins. Will create End User Manual for students and parents in both English & Telugu on how to access the Online Live Classes.
Monitor system performance and user adoption and provide helpdesk support for technical issues faced by teachers, students or parents.

## Slide 16: RESOURCES:
People: Requires a cross-functional team of 8-10 members from The Sun School and MyClassboard working collaboratively. Project Sponsor for budgeting, approvals and high level decision making. Business Analyst for requirement gathering, documentation, stakeholder communication and UAT Coordination. Skilled UI/UX designer to design, skilled and experienced developers to build and code LMS modules and integration. Testers for testing, bug tracking and QA. And technical team for post deployment and to conduct training.
Time: Since this is a Waterfall project, timelines for each phase must be clearly defined before starting the next phase. And the delivery of the software will be in 10 weeks and it might defer if there's any change request happens in the middle of the project.
Budget: The budget should cover the development, licensing, infrastructure and training costs.
  Development Cost:
  Licensing Fees: Zoom & Microsoft Teams integration licenses.
  Infrastructure Costs: Servers, Hosting, Cloud storage and backup.
  Training Costs: Sessions for teachers, coordinators and admins.

## Slide 17: RESOURCES:
Other Resources: Devices for stakeholders like laptops or PC with webcam and headsets. Cloud storage for storing attendance reports and assessment reports and video conferencing data. Training materials which includes User Manual, Tutorial videos and FAQ's to access Online Classes. Communication Tools like WhatsApp groups, email or school communication portal for updates.
Technologies Required:
  JavaScript
  Node.js
  MySQL
  Zoom & Microsoft Teams API
  Google Cloud Storage
  Custom BI Dashboards
  LMS Dashboards
  Google Docs

## Slide 18: RISKS AND DEPENDENCIES:
RISKS:
Poor adoption of LMS by teachers and students due to low technical skills.
Data security breach exposing student/teacher information
Technical issues with Zoom or Microsoft Teams APIs during integration
Internet connectivity issues during live classes, especially for rural students
System downtime during peak class hours
Mismanagement of class schedules leading to overlaps or conflicts

## Slide 19: RISKS AND DEPENDENCIES:
DEPENDENCIES:
Completion of student and teacher data intgration from the ERP before LMS go-live
Timely feedback from academic coordinators and teachers during UAT
Proper integration with MyClassboard’s existing ERP modules (Finance, Attendance, etc.)
Availability of Zoom and Microsoft Teams API keys and documentation
Internet bandwidth availability for live classes
Training materials readiness before deployment
Budget approval and fund release by school management

## Slide 20: THANK YOU