AGILE DOCUMENTS

Document 1: Definition of Done

Definition of Done (DoD) is a shared understanding within the Scrum team of what it means for work to be considered complete. The DoD ensures that every backlog item meets agreed standards of quality, functionality, and acceptance criteria before being delivered.

The DoD acts as a checklist for the team, reducing ambiguity, ensuring consistent quality, and aligning delivery expectations across stakeholders.

Levels of Definition of Done

- User Story Level: Applied to individual backlog items (features or enhancements).

- Sprint Level: Ensures all work within a sprint is integrated, tested, and potentially shippable.

- Release Level: Ensures all features are production-ready, compliant, and meeting business objectives.

Checklist for DoD

The following criteria must be fulfilled before a backlog item is considered “Done”:

- All acceptance criteria of the User Story are met.

- Code is written, reviewed (peer code review), and merged with the main branch.

- Unit tests are created and passed with ≥ 80% coverage.

- Functional and integration tests are executed and passed.

- No critical/severe defects remain open.

- Compliance/security checks are performed (data encryption, audit logs, RBI/NHB requirements).

- Documentation (user guide, release notes, technical notes) is updated.

- Product Owner reviewed and accepted the story

- Feature ok-ed by Product Owner.

- Assumptions of the user story are met.

- Automated/manual tests performed on supported devices and browsers.

- Feature reviewed and ok-ed by UX designer.

- UI/UX consistency verified with design guidelines.

- Meets quality criteria defined for the release.

- Deployed successfully to a test environment identical to production.

- Deployment verified.

- Documentation (user guide, technical, release notes) updated.

Document 2- Product Vision

| Scrum Project Name: | Loan Operation System Enhancement – Kotak Mahindra Bank Ltd |  |  |
| --- | --- | --- | --- |
| Venue: | Kotak Mahindra Bank Project Office |  |  |
| Date: 24/09/2025 | Start time: 12:00 PM | End time: 2:00PM | Duration: 2 hrs |
| Client: | Kotak Mahindra Bank Ltd |  |  |
| Stakeholder list: |  |  |  |
| 1) Head of Retail Loan Operations |  |  |  |
| 2) Compliance Officer (RBI/NHB Reporting) |  |  |  |
| 3) IT Department Head |  |  |  |
| 4) Risk & Audit Manager |  |  |  |
| 5) Branch Loan Officers Representative |  |  |  |
| 6) Customer Service Head |  |  |  |
| Scrum Team |  |  |  |
| Scrum Master: | SR |  |  |
| Product owner: | NJ- likely from Loan Operations/Business Side |  |  |
| Scrum Developer 1: | JK- Backend Specialist |  |  |
| Scrum Developer 2: | SJ- Frontend/UI Specialist |  |  |
| Scrum Developer 3: | PK- QA/Test Automation Engineer |  |  |
| Scrum Developer 4: | KM- Integration/API Specialist |  |  |
| Scrum Developer 5: | MS- Data & Reporting Specialist |  |  |

| Vision: | Our vision is to create a modern, automated, and scalable Loan Operation System that simplifies loan origination, disbursement, servicing, collections, and compliance reporting. The overarching goal is to improve operational efficiency, customer satisfaction, and regulatory compliance while supporting the bank’s digital transformation journey. |  |  |  |
| --- | --- | --- | --- | --- |
| Target group |  | Needs | Product | Value |
| Market Segment: Retail and SME loan management segment within the Indian banking industry. Target Users: Internal users: Loan officers, branch managers, compliance teams, audit and risk teams, IT operations staff. External users (indirect beneficiaries): Retail customers, SME borrowers, and collection agents. |  | Problem: Current system has high manual dependency, limited automation, and slow adaptability to regulatory changes, leading to delays, compliance risks, and customer dissatisfaction. Solution / Benefit: The enhanced system provides: -Faster loan processing and disbursement. -Automated compliance reporting for RBI/NHB. -Improved data accuracy, auditability, and reduced operational risks. -Self-service and transparency for customers. | An enhanced Loan Operation System with integrated workflows, real-time dashboards, automation, and regulatory compliance features. Desirability: -Provides seamless digital loan servicing experience. -Reduces loan turnaround time (TAT). -Offers predictive analytics for risk and collections. Feasibility: Yes – With Agile Scrum delivery, modular architecture, and integration with existing banking systems, the product is technically feasible. | Company Benefit: -Strengthens Kotak Mahindra Bank’s competitive edge in retail and SME lending. -Ensures regulatory compliance, avoiding penalties and reputational risks. -Enhances operational efficiency, reducing costs of manual interventions. Business Goals: --Reduce loan processing time by at least 30%. -Enhance customer satisfaction scores through faster loan servicing. -Improve regulatory compliance reporting accuracy to 100%. Business Model: -Internal efficiency gains - reduced operational costs. -Faster disbursements - higher loan portfolio growth. -Better compliance - lower risk exposure and penalties. -Enhanced customer experience- increased retention and cross-sell opportunities. |

Document 3: User stories

| User Story 1 | Task 1 – Develop loan application form UI & backend | Priority: HIGHEST |
| --- | --- | --- |
| As a customer I want to submit my loan application online So that I can apply without visiting the branch |  |  |
| BV: 1000 |  | CP: 5 |
| Acceptance Criteria: Online form available on web & mobile; mandatory fields validated; confirmation number generated. |  |  |

| User Story 2 | Task 2 – Build document upload & validation | Priority: HIGHEST |
| --- | --- | --- |
| As a customer I want to upload KYC documents digitally so that I don’t need to provide hard copies |  |  |
| BV: 1000 |  | CP: 5 |
| Acceptance Criteria: System accepts PDF/JPEG formats, validates against CKYC, provides success/failure message. |  |  |

| User Story 3 | Task 3 – Integrate CKYC API | Priority: HIGH |
| --- | --- | --- |
| As a loan officer I want to validate documents through CKYC so that I can reduce fraud risk. |  |  |
| BV: 1000 |  | CP: 8 |
| Acceptance Criteria: CKYC response received within 5 seconds, mismatched documents flagged |  |  |

| User Story 4 | Task 4 – Integrate CIBIL API | Priority: HIGHEST |
| --- | --- | --- |
| As a credit analyst I want to fetch CIBIL score automatically so that I can assess creditworthiness faster |  |  |
| BV: 500 |  | CP: 8 |
| Acceptance Criteria: CIBIL score fetched successfully, displayed on applicant profile. |  |  |

| User Story 5 | Task 5 – Aadhaar/PAN API integration | Priority: HIGH |
| --- | --- | --- |
| As a loan officer I want to auto-validate Aadhaar/PAN via API so that I can reduce manual errors |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: System confirms valid/invalid PAN/Aadhaar instantly, stores verification results |  |  |

| User Story 6 | Task 6 – Build pipeline dashboard | Priority: Medium |
| --- | --- | --- |
| As a branch manager I want to view the pipeline of loan applications so that I can monitor productivity. |  |  |
| BV: 800 |  | CP: 6 |
| Acceptance Criteria: Dashboard displays pending/approved/rejected applications by branch |  |  |

| User Story 7 | Task 7 – Status tracking module | Priority: HIGH |
| --- | --- | --- |
| As a customer I want to track my loan application status online so that I know the progress. |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Customer portal shows real-time status with last update timestamp |  |  |

| User Story 8 | Task 8 – Sanction letter generation | Priority: Medium |
| --- | --- | --- |
| As a loan officer I want to auto-generate a loan sanction letter so that I can speed up Disbursements |  |  |
| BV: 1000 |  | CP: 5 |
| Acceptance Criteria: Customer portal shows real-time status with last update timestamp |  |  |

| User Story 9 | Task 9 – E-sign integration | Priority: High |
| --- | --- | --- |
| As a customer I want e-signature support for loan documents so that I don’t have to visit the branch |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: Customers can sign digitally, signed document stored in system. |  |  |

| User Story 10 | Task 10 – Build system log | Priority: Medium |
| --- | --- | --- |
| As a compliance officer I want to log all loan applications with timestamps so that I can audit later |  |  |
| BV: 500 |  | CP: 4 |
| Acceptance Criteria: All application activities captured in system logs with user/time. |  |  |

| User Story 11 | Task 11 – Workflow automation | Priority: HIGH |
| --- | --- | --- |
| As a loan operations manager I want automated loan disbursement workflows so that payouts are faster |  |  |
| BV: 1000 |  | CP: 8 |
| Acceptance Criteria: Loan disbursement auto-triggered after approvals, tracked in dashboard |  |  |

| User Story 12 | Task 12 – Bank account validation | Priority: High |
| --- | --- | --- |
| As a system I want to validate account details before disbursement so that funds don’t fail |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: Invalid account flagged, disbursement blocked until corrected |  |  |

| User Story 13 | Task 13 – Voucher generation | Priority: High |
| --- | --- | --- |
| As a finance officer I want a disbursement voucher auto-generated so that I can reconcile easily. |  |  |
| BV: 500 |  | CP: 4 |
| Acceptance Criteria: Voucher auto-generated after payout, available for download. |  |  |

| User Story 14 | Task 14 – SMS/email integration | Priority: High |
| --- | --- | --- |
| As a customer I want SMS confirmation after disbursement so that I know the loan is credited |  |  |
| BV: 500 |  | CP: 3 |
| Acceptance Criteria: SMS/email sent immediately after fund transfer. |  |  |

| User Story 15 | Task 15 – CBS API integration | Priority: High |
| --- | --- | --- |
| As a treasury officer I want integration with core banking so that disbursements are seamless |  |  |
| BV: 1000 |  | CP: 9 |
| Acceptance Criteria: Disbursement posted in CBS instantly, reconciliation accurate |  |  |

| User Story 16 | Task 16 – Approval workflow | Priority: High |
| --- | --- | --- |
| As a Manager I want to set approval hierarchies so that high-value cases require dual approval |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: Loans above threshold routed to 2nd approver automatically |  |  |

| User Story 17 | Task 17 – Tranche disbursement | Priority: Medium |
| --- | --- | --- |
| As a loan officer I want partial disbursement options so that I can release funds in tranches |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: Loan disbursement can be split into multiple tranches with audit trail |  |  |

| User Story 18 | Task 18 – Build audit trail | Priority: High |
| --- | --- | --- |
| As a compliance officer I want disbursement logs with audit trails so that I can trace every payout. |  |  |
| BV: 1000 |  | CP: 4 |
| Acceptance Criteria: Every disbursement transaction logged with time, user, reference |  |  |

| User Story 19 | Task 19 – Condition validation | Priority: High |
| --- | --- | --- |
| As a customer I want pre-disbursement conditions checked automatically so that I meet all requirements. |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: Disbursement blocked if conditions not met, customer notified |  |  |

| User Story 20 | Task 20 – Retry mechanism | Priority: Medium |
| --- | --- | --- |
| As a finance officer I I want failed disbursements to auto-retry so that manual intervention is reduced. |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: Failed disbursements retried up to 3 times before escalation |  |  |

| User Story 21 | Task 21 – ECS/NACH integration | Priority: High |
| --- | --- | --- |
| As a customer I want to set up auto-debit (ECS/NACH) for EMI so that I don’t miss payments. |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Customers can link bank accounts, EMIs auto-debited on due date, confirmation sent. |  |  |

| User Story 22 | Task 22 – Reminder system | Priority: High |
| --- | --- | --- |
| As a collections officer I want EMI reminders sent before due dates so that I can reduce defaults |  |  |
| BV: 1000 |  | CP: 4 |
| Acceptance Criteria: Reminder notifications sent 3 days before EMI due date via SMS/email |  |  |

| User Story 23 | Task 23 – Multi-channel notifications | Priority: High |
| --- | --- | --- |
| As a customer I want to receive EMI reminders across channels so that I don’t forget payments |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: Reminder delivered across selected channels, message logged in system |  |  |

| User Story 24 | Task 24 – Overdue report module | Priority: High |
| --- | --- | --- |
| As a branch manager I want to view overdue EMI reports so that I can monitor NPAs |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: Dashboard displays list of overdue customers with overdue amount & days |  |  |

| User Story 25 | Task 25 – Recovery escalation rules | Priority: High |
| --- | --- | --- |
| As a collections officer I want overdue accounts to auto-escalate to recovery teams so that action is fast. |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: Accounts >30 days overdue routed to recovery queue automatically. |  |  |

| User Story 26 | Task 26 – Prepayment module | Priority: High |
| --- | --- | --- |
| As a customer I want to prepay my loan partially so that I can reduce interest burden |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Prepayment accepted, EMI schedule updated instantly. |  |  |

| User Story 27 | Task 27 – Foreclosure workflow | Priority: High |
| --- | --- | --- |
| As a loan officer I want to process foreclosure requests digitally so that I can close loans faster |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Foreclosure processed within system, NOC auto-generated. |  |  |

| User Story 28 | Task 28 – Repayment schedule module | Priority: Medium |
| --- | --- | --- |
| As a customer I want to download repayment schedules so that I know future EMI dates and amount |  |  |
| BV: 500 |  | CP: 4 |
| Acceptance Criteria: PDF repayment schedule downloadable from portal |  |  |

| User Story 29 | Task 29 – Bounce detection | Priority: High |
| --- | --- | --- |
| As a collections officer I want bounced EMI transactions flagged automatically so that I can follow up |  |  |
| BV: 500 |  | CP: 5 |
| Acceptance Criteria: Bounced EMI flagged, alert sent to collections officer |  |  |

| User Story 30 | Task 30 – Penalty calculator | Priority: Medium |
| --- | --- | --- |
| As a system I want to auto-calculate penalties for late EMI payments so that charges are accurate |  |  |
| BV: 500 |  | CP: 4 |
| Acceptance Criteria: Penalty added to overdue EMI based on defined interest rules |  |  |

| User Story 31 | Task 31 – Report generator | Priority: Highest |
| --- | --- | --- |
| As a compliance officer I want automated RBI/NHB reports generated so that submissions are timely. |  |  |
| BV: 1000 |  | CP: 8 |
| Acceptance Criteria: Reports generated in prescribed format, available for download & submission |  |  |

| User Story 32 | Task 32 – Transaction logging | Priority: High |
| --- | --- | --- |
| As an auditor I want audit trails for all loan transactions so that I can verify activities. |  |  |
| BV: 500 |  | CP: 6 |
| Acceptance Criteria: Every transaction logged with user ID, timestamp, old/new values. |  |  |

| User Story 33 | Task 33 – AML rules engine | Priority: High |
| --- | --- | --- |
| As a compliance officer I want suspicious transactions flagged so that I can meet AML norms |  |  |
| BV: 1000 |  | CP: 8 |
| Acceptance Criteria: System flags transactions crossing AML thresholds & alerts compliance |  |  |

| User Story 34 | Task 34 – Performance reporting | Priority: Medium |
| --- | --- | --- |
| As a manager I want branch-wise performance reports so that I can assess business growth |  |  |
| BV: 500 |  | CP: 7 |
| Acceptance Criteria: Reports generated by branch, product, time-period with KPIs. |  |  |

| User Story 35 | Task 35 – Risk analytics engine | Priority: High |
| --- | --- | --- |
| As a risk officer I want portfolio risk analytics o so that I can identify high-risk borrowers |  |  |
| BV: 1000 |  | CP: 9 |
| Acceptance Criteria: Risk reports with delinquency rates & probability of default generated monthly. |  |  |

| User Story 36 | Task 36 – Data masking & consent mgmt. | Priority: High |
| --- | --- | --- |
| As a compliance officer I want GDPR/data privacy compliance o so that customer data is protected |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Customer data masked/anonymized, consent captured, access restricted. |  |  |

| User Story 37 | Task 37 – Branch performance dashboard | Priority: Medium |
| --- | --- | --- |
| As a branch manager I want a dashboard showing disbursement, collections, and NPAs so that I can track performance |  |  |
| BV: 500 |  | CP: 6 |
| Acceptance Criteria: Dashboard shows KPIs updated daily, exportable in PDF/Excel. |  |  |

| User Story 38 | Task 38 – Collateral module | Priority: High |
| --- | --- | --- |
| As a Credit user I want a to check the collateral details so that I can calculate LTV |  |  |
| BV: 1000 |  | CP: 6 |
| Acceptance Criteria: System should reflect the collateral details along with address, MV, COP, FSV. |  |  |

| User Story 39 | Task 39 – RBAC setup | Priority: High |
| --- | --- | --- |
| As a system admin I want role-based access control so that sensitive data is protected |  |  |
| BV: 1000 |  | CP: 7 |
| Acceptance Criteria: Users restricted to relevant modules; unauthorized access blocked/logged |  |  |

| User Story 40 | Task 40 – Chatbot integration | Priority: medium |
| --- | --- | --- |
| As a customer I want chatbot support for loan queries so that I get instant help |  |  |
| BV: 500 |  | CP: 4 |
| Acceptance Criteria: Chatbot answers FAQs, routes complex queries to human support. |  |  |

Document 4: Agile PO Experience

The Product Owner (PO) plays a crucial role in bridging the gap between business stakeholders and the Scrum team. The PO owns the product vision, prioritizes requirements, and ensures the delivered solution aligns with business goals, market demand, and customer expectations.

Responsibilities of the Product Owner

- Market Analysis

- Analyze the market demand for enhanced loan operations.

- Conduct a competitive study on similar banking solutions in the market.

- Identify customer pain points such as delayed disbursements, manual paperwork, and compliance issues.

- Enterprise Analysis

- Perform due diligence on opportunities to enhance loan servicing.

- Assess ROI and feasibility of proposed enhancements.

- Identify regulatory requirements (RBI/NHB compliance) impacting the product.

- Product Vision and Roadmap

- Create a product vision aligned with Kotak Mahindra Bank’s strategy of digital transformation.

- Define a product roadmap with high-level features (loan onboarding, disbursement automation, EMI management, compliance reporting, dashboards).

- Align roadmap milestones with market needs and business goals.

- Managing Product Features

- Prioritize features and enhancements based on criticality and ROI.

- Manage stakeholder expectations by balancing business value vs. complexity.

- Refine and split features into Epics and User Stories.

- Managing Product Backlog

- Maintain a well-prioritized product backlog.

- Reprioritize backlog items based on stakeholder feedback or changing regulations.

- Group backlog items into Epics, Features, and Stories for sprint planning.

- Managing Overall Iteration Progress

- Participate in Sprint Planning to set sprint goals and commit to backlog items.

- Review daily progress and collaborate with the Scrum Master to remove impediments.

- Conduct Sprint Review sessions with stakeholders for feedback.

- Participate in Sprint Retrospectives with the Business Analyst to identify improvements.

Experience in Handling Sprint Meetings

- Sprint Planning Meeting: Defined sprint goals and selected backlog items.

- Daily Scrum Meeting: Ensured transparency on priorities and clarified requirements when needed.

- Sprint Review Meeting: Demonstrated completed functionality and gathered stakeholder feedback.

- Sprint Retrospective Meeting: C ollaborated to improve processes and backlog clarity.

- Backlog Refinement Meeting: Groomed the backlog with updated priorities, acceptance criteria, and dependencies.

Experience in Creating User Stories

Learned to create user stories with: Story No., Tasks, Priority,  Acceptance Criteria, Business Value (BV), Complexity Points (CP).

Example:
As a loan officer, I want to validate customer documents digitally so that I can reduce loan processing delays.

Product Owner as Liaison Across the Organization

- Acted as a bridge between business stakeholders and the Scrum team.

- Ensured all stakeholders (operations, compliance, IT, customer service) remained informed about progress.

- Translated business needs into actionable backlog items for the Scrum team

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog

| User Story ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | As a customer, I want to submit my loan application online so that I can apply without visiting the branch | Task 1 – Develop loan application form UI & backend | Highest | 500 | 5 | Sprint 1 |
| US02 | As a customer, I want to upload KYC documents digitally so that I don’t need to provide hard copies | Task 2 – Build document upload & validation | Highest | 500 | 5 | Sprint 1 |
| US03 | As a loan officer, I want to validate documents through CKYC so that I can reduce fraud risk | Task 3 – Integrate CKYC API | High | 500 | 13 | Sprint 1 |
| US04 | As a credit analyst, I want to fetch CIBIL score automatically so that I can assess creditworthiness faster | Task 4 – Integrate CIBIL API | High | 200 | 8 | Sprint 1 |
| US05 | As a loan officer, I want to auto-validate Aadhaar/PAN via API so that I can reduce manual errors | Task 5 – Aadhaar/PAN API integration | High | 100 | 5 | Sprint 6 |
| US06 | As a branch manager, I want to view the pipeline of loan applications so that I can monitor productivity | Task 6 – Build pipeline dashboard | Medium | 200 | 5 | Sprint 2 |
| US07 | As a customer, I want to track my loan application status online so that I know the progress | Task 7 – Status tracking module | High | 500 | 8 | Sprint 2 |
| US08 | As a loan officer, I want to auto-generate a loan sanction letter so that I can speed up disbursements | Task 8 – Sanction letter generation | Medium | 500 | 5 | Sprint 2 |
| US09 | As a customer, I want e-signature support for loan documents so that I don’t have to visit the branch | Task 9 – E-sign integration | High | 500 | 13 | Sprint 2 |
| US10 | As a compliance officer, I want to log all loan applications with timestamps so that I can audit later | Task 10 – Build system log | Medium | 200 | 3 | Sprint 2 |
| US11 | As a loan ops manager, I want automated loan disbursement workflows so that payouts are faster | Task 11 – Workflow automation | High | 200 | 8 | Sprint 3 |
| US12 | As a system, I want to validate account details before disbursement so that funds don’t fail | Task 12 – Bank account validation | High | 500 | 8 | Sprint 3 |
| US13 | As a finance officer, I want a disbursement voucher auto-generated so that I can reconcile easily | Task 13 – Voucher generation | High | 200 | 3 | Sprint 3 |
| US14 | As a customer, I want SMS confirmation after disbursement so that I know the loan is credited | Task 14 – SMS/email integration | High | 200 | 3 | Sprint 3 |
| US15 | As a treasury officer, I want integration with core banking so that disbursements are seamless | Task 15 – CBS API integration | High | 500 | 13 | Sprint 6 |
| US16 | As a manager, I want to set approval hierarchies so that high-value cases require dual approval | Task 16 – Approval workflow | High | 500 | 5 | Sprint 3 |
| US17 | As a loan officer, I want partial disbursement options so that I can release funds in tranches | Task 17 – Tranche disbursement | Medium | 500 | 8 | Sprint 9 |
| US18 | As a compliance officer, I want disbursement logs with audit trails so that I can trace payouts | Task 18 – Build audit trail | High | 500 | 5 | Sprint 6 |
| US19 | As a customer, I want pre-disbursement conditions checked automatically so that I meet requirements | Task 19 – Condition validation | High | 200 | 5 | Sprint 6 |
| US20 | As a finance officer, I want failed disbursements to auto-retry so that manual intervention is reduced | Task 20 – Retry mechanism | Medium | 200 | 5 | Sprint 6 |
| US21 | As a customer, I want to set up auto-debit (ECS/NACH) for EMI so that I don’t miss payments | Task 21 – ECS/NACH integration | High | 500 | 8 | Sprint 4 |
| US22 | As a collections officer, I want EMI reminders sent before due dates so that I can reduce defaults | Task 22 – Reminder system | High | 500 | 5 | Sprint 4 |
| US23 | As a customer, I want to receive EMI reminders across channels so that I don’t forget payments | Task 23 – Multi-channel notifications | High | 200 | 5 | Sprint 4 |
| US24 | As a branch manager, I want to view overdue EMI reports so that I can monitor NPAs | Task 24 – Overdue report module | High | 50 | 3 | Sprint 4 |
| US25 | As a collections officer, I want overdue accounts to auto-escalate so that action is fast | Task 25 – Recovery escalation rules | High | 100 | 8 | Sprint 4 |
| US26 | As a customer, I want to prepay my loan partially so that I can reduce interest burden | Task 26 – Prepayment module | High | 200 | 13 | Sprint 7 |
| US27 | As a loan officer, I want to process foreclosure requests digitally so that I can close loans faster | Task 27 – Foreclosure workflow | High | 500 | 8 | Sprint 7 |
| US28 | As a customer, I want to download repayment schedules so that I know future EMI details | Task 28 – Repayment schedule module | Medium | 50 | 5 | Sprint 7 |
| US29 | As a collections officer, I want bounced EMI transactions flagged so that I can follow up | Task 29 – Bounce detection | High | 100 | 3 | Sprint 7 |
| US30 | As a system, I want to auto-calculate penalties for late EMI payments so that charges are accurate | Task 30 – Penalty calculator | Medium | 20 | 3 | Sprint 7 |
| US31 | As a compliance officer, I want automated RBI/NHB reports so that submissions are timely | Task 31 – Report generator | High | 500 | 13 | Sprint 5 |
| US32 | As an auditor, I want audit trails for all loan transactions so that I can verify activities | Task 32 – Transaction logging | High | 200 | 13 | Sprint 5 |
| US33 | As a compliance officer, I want suspicious transactions flagged so that I can meet AML norms | Task 33 – AML rules engine | High | 200 | 13 | Sprint 8 |
| US34 | As a manager, I want branch-wise performance reports so that I can assess growth | Task 34 – Performance reporting | Medium | 100 | 8 | Sprint 5 |
| US35 | As a risk officer, I want portfolio risk analytics so that I can identify risky borrowers | Task 35 – Risk analytics engine | High | 500 | 13 | Sprint 9 |
| US36 | As a compliance officer, I want GDPR/data privacy compliance so that customer data is protected | Task 36 – Data masking & consent mgmt | High | 500 | 5 | Sprint 8 |
| US37 | As a branch manager, I want a dashboard showing disbursement/collections/NPAs so that I can track | Task 37 – Branch performance dashboard | Medium | 200 | 8 | Sprint 8 |
| US38 | As a credit user, I want to check collateral details so that I can calculate LTV | Task 38 – Collateral module | High | 200 | 21 | Sprint 5 |
| US39 | As a system admin, I want role-based access control so that sensitive data is protected | Task 39 – RBAC setup | High | 500 | 5 | Sprint 8 |
| US40 | As a customer, I want chatbot support for loan queries so that I get instant help | Task 40 – Chatbot integration | Medium | 100 | 3 | Sprint 9 |

Sprint Backlog

Sprint 1

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US01 | As a customer, I want to apply for a loan digitally so that I can save time and avoid branch visits. | Enable online loan application submission | Developer 1 | Done | 5 |
| US02 | As a customer, I want to upload documents digitally so that I can complete my loan application online. | Document upload & validation | Developer 2 | Done | 5 |
| US03 | As a loan officer, I want to auto-verify customer KYC so that I can reduce manual checks. | CKYC/NPCI integration | Developer 3 | Done | 13 |
| US04 | As a customer, I want to track my loan application status so that I stay informed. | Application tracking dashboard | Developer 4 | Done | 8 |

Sprint2

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US06 | As a branch manager, I want to view the pipeline of loan applications so that I can monitor productivity | Task 6 – Build pipeline dashboard | Developer 5 | Done | 5 |
| US07 | As a customer, I want to track my loan application status online so that I know the progress | Task 7 – Status tracking module | Developer 2 | Done | 8 |
| US08 | As a loan officer, I want to auto-generate a loan sanction letter so that I can speed up disbursements | Task 8 – Sanction letter generation | Developer 3 | Done | 5 |
| US09 | As a customer, I want e-signature support for loan documents so that I don’t have to visit the branch | Task 9 – E-sign integration | Developer 4 | Done | 13 |
| US10 | As a compliance officer, I want to log all loan applications with timestamps so that I can audit later | Task 10 – Build system log | Developer 1 | Done | 3 |

Sprint 3

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US11 | As a loan ops manager, I want automated loan disbursement workflows so that payouts are faster | Task 11 – Workflow automation | Developer4 | Done | 8 |
| US12 | As a system, I want to validate account details before disbursement so that funds don’t fail | Task 12 – Bank account validation | Developer5 | Done | 8 |
| US13 | As a finance officer, I want a disbursement voucher auto-generated so that I can reconcile easily | Task 13 – Voucher generation | Developer2 | Done | 3 |
| US14 | As a customer, I want SMS confirmation after disbursement so that I know the loan is credited | Task 14 – SMS/email integration | Developer 4 | Done | 3 |
| US16 | As a manager, I want to set approval hierarchies so that high-value cases require dual approval | Task 16 – Approval workflow | Developer 1 | Done | 5 |

Sprint 4

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US21 | As a customer, I want to set up auto-debit (ECS/NACH) for EMI so that I don’t miss payments | Task 21 – ECS/NACH integration | Developer 1 | Done | 8 |
| US22 | As a collections officer, I want EMI reminders sent before due dates so that I can reduce defaults | Task 22 – Reminder system | Developer 5 | Done | 5 |
| US23 | As a customer, I want to receive EMI reminders across channels so that I don’t forget payments | Task 23 – Multi-channel notifications | Developer 2 | Done | 5 |
| US24 | As a branch manager, I want to view overdue EMI reports so that I can monitor NPAs | Task 24 – Overdue report module | Developer 3 | Done | 3 |
| US25 | As a collections officer, I want overdue accounts to auto-escalate so that action is fast | Task 25 – Recovery escalation rules | Developer 4 | Done | 8 |

Sprint 5

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US31 | As a compliance officer, I want automated RBI/NHB reports so that submissions are timely | Task 31 – Report generator | Developer 3 | Done | 13 |
| US32 | As an auditor, I want audit trails for all loan transactions so that I can verify activities | Task 32 – Transaction logging | Developer 1 | Done | 13 |
| US34 | As a manager, I want branch-wise performance reports so that I can assess growth | Task 34 – Performance reporting | Developer 2 | Done | 8 |
| US38 | As a credit user, I want to check collateral details so that I can calculate LTV | Task 38 – Collateral module | Developer 5 & Developer 4 | Done | 21 |

Sprint 6

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US05 | As a loan officer, I want to auto-validate Aadhaar/PAN via API so that I can reduce manual errors | Task 5 – Aadhaar/PAN API integration | Developer 3& 4 | Done | 5 |
| US15 | As a treasury officer, I want integration with core banking so that disbursements are seamless | Task 15 – CBS API integration | Developer 4 | Done | 13 |
| US18 | As a compliance officer, I want disbursement logs with audit trails so that I can trace payouts | Task 18 – Build audit trail | Developer 3 | Done | 5 |
| US19 | As a customer, I want pre-disbursement conditions checked automatically so that I meet requirements | Task 19 – Condition validation | Developer 1 | Done | 5 |
| US20 | As a finance officer, I want failed disbursements to auto-retry so that manual intervention is reduced | Task 20 – Retry mechanism | Developer 2 | Done | 5 |

Sprint 7

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US26 | As a customer, I want to prepay my loan partially so that I can reduce interest burden | Task 26 – Prepayment module | Developer 4 | Done | 13 |
| US27 | As a loan officer, I want to process foreclosure requests digitally so that I can close loans faster | Task 27 – Foreclosure workflow | Developer 2 | Done | 8 |
| US28 | As a customer, I want to download repayment schedules so that I know future EMI details | Task 28 – Repayment schedule module | Developer 3 | Done | 5 |
| US29 | As a collections officer, I want bounced EMI transactions flagged so that I can follow up | Task 29 – Bounce detection | Developer 1 | Done | 3 |
| US30 | As a system, I want to auto-calculate penalties for late EMI payments so that charges are accurate | Task 30 – Penalty calculator | Developer 2 | Done | 3 |

Sprint 8

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US33 | As a compliance officer, I want suspicious transactions flagged so that I can meet AML norms | Task 33 – AML rules engine | Developer 1 | Done | 13 |
| US36 | As a compliance officer, I want GDPR/data privacy compliance so that customer data is protected | Task 36 – Data masking & consent mgmt | Developer 3 & 4 | Done | 5 |
| US37 | As a branch manager, I want a dashboard showing disbursement/collections/NPAs so that I can track | Task 37 – Branch performance dashboard | Developer 5 | Done | 8 |
| US39 | As a system admin, I want role-based access control so that sensitive data is protected | Task 39 – RBAC setup | Developer 2 | Done | 5 |

Sprint 9

| User Story ID | User Story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US17 | As a loan officer, I want partial disbursement options so that I can release funds in tranches | Task 17 – Tranche disbursement | Developer 1 & 5 | Done | 8 |
| US35 | As a risk officer, I want portfolio risk analytics so that I can identify risky borrowers | Task 35 – Risk analytics engine | Developer 2 & 3 | Done | 13 |
| US40 | As a customer, I want chatbot support for loan queries so that I get instant help | Task 40 – Chatbot integration | Developer 4 | Done | 3 |

Sprint Burndown Chart

Product Burndown Chart

Document 6: Sprint meetings

Meeting Type 1: Sprint Planning meeting

| Date | 26-09-2025 |
| --- | --- |
| Time | 10:00 AM – 12:10 PM |
| Location | Conference Room 2B / MS Teams (Hybrid) |
| Prepared By | Scrum Master |
| Attendees | Product Owner, Scrum Master, Development Team (Developers 1–5), Business Analyst, QA Lead |

Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Review Product Backlog and priorities | Product Owner | 20 mins |
| Define Sprint Goal | Scrum Master & Product Owner | 15 mins |
| Select User Stories for Sprint 1 | Development Team | 30 mins |
| Break down selected stories into tasks | Development Team | 30 mins |
| Estimate effort for each task | Development Team | 15 mins |
| Define team capacity and commitment | Scrum Master | 10 mins |
| Confirm Sprint Backlog | Scrum Master & Team | 10 mins |

Other Information

- Sprint Duration: 2 Weeks

- Sprint Goal: Deliver online loan application submission and KYC document upload features with initial integrations (CKYC, CIBIL).

Meeting Type 2: Sprint review meeting

| Date | 09-10-2025 |
| --- | --- |
| Time | 3:00 PM – 4:00 PM |
| Location | Conference Room 2B / MS Teams (Hybrid) |
| Prepared By | Scrum Master |
| Attendees | Product Owner, Scrum Master, Development Team (Developers 1–5), Business Analyst, QA Lead, Key Stakeholders |

| Sprint status | Things to demo | Quick updates | What’s next |
| --- | --- | --- | --- |
| Sprint 1 completed successfully | Online loan application submission form (Web + Mobile). | API integration with CIBIL score service is partially complete, will move to next sprint | Plan Sprint 2 |
| All 5 committed user stories are completed | Digital document upload with validation (PDF/JPEG formats) | UAT feedback collected from 10 pilot users – overall positive with suggestions for UI improvement | Target features: CIBIL integration, Aadhaar/PAN auto-validation, sanction letter generation, e-signature support. |
| Sprint Goal achieved: Online loan application submission and digital KYC upload with CKYC validation | Auto-KYC validation through CKYC | Security review pending for document upload service. | Focus on addressing UI feedback and ensuring data privacy compliance |
|  | Automated SMS/email notifications for application submission |  |  |

Meeting Type 3: Sprint retrospective meeting

| Agenda | What Went Well | What Didn’t Go Well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Team Collaboration | Good coordination between Dev, QA, and BA. | Daily stand-ups sometimes went beyond timebox. | How can we timebox better without losing valuable discussions? | Scrum Guide – Daily Scrum |
| Sprint Delivery | 5 stories completed, Sprint Goal achieved. | One story (sanction letter generation) slipped to next sprint. | Should we commit more stories and ensure 100% delivery? | Product Backlog (Sprint 1) |
| Quality | No major defects found during UAT. | Security review pending for document upload. | How can we integrate security checks earlier in sprint? | Definition of Done |
| Stakeholder Engagement | Stakeholders attended sprint review and gave valuable feedback. | Late API credentials from vendor delayed CIBIL integration. | How can we get vendor dependencies resolved earlier? | RACI Matrix / Vendor SLA |
| Tools & Processes | JIRA board usage improved transparency. | Some team members found burndown chart confusing. | Do we need training on interpreting agile metrics? | Agile Metrics Handbook |

Meeting Type 4: Daily Stand-up meeting

| Question | Name/Role | Week 1 (From26-09-2025 to 9-10-2015) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| What did you do yesterday? | Developer 1 | Worked on online loan application UI | Fixed form validation bugs | Completed integration with backend API | Wrote unit test cases | Deployed module to QA | UAT support | — |
|  | Developer 2 | Set up document upload service | Implemented OCR validation | Fixed upload error handling | Reviewed peer code | Prepared deployment package | Supported QA testing | — |
|  | Developer 3 | Integrated CKYC API | Debugged CKYC response issues | Completed CKYC validation | Updated error messages | Conducted API testing | Supported BA in demo prep | — |
|  | Developer 4 | Worked on loan status tracking dashboard | Linked status with workflow engine | Completed UI design | Wrote test cases for dashboard | Fixed UI alignment issues | UAT support | — |
|  | Developer 5 | Created database tables for loan applications | Wrote stored procedures | Optimized queries | Conducted DB performance test | Prepared DB migration scripts | Deployed DB changes | — |
| What will you do today? | Developer 1 | Complete UI polishing | Write unit tests | Support QA in bug fixing | Prepare for Sprint Review | Assist with demo | Close pending tasks | — |
|  | Developer 2 | Write test cases for upload | Fix QA bugs | Enhance OCR validation | Prepare demo | Conduct peer review | Support Sprint Review | — |
|  | Developer 3 | Conduct CKYC UAT | Document API flows | Support compliance testing | Fix defects | Demo preparation | Retrospective notes | — |
|  | Developer 4 | Finalize dashboard | Conduct UAT with BA | Fix feedback items | Prepare demo slides | Sprint Review demo | Close backlog item | — |
|  | Developer 5 | Validate DB reports | Fix DB-related bugs | Support integration | Performance testing | Provide DB extracts for review | Wrap up sprint work | — |
| What (if any) is blocking your progress? | Developer 1 | None | Waiting for QA feedback | None | None | None | None | — |
|  | Developer 2 | Pending OCR library update | None | None | None | None | None | — |
|  | Developer 3 | Delay in CKYC sandbox credentials | None | None | None | None | None | — |
|  | Developer 4 | Dependency on backend API | None | None | None | None | None | — |
|  | Developer 5 | Delay in DB access from infra team | None | None | None | None | None | — |