## Slide 1
Enhancement of Saksham Application
Enhanced Loan Management System
Prepared By : Mayur Mange Date : 01/10/2025
Axis Bank

## Slide 2
Situation
Currently, in the Saksham application, only basic Banking Operation related work can be done
For Loan - employees need to check eligibility using multiple tools, refer to policy documents, and verify details through various departments. There is no Centralized System that is automated and documented in one place. It is a time-consuming process and also increases the chances of calculation errors which leads to inconsistent decisions across branches.

## Slide 3
Problem Statement
Title : Challenges Identified
1. Time-consuming process due to manual data validation and cross-checking.
2. Lack of transparency in the loan approval workflow — difficult to track application status.
3. Limited data accessibility — employees need to refer to different systems for eligibility, salary details, and approval status.
4. Higher error chances in eligibility calculations and approvals.
5. No automated alerts or notifications for pending approvals or disbursements.
6. Absence of real-time reporting and analytics for management review.

## Slide 4
Opportunity
Introducing an enhanced module Enhanced Loan Management System (ELMS)
1. Automate the end-to-end loan workflow inside Saksham.
2. Improve employee experience and reduce turnaround time.
3. Enhance decision-making with real-time data, reports, and audit trails.
4. Reduce processing time by 70%

## Slide 5
Purpose Statement
The purpose of this project is to design and implement enhanced functionalities within the Saksham with Enhanced Loan Management System to improve efficiency, accuracy, and user experience for both employees and customers. The new features will automate eligibility checks, streamline loan processing workflows, and introduce real-time dashboards for performance tracking.
By implementing these improvements, employees will experience up to 40% reduction in manual data processing time, enabling faster decision-making and better customer service. Customers will benefit from quicker loan approvals, transparent eligibility criteria, and an improved digital experience, aligning with the organization’s vision of operational excellence and digital transformation.

## Slide 6
Project Objectives
1. Automate Customer Loan Eligibility
Implement rule-based algorithms to instantly validate customer loan applications using parameters like income, credit history, account balance, and banking relationship.
2. Develop Customer Loan Dashboard
Provide a unified interface where customers can submit applications, track loan status in real time, and view repayment schedules digitally.
3. Integrate with Core Banking System (CBS)
Connect with existing banking systems to fetch account, transaction, and KYC data for automated processing and reduce manual interventions.
4. Real-Time Reporting & MIS Analytics
Provide management with dashboards showing loan applications, approval rates, repayment schedules, and trend analysis for better decision-making.
5. Workflow Automation & Reduced Processing Time
Replace manual verification steps with system-driven checks, reducing customer loan processing time by up to 35%.
6. Notification & Alerts System
Configure automated SMS, email, or in-app alerts for each stage of the loan lifecycle: application received, verification, approval/rejection, and repayment reminders.

## Slide 7
Success Criteria
Efficiency Improvement: Automation of manual eligibility checks will reduce employee workload by up to 40%, allowing staff to focus on complex cases rather than repetitive tasks.
Reduced Errors: System-driven verifications will lower human error in loan approvals by approximately 30%.
Faster Processing: Staff can manage more loan applications in less time, reducing overall turnaround by 35%.
Customers get Faster Loan Approvals and better experience
Management gets better data driven insights with accurate data helps them in improved decision making
Aligns with banking needs and does not require new system migration.

## Slide 8
Waterfall Model/Approach
Requirement Gathering – 15 days
Collect feedback from stakeholders, Branch employees, customers, Management, It Team
Requirement Elicitation
Interviews with the bank staff to understand current process,
Workshops with stakeholders to prioritize features,
Document Analysis – Review current loan forms, approval workflows, and other reports to identity gaps
Observation – observe current loan process to understand delay, errors and steps
Surveys/ Questionnaire – Collect feedback from customers employees
3. Requirement Documentation
Business Requirement Document (BRD) – captures business needs, goals, and scope.
Functional Requirement Specification (FRS) – lists all system functionalities in detail.
Use Case Diagrams & Descriptions – visual representation of loan processes and interactions.
Data Flow Diagrams (DFD) – show data movement between modules and CBS integration.
Requirement Traceability Matrix (RTM) – maps requirements to design, development, and testing phases.
Stakeholder Sign-Off Forms – for approval of requirements and scope.

## Slide 9
Waterfall Model/Approach
Design – 15 days
To create a comprehensive system design that translates the gathered requirements into a functional and technical blueprint, ensuring smooth development, integration, and scalability of the ELMS system.
Define system architecture including frontend, backend, and database layers.
Identify modules and components:
Loan Eligibility Engine
Customer Dashboard
Notifications & Alerts Module
MIS Reporting & Analytics
Plan integration points with Core Banking System (CBS) and other existing banking modules.
Define security architecture: role-based access, encryption, and audit logs.
Create detailed workflow diagrams for each module:
Loan application submission → Eligibility check → Approval/Rejection → Notification → MIS update
Design database schema and tables for customer loan data, eligibility rules, repayment schedules, and logs.
Define UI wireframes and layouts for dashboards, application forms, and notification screens.
Prepare API specifications for integration with CBS and notification services (email/SMS).
Design Reviews
Conduct peer and stakeholder reviews for HLD and LLD.
Validate design against requirements in BRD/FRS.
Incorporate feedback and finalize design documents.
Prototype Development
Create a small prototype or mockup for critical modules like the customer dashboard and loan eligibility engine.
Helps stakeholders visualize workflow before full development.

## Slide 10
Waterfall Model/Approach
Development : 1.5 Months
Key Activities:
1. Environment Setup:
  Configure development servers, databases, and tools.
  Assign access rights to developers.
2. Module Development:
  Build individual components such as dashboards, forms, and reporting modules.
  Implement business logic and integrate with backend systems.
3. Database Implementation:
  Create and test database schemas, tables, and stored procedures.
4. Integration:
  Combine modules and ensure smooth data flow across all system components.
5. Unit Testing:
  Each module is tested individually by developers to verify correctness.
6. Code Review & Optimization:
  Peer review of code for quality, performance, and compliance with standards.

## Slide 11
Waterfall Model/Approach
Development : 1 - 1.5 Months
Deliverables:
Developed application modules
Unit test reports
Integration test results
Updated technical documentation
Outcome: A fully functional and integrated LMS enhancement system ready for system testing and UAT (User Acceptance Testing).
Module | Description | Developer Responsibility
Loan Eligibility Engine | Automates eligibility computation based on credit score, income, and loan type | Backend Developer
Customer Application Interface | Web-based form for customers to apply and check loan status | Frontend Developer
Document Upload & Verification | Secure upload of KYC, income proof, and address documents | Backend Developer
MIS & Reporting Dashboard | Generates real-time reports for management and auditors | Data Analyst / Developer
Notifications Module | Auto email/SMS alerts for application updates | Integration Developer

## Slide 12
Waterfall Model/Approach
Testing 15 – 20 days
Key Activities:
1. Test Planning:
  Prepare test strategy, test plan, and define testing scope.
  Identify test cases for functional and non-functional testing.
2. Test Case Execution:
  Perform Unit Testing, System Testing, and Integration Testing.
  Conduct Regression Testing after each bug fix to ensure stability.
3. User Acceptance Testing (UAT):
  Business users (from the bank) validate the system against real-life scenarios.
  Collect and implement feedback for final refinements.
4. Performance & Security Testing:
  Verify system response time, load handling, and security compliance.
5. Defect Tracking & Resolution:
  Record bugs in a defect log, prioritize, fix, and retest.
Deliverables:
Test Plan Document
Test Cases & Test Reports
Defect Log
UAT Sign-Off Report
Outcome: A verified, stable, and high-performing LMS enhancement system that meets business and customer requirements.

## Slide 13
Waterfall Model/Approach
User Acceptance Testing (UAT) Phase 5-7 Days
Key Activities:
1. UAT Planning:
  Identify UAT participants (branch staff, loan officers, and a few customer representatives).
  Define test scenarios and acceptance criteria based on real-life loan processes.
2. Execution of UAT:
  Users perform tests using real or dummy data to simulate actual workflows.
  Record all feedback, issues, and suggestions during testing.
3. Defect Resolution:
  Developers fix reported bugs or usability issues.
  Re-test the system after corrections.
4. Sign-Off:
  Obtain official sign-off from business users confirming the system is ready for deployment.
Deliverables:
UAT Test Plan
UAT Test Cases & Results Report
UAT Feedback Log
User Sign-Off Document
Outcome: Validated and approved ELMS enhancement system that meets user expectations and is ready for production deployment.

## Slide 14
Waterfall Model/Approach
Deployment Phase – 5-7 Days
Key Activities:
Pre-Deployment Setup:
  Prepare production servers and verify compatibility.
  Backup existing LMS data to prevent data loss.
System Deployment:
  Install and configure the new ELMS modules in the production environment.
  Migrate required data from the old system to the new version.
Post-Deployment Verification:
  Conduct sanity testing to ensure all functionalities work as expected.
  Monitor system performance for the first few days.
User Training & Communication:
  Conduct training sessions for employees and customer support teams.
  Share release notes and user manuals with all relevant stakeholders.
Deliverables:
Deployment Plan
Backup & Rollback Plan
Release Notes
Training Manuals
Outcome: A successfully deployed and operational ELMS enhancement system that is ready for real-time use by employees and customers.

## Slide 15
Resources
Role | Nos | Period
Project Manager | 1 | Full Project 4 Months
Java Developers | 5 | Design to Testing 2.5 Months
Database Admins | 2 | Design to Testing 1.75 Months
System Admins | 2 | Dev, Testing, UAT 1.25 Months
QA Testers | 3 | Testing and UAT 1.5 Months
Business Analyst | 1 | Entire Project 4 Months

## Slide 16
Total Duration 4 Months | Total Estimated Budget – 10,00,000
Phase | Duration | Key Activities | Estimated Cost (INR) | Remarks
1. Requirement Gathering & Analysis | Month 1 (Weeks 1–4) | • Identify business needs through stakeholder interviews • Draft and finalize BRD, SRS, and Use Cases • Conduct feasibility & gap analysis • Get sign-off from department heads | ₹2,00,000 | Extensive analysis ensures no scope gaps.
2. System Design Phase | Month 2 (Weeks 5–6) | • Prepare system architecture & data model • Create wireframes & UI mockups • Design module structure & workflows • Validate design with stakeholders | ₹1,50,000 | Involves BA, system architect, and lead developer.
3. Development Phase | Month 2–3 (Weeks 7–12) | • Backend & frontend coding • API integration with core banking systems • Unit testing by developers • Internal code reviews & optimization | ₹3,50,000 | Longest phase involving 3 developers + lead.
4. Testing Phase (QA & UAT) | Month 3 (Weeks 13–14) | • Functional & regression testing • UAT with selected staff • Performance testing • Bug fixing and documentation | ₹1,20,000 | Ensures system reliability & business accuracy.
5. Deployment Phase | Month 4 (Weeks 15–16) | • Final migration to production • Configuration setup • Access rights assignment • Training sessions for staff | ₹1,00,000 | Controlled rollout with backup plan.
6. Maintenance & Support (Post Go-Live) | Month 4 (Week 17 onward) | • 30-day hypercare support • Monitor system stability • Resolve post-go-live issues • Plan for next enhancement cycle | ₹80,000 (initial) | Transition to long-term maintenance phase.

## Slide 17
Other Resources :
Hardware
Dedicated Servers for Hosting the application and Database
Backup and Disaster recovery system
Software
Development tools (Java IDE’s, Database tools)
Automated email parsing tools
Certificate template design tools
Network
High Speed Internet connections
VPN’s or secure email gateways for handling clients data securely

## Slide 18
Deliverables:
Enhanced Loan Management System
Staff training materials & user manuals
Integration with existing credit bureau APIs
Pilot rollout in selected branches
User training guides
Later full rollout

## Slide 19
Risks and Dependencies
Technical Risk - The new ELMS features may face issues while connecting with the existing Saksham system. Dependency: API documents and test environment from IT team.
Data Migration Risk - Some customer data may get missed or duplicated while transferring records.
Dependency: Access to correct and clean old data.
Budget and Timeline Risk - If development or testing takes longer, cost may go beyond plan.
Dependency: Timely approvals from project sponsor.
4. Testing and Quality Risk - Some bugs may go unnoticed or system may slow down during peak usage.
Dependency: QA team and proper test setup.
5. Compliance Risk - Missing any RBI or audit rule may cause delay in approval.
Dependency: Legal and compliance team approval.
6. User Adoption Risk - Employees may take time to understand and use the new system.
Dependency: Support from HR for scheduling training sessions.

## Slide 20
Conclusion / Project Summary
The Enhanced Loan Management System (ELMS) is designed to modernize the current Saksham banking platform by improving efficiency, accuracy, and user experience for both employees and customers.
This enhancement will automate several manual loan-related activities and bring transparency to the process. By focusing on digital automation, data accuracy, and real-time access, the system aims to create a seamless experience within the organization.
The project follows the Waterfall Model, ensuring each phase — from requirement gathering to deployment — is completed with proper documentation and approval.
The enhancements are customer-focused, ensuring faster loan processing, fewer manual errors, and improved data visibility.
Employees will benefit from an easy-to-use interface, automated reports, and reduced workload.
Stakeholders gain real-time insights and performance tracking, improving decision-making and operational control.
Post-implementation, the system is expected to improve overall loan processing speed by 35–40%, and reduce manual intervention by 50%.