## Slide 1: Procurement Operations Lifecycle – Mount Sinai Healthcare
Business Process Analysis Using Waterfall Methodology
Presented by: [Your Name]
Business Analyst – Finance & Procurement Operations
Notes: Introduces purpose: structured procurement using Waterfall ensuring efficiency, compliance, and transparency.

## Slide 2: SITUATION - What situation created to develop this project .
Mount Sinai Healthcare, a major hospital network based in New York, USA, manages large-scale healthcare procurement involving medical equipment, consultants, software, and services & also maintenance.
Their existing procurement process was highly decentralized and manual, handled internally across multiple hospital departments. That was too much to handle .
This led to inconsistencies, delayed approvals, and poor visibility over budgets and payments.
Each department managed its own approvals, SOW / Quote validation, and fund allocations to create new request to get the purchase order numbers
No unified system existed to track CAPEX/OPEX usage across functions.
Stakeholders lacked real-time dashboards to monitor request status or vendor payments.
Fund validation, PO creation, invoice mapping took longer time.

## Slide 3: PROBLEM - What problems we faced during the initial phase of this project
Mount Sinai Healthcare, a major hospital network based in New York, USA, manages large-scale healthcare procurement involving medical equipment, consultants, software, and services & also maintenance.
Creating process flow digram/ Framing SOP or DTP for all the activities which we are handling & get it approved and signed by the client
Getting adapted to the new ERP – Tool and its functionality . There are around 2 main ERP Tools (Cloud – Client dedicated tool for request creation / Oracle )
Handling huge volumes (Inflow) for request creation & email queries
Cross validation of budget files (CAPEX/ OPEX) . Locating the correct budget approvers and routing it to them before the request creation.
Delays in approvals and misunderstanding of process ownership. Because of time zone.
Set up bi-weekly governance calls to align both onsite and offshore stakeholders.
Handling issues/ escalations and preparing ROOTCAUSE analysis
Approvers often missed emails, causing backlogs in fund request and invoice queues. So keep sending follow-up emails
Initially, there was no dashboard or KPI system to monitor request status, pending queues, or SLA adherence.
Leadership had no single source of truth for procurement performance

## Slide 4: OPPROTUNITIES
Thinking of advanced automation and workflow enhancements
Created weekly and monthly dashboards using ERP data extracts and Power BI reports.
Published KPI metrics — Approval turnaround time, PO-to-Invoice accuracy, SLA performance — for leadership review are in green.
Client appreciation emails for handling their monthly & daily activity without any noise / concerns.
With Accenture’s offshore team now experienced in Mount Sinai’s processes, the model can scale easily to include: Procurement for new departments or hospital acquisitions.
Additional finance functions (e.g., contract management, procurement analytics, accounts payable automation
The stable, documented, and automated workflow ensures strong audit readiness and regulatory compliance (HIPAA, SOX, internal finance policies).
Reduces audit exceptions to near zero.
Once stabilized, the Mount Sinai Procurement project transforms into a strategic platform for automation, analytics, and scalability. The standardized process, accurate data, and offshore delivery capability create long-term opportunities for Mount Sinai to improve cost efficiency, vendor trust, compliance control, and decision-making intelligence

## Slide 5: PURPOSE STATEMENT (GOALS)
To design, implement, and stabilize a standardized, audit-ready procurement process for Mount Sinai Healthcare that integrates finance, procurement, and IT functions — ensuring operational efficiency, budget control
Goals - Establish a consistent, end-to-end procurement framework covering SOW validation, request creation, PO generation, invoice approval, and payment release.
Purpose - To create request based on the SOW/ QUOTE / INVOICE and validating the fund code to be applied and to get the approval from the fund owner & also from IT Finance head & then once the Purchase Order gets generated , the PO Copy will be shared with the requestor to apply that with the respective Invoices to make payment for the services or maintenance or any physical shipment

## Slide 6: PROJECT OBJECTIVES
Project Initiation & Governance
Objective: align scope, roles, governance and measures of success with Mount Sinai. Key activities
Conduct workshops with Finance, Procurement, IT, requestors and vendors.
Map AS-IS processes (SOW validation, fund checks, request creation, PO, invoice).
Identify exceptions/rules for CAPEX vs OPEX.
Create SOPs / DTPs for every transaction type and exception case.
Define approval matrices, escalation rules and time windows (SLA).
Cleanse vendor master, fund codes, cost centers; de-duplicate records.
Run monthly performance reviews; convert improvement ideas into prioritized sprints or waterfall releases.

## Slide 7: SUCCESS CRITERIA
Process Standardization Achieved
A single, unified procurement workflow is successfully adopted across all Mount Sinai departments.
All SOWs, Quotes, and fund validations follow one approved SOP / DTP process.
Approval Turnaround Time Improved
Average approval turnaround time (from request creation → PO generation) reduced by ≥30% compared to baseline.
Accurate Fund Validation & Budget Control
100% of procurement requests validated against the correct CAPEX/OPEX fund codes before PO creation.
PO–Invoice Mapping Accuracy
≥95% of Invoices correctly mapped to their respective Purchase Orders
Real-Time Reporting & KPI Dashboard Availability
Request Creation Volume / Approval Turnaround time/ Que backlog/ PO Invoice accuracy / SLA
Audit Readiness & Compliance
Stakeholder & Vendor Satisfaction
Team Efficiency & Knowledge Transition

## Slide 8: Methods and Approaches
Requirement Gathering & Stakeholder Engagement
Identified and engaged key stakeholders — Finance approvers, Procurement leads, IT system admins, and Requestors across Mount Sinai. Document analysis (SOWs, Quotes, fund request forms). Used elicitation tech Document analysis (SOWs, Quotes, fund request forms)
Process Mapping and Analysis
Documented all manual steps in the existing procurement flow — from SOW validation to invoice payments.
Cross-Functional Coordination
Weekly stand-ups with finance, procurement, and IT leads.
Data Validation & Reporting Accuracy
Partnered with reporting teams to define KPI metrics:/ Approval turnaround time
Continuous Improvement & Future Roadmap
Analyzed monthly KPI trends to identify process improvement areas.
Compliance & Audit Controls

## Slide 9: Resources
BA gathers and validates requirements → with onsite Finance/Procurement teams. (QUOTE/ SOW/ RFP) along with fund code for request creation. Validates CAPEX/ OPEX Budget file
Solution Architect + Developers configure ERP workflows in test environment.
Testers validate the end-to-end procurement cycle (request → PO → invoice).
Reporting Analyst builds Power BI dashboard using ERP extracts.
Project Manager + BA review dashboards and workflows with stakeholders in governance calls.
Time – The project is a contract basis (Agreed for 2 Years (2024-2026). Renewal of the project will happen based on the Accenture (Service Provider) Performance.

## Slide 10: BUDGET OVERVIEW – Mount Sinai Procurement Project
Chart: 
| Resource Cost | Infrastructure & Tools | Training & Change | Travel & Governance | Contingency Reserve
Budget (USD) | 890000 | 178000 | 35000 | 40000 | 114000
Chart: 
| Resource Cost | Infrastructure & Tools | Training & Change | Travel & Governance | Contingency Reserve
Budget Distribution | 890000 | 178000 | 35000 | 40000 | 114000
Estimated Total Project Budget: ≈ $1.25 Million USD
Key Highlights:
• Total Project Cost ≈ $1.25 Million USD (12 months duration)
• Largest spend on Resource Costs (≈ 71%)
• Infrastructure & ERP licensing contributes ≈ 14%
• Balanced investment across Training, Governance & Contingency
• Post-Go-Live BAU operations expected ≈ $300K/year

## Slide 11: RISK & DEPENDENCIES
Knowledge Transition & Domain Understanding
Initial lack of domain knowledge about Mount Sinai’s healthcare procurement policies, vendor contracts, and compliance (HIPAA, SOX).
Conduct Knowledge transition session with client SME’s
ERP Tool & System Access Delays
Delay in provisioning ERP tool access (Client Cloud / Oracle) for offshore team.
Time Zone & Communication Gaps
  Time zone difference (New York vs India) caused delays in approvals, clarifications, and ticket resolution.
Real-time issue escalation was challenging in early stages.
Technology Integration Delays
Interface issues between Mount Sinai’s ERP and Power BI dashboards (data refresh lag, API limitations).