# Document 1: Definition of Done

### Purpose

### The Definition of Done (DoD) is a shared agreement within the project team to ensure that every backlog item, sprint, and release delivers the exact value and quality expected by the client. It acts as a checklist of conditions that must be satisfied before we mark any work as complete. This ensures transparency, consistency, and confidence in every deliverable of the Jewellery e-commerce Platform.

Scope

The Definition of Done will be applied at three levels in this project:

- User Story Level:  Every feature or requirement requested by the client.

- Sprint Level:  Completion of a group of user stories planned for each sprint.

- Release Level:  The combined delivery at the end of multiple sprints, ready for client use.

Agreed Definition of Done - Checklist

| Level of Work | Checklist Criteria | Explanation |
| --- | --- | --- |
| User Story | • All acceptance criteria are met • Code is reviewed and approved • Unit testing is completed with no critical issues • UI/UX matches agreed design • Functionality integrated with APIs where applicable | Ensures each story is functionally complete, tested, and aligned with client expectations. |
| Sprint | • All user stories planned for the sprint meet their DoD • Regression testing completed • No open high/critical defects • Demonstrated successfully in Sprint Review | Ensures that the sprint outcome is stable, functional, and ready for client feedback. |
| Release | • All sprints meet DoD • End-to-end system testing completed • Performance and security checks passed • Deployment checklist completed • Approved by Product Owner and Project Sponsor | Ensures the entire system is production-ready and safe for customer use. |

### Quality & Acceptance Alignment

- Acceptance Criteria - Each backlog item will only be marked as “Done” when it fully satisfies the business requirements shared by the client.

- Quality Criteria - The team will ensure bug-free, secure, and user-friendly delivery by following testing, code review, and UI/UX standards.

### Benefits for the Client

By following this Definition of Done, the project ensures that:

- Deliverables are consistent and measurable.

- No partial or incomplete features are presented.

- Quality and customer trust are maintained at every stage.

- Every sprint output is usable, even before the final release.

This Definition of Done will be followed by all team members throughout the project and will be visible in the shared project space for full transparency.


Document 2: Product Vision

Scrum Project Information

| Field | Details |
| --- | --- |
| Scrum Project Name | Jewellery E-Commerce Website Development |
| Venue | Client Office - Hyderabad & Online (Zoom/Teams/GMeet) |
| Date | 12th March 2025 |
| Start Time | 10:00 AM |
| End Time | 5:00 PM |
| Duration | Full Day (Project Kick-off) |
| Client | SHiNEDOVE Omni Channel Communications |
| Stakeholder List | CEO, Head of Operations, Head of Sales & Marketing, IT Manager, Finance Head, Jewellery Designers Representative. |

Scrum Team

| Role | Assigned Person |
| --- | --- |
| Scrum Master | Kamal Nandagopal |
| Product Owner | Kokila |
| Scrum Developer 1 | Frontend Developer |
| Scrum Developer 2 | Backend Developer |
| Scrum Developer 3 | UI/UX Designer |
| Scrum Developer 4 | QA Tester |
| Scrum Developer 5 | Database Engineer |

## Vision Statement

Our vision is to deliver a modern, secure, and scalable Jewellery E-Commerce platform that allows customers to seamlessly browse, customize, and purchase jewellery online while ensuring real-time inventory visibility, smooth order processing, and strong integration with payment & logistics systems. This vision aligns with your company’s strategy to expand digital reach, improve customer experience, and increase revenue from online channels.

Vision Framework

| Category | Guiding Questions | Project-Specific Input |
| --- | --- | --- |
| Target Group | • Which market segment does the product address? • Who are the target users and customers? | • Jewellery buyers across India customers. • Primary target: Women aged 25–45 (urban professionals & homemakers). • Secondary target: Gifting customers & corporate buyers. |
| Needs | • What problem does the product solve? • Which benefit does it provide? | • Provides a trusted digital platform for purchasing jewellery without store visits. • Ensures real-time inventory check and easy order tracking. • Offers personalized experience with design customization options. • Reduces dependency on physical store footfall. |
| Product | • What product is it? • What makes it desirable and special? • Is it feasible to develop the product? | • A scalable E-Commerce website for jewellery with advanced catalogue and secure payment gateway. • Special features: Real-time gold/silver price sync, certification for authenticity, integrated loyalty program. • Feasible with Agile iterations: MVP launch in 3 months, followed by feature enhancements. |
| Value | • How is the product going to benefit the company? • What are the business goals? • What is the business model? | • Expands market reach to Tier-1,2 & 3 cities • Business Goals: Increase online sales by 30% in first year, reduce store dependency by 20%. • Business Model: Direct-to-Customer online jewellery sales with upselling (custom designs, gift packs). |

- This product vision ensures alignment between your business objectives and our Agile execution.

- It clearly identifies who we are building for, why it matters, and how it will generate value for your organization.

- The structured approach under Target Group, Needs, Product, and Value provides both business clarity and technical feasibility assurance.

- This document will serve as the foundation for backlog prioritization, sprint planning, and release roadmaps.

Document 3: User stories

| User story No: 1 | Tasks: Implement secure login & signup | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to create an account securely so that I can access personalized features. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | User should be able to register/login with email or mobile OTP, and system validates credentials securely. |  |

| User story No: 2 | Tasks: Develop product catalog with categories | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to browse jewellery by categories so that I can easily find items of my interest. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Categories like Rings, Necklaces, Earrings should be visible with smooth navigation. |  |

| User story No: 3 | Tasks: Build advanced search function | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to search jewellery items using keywords so that I can quickly find specific products. |  |
| BV: High | CP: 4 |  |
| Acceptance Criteria | Search bar should return relevant items with predictive suggestions. |  |

| User story No: 4 | Tasks: Add product filters (price, metal, weight, design) | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to filter products by price, material, and design so that I can refine my selection. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Filters should instantly update product list without page reload. |  |

| User story No: 5 | Tasks: Display product detail page | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to view detailed product information so that I can make an informed purchase decision. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Page should show product description, price, images, certifications, and stock availability. |  |

| User story No: 6 | Tasks: Enable “Add to Cart” functionality | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to add items to my cart so that I can review before making payment. |  |
| BV: High | CP: 4 |  |
| Acceptance Criteria | Selected items must appear in the cart with price calculation and editable quantity. |  |

| User story No: 7 | Tasks: Implement secure checkout process | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want a smooth checkout process so that I can complete my purchase easily. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Checkout should include address, delivery options, and payment gateway integration. |  |

| User story No: 8 | Tasks: Integrate payment gateway | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to pay using multiple methods so that I can choose what’s convenient. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Options like Credit/Debit card, Net Banking, UPI should be available and functional. |  |

| User story No: 9 | Tasks: Implement “Buy Gold Now, Pay Later” (API Integration) | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to purchase gold using a “Pay Later” option so that I can manage my payments flexibly. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Partner API integration should allow EMI or delayed payment facility with instant confirmation. |  |

| User story No: 10 | Tasks: Add SIP (Systematic Investment Plan) feature | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want to set up a SIP for gold jewellery so that I can invest monthly and buy later. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | SIP dashboard should allow plan selection, monthly amount setup, and track accumulated value. |  |

| User story No: 11 | Tasks: Provide Jewellery Insurance option (API Integration) | Priority: Medium |
| --- | --- | --- |
| Value Statement | As a user, I want to insure my jewellery so that I feel secure about my purchase. |  |
| BV: Medium | CP: 5 |  |
| Acceptance Criteria | Insurance option should be available at checkout with API integration to insurance partner. |  |

| User story No: 12 | Tasks: Show order tracking | Priority: Medium |
| --- | --- | --- |
| Value Statement | As a user, I want to track my order status so that I know when my jewellery will be delivered. |  |
| BV: Medium | CP: 4 |  |
| Acceptance Criteria | Tracking info should show status updates from order placed to delivered. |  |

| User story No: 13 | Tasks: Wishlist feature | Priority: Medium |
| --- | --- | --- |
| Value Statement | As a user, I want to save items in my wishlist so that I can revisit them later for purchase. |  |
| BV: Medium | CP: 4 |  |
| Acceptance Criteria | User should be able to add/remove items to wishlist linked to their profile. |  |

| User story No: 14 | Tasks: Customer reviews & ratings | Priority: Medium |
| --- | --- | --- |
| Value Statement | As a user, I want to read/write reviews so that I can trust the product quality. |  |
| BV: Medium | CP: 4 |  |
| Acceptance Criteria | Ratings (1–5) and text reviews should appear under each product. |  |

| User story No: 15 | Tasks: Push notifications & alerts | Priority: Low |
| --- | --- | --- |
| Value Statement | As a user, I want to receive alerts for offers, order updates, and SIP reminders so that I stay informed. |  |
| BV: Medium | CP: 4 |  |
| Acceptance Criteria | Notifications should be configurable (email, SMS, app). |  |

| User story No: 16 | Tasks: Admin dashboard | Priority: High |
| --- | --- | --- |
| Value Statement | As an admin, I want to manage inventory, prices, and user orders so that the platform runs smoothly. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | Dashboard should allow adding products, updating stock, and monitoring sales. |  |

| User story No: 17 | Tasks: Security & compliance | Priority: High |
| --- | --- | --- |
| Value Statement | As a user, I want my personal and payment data to be secure so that I can trust the platform. |  |
| BV: High | CP: 5 |  |
| Acceptance Criteria | System should use encryption, OTP verification, and follow compliance standards (PCI-DSS). |  |

## Document 4: Agile PO Experience

1. Product Owner Vision for the Project

The Product Owner (PO) will act as the custodian of your business vision, ensuring that every feature delivered reflects both current market opportunities and long-term strategic goals. For this Jewellery E-Commerce platform, the PO will maintain focus on:

- Building a competitive online platform with unique offerings like Gold SIP, Pay Later, and Jewellery Insurance.

- Ensuring customer convenience and trust through secure transactions and reliable delivery.

- Creating a roadmap-driven product journey with phased releases for faster time-to-market.

2. Core Responsibilities of the Product Owner

| Responsibility Area | Detailed Approach for Your Project |
| --- | --- |
| Market Analysis | - Study customer buying behavior in jewellery online vs offline. - Benchmark against leading e-commerce jewellery competitors (e.g., CaratLane, Bluestone). - Identify gaps in features such as Pay Later EMI, Gold SIP Plans, and Insurance add-ons. - Evaluate regional demand (Hyderabad, Tier-1,2 & 3 cities) to tailor campaigns. |
| Enterprise Analysis | - Perform due diligence on jewellery e-commerce growth potential. - Validate investment through ROI models. - Recommend high-value partnerships (e.g., Insurance providers, Payment gateways). |
| Product Vision & Roadmap | - Vision: To become a trusted jewellery marketplace that balances affordability, trust, and modern payment flexibility. - Roadmap: • Phase 1 – MVP (3 months): Product catalogue, secure checkout, order tracking. • Phase 2 – Core Features (6 months): Gold SIP, Pay Later APIs, Digital Wallet. • Phase 3 – Enhancements (9–12 months): Insurance integration, AI-powered recommendations, loyalty rewards. |
| Managing Product Features | - Align with stakeholders on must-have vs nice-to-have features. - Define epics → features → user stories hierarchy. - Prioritize based on ROI, customer value, and regulatory needs. - Example: “Insurance Integration” may be high effort but provides strong differentiation. |
| Managing Product Backlog | - Maintain a dynamic backlog visible to all stakeholders. - Categorize into Epics (Payments, Insurance, Catalogue). - Prioritize continuously using MoSCoW (Must, Should, Could, Won’t). - Ensure backlog reflects both business priorities and technical feasibility. |
| Managing Iteration Progress | - Sprint Planning: Agree on sprint goals and commitment. - Daily Scrums: Ensure progress transparency. - Sprint Review: Showcase increments to stakeholders. - Retrospectives: Gather improvement points and refine processes. - Example: If Pay Later API testing is delayed, adjust backlog priorities for the next sprint. |

## 3. Agile Ceremonies Facilitated by the Product Owner

The PO ensures ceremonies are not just “meetings” but decision-making checkpoints:

- Sprint Planning - Align backlog items with sprint goals, negotiate priorities.

- Daily Scrum - Review blockers and support the Scrum Master in unblocking tasks.

- Sprint Review - Present sprint increment to stakeholders, gather live feedback.

- Sprint Retrospective - Identify learnings, refine user story detailing.

- Backlog Refinement - Break down epics, refine acceptance criteria, and adjust priorities.

## 4. User Story Development

Each User Story will include business-driven and measurable details:

| Attribute | Explanation (Example: Gold SIP Feature) |
| --- | --- |
| Story No. | US-012 |
| Tasks | API integration with SIP partner, UI design for SIP dashboard, Testing workflows. |
| Priority | High (critical business differentiator). |
| Acceptance Criteria | User should be able to subscribe to a SIP, view maturity date, and cancel anytime. |
| Business Value (BV) | Increase customer retention and recurring purchases. |
| Completion Points (CP) | 8 story points (medium-high effort). |

## 5. Backlog Hierarchy

| Epic ID | Epic Name | What this covers (scope of project) | Sample User Stories (from Doc-3) |
| --- | --- | --- | --- |
| E1 | Customer Accounts & Identity | Secure sign-up/login (OTP/email), profile, address book, KYC (if required for BNPL/SIP). | US-01 (Login/Signup) |
| E2 | Catalogue & Product Content | Categories, sub-categories (Gold, Silver, Diamonds, Gemstones), product data model, media gallery. | US-02 (Catalogue), US-05 (PDP) |
| E3 | Discovery (Search & Filters) | Keyword search, autosuggest, filters (price, weight, metal, purity, stone), sort options. | US-03 (Filters), US-04 (Search) |
| E4 | Cart & Wishlist | Add to cart, edit/remove, totals, wishlist add/move to cart. | US-06 (Cart), US-12 (Wishlist) |
| E5 | Checkout & Core Payments | Address selection, order summary, payment gateway (Cards/UPI/Net-banking), coupons, taxes, invoices. | US-07 (Checkout), US-08 (Payment), US-10 (Coupons) |
| E6 | Finance Partner – Buy Gold Now Pay Later (API) | BNPL eligibility check, plan selection, EMI schedule, consent, callbacks/webhooks, settlement. | US-09 (BNPL API) |
| E7 | Gold SIP (Systematic Investment Plan) | Plan creation, auto-debit, SIP ledger, pause/cancel, maturity redemption to purchase. | US-11 (SIP) |
| E8 | Insurance Partner – Jewellery Insurance (API) | Quote at checkout, premium calc, policy issuance, certificate PDF/email, claims entry point. | US-10 (Insurance API) |
| E9 | Orders, Logistics & Notifications | Order lifecycle, tracking, courier integration (status updates), email/SMS/WhatsApp notifications, reviews/ratings. | US-13 (Tracking), US-14 (Notifications), US-15 (Reviews) |
| E10 | Admin, CMS, Analytics & Reports | Admin console, product & price mgmt, inventory, promotions, dashboards, sales reports, SEO content blocks. | US-16 (Admin), US-08 (Reports) |

## 6. Product Roadmap

| Sprint | Dates | Primary Epics & Scope Delivered | Key Outcomes |
| --- | --- | --- | --- |
| Sprint 1 | 12 Mar – 08 Apr 2025 | E1, E2 (Foundations): Auth (OTP/email), Profile basics, Category tree, product schema, PDP skeleton, core UI kit. | Users can sign up/login; browse categories; basic product pages visible. |
| Sprint 2 | 09 Apr – 06 May 2025 | E3, E4: Search + autosuggest, filters & sort, Add to Cart, Wishlist. PDP complete with images/zoom/specs. | Complete discovery journey → add to cart & wishlist. |
| Sprint 3 | 07 May – 03 Jun 2025 | E5: Address book & checkout flow, payment gateway (Cards/UPI/Net-banking), coupons, price/tax calc, order confirmation/invoice. | End-to-end purchase with standard payments. |
| Sprint 4 | 04 Jun – 01 Jul 2025 | E6 (BNPL API): Eligibility check, plan options, EMI schedule view, consent screen, webhook handling; hardening of E5. | Buy Gold Now Pay Later fully available at checkout. |
| Sprint 5 | 02 Jul – 29 Jul 2025 | E7 (Gold SIP): Plan creation, auto-debit setup, SIP dashboard (ledger, next due), pause/cancel; start E8 (Insurance quote flow). | Gold SIP live; Insurance quote visible in checkout. |
| Sprint 6 | 30 Jul – 26 Aug 2025 | E8, E9, E10: Insurance policy issuance + certificate, full order tracking & notifications, Admin console (products/prices/inventory), analytics dashboards; full regression & security/perf tests, UAT & go-live prep. | Platform ready for UAT sign-off and go-live. |

## 7. Product Owner as the Liaison

The PO will ensure smooth communication between:

- Business Stakeholders - Validate business ROI and competitive positioning.

- Scrum Team - Clarify requirements and support sprint execution.

- Clients & Partners - Coordinate external dependencies (Payment APIs, Insurance partners).

## 8. Expected Outcomes for Your Project

By following this structured approach, the PO ensures:

- Faster Time-to-Market - MVP within 3 months with iterative feature delivery.

- High Business Alignment - Prioritization ensures maximum ROI.

- Customer-Centric Delivery - Features tailored for customer trust and convenience.

- Transparency - Clear backlog visibility, sprint reviews, and roadmap tracking.

Document 5: Product and sprint backlog and product and sprint burndown charts

As part of our Agile-Scrum implementation for the Jewellery E-Commerce Project, we have structured the backlog into Epics and User Stories aligned to your business priorities. The following backlog tables provide clear visibility of how requirements will be delivered across sprints.

Product backlog:

| User Story ID | User Story | Tasks | Priority | BV (Business Value) | CP (Complexity Points) | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US-01 | As a customer, I want to view jewellery categories so I can easily browse | Define categories, design catalogue layout, upload product data | High | 9 | 3 | Sprint 1 |
| US-02 | As a customer, I want to filter products by metal, price, weight | Build filter logic, UI integration, backend query setup | High | 10 | 5 | Sprint 1 |
| US-03 | As a customer, I want a product search bar | Design search field, integrate search API, testing | Medium | 8 | 3 | Sprint 2 |
| US-04 | As a customer, I want to add jewellery to cart & wishlist | Cart page design, backend linking, wishlist save function | High | 10 | 5 | Sprint 2 |
| US-05 | As a customer, I want secure checkout with multiple payment options | Payment gateway integration, EMI/BNPL setup, security compliance | High | 10 | 8 | Sprint 3 |
| US-06 | As a customer, I want to insure my jewellery during purchase | Integrate insurance API, option in checkout, test workflow | Medium | 9 | 6 | Sprint 3 |
| US-07 | As a customer, I want jewellery SIP option for savings | SIP module design, recurring payment setup, notifications | Medium | 8 | 7 | Sprint 4 |
| US-08 | As a customer, I want to give product reviews | Review form, approval system, display on product page | Low | 6 | 3 | Sprint 4 |
| US-09 | As a customer, I want to track my order | Order tracking page, SMS/email integration, status updates | High | 9 | 4 | Sprint 5 |
| US-10 | As an admin, I want to manage stock and sales reports | Admin dashboard, stock entry module, reporting tools | High | 10 | 7 | Sprint 6 |
| US-11 | As an admin, I want to generate invoices & handle returns/exchanges | Invoice generator, return policy integration, workflow setup | Medium | 8 | 5 | Sprint 6 |

Sprint backlog:

Sprint 1 – Foundational Features

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-01 | As a customer, I want to view jewellery categories | Define categories, upload sample product data, design catalogue UI | Frontend Developer | Completed | 8 hrs |
| US-02 | As a customer, I want to filter products by metal, price, etc. | Create filter logic, integrate with DB, test filtering functionality | Backend Developer | In Progress | 10 hrs |
| US-03 | As a customer, I want a product search bar | Design search UI, integrate with backend search API, testing | Full Stack Developer | To Do | 6 hrs |

Sprint 2 – Shopping Experience

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-04 | As a customer, I want to add jewellery to cart & wishlist | Cart page design, DB linking, wishlist save & retrieve | Frontend Developer | To Do | 12 hrs |
| US-05 | As a customer, I want secure checkout with multiple payment options | Payment gateway integration, EMI setup, encryption & PCI compliance checks | Backend Developer | To Do | 15 hrs |

Sprint 3 – Value Additions

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-06 | As a customer, I want to insure my jewellery during purchase | Integrate Insurance API, add checkbox in checkout, validate workflow | API Integration Specialist | To Do | 14 hrs |
| US-07 | As a customer, I want jewellery SIP option for savings | Design SIP plan module, recurring payment setup, notification scheduler | Backend Developer | To Do | 16 hrs |

Sprint 4 – Engagement & Trust

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-08 | As a customer, I want to give product reviews | Review form UI, admin approval workflow, display reviews on product page | UI/UX Designer | To Do | 8 hrs |
| US-09 | As a customer, I want to track my order | Order tracking page, integrate SMS/email updates, status display logic | Full Stack Developer | To Do | 12 hrs |

Sprint 5 – Customer Operations

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-10 | As an admin, I want to manage stock and sales reports | Admin dashboard, stock entry module, generate monthly/quarterly reports | Data Analyst / Backend Developer | To Do | 16 hrs |
| US-11 | As an admin, I want to generate invoices & handle returns/exchanges | Invoice generator, return request form, integration with refund. | Full Stack Developer | To Do | 14 hrs |

## Sprint 6 – Stabilization & Enhancements

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US-12 | As a customer, I want personalized recommendations | AI-based recommendation engine, product suggestion module | AI/ML Engineer | To Do | 15 hrs |
| US-13 | As a customer, I want push/email notifications for offers | Notification service integration, template creation, testing | Frontend Developer | To Do | 10 hrs |
| US-14 | As a system, I want automated performance and security monitoring | Monitoring tools setup, performance tuning, security vulnerability scan | DevOps Engineer | To Do | 18 hrs |

## Document 6: Sprint meetings

Meeting Type 1: Sprint Planning Meeting

## Meeting Details

| Date | Time | Location | Prepared By | Attendees |
| --- | --- | --- | --- | --- |
| 12th March 2025 | 10:00 AM – 12:00 PM | Project War Room – Conference Hall A / MS Teams (Hybrid) | Scrum Master | Product Owner, Scrum Master, BA, Development Team (5 members), QA Team (2 members) |

## Agenda Topics

| Topic | Presenter | Time Allotted |
| --- | --- | --- |
| Review of Product Backlog | Product Owner | 20 mins |
| Selection of Sprint Backlog Items | Scrum Team | 30 mins |
| Effort Estimation (Story Points) | Developers + QA | 40 mins |
| Sprint Goal Definition | Scrum Master | 15 mins |
| Finalization of Deliverables & Risks | BA + Product Owner | 15 mins |

## Other Information

| Observers | Resources | Special Notes |
| --- | --- | --- |
| Client Stakeholder (joined virtually) | Jira Board, Burndown Chart template, Product Backlog Document | Some stories dependent on 3rd party API integration marked as “Partial/In Progress” |

## Meeting Type 2: Sprint Review Meeting

## Meeting Details

| Date | Time | Location | Prepared By | Attendees |
| --- | --- | --- | --- | --- |
| 26th March 2025 | 3:00 PM – 4:30 PM | Client Office – Conference Room B / Zoom | Business Analyst | Product Owner, Scrum Master, Development Team, QA Team, Client Stakeholders |

## Sprint Review Agenda

| Sprint Status | Things to Demo | Quick Updates | What’s Next |
| --- | --- | --- | --- |
| Completed: 6 User Stories Incomplete: 2 Stories (due to dependency on API) | Jewellery Catalogue Filter Module Cart Checkout Functionality Product Image Zoom Feature | Minor defects raised in QA regression, fixed during sprint. | Plan to pick Payment Gateway Integration & Loyalty Points Module in Sprint 2. |

Meeting Type 3: Sprint Retrospective Meeting

Meeting Details

| Date | Time | Location | Prepared By | Attendees |
| --- | --- | --- | --- | --- |
| 27th March 2025 | 10:00 AM – 11:00 AM | Scrum Room / MS Teams | Scrum Master | Development Team, QA Team, Product Owner, BA |

Retrospective Agenda

| What went well | What didn’t go well | Questions Raised | Reference/Action Items |
| --- | --- | --- | --- |
| Good collaboration between QA & Dev | Dependency delay on Payment API | Can we have earlier confirmation from 3rd party vendors? | Client PO to follow up with vendor support |
| Daily stand-ups were crisp & clear | Sprint stories spilled over due to underestimation | Can estimation techniques be improved? | BA to refine backlog items with PO before Sprint Planning |
| Demo appreciated by stakeholders | Some rework in UI design alignment | Should we have mock-up approval step? | To add a UX checkpoint in Sprint 2 |

Meeting Type 4: Daily Stand-up Meeting (Week: 12th–18th March 2025)

What did you do yesterday?

| Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UI Developer | Designed Login Page UI | Worked on Product Catalogue screen | Fixed UI alignment issues | Integrated front-end with backend API calls | Prepared demo UI flow | – | – |
| Backend Developer | Set up Database schema | Developed API for Catalogue | Worked on Checkout API | Debugged authentication service | Code refactoring | – | – |
| QA Engineer | Created initial test cases | Tested Login & Registration | Reported 5 defects | Retested bug fixes | Regression testing | – | – |
| Business Analyst (BA) | Refined user stories with PO | Updated acceptance criteria | Clarified doubts with Dev Team | Supported QA in understanding scenarios | Prepared notes for Sprint Review | – | – |
| Product Owner (PO) | Reviewed backlog items | Prioritized catalogue stories | Aligned sprint scope with client | Attended client sync call | Final approval on demo items | – | – |

What will you do today?

| Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UI Developer | Work on Checkout Page | Testing with QA | Polish UI & fix defects | Assist QA with demo screens | Finalize UI for review | – | – |
| Backend Developer | API Testing | Link APIs with UI | Checkout validation | Optimize queries | Support QA in defects | – | – |
| QA Engineer | Continue test execution | Prepare demo checklist | Verify fixes | Execute regression | Prepare test summary | – | – |
| BA | Support PO in backlog grooming | Prepare Sprint Review doc | Attend stakeholder calls | Draft Sprint 2 backlog | Document feedback from Review | – | – |
| PO | Approve demo script | Review test results | Confirm feature readiness | Collect client feedback | Wrap up sprint review notes | – | – |

Any blockers?

| Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| UI Developer | Dependency on API data | – | – | Waiting for UX confirmation | – | – | – |
| Backend Developer | API documentation delay | – | – | – | – | – | – |
| QA Engineer | Test data dependency | – | – | – | – | – | – |
| BA | None | – | – | – | – | – | – |
| PO | Pending vendor response | – | – | – | – | – | – |