Document 1: Definition of Done

DOD:

- User Story is clearly defined and approved by the Product Owner.

- Code is reviewed and approved by at least one peer (peer review completed).

- APIs, database changes, and integrations are documented.

- Unit testing completed with ≥ 90% code coverage.

- Integration testing completed for linked modules (e.g., Sales ↔ Recruitment ↔ Payroll).

- Functional testing passed with all acceptance criteria met.

- Functional and technical documentation updated in the project repository.

- Code successfully deployed to staging environment without errors.

- UAT completed and approved by business stakeholders.

- Security and role-based access verified.

- Data integrity and consistency confirmed across modules.

- End-user training conducted.

- Performance meets system standards (response time, load handling).

Document 2- Product Vision

| Scrum Project Name: | Hubble Sales Module Enhancement (Requirements & Opportunities Workflow + KPI Dashboard Implementation) |  |  |
| --- | --- | --- | --- |
| Venue: | Miracle Software Systems |  |  |
| Date: July 1st, 2024 | Start Time: 10:00 AM | End Time: | Duration: |
| Stakeholder List: |  |  |  |
| Nag Mada – Director of Sales |  |  |  |
| Paul Byroj – Sales Regional Manager |  |  |  |
| Satish Bessetti – Sales Regional Manager |  |  |  |
| Prithviraj Naramsetty – Director of Recruitment |  |  |  |
| Santhosh Soni – Delivery Head |  |  |  |
| Pavani Eeti – Payroll Head |  |  |  |
| Chanakya Lokam – Business Owner |  |  |  |
| Scrum Team |  |  |  |
| Scrum Master: | Bharathi Ramchandram |  |  |
| Product Owner: | Samuel John |  |  |
| Scrum Developer 1: | Gnaneswar Rao |  |  |
| Scrum Developer 2: | Kavya Pasumarthi |  |  |
| Scrum Developer 3: | Manoj Das |  |  |
| Scrum Developer 4: | Aasha Panduri |  |  |
| Scrum Developer 5: | Amin Mohammed |  |  |
| Scrum Developer 6: | Chaitanya Kumar |  |  |

| Vision: To enhance the Hubble internal sales platform by automating the complete requirements and opportunities workflow and implementing a real-time KPI dashboard to track the sales process. |  |  |  |
| --- | --- | --- | --- |
| Target Group | Needs | Product | Value |
| Sales Team | Need a single platform to manage requirements, opportunities, and track performance metrics without using external tools or emails. | Enhanced Hubble Sales Module with automated requirement workflow and real-time KPI Dashboard. | Streamlined sales operations, improved productivity, and transparent performance tracking. |
| Delivery / Practice Heads | Need visibility into candidate shortlisting, interview progress, and approvals within the same system. | End-to-end tracking of recruitment and delivery activities in Hubble. | Improved decision-making, faster approvals, and reduced delays. |
| Payroll Team | Need access to approved profiles and rate details for billing without dependency on manual communication. | Automated status updates and data sharing within Hubble. | Reduced manual errors, quicker billing cycle, and data accuracy. |
| Management / Directors | Need real-time visibility of requirements & opportunities status and team performance, KPI achievements, and process efficiency. | KPI Dashboard showing team-wise and individual metrics (calls, requirements, NDAs, etc.). | Improved transparency, data-driven decisions, and effective performance evaluation. |

Document 3: User stories

| User Story No: 01 | Task: 01 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SALESPERSON I WANT TO POST NEW REQUIREMENT SO THAT RECRUITMENT TEAM CAN START SOURCING CANDIDATES |  |  |  |
| BV: 500 |  | CP: 3 |  |
| Acceptance Criteria: Requirement form should allow entry of title, technology, location, rate, and urgency. Once submitted, it should notify the Recruitment Head and respective Practice Head |  |  |  |

| User Story No: 02 | Task: 01 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance Criteria: Salesperson dashboard displays all requirements with real-time status (Open, Assigned, Interviewing, Selected, Billed). Last activity date and responsible user are visible. Notifications should be sent automatically for every step. |  |  |  |

| User Story No: 03 | Task: 01 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY HEAD I WANT TO REVIEW AND SHORTLIST CANDIDATES SO THAT ONLY SUITABLE CANDIDATES WILL MOVE FORWARD TO INTERVIEW |  |  |  |
| BV: 500 |  | CP: 5 |  |
| Acceptance Criteria: Delivery Head can approve or reject resumes, add remarks, and send feedback within Hubble. Notifications should be sent to recruiters and salespersons automatically. |  |  |  |

| User Story No: 04 | Task: 02 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY HEAD I WANT TO APPROVE THE FINAL SELECTED CANDIDATE AND DEFINE BILLING RATE SO THAT PAYROLL TEAM CAN PROCESS BILLING ACCORDINGLY |  |  |  |
| BV: 500 |  | CP: 5 |  |
| Acceptance Criteria: Delivery Head can mark a candidate as “Selected.” Hourly rate entry is mandatory for approval. Approved profile automatically becomes visible to Payroll. |  |  |  |

| User Story No: 05 | Task: 02 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A PAYROLL TEAM MEMBER I WANT TO ACCESS APPROVED CANDIDATE AND BILLING DATA IN HUBBLE SO THAT I CAN PROCESS INVOICES WITHOUT MANUAL DEPENDENCIES |  |  |  |
| BV: 500 |  | CP: 5 |  |
| Acceptance Criteria: Payroll team can view only approved profiles. Billing rate and project details are auto populated. Data export or API integration is available for payroll processing. |  |  |  |

| User Story No: 06 | Task: 02 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A USER I WANT TO RECEIVE AUTOMATED NOTIFICATIONS FOR ALL KEY WORKFLOWS SO THAT I STAY INFORMED WITHOUT MANUAL FOLLOWUPS |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance Criteria: Notifications trigger automatically for key status changes. Users will get emails for every key status changes. Notification history is stored for reference. |  |  |  |

| User Story No: 07 | Task: 03 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SALESPERSON I WANT TO VIEW MY PERSONAL KPI SO THAT I CAN TRACK MY PROGRESS TOWARDS MONTHLY TARGETS |  |  |  |
| BV: 200 |  | CP: 8 |  |
| Acceptance Criteria: Dashboard shows metrics achieved vs target. KPIs include discovery calls, L1/L2 calls, opportunities, NDAs, etc. KPI’s should be based on experience of salesperson (0-1 year, 1-3 years, 3+ years) Progress indicators and trend charts are available. |  |  |  |

| User Story No: 08 | Task: 03 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SALES MANAGER I WANT TO VIEW THE MONTHLY KPI DASHBOARD FOR OF TEAM SO THAT I CAN MONITOR PERFORMANCE AND IDENTIFY AREAS FOR IMPROVEMENT |  |  |  |
| BV: 500 |  | CP: 8 |  |
| Acceptance Criteria: Dashboard displays metrics: calls, activities, opportunities, requirements, NDAs. Filters for team member, month, and quarter are available. Data refreshes automatically in real time. |  |  |  |

| User Story No: 09 | Task: 04 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A MANAGEMENT MEMBER I WANT TO VIEW CONSOLIDATED AND INDIVIDUAL ANALYTICS OF SALES PERFORMANCE SO THAT I CAN MAKE DATA DRIVEN BUSINESS DECISIONS |  |  |  |
| BV: 500 |  | CP: 13 |  |
| Acceptance Criteria: Dashboard shows team-wide KPIs, individual KPIs, Monthly/Quarterly comparisons, and efficiency metrics. Export option for management reports is available. |  |  |  |

| User Story No: 10 | Task: 04 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SYSTEM ADMINISTRATOR I WANT TO MANAGE USER ROLES, PERMISSION & ACCESS TO THE MODULES SO THAT DATA EACH ROLE SEES ONLY RELEVANT INFORMATION |  |  |  |
| BV: 500 |  | CP: 5 |  |
| Acceptance Criteria: Admin can add/edit/delete users and assign roles. Role-based access is enforced for each module (Sales, Recruitment, Delivery, Payroll). Unauthorized users cannot access restricted data. |  |  |  |

| User Story No: 11 | Task: 01 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS OF EACH REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE |  |  |  |
| BV: 200 |  | CP: 5 |  |
| Acceptance Criteria: Salesperson dashboard displays all requirements with real-time status (Open, Assigned, Interviewing, Selected, Billed). Last activity date and responsible user are visible. Email notification for every step |  |  |  |

Document 4: Agile PO Experience

1. Project Initiation Phase:

- Identified the business need for automating manual processes within Hubble.

- Defined and project vision document aligning with sales and management goals.

- Collaborated with Business Analyst and stakeholders (Sales, Recruitment, Delivery, Payroll) to outline high-level goals.

- Prioritized enhancement requests based on business value and urgency.

2. Requirement Elicitation & Refinement:

- Conducted requirement workshops and brainstorming sessions with stakeholders.

- Reviewed existing pain points in the manual workflow.

- Used elicitation techniques like interviews, document analysis, and workflow observation.

- Collaborated with BA to finalize User Stories, Acceptance Criteria, and Definition of Done (DoD)

- Created User Stories with Acceptance Criteria, Business Value and Complexity Points and Product Backlog items.

3. Backlog refinement meeting:

- Reviewed and clarified user stories to ensure alignment with business goals for Hubble’s workflow and KPI dashboard.

- Prioritized backlog items based on business value, urgency, and stakeholder needs.

- Collaborated with development and QA teams to estimate story points and refine acceptance criteria.

- Ensured all stories met the Definition of Ready (DoR) and were clear, testable, and achievable within a sprint.

- Facilitated communication between business stakeholders and the technical team to maintain alignment.

- Prepared the top backlog items for sprint planning, ensuring smooth transition into execution.

4. Sprint Planning Meeting:

- Conducted sprint planning meetings at the beginning of each sprint with Scrum Master and development team.

- Defined sprint goals aligning with business priorities.

- Estimated tasks based on complexity and dependencies.

- Ensured balance between development, testing, and review activities per sprint.

5. Development Phase:

- Worked closely with developers during sprint execution.

- Clarified requirements, removed blockers, and ensured alignment with acceptance criteria.

- Participated in Daily Stand-ups to monitor progress and address issues.

- Reviewed incremental builds and provided feedback early.

- Ensured KPI metrics and workflow changes matched business expectations.

6. Testing & Validation:

- Validated UAT (User Acceptance Testing) scenarios for end users.

- Reviewed and approved QA test cases based on business requirements.

- Collected user feedback for refinement.

- Ensured data accuracy and dashboard metric validation.

7. Sprint Review & Retrospective:

- Facilitated Sprint Review meetings to demonstrate deliverables to stakeholders.

- Conducted demos with stakeholders to confirm alignment with business goals.

- Captured business feedback and identified backlog improvements.

- Conducted Retrospective meetings to discuss process improvements.

- Acknowledged team efforts and captured lessons learned for future sprints.

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog:

| User Story ID | User Story | Task | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | AS A SALESPERSON I WANT TO POST NEW REQUIREMENT SO THAT RECRUITMENT TEAM CAN START SOURCING CANDIDATES | Design “Add Requirement” form, implement validation, auto-notification setup, test submission flow. | High | 500 | 3 | Sprint 1 |
| US02 | AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE | Build real-time status tracking dashboard, activity log, filters by status/date. | High | 200 | 3 | Sprint 1 |
| US03 | AS A DELIVERY HEAD I WANT TO REVIEW AND SHORTLIST CANDIDATES SO THAT ONLY SUITABLE CANDIDATES WILL MOVE FORWARD TO INTERVIEW | Create review screen, approve/reject function, feedback comment system. | High | 500 | 5 | Sprint 2 |
| US04 | AS A DELIVERY HEAD I WANT TO APPROVE THE FINAL SELECTED CANDIDATE AND DEFINE BILLING RATE SO THAT PAYROLL TEAM CAN PROCESS BILLING ACCORDINGLY | Develop approval workflow, link billing details to payroll table. | High | 500 | 5 | Sprint 2 |
| US05 | AS A PAYROLL TEAM MEMBER I WANT TO ACCESS APPROVED CANDIDATE AND BILLING DATA IN HUBBLE SO THAT I CAN PROCESS INVOICES WITHOUT MANUAL DEPENDENCIES | Payroll view screen, data integration, export to Excel/CSV. | High | 500 | 3 | Sprint 3 |
| US06 | AS A USER I WANT TO RECEIVE AUTOMATED NOTIFICATIONS FOR ALL KEY WORKFLOWS SO THAT I STAY INFORMED WITHOUT MANUAL FOLLOWUPS | Create notification module, trigger setup, send email notification | Medium | 200 | 3 | Sprint 3 |
| US07 | AS A SALESPERSON I WANT TO VIEW MY PERSONAL KPI SO THAT I CAN TRACK MY PROGRESS TOWARDS MONTHLY TARGETS | Build personal KPI dashboard, connect to sales data, target vs achieved view. | Medium | 200 | 8 | Sprint 4 |
| US08 | AS A SALES MANAGER I WANT TO VIEW THE MONTHLY KPI DASHBOARD FOR OF TEAM SO THAT I CAN MONITOR PERFORMANCE AND IDENTIFY AREAS FOR IMPROVEMENT | Create KPI dashboard UI, data aggregation, filter logic, chart integration. | High | 500 | 8 | Sprint 4 |
| US09 | AS A MANAGEMENT MEMBER I WANT TO VIEW CONSOLIDATED AND INDIVIDUAL ANALYTICS OF SALES PERFORMANCE SO THAT I CAN MAKE DATA DRIVEN BUSINESS DECISIONS | Implement logic for grouping users by experience, data visualization layer. | High | 500 | 13 | Sprint 5 |
| US10 | AS A SYSTEM ADMINISTRATOR I WANT TO MANAGE USER ROLES, PERMISSION & ACCESS TO THE MODULES SO THAT DATA EACH ROLE SEES ONLY RELEVANT INFORMATIO | Role-based access module, CRUD for users and roles, permission validation. | Medium | 500 | 3 | Sprint 5 |
| US11 | AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS OF EACH REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE | Build real-time status tracking dashboard, activity log, filters by status/date. | High | 200 | 5 | Sprint 6 |

Sprint Backlog:

| User Story ID | User Story | Task | Owner | Status | Estimated effort (Hours) |
| --- | --- | --- | --- | --- | --- |
| US01 | AS A SALESPERSON I WANT TO POST NEW REQUIREMENT SO THAT RECRUITMENT TEAM CAN START SOURCING CANDIDATES | Design “Add Requirement” form, implement validation, auto-notification setup, test submission flow. | Dev / BA | Completed | 24 |
| US02 | AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE | Build real-time status tracking dashboard, activity log, filters by status/date. | Developer | Completed | 26 |
| US03 | AS A DELIVERY HEAD I WANT TO REVIEW AND SHORTLIST CANDIDATES SO THAT ONLY SUITABLE CANDIDATES WILL MOVE FORWARD TO INTERVIEW | Create review screen, approve/reject function, feedback comment system. | Delivery Head | Completed | 22 |
| US04 | AS A DELIVERY HEAD I WANT TO APPROVE THE FINAL SELECTED CANDIDATE AND DEFINE BILLING RATE SO THAT PAYROLL TEAM CAN PROCESS BILLING ACCORDINGLY | Develop approval workflow, link billing details to payroll table. | Delivery Head | In Progress | 20 |
| US05 | AS A PAYROLL TEAM MEMBER I WANT TO ACCESS APPROVED CANDIDATE AND BILLING DATA IN HUBBLE SO THAT I CAN PROCESS INVOICES WITHOUT MANUAL DEPENDENCIES | Payroll view screen, data integration, export to Excel/CSV. | Payroll Team Member | In Progress | 18 |
| US06 | AS A USER I WANT TO RECEIVE AUTOMATED NOTIFICATIONS FOR ALL KEY WORKFLOWS SO THAT I STAY INFORMED WITHOUT MANUAL FOLLOWUPS | Create notification module, trigger setup, send email notification | Developer | In Progress | 20 |
| US07 | AS A SALESPERSON I WANT TO VIEW MY PERSONAL KPI SO THAT I CAN TRACK MY PROGRESS TOWARDS MONTHLY TARGETS | Build personal KPI dashboard, connect to sales data, target vs achieved view. | Developer | In Progress | 22 |
| US08 | AS A SALES MANAGER I WANT TO VIEW THE MONTHLY KPI DASHBOARD FOR OF TEAM SO THAT I CAN MONITOR PERFORMANCE AND IDENTIFY AREAS FOR IMPROVEMENT | Create KPI dashboard UI, data aggregation, filter logic, chart integration. | Dev / BI Analyst | Not Started | 30 |
| US09 | AS A MANAGEMENT MEMBER I WANT TO VIEW CONSOLIDATED AND INDIVIDUAL ANALYTICS OF SALES PERFORMANCE SO THAT I CAN MAKE DATA DRIVEN BUSINESS DECISIONS | Implement logic for grouping users by experience, data visualization layer. | Developer / BI Analyst | Not Started | 28 |
| US10 | AS A SYSTEM ADMINISTRATOR I WANT TO MANAGE USER ROLES, PERMISSION & ACCESS TO THE MODULES SO THAT DATA EACH ROLE SEES ONLY RELEVANT INFORMATIO | Role-based access module, CRUD for users and roles, permission validation. | Dev / QA | Not Started | 22 |
| US11 | AS A SALESPERSON I WANT TO TRACK THE REAL TIME STATUS OF EACH REQUIREMENT POSTED SO THAT I CAN FOLLOWUP WITH TEAMS AND ENSURE TIMELY CLOSURE | Build real-time status tracking dashboard, activity log, filters by status/date. | Developer | Not Started | 26 |

Sprint Burndown Chart:

Document 6: Sprint meetings

1. Sprint Planning meeting:

| Date | 13th October 2025 |
| --- | --- |
| Time | 10:00 AM – 12:30 PM (IST) |
| Location | Miracle Software Systems – Conference Room B |
| Prepared by | Samuel John – Product Owner |
| Attendees | Chanakya Lokam – Business Owner Nag Mada – Director of Sales Prithviraj Naramsetty – Director of Recruitment Santhosh Soni – Delivery Head Bharathi Ramchandram – Scrum Master Gnaneswar Rao – Scrum Developer Kavya Pasumarthi – Scrum Developer |
| Observers | Delivery Head and IT Support Team |
| Resources | Projector, Hubble access for demo, JIRA Board, Sprint Backlog Document, Velocity Chart, KPI Tracker |
| Special Notes | Sprint duration: 2 weeks (14 Oct – 28 Oct 2025) Sprint Goal: Automate initial requirement posting & assignment flow and set up base structure for KPI dashboard. |

Agenda Topics:

| Agenda Item | Presenter | Time Allotted |
| --- | --- | --- |
| 1. Welcome & Sprint Objectives Overview | Bharathi Ramchandram | 10 mins |
| 2. Review of Product Backlog & Prioritized User Stories | Samuel John | 20 mins |
| 3. Discussion on Sprint Goal & Scope | Scrum Master | 15 mins |
| 4. Task Breakdown for Each User Story (US01–US03) | Development Team | 30 mins |
| 5. Estimation Review (Story Points / Hours) | Gnaneswar Rao Kavya Pasumarthi | 15 mins |
| 6. Risk Identification & Dependencies Discussion | Bharathi Ramchandram | 15 mins |
| 7. Sprint Capacity Planning (Team Velocity Check) | Bharathi Ramchandram | 10 mins |
| 8. Review of Definition of Done (DoD) & Acceptance Criteria | Manoj Das | 10 mins |
| 9. Confirmation of Sprint Commitment | All Team Members | 10 mins |
| 10. Closing Notes & Next Steps | Samuel John | 5 mins |

2. Sprint review meeting:

| Date | 27th October 2025 |
| --- | --- |
| Time | 3:00 PM – 4:00 PM (IST) |
| Location | Miracle Software Systems – Conference Room B |
| Prepared By | Samuel John – Product Owner |
| Attendees | Nag Mada – Director of Sales Prithviraj Naramsetty – Director of Recruitment Santhosh Soni – Delivery Head Bharathi Ramchandram – Scrum Master Gnaneswar Rao – Scrum Developer Kavya Pasumarthi – Scrum Developer |

Sprint Status:

- Sprint Duration: 14 Oct – 28 Oct 2025

- Total Stories: 3 (US01–US03)

- Completed: 3 (100%)

- Sprint Goal: Automate requirement posting, recruiter assignment, and resume submission.

Things to Demo:

- Requirement Posting Module (US01): Demonstration of the new "Add Requirement" feature with real-time data validation and automated notifications.

- Recruitment Assignment (US02): Assigning recruiters to posted requirements and viewing assignment updates.

- Resume Submission Workflow (US03): Uploading candidate resumes, mapping to requirements, and progress tracking within Hubble.

- Notification Integration: Email triggered at each stage (posting, assignment, submission).

Quick Updates:

- Code peer-reviewed and merged successfully in main branch.

- QA testing completed with zero critical defects.

- UAT feedback collected from Recruitment Head – positive response.

- Documentation and user guides updated in Confluence.

- Data validation rules enhanced based on stakeholder feedback.

What’s Next:

- Begin Sprint 2 on 29th October 2025 focusing on:

  - Candidate review and feedback module (US04).

  - Interview scheduling feature (US05).

  - Delivery Head approval and billing integration (US06).

- Conduct Sprint Planning for Sprint 2 on 29th October 2025 – 10:00 AM.

- Plan early demo of KPI dashboard wireframe in upcoming sprint.

3. Sprint retrospective meeting:

| Date | 27th October 2025 |
| --- | --- |
| Time | 3:00 PM – 4:30 PM (IST) |
| Location | Miracle Software Systems – Conference Room B |
| Prepared By | Samuel John – Product Owner |
| Attendees | Nag Mada – Director of Sales Prithviraj Naramsetty – Director of Recruitment Santhosh Soni – Delivery Head Bharathi Ramchandram – Scrum Master Gnaneswar Rao – Scrum Developer Kavya Pasumarthi – Scrum Developer |

| Agenda | What Went Well | What Didn’t Go Well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint Planning & Execution | Sprint goal was clearly defined, and all 3 user stories were completed on time. Team collaboration and communication were strong. | Some confusion during initial task allocation; estimates needed refinement. | How can we improve clarity in story estimation and workload balancing? | Sprint 1 Backlog & Velocity Chart |
| Development Process | Code quality was good; peer reviews caught minor issues early. | Some dependency delays from recruitment data side slowed early progress. | Should we involve the Recruitment Head earlier in backlog grooming? | JIRA Task Board / Code Review Logs |
| Testing & Quality Assurance | QA team executed full test coverage; no major defects found. | Testing environment setup took extra time due to limited access permissions. | Can IT provide early test environment setup before Sprint start? | QA Reports / Test Case Sheet |
| Communication & Collaboration | Daily stand-ups were productive and helped resolve blockers quickly. | Few stakeholders missed sprint review due to meeting overlap. | Can we fix a standard review time slot to avoid conflicts? | Daily Scrum Notes / Meeting Calendar |
| Tools & Infrastructure | Hubble test environment performed smoothly; no downtime. | Initial notification module had integration delays with email service. | Can we prioritize API readiness before development next sprint? | Integration Log / API Tracker |

4. Daily Stand-up meeting:

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday |
| --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Dev 1: Backend | Completed API integration for Requirements module | Reviewed data validation logic | Fixed bugs in Opportunity workflow | Finalized test cases for API module | Code merged to dev branch |
|  | Dev 2: Frontend | Designed UI for KPI Dashboard | Implemented chart components | Integrated frontend with backend APIs | Resolved CSS and alignment issues | Conducted peer testing with QA |
|  | Dev 3: QA Engineer | Prepared test scripts | Executed functional testing for Requirement module | Logged defects in JIRA | Retested resolved bugs | Validated dashboard metrics |
| What will you do today? | Dev 1: Backend | Work on performance tuning | Support QA during integration testing | Create logs for error handling | Assist in deployment setup | Update API documentation |
|  | Dev 2: Frontend | Add filters to dashboard | Validate data binding | Review UI feedback from stakeholders | Conduct final UI testing | Prepare demo build |
|  | Dev 3: QA Engineer | Continue regression testing | Verify fixes | Update test summary report | Prepare test closure document | Support Sprint Review demo |
| What (if any) is blocking your progress? | Dev 1: Backend | None | Delay in test data from Recruitment system | None | None | None |
|  | Dev 2: Frontend | Awaiting final KPI formula confirmation | None | None | None | None |
|  | Dev 3: QA Engineer | Test environment access delay | None | None | None | None |