1. Identify Business Process Model for Online Agriculture Store- (Goal, Inputs,

Resources, Outputs, Activities, Value created to the end customer).

GOAL - To build an online platform where farmers can buy fertilizers, seeds, and

pesticides directly from manufactures. To make the buying process easy,

fast, and accessible, especially for farmers in remote areas.

INPUTS - Requirements from farmers and manufacturers.

Project Budget is ₹2 crores and 18 months’ Time Frame.

Skilled Team includes Project Manager, Business Analyst, Developers,

Testers, Database Administrator, Network Administrator.

Technology - Java, Database, Network setup.

Product details provided by manufacturers

RESOURCES- Human: Project Manager, Business Analyst, Developers, Testers.

Technical: Computers, Java Software, Servers, and Internet Connectivity.

Financial: Funds from SOONY Company.

Information: Requirements and product data.

ACTIVITIES - Gather and analyze requirements from all stakeholders.

Design the system (UI, Database, and Flow).

Develop the online store modules.

Test each module to ensure quality.

Get user approval (UAT) and deploy the system.

Provide maintenance and support.

OUTPUTS - An Online (web/mobile) app for Agriculture Product Store.

Reports and Documents (BRD, SRS, RISK, GNATT CHART).

Farmers can easily order and receive products online.

VALUE CREATED     -   Farmers can buy products anytime and anywhere.

TO END CUSTOMER    No need to travel long distances.

Direct connection between farmers and manufacturers.

Improved productivity and farming convenience.

2. Mr. Karthik is doing SWOT Analysis before he accepts this project. What Aspects he should consider as Strength, as Weakness, as Opportunity, and as Threats.

S - Strengths - Helps farmers buy seeds, fertilizers, and pesticides easily from

Anywhere.

User friendly and accessible through web or mobile app.

Direct link between farmers and manufacturers - no middleman.

Strong team with skilled developers, testers, and BA.

Funded under CSR (Corporate Social Responsibility), so financial risk is low.

W - WEAKNESSES - Farmers in rural areas may have limited internet access and also, they

Don’t have digital knowledge.

Initial setup cost and time for development are high.

Training and awareness needed for farmers to use the system.

System may face technical issues (server, bugs) during early stages.

O - OPPURTUNITIES - Can expand to include other agricultural products

(tools, equipment, services).

Supports digital transformation in agriculture.

Can help increase farmer income by reducing dependency on local

Vendors.

Potential for mobile app upgrades and multi-language support.

T -THREATS - Competition from existing online Agri-stores or e-commerce platforms.

Cybersecurity risks- data theft, online fraud.

Market acceptance - farmers may take time to trust online buying.

Changing government policies or import/export regulations.

3. Mr. Karthik is trying to do feasibility study on doing this project in Technology(java),

Please help him with points (HW SW Trained Resources Budget Time frame) to

Consider in feasibility study.

Feasibility study: Mr. Karthik is checking if it is possible and practical to develop this

Project using java technology within the given budget and time.

1. HARDWARE REQUIREMENTS: Computers/laptops for developers and testers.

A Server to host the application and database.

Internet Connection for development and testing.

Backup devices (external drives, cloud storage).

2. SOFTWARE REQUIREMENTS: Programming language: Java

Database: MySQL Or Oracle

Web server: Apache Tomcat

Development tools: Eclipse/Intelli J IDEA (for coding)

Testing tools: Selenium or Junit

Version control: GitHub or Bitbucket

3. TRAINED RESOURCES: Project Manager: Manages the whole project.

Business Analyst: Gathers and documents requirements.

Developers (java team): Build the application.

Testers: Test the application.

DB Admin: Manages the Database.

Network Admin: Handles network and Connectivity.

4. BUDGET:                       Total Budget: ₹2 Crores (CSR Fund).

Covers salaries, hardware/software costs, testing, deployment

And maintenance.

5. TIME FRAME:                Total Duration: 18 months.

The phases include:

Gathering and Analyzing the Requirements.

Design & Development.

Testing & UAT.

Deployment and Maintenance.

The Feasibility study shows that:

The hardware and software needed are easily available.

The team is well trained in java and project tools.

The budget and time are suitable for the planned work.

So, developing the online Agriculture Store using Java Technology is Feasible and Practical.

4. Mr. Karthik must submit Gap Analysis to Mr. Henry to convince to initiate this

Project. What points (compare AS-IS existing process with TO-BE future process)

To showcase in the Gap Analysis.

Mr. Karthik needs to show Mr. Henry how the current process (AS-IS) of farmers buying

Agricultural products is problematic and how the new system (TO-BE) will solve those

Problems using the online platform.

Consider (AS-IS) Aspect: Right now, farmers buy products manually from local shops,

Which takes time and has limited options. In the new online system, farmers can buy

Directly from manufacturers through a website or mobile app. It saves time, gives

Better prices and makes everything more convenient.

Aspect; AS-IS Existing Process; TO-BE Future Process. Product Purchase; Farmers go to local shops or cities to buy seeds, pesticides.; Farmers can buy all products Online from their mobile/computer.. Availability; Limited products in local markets, farmers depend on few suppliers.; Wide range of products available from multiple manufacturers.. Time & Effort; Takes a lot of time and travel to find and buy products.; Products can be ordered instantly online-saves time &effort.. Price Transparency; Prices vary from shop to shop, often not clear.; All prices are shown clearly online-farmers can compare and choose.. Communication; No direct communication between farmers and companies.; Direct communication through The online platform (queries &support).. Payment; Mostly done in cash after Physical purchase.; Online payments through Secure digital options.. Delivery; Farmers carry the goods themselves/ hire transport.; Products delivered directly to Farmer’s location.. Record Keeping; Manual bills or no record Of purchases.; Automatic digital receipts and order history available.. Reach; Only limited to nearby shops or towns.; Accessible to farmers even in Remote areas with internet..

The current process is manual, time - consuming and costly for farmers. The future online process is digital, fast, transparent, and convenient. By moving from AS-IS to TO-BE, farmers will save time, money, and effort while getting better product choices and direct company support.

5. List down different Risk factors that may be involved (BA Risks and Process/Project

Risks).

In any project, risks are the possible problems that may happen in the future and

Affect the project’s success.

As a business analyst, we need to identify risks early so that we can plan to avoid or

Reduce them.

In this Agriculture Store project, both BA Risks and Project/Process risks are possible.

BUSINESS ANALYST RISKS:

1. Incomplete Requirements: Farmers or companies may not clearly explain what

They need, leading to missing the requirements.

2. Miscommunication: Since stakeholders (farmers, manufacturers, committee) are

From different locations, there may be misunderstanding

Between BA and users.

3. Frequent Requirement Change: Farmers or the committee might keep changing

Their needs after the project starts, causing confusion and

Delays.

4. Lack of Domain    BA might not fully understand agricultural terms or processes,

Knowledge     :   which can affect requirement accuracy.

5. Poor Documentation: If the BA doesn’t document requirements properly (BRD,SRS

Developers and testers may be get confused.

6. Stakeholder Unavailability: Sometimes key people (like Mr. Henry or Farmers)

Might not be available for meetings or clarifications.

7. Conflicting Requirements: Different stakeholders may have opposite needs

(e.g.: one wants offline mode, another doesn’t).

BA must resolve such conflicts.

PROCESS/PROJECT RISKS:

These are risks that affect the overall project progress, cost, time, or quality.

1. Budget Overrun: The project might cost more than the planned ₹2 Crores.

2. Delay in Schedule: Development or testing may take longer than the planned

18 months.

3. Technical Issues: Since the app is developed using Java, technical errors or

Performance issues may occur.

4. Resource Unavailability: Key team members (developers, tester, DBA) might

Leave or not be available on time.

5. Integration Problems: Issues may occur while connecting different modules (like

Product upload, order, and payment).

6. Data Security Risk: Farmer’s personal and payment data must be protected.

Any leak can cause big problems.

7. Poor Quality/Testing Gaps: If testing is not done properly, the app might have

Bugs after release.

8. Lack of User Training: Farmers may not know how to use the app if proper

Guidance or help manual is not given.

9. Vendor/Internet Dependency: Since it’s an online store, if the server or internet

Fails, the app will not work.

10. Scope creep: Adding new features beyond what was planned (like adding

Weather updates or chat) can delay and increase cost.

6. Perform stakeholder analysis (RACI Matrix) to find out the key stakeholders who can

Take decisions and who are the influencers.

STAKEHOLDER ANALYSIS:

It helps to identify who is involved in the project, what their roles are, and how much influence or decision-making power they have.

In this project stakeholders include people like Mr. Henry, the committee members,

Project manager, developers, testers, and farmers.

RACI MATRIX:

R - Responsible - Person who actually does the work.

A - Accountable - Person who takes final decision/ owns the task.

C - Consulted - Person who gives input, advice, or suggestions.

I - Informed - Person who is updated about progress or results.

STAKEHOLDERS IN THIS PROJECT:

Mr. Henry - Project Sponsor (funding through CSR initiative)

Mr. Pandu - Financial head (budget approvals)

Mr. Dooku - Project coordinator (communication between sponsor and vendor)

Mr. Karthik - Delivery head (overall project control from APT IT solutions)

Mr. Vandanam - Project manager (day to day project execution)

Ms. Anusha - Business Analyst (Requirement gathering and documentation)

Developers - Java development team (Juhi, Teyson, Lucie, Tucker, Bravo)

Testers - Testing team (Jason, Alekya)

John (DB Admin) - Database setup and management

Mike (Network Admin) - Server and connectivity

Farmers (Peter, Kevin, Ben) - End users providing requirements and feedback

RACI MATRIX TABLE:

| PROJECT ACTIVITY | SPONSOR | FINANCE HEAD | COORDI -NATOR | DELIVERY HEAD | PM | BA | DEVELOPERS | TESTERS | DB ADMIN | NETWORK ADMIN | END USERS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REQ GATHERING | I | I | C | A | C | R | I | I | I | I | C |
| REQ APPROVAL | A | C | C | C | I | R | I | I | I | I | C |
| SYS TEM DESIGN | I | I | I | C | A | C | R | I | C | C | I |
| DEVELOPMENT PHASE | I | I | I | C | A | C | R | I | C | C | I |
| TESTING PHASE | I | I | I | C | A | C | C | R | C | I | I |
| UAT | I | I | I | C | C | C | I | C | I | I | A/R |
| DEPLOYMENT&IMPLEMENTATION | I | I | I | A | R | C | C | C | C | C | I |
| BUDGET APPROVAL | A | R | C | C | I | I | I | I | I | I | I |
| PROJECT REPORTING | A | C | C | R | R | C | I | I | I | I | I |

7.  Help Mr. Karthik to prepare a business case document.

BUSINESS CASE DOCUMENT:

Project Title: Online Agriculture Product Store.

Prepared by: Mr. Karthik - Delivery Head, APT IT Solutions

Submitted to: Mr. Henry - Project Sponsor, SOONY Company.

Date: (Insert Date)

Project Duration: 18 Months

Project Budget: ₹ 2 crores (CSR Initiative)

1. EXECUTIVE SUMMARY:  This business case proposes the development of an

Online Agriculture Products Store to connect farmers in remote areas directly with

Verified manufacturers of fertilizers, seeds, and pesticides. The project aims to

Eliminate middlemen, ensure quality, and provide farmers with easy access to

Agricultural inputs at transparent prices through a digital platform.

The initiative is funded under CSR and will create long-term social and

Operational benefits.

2. PROJECT INITIATION: The project is initiated by Mr. Henry and coordinated by

Mr. Dooku under the guidance of Mr. Karthik, delivery head at APT IT solutions.

Rural farmers face major challenges in procuring authentic agro-inputs, leading to

Inefficiencies and crop loss. The digital platform will act as a bridge between

Manufacturers and farmers.

3. CURRENT PROBLEMS: Farmers depend heavily on intermediaries.

Price variation and lack of product authenticity.

Limited access to technical product information.

High travel costs and delayed availability.

4. PROPOSED SOLUTION: Develop a web and mobile based platform where

Manufacturers list verified products.

Farmers can register, search, compare, and purchase.

Secure digital and COD payments are supported.

Orders are delivered through integrated logistics.

Analytics provide manufacturers with demand insights.

5.BENEFITS/PROBLEMS SOLVED:

| PROBLEM | SOLUTION |
| --- | --- |
| Middlemen dependency | Direct manufacturer to farm platform |
| Price Inconsistency | Transparent online pricing |
| Product quality doubts | Verified manufacturers and reviews |
| Access delays | Online ordering and doorstep delivery |

Additional Benefits:

Support CSR social- impact goals.

Builds data on farmer demand patterns.

Enhances brand reputation of the sponsor.

6. RESOURCES REQUIRED:

Human: PM, BA, 4 Developers, 2 Testers, DB Admin, Network Admin, UI Designer.

Technology: Java (sprint boot), React, MySQL, AWS Cloud, Payment Gateway, Logistics API.

Finance: ₹ 2 Crores CSR funding (Includes development, testing, infrastructure, and training).

7. ORGANIZATIONAL CHANGE REQUIREMENTS:

Moderate change: IT setup training for support teams.

External stakeholders(farmers/manufacturers) will require brief orientation and support to use the digital system.

8. TIMELINE/ROI (return of investment) ESTIMATION:

| PHASE | DURATION |
| --- | --- |
| Requirement & Design | 3 months |
| Development & Testing | 9 months |
| Pilot & UAT | 3 months |
| Rollout & Support | 3 months |

Total: 18 Months

ROI:

Non- Financial(social): within 12 months - reduced farmer procurement cost and time.

Operational benefits: within 18 months - scalable platform, improved CSR impact metrics.

9. STAKEHOLDERS:

SPONSOR: Mr. Henry (CSR Committee)

FINANCIAL HEAD: Mr. Pandu

PROJECT COORDINATOR: Mr. Dooku

DELIVERY HEAD/BA: Mr. Karthik

PROJECT MANAGER: Mr. Vandanam

DEVELOPMENT TEAM: Juhi, Tayson, Lucie, Tucker, Bravo

TESTING TEAM: Jason, Alekya

DB & NETWORK: John, Mike

EXTERNAL: Farmers (Peter, Kevin, Ben), Manufacturers, Logistics Partners.

10. RISK SUMMARY (HIGH-LEVEL)

| RISK | IMPACT | MITIGATION |
| --- | --- | --- |
| Low farmer digital literacy | Medium | Provide training, agent support |
| Connectivity issues | High | Offline/order by SMS support |
| Scope creep | Medium | Strict change control process |
| Budget overrun | Medium | Regular review, phase budgeting |
| Counterfeit product risk | High | Verified supplier onboarding |

11. RECOMMENDATION:

Proceed with the Online Agriculture Products Store under the CSR program using the

V- Model SDLC. This approach ensures quality, verification, and traceability of requirements and test coverage. Pilot in select districts, collect feedback, and scale across regions within the 18 months’ timeline.

SIGN OFF:

| NAME | ROLE | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Mr. Henry | sponsor |  |  |
| Mr. Pandu | Financial head |  |  |
| Mr. Karthik | Business analyst |  |  |
| Mr. Vandanam | Project manager |  |  |

8. The Committee of Mr. Henry, Mr. Pandu, and Mr. Dooku and Mr. Karthik are

Having a discussion on Project Development Approach.

Mr. Karthik explained to Mr. Henry about SDLC and four methodologies like

Sequential iterative evolutionary and Agile. Please share your thoughts and

Clarity on methodologies.

SDLC (SOFTWARE DEVELOPMENT LIFE CYCLE):

It’s the step-by-step process of planning, creating, testing, and delivering a software product.

Different methodologies are used to manage how the project moves through these steps.

1. SEQUENTIAL MODEL (WATERFALL MODEL):

Work goes step by step - like a waterfall. First gather requirements, then design, then develop, test, and finally deliver.

Each stage must finish before the next begins.

EXAMPLE: Like building a house - you finish the foundation before starting the walls.

BEST FOR: Projects where requirements are clear and unlikely to change.

PROS:  simple, easy to manage.

CONS: hard to change once you start.

2. ITERATIVE MODEL:

The project is developed in small cycles(iterations). Each cycle produces an improved version of the software based on feedback.

EXAMPLE: Like writing an essay - you write a draft, review it, improve it, and repeat until it’s perfect.

BEST FOR: Projects where requirements may evolve over time.

PROS: Feedback early, less risk.

CONS: Needs more time and stakeholder involvement.

3. EVOLUTIONARY MODEL:

You build a basic version (prototype) first then keep adding a new features and improvements over time until the final system is ready.

EXAMPLE: Like developing a mobile app- you first release a basic version, then keep updating it with new features.

BEST FOR: Projects where requirements are not fully clear at the beginning.

PROS: User feedback shapes the product; flexible.

CONS: Hard to control cost and scope sometimes.

4. AGILE MODEL:

Agile is about working in short cycles (called sprints) with continuous collaboration between business and technical teams.

Software is delivered in small, usable parts, and feedback is taken frequently.

EXAMPLE: Like baking cupcakes in batches- you bake a few, taste, adjust, then bake more.

BEST FOR: Dynamic projects where requirements can change often.

PROS: Fast delivery, flexible, customer-focused.

CONS: Needs active team communication and quick decisions.

| MODEL | KEY IDEA | WHEN TO USE | MAIN ADVANTAGE | SHAPE/FLOW |
| --- | --- | --- | --- | --- |
| SEQUENTIAL | Step by step, one phase after another | Clear & fixed | Simple & structured | Straight downward flow |
| ITERATIVE | Build, review, improve repeatedly | Evolving requirements | Early feedback, less risk | Repeating loops |
| EVOLUTIONARY | Start small, grow product gradually | Unclear requirements | Adapts to user feedback | Expanding spiral |
| A GILE | Short cycles with teamwork &feedback | Changing & fast projects | Quick delivery, Flexibility | Short repeating sprint cycles |

9.  They discussed models in SDLC like waterfall RUP Spiral and Scrum. You put forth

Your understanding on these models.

When the APT IT Solutions Company got the project to make this online agriculture

Product store, there is a difference of opinion between a couple of SMEs and the

Project team regarding which methodology would be more suitable for this project.

SMEs are stressing on using the V model and the project team is leaning more onto

The side of waterfall model. As a business analyst, which methodology do you think

Would be better for this project.

WATERFALL MODEL:

TYPE: Each phase (requirement- design-development-testing-deployment) must

Be completed before the next starts.

BEST FOR: Projects with clear, stable requirements.

ADVANTAGES: Easy to manage, well-documented, suitable for short-term projects.

DISADVANTAGES: Difficult to accommodate changes once development starts,

Testing, happens late.

RUP (RATIONAL UNIFIED PROCESS):

TYPE: Iterative and incremental.

PROCESS: Divided into phases- inception, elaboration, construction, transition.

BEST FOR: Medium to large projects where requirements evolve.

ADVANTAGES: Iterative feedback, risk reduction, promotes reusability.

DISADVANTAGES: Complex to manage, requires skilled teams.

SPIRAL MODEL:

TYPE: Risk-driven, iterative model.

PROCESS: Each iteration(spiral) involves planning-risk analysis-engineering-

Evaluation.

BEST FOR: High-risk, large-scale projects with unclear requirements.

ADVANTAGES: Continuous risk analysis, customer feedback in every phase.

DISADVANTAGES: Costly, requires strong risk management expertise.

SCRUM (AGILE FRAMEWORK):

TYPE: agile and iterative.

PROCESS: Product developed in short cycles (sprints) with regular reviews and

Stakeholder feedback.

BEST FOR: Projects requiring flexibility, continuous improvement, and customer

Collaboration.

ADVANTAGES: Quick feedback, adaptability, early delivery.

DISADVANTAGES: Needs strong team collaboration and experienced scrum roles

(PO, SM).

UNDERSTANDING THE SITUATION:

SMEs prefer V-Model.

Project team prefers Waterfall Model.

The Project: Online Agriculture Product Store- involves farmers (non-technical users)

And product manufacturers, requiring user-friendliness, accuracy and

Proper testing.

COMPARISION- WATERFALL VS V- (VERIFICATION & VALIDATION) MODEL.

| ASPECT | WATERFALL MODEL | V MODEL |
| --- | --- | --- |
| TESTING | Done after development is complete. | Testing is planned alongside each development phase. |
| ERROR DETECTION | Late in process | Early, at each stage. |
| FLEXIBILITY FOR CHANGES | Very low | Slightly more structured for quality assurance. |
| DOCUMENTATION | Sequential and static | Detailed with traceability from requirements to testing. |
| BEST SUITED FOR | Simple, low risk projects | Medium-to-high risk projects where validation is crucial. |

AS A BA, I WOULD RECOMMED: V- MODEL.

1. QUALITY & VALIDATION: Since this is a new application targeting first-time users (farmers),

Ensuring usability and correctness is critical. V-Model allows

Parallel testing planning for every phase.

2. TRACEABILITY: Each requirement can be traced directly to its corresponding test case.

3. REDUCED RISK: Early verification reduces post - deployment defects.

4. STAKEHOLDER CONFIDENCE: SMEs prefer quality assurance, and V-Model supports their

Validation needs.

5. PROJECT CONTEXT FIT: With a fixed budget (2 crores INR) and 18- months timeline,

Controlled and predictable development (like V-Model) is safer than a

Purely sequential waterfall.

10. 20 write down the differences between waterfall model and v model.

| NO | WATERFALL MODEL | V MODEL |
| --- | --- | --- |
| 1 | Follows a linear step by step process. | Follows a v shaped process of development and testing. |
| 2 | Testing is done after development is finished. | Testing happens parallel to each development stage. |
| 3 | Errors are found late in the project. | Errors are found early in the project. |
| 4 | Difficult to go back to previous phases. | Easier to trace and correct mistakes early. |
| 5 | Mainly focuses on development activities. | Focuses on both development and testing equally. |
| 6 | The model is simple but rigid. | The model is structured and quality focused. |
| 7 | No testing plan is prepared in early stages. | Testing plan is created during requirements and design stages. |
| 8 | Best for small and simple projects. | Best for medium or large projects needing high quality. |
| 9 | Testing starts after coding is complete. | Testing starts from the requirement stage. |
| 10 | High chance of defects in final stage. | Less chance of defects due to early verification. |
| 11 | Customer involvement is only at the end. | Customer involvement is seen at many stages. |
| 12 | Late feedback from users. | Early feedback can be taken and used. |
| 13 | Documentation-heavy but less testing-oriented. | Documentation and testing both are well balanced. |
| 14 | Quality assurance comes after development. | Quality assurance runs along with development. |
| 15 | Changes are costly and time-consuming. | Changes are easier to handle early on. |
| 16 | Suitable when requirements are very clear. | Suitable when testing and validation are critical. |
| 17 | Each phase depends on the completion of the previous one. | Each phase is verified and validated with testing. |
| 18 | Less focus on risk management. | Strong focus on risk reduction and quality. |
| 19 | No mapping between development and test phases. | Each development phase has a corresponding test phase. |
| 20 | Example stages: requirements-design-coding-testing-deployment. | Ex stages: requirements& acceptance testing-design& system testing - coding& unit testing. |

11.  As a BA, state your reason for choosing one model for this project.

As a business analyst, I would choose the V-Model for this project because it gives equal

Importance to both development and testing.

In this project, farmers and manufacturers will use the system, so quality and accuracy

Are very important. The V-Model allows us to test each phase right from the beginning,

Which helps in finding and fixing errors early.

This ensures the final product is reliable, user-friendly, and meets all requirements.

It also gives clear visibility of progress and helps maintain good communication

Between BA, developers, and testers.

12.  The committee of Mr. Henry, Mr. Pandu, and Mr. Dooku discussed with Mr.        Karthik and finalized on the V Model approach (RG, RA, design, D1, T1, D2, T2, D3,    T3, D4, T4 and UAT)

Mr. Vandanam is mapped as a PM to this project. He studies this project and prepares a Gnat chart with V model (RG, RA, design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) as

Development process and the resources are PM, BA, JAVA DEVELOPERS, TESTERS, DB ADMIN, NW ADMIN.

A Gnatt Chart is a project planning tool that shows the timeline of all project activities.

It displays tasks, their start and end dates, duration, and who is responsible for each task.

It helps the PM and team to track progress and ensure the project stays on schedule.

| PHASE | DESCRIPTION | RESPONSIBLE PERSON | TIMELINE |
| --- | --- | --- | --- |
| Requirement gathering (RG) | Collect requirements from stakeholders. | BA | 1-2 weeks |
| Requirement Analysis (RA) | Analyze and finalize requirements. | BA, PM | 3-4 weeks |
| Design(D1) | Create system design. | Developers | 5-6 weeks |
| Testing (T1) | Test design components. | Testers | Week 7 |
| Development (D2, D3, D4) | Build modules of the application. | Developers | 8-14 weeks |
| Testing (T2, T3, T4) | Test each module after development. | Testers | 9- 15 weeks |
| User acceptance testing UAT | Users test full system. | BA, Testers, Users | 16 - 17 weeks |
| Deployment | Go live with final product. | PM, Developers | Week 18 |

13. Explain the difference between fixed bid and billing projects.

In a Fixed Bid project, the price and scope are decided at the beginning - even if more

Time is needed; the company cannot charge extra. In a Billing project, payment is made

Based on the number of hours or resources used. Fixed Bid is good for projects with

Clear requirements, while Billing is better when requirements can change.

| POINT | FIXED BID PROJECT | BILLING (TIME & MATERIAL) PROJECT. |
| --- | --- | --- |
| DEFINITION | The total cost is fixed before the project starts. | The cost is based on the actual time and resources used. |
| BUDGET | Pre decided and fixed budget. | Flexible budget- depends on hours worked. |
| SCOPE | Clearly defined scope- no major changes allowed. | Scope can be changed anytime by the client. |
| RISK | Risk is taken by the vendor. | Risk is shared or taken by the client. |
| PAYMENT | Payment is made after project completion or in milestones. | Payment is made regularly(weekly/monthly) based on hours. |
| TIMELINE | Has a strict deadline. | Timeline is flexible as work is charged by time. |
| CONTROL | Client has less control once project starts. | Client has more control and visibility. |
| MONITORING | Managed mainly by the vendor. | Both client and vendor track progress together. |
| BEST SUITED FOR | Small or well-defined projects. | Long term or changing requirement projects. |
| EXAMPLE | Building a website with fixed features and delivery date. | A support or maintenance project where work changes every month. |

14. Design timesheet of a BA.

Development timesheet of a BA.

Testing timesheet of a BA.

UAT timesheet of a BA.

Deployment n implementation timesheet of a BA.

1. DESIGN PHASE - BA TIMESHEET

| DATE | TASK | DESCRIPTION | HOURS |
| --- | --- | --- | --- |
| DAY 1 | Requirement gathering | Collect business requirements from stakeholders | 4 |
| DAY 2 | Requirement analysis | Analyze and categorize functional/non-functional requirements | 5 |
| DAY 3 | Prepare brd | Create business requirement document | 6 |
| DAY 4 | Review meeting | Discuss and finalize brd with stakeholders | 4 |

2. DEVELOPMENT PHASE - BA TIMESHEET

| DATE | TASK | DESCRIPTION | HOURS |
| --- | --- | --- | --- |
| DAY 1 | Review design documents | Verify that the design meets business needs | 5 |
| DAY 2 | Clarify requirements | Support development team with requirement clarifications | 5 |
| DAY 3 | Update traceability matrix | Ensure each req mapped to a design component. | 3 |

3. TESTING PHASE - BA TIMESHEET

| DATE | TASK | DESCRIPTION | HOURS |
| --- | --- | --- | --- |
| DAY 1 | Prepare test scenarios | Review and validate test cases as per requirements | 4 |
| DAY 2 | Requirement validation | Ensure requirements are covered in test cases | 4 |
| DAY 3 | Support testing | Clarify business logic during test execution | 5 |

4. UAT PHASE - BA TIMESHEET

| DATE | TASK | DESCRIPTION | HOURS |
| --- | --- | --- | --- |
| DAY 1 | Conduct UAT sessions | Coordinate UAT with end users | 4 |
| DAY 2 | Record feedback | Doc issues and user feedback | 5 |
| DAY 3 | Req sign off | Get formal approval from business stakeholders | 3 |

5. DEPLOYMENT & IMPLEMENTATION PHASE - BA TIMESHEET

| DATE | TASK | DESCRIPTION | HOURS |
| --- | --- | --- | --- |
| DAY 1 | Release coordination | Coordinate with technical team for go - live | 3 |
| DAY 2 | Post deployment review | Validate functionality after deployment | 4 |
| DAY 3 | User training support | Conduct training sessions for end users | 5 |