Live project- Waterfall Approach Evaluation Part-2

Q.1) Business Case Document Template

Ans.1)

| Date | 27-06-25 |
| --- | --- |
| Submitted By | Sumit Pandey |
| Title/Role | Business Analyst |

The sole aim to initiate this project is to develop a solution for the member & top level management in the organization is to help them to solve the problem related to inefficient monitoring of key parameters of the process, provide them & their workers in ease of operation, provide them better workplace by creating inefficient workmanship, reduce the defect rate by 90%, To achieve the overall equipment effectiveness by 95%, Improve productivity and decide on reducing the manpower cost by 50%. Hence by developing such a solution the organization can achieve long term on various KPI’s

Why is this Project Initiated

The current problem being faced by the company is low level of [productivity, High defect rate on product manufacturing, High rework cost, High energy consumption, High rejection cost, High manpower cost, Inefficiency of workers leading to major challenges being faced by the company. Facing challenges on all the key parameters of manufacturing companies per product cost compared to Competitor Company is on higher side. Hence organization has decided to develop an in-house solution for control, monitoring and digitalization of key functional areas such that people around organization can work efficiently to improve the overall functionalities of the company

What are the current Problems

With accomplishment of this project organization can have better control of the key parameters such OEE, Productivity, can reduce defect rate by introduction low cost automation solution with software such PLC,SCADA, HMI which will result in better yield as it reduced the manpower engagement at improved level. High end automation solution such as building SCARA robotic solution can result in high yield by improving productivity, Digitalization of key processes can help team & management to monitor their daily yield and can decide to increase strike rate and curb on particular resources, Energy cost can be reduced with proper monitoring of energy cost for each functions on live data basis. Hence solving many problems for the business to grow efficiently.

With this Project how many problems can be solved

The resources required allocation of budget for developing software solution for OEE, Quality defect rate, Digitalization dashboard for Production including machine uptime, downtime report, defect rate for different processes, 4M changes and energy monitoring dashboard for maintenance & utility. New PCS were required different functions, Establishment of war room to allocate developers, testers, engineers, and people from different functionalities.

What are the resources required

Organizational changes were also required such as hiring of software developer, engineers were hired to look after advanced automation project while development & implementation. Robotics engineer were also required for installation of in-house robots. Testers required to handle testing after each phase development.

How much organizational change is required to adopt technology

The time frame required for return of investment is 1 year considering development cost, hiring cost for people from different functionalities, implementation and maintenance cost will be on higher side hence the ROI will go around 1 year.

Time frame to recover ROI

Identifying stakeholders include systematic processes using brainstorming, reviewing project documents and utilizing stakeholders analysis tools to identify all individuals or groups who are impacted by or can impact the project. Other tools such as interviews, surveys and focus group for conducting direct interaction with potential stakeholders.

How to identify Stakeholders

Q2.) Case study

Ans.2) A business analyst (BA) approach for project completion is by planning and executing a comprehensive business analysis approach, which involves defining the project's scope and objectives, identifying stakeholders, analysing requirements, developing solutions, and ensuring successful implementation and value assessment.

Key steps in a BA approach strategy to complete a project:

- Intiaition & Planning: - Iidentify the business problem or opportunity, and understand the project's objectives and high-level scope. Identify all key stakeholders, their roles, and their influence on the project.

- Elicitation and Analysis: - Use various techniques like workshops, interviews, and document analysis to collect detailed business and user requirements from stakeholders.

- Solution Development and Implementation:- Based on analyzed requirements, propose and evaluate potential solutions, considering technical feasibility and business needs.

- Validation and Closure: - Evaluate the implemented solution against the defined requirements and business objectives, often through testing and user acceptance.

Elicitation technique to Apply:-

Various combination techniques should be applied, including interviews, brainstorming, document analysis, focus groups, prototyping, observation, surveys/questionnaires, and workshops

How to do Stakeholder analysis RACL/ILS.

Stakeholder analysis is the process of identifying the individuals or groups that are likely to affect or be affected by a proposed action, and sorting them according to their impact on the action and the impact the action will have on them.

RACI is an acronym that stands for Responsible, Accountable, Consulted, and Informed. The RACI categorization provides clarification of responsibilities that each party plays in relation with activities that are needed to be performed and decisions that have to be accomplished

Responsible: Does the work to achieve the task

- Person who perform a task/activity; refer to the doer, responsible for action/implementation

- The degree of responsibility is defined by the Accountable person

- Responsibility can be shared and delegated

Accountable: Has authority to approve or disapprove the result

- Person who has ultimate accountability and authority

- Only one accountable “A” to each task/activity

- Accountability cannot be delegated

Consulted: Possesses needed input to the task

- Person to be consulted before a final decision or action is taken

Informed: Needs to be informed of the result

- Person that needs to be informed after a decision or action is taken

- Refer to a one way communication

What documents to write?

Preparing documents is one of the most critical tasks that every responsible business analyst does. A Business Analyst not only documents the clients’ requirements but also happens to document the progress and every change that has occurred during the project lifecycle

- Project vision Document

- Business Analysis Plan

- Business Requirements Document

- Functional requirement specification (FRS)/ Functional Specification Document (FSD)

- System requirement specification (SRS)/ System Requirement Document (SRD)

- Requirement traceability matrix (RTM)

- Use Case Diagrams

- Wireframes, Mock-ups

- Change Request Document

What Process to follow to sign off the documents

To take sign-off on documents, follow a formal process that involves document preparation, stakeholder identification, thorough review and approval, signature capture, and finalization and archival

How to take approvals from client

To effectively gain client approval, clearly communicate what needs to be approved, provide necessary context and documentation, specify a deadline for response, and offer to answer questions or provide clarification.

What communication channels to establish & implement

Key channels to consider include face-to-face, verbal (phone calls, video conferencing), written (email, reports), and digital (instant messaging, social media, project management platforms).

How to handle change request

There are a lot of obstacles to overcome when trying to deliver on a project. A change request will often come up throughout the course of most projects. Change requests are necessary and can offer many benefits. Managing this process in an effective way can allow for greater internal communication, efficiency, and alignment with overall business goals

Effectively managing of change request can involve five steps.

Request any supporting materials

Determine whether the change request is inside or outside the scope

Analysing the priority of change request

Approve or reject the change request

Decide on how to approach towards change request

How to update the progress of the project to stakeholders

Progress reports are necessary due accountability, Alignment, visibility and forecasting.

Establish a Routine

Set a specific day and time each week for updates.

Collect Key Information

Include progress reports, metrics, roadblocks, and milestones.

Tailor the Content

Customize updates to the interests and needs of different stakeholders.

Choose the Right Tools

Use email, presentations, project management software, or meetings for delivery.

Be Consistent and Concise

Provide a predictable structure for updates, keeping them brief but informative. Now it is the time to start crafting yours.

How to take sign-off on UAT

To obtain UAT sign-off from a business analyst's perspective, you need to formally document that stakeholders agree the system meets business requirements and is ready for production release, typically through a sign-off document or email, after thoroughly documenting UAT results, issues, and resolutions.

Key steps to obtain sign-off are:-

Define UAT criteria and scope

Prepare UAT documentation

Create a UAT summary report

Facilitate UAT feedback meeting

Obtaining formal sign-off

Q.3) Functional Specification?

Ans.3)

| Project name | In-house development of automation solution Powertrack+ |
| --- | --- |
| Customer name | Havells India Ltd. |
| Project vendor | Delmia Aprizo |
| Project Sponsor | Havells India Ltd. |
| Project Manager | Mr. Sher Singh Sharma |
| Project Initiation date | 15-06-25 |

| Req ID | Req Name | Req Description | Priority |
| --- | --- | --- | --- |
| FR001 | Sign-In | User should be able to login to the application | 1 |
| FR002 | Login | User should be able to login directly if already have an user ID | 2 |
| FR003 | Data monitoring | User should be able to track their respective domain data | 1 |
| FR004 | Data collection | User should be able export all the data required to analyse data | 3 |
| FR005 | Program execution | User should be able to write specific program using Programming software | 4 |
| FR006 | Dashboard Online | User should be able to take remote operation for dashboard | 6 |
| FR007 | Domain addition | User should be able to add new domain as per req. | 7 |
| FR008 | Data write | User should be able to write of change specific data as per user req. | 8 |

Q.4) Requirement Traceability matrix?

Ans.4)

| Req ID | Req Name | Req description | D1 | T1 | D2 | T2 | UAT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FR001 | Sign-off | User should be able to sign off for the first time they are using the application | Yes | Yes | No | No | Yes |
| FR002 | Login | User should be able to login directly if having user ID & password | Yes | No | Yes | Yes | Yes |
| FR003 | Password | User should be able to create new password | Yes | Yes | No | No | No |
| FR004 | Data monitoring | User should be able to monitor the data for their respective domain | Yes | Yes | Yes | No | Yes |
| FR005 | Data validation | User should be able to validate their data | Yes | No | Yes | No | Yes |
| FR006 | Program execution | User should be able to develop their program as per Req | Yes | Yes | Yes | No | Yes |

Q.5) BRD Template

Ans.5)

Document revision

| Date | Version no. | Document changes |
| --- | --- | --- |
| 01/06/25 | 0.1 | Initial draft |
| 10/06/25 | 0.2 | Req. analysis |
| 14/06/25 | 0.3 | SRS prep |
| 16/06/25 | 0.4 | Design & dev |
| 25/06/25 | 0.5 | Testing |
| 29/06/25 | 0.6 | UAT sign off |

Approvals

| Role | Name | Title | Signature | date |
| --- | --- | --- | --- | --- |
| Project sponsor | Havells India | Organisation |  |  |
| Business owner | XXXX |  |  |  |
| Project manager | Sher Singh Sharma | AGM |  |  |
| System architect | Shubham | DM |  |  |
| Development lead | Manish dhiman | Manager |  |  |
| User experience | anshul | Manager |  |  |
| Quality lead | neeraj | DM |  |  |
| Content lead | sudarshan | AM |  |  |

| Name | Position | * | R | A | S | C | I |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rajiv Yadav |  | yes |  |  |  |  | yes |
| Sher singh |  |  |  |  |  | yes | yes |
| manish |  |  | yes |  |  | yes | yes |
| neeraj |  |  |  | yes | yes |  |  |
| shubham |  |  | yes | yes | yes |  |  |
| jyoti |  |  |  |  | yes |  |  |
| Sumit pandey |  |  |  |  | yes |  | yes |

Business Goals:

Organisation policies- The organisation policies is to build an environment where people can learn & grow innovatively and their skill can help the organisation grow with innovative customer solution & high quality product.

Business objectives:- The business objective is to provide high end innovative solution to the customes with energy efficient product with world class manufacturing facilities and quality.

Business Rules

Procedures: The organisation procedure outlines how the processes will be carried out in the business, it provided the clear guidelines and roles & responsibilities for each individual

Rules & regulation:- The rules & regulation of the organisation outlines how an individual must perform their duty being in company norms.

Project background:

The project revolves around developing such type of solution which will in result give productive output in terms data monitoring, validation, top level report generation, High yield in production, and manpower reduction in specific section to significant amount which will help the business to grow rapidly in terms of per cost product as compared to other competitors

Project scope

The scope of this project is to provide the organisation with improve quality on product, Provide advanced technology, lower cost of workforce with best in class services to the customer with innovative and new technology.

In scope functionality

. Developing dashboard for energy monitoring

. Developing PLC system

.  Developing SCADA system for control & monitoring

. Developing dashboard for downtime, production OEE and quality defect pareto chart.

Out scope functionality

. MES system for control quality gates

. IOT for online monitoring of system from mobile application

. To log and report downtime through mob application etc.

Constraints:

The main constraint of this project is the return of investment because due to lack of understanding of the application for new user, hesitation in using the software, less knowledge of software can lead long time for the organisation get result from this software. Hence ROI can take much longer than as it expected, Also the after deployment maintenance cost can also be higher due to increase in domain by time.

Risk:

The major risk in developing this project is hesitation for old operators in using the software due to new technology can lead to failure of project. High training cost, High downtime cost.etc.manpower losses can lead to increase in CT.

Avoid: - Frequent training to understand the operators about the advantages of software.

Technological risk

The understanding of new technology and hesitation of using this are the biggest risk an organisation can face.

Skill Risk

Being a new technology it can be difficult to find developers and testers for this software,

Business risk

Failure of this project can lead to huge capital lost as there is huge downtime and capital investment during development phase

Requirement risk:

The risk associated with req risk is being a new technology many stakeholders cannot provide exact requirement due to lack of domain knowledge hence it can be difficult for the BA to gather requirements

Business Process overview:

Process flow diagram

AS-IS

No digital system for inventory control

Material IN

No method for inventory control

Child part on Prod line

No method to monitor hourly prod

Production on line

Machine breakdown

No method to report B/D

Breakdown maint

No method to log breakdown

Quality defects on line

No provision of automated system to control quality failure

No digital monitoring system to analyze utility consumption

Energy monitoring system

PLC, SCADA system for automation in-house for machine

Manual intervention on CTQ m/c

TO-BE PROCESS FLOW:

Digital monitoring system for FIFO

Digital monitoring system for hourly production system

Digital monitoring system for machine Uptime

Automated system on assy lines to control quality defects

PLC,SCADA system for low cost automation for manpower elimination

Business requirements

The specific requirement from the business is to develop a solution which will help in achieving the key process with effective proportion such as high output yield by increase in OEE, high productivity by online monitoring of hourly production, better manpower allocation, reduce energy cost by online live power reading from each section hence decision can be taken for effective running of manufacturing lines. Reduce in machine downtime can result in avoidance of sales failure such that better planning can be done in advance. Better spare parts management can be done which will help in lower inventory cost.

Hence the very specific business requirement to complete monitoring of system such that each key manufacturing area yield better result.