Scrum Project Name: Scrum Foods (Foods Delivery Applications)

Question 1 – Write Agile Manifesto

Answer

Agile Manifesto - The Agile Manifesto is a foundational document for Agile software development. It was created in 2001 by a group of software developers and thought leaders to provide guiding principles and values that prioritize collaboration, adaptability, and delivering high-quality software. The Agile Manifesto reflects a shift from traditional, rigid project management approaches to more flexible and iterative development processes.

The Agile Manifesto outlines four key values:

- Individuals and Interactions over Processes and Tools - Focus on effective communication and collaboration among team members rather than rigid adherence to predefined processes or reliance on specific tools.

- Working Software over Comprehensive Documentation - Deliver functional software frequently, prioritizing practical outcomes over exhaustive documentation.

- Customer Collaboration over Contract Negotiation - Engage customers actively throughout the project to ensure their needs are met, rather than relying solely on pre-defined agreements.

- Responding to Change over Following a Plan - Embrace and adapt to changes in requirements, even late in development, instead of strictly adhering to a fixed project plan.

The Agile Manifesto is supported by twelve principles:

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile process harness change for the customer’s competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to that shorter timescale.

- Businesspeople and developers must work together daily throughout the project.

- Build project around motivated individuals. Give them the environment and support they need and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face to face conversation.

- Working software is the primary measure of progress.

- Agile process promotes sustainable development. The sponsors, developers and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhance agility.

- Simplicity – The art of maximizing the amount of work not done, is essential.

- The best architectures, requirements, and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behaviour accordingly.

Question 2 - Write minimum 40 User stories and their Acceptance Criteria along with their BV and CP.

Answer

User Stories - A User Story is a concise and simple description of a feature or functionality from the perspective of an end user or customer. It is a key component of Agile development methodologies, helping teams understand what users need and why. User stories are written in plain language and focus on delivering value to the user, guiding the team on what needs to be built.

Example of User Stories are shown below –

| User Story No.1 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO REGISTER IN SCRUM FOODS |  |  |
| SO THAT I CAN DELIVER ORDERS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| Registration Screen |  |  |
| Text Boxes for Username, Password, Nation ID, Mobile no, Email, Address, |  |  |
| Phone Number. |  |  |
| Click on Registration Button. |  |  |
| Send Successful Notification to the user |  |  |

| User Story No. 2 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A RESTAURANT OWNER |  |  |
| I WANT TO VIEW ORDERS |  |  |
| SO THAT I CAN VIEW THE LIST OF RECORDS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| View order, Display List of Orders in the Tabular Form |  |  |

| User Story No. 3 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO ADD THE ADDRESS |  |  |
| SO THAT I CAN GET THE ORDER TO MY ADDRESS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text Box to enter. |  |  |
| Business Rules: Within the radius of 5 km. |  |  |

| User Story No. 4 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO SELECT THE PAYMENT MODE |  |  |
| SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |
| BV: 500 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| Display payment modes, radio button to select payment modes, |  |  |
| Payments button. |  |  |
| Business Rule: Can select only one payment mode. |  |  |

| User Story No. 5 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A ADMIN |  |  |
| I WANT TO VIEW THE RESTAURANTS |  |  |
| SO THAT I CAN APPROVE THEIR REGISTRATION |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| List of restaurants, select restaurant, verify restaurant details, |  |  |
| approve button, reject button, notification to the restaurant |  |  |

| User Story No. 6 | Tasks: 2 | Priority: LOW |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO VIEW THE PRICE |  |  |
| SO THAT I CAN ORDER THE FOOD |  |  |
| BV: 50 | CP: 01 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1. Display price in the list of menu item. |  |  |

| User Story No. 7 | Tasks: 2 | Priority: LOW |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO VIEW THE CONTACTNUMBER OF DELIVERY BOY |  |  |
| SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |
| BV: 50 | CP: 01 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1. Display delivery boy mobile number |  |  |
| 2. Display Delivery boy name in tracking field |  |  |
| 3. Display delivery boy picture |  |  |
| User Story No. 8 | Tasks: 2 | Priority: MEDIUM |
| AS A RESTAURANT OWNER |  |  |
| I WANT TO PROVIDE TIME SLOTS |  |  |
| SO THAT CUSTOMER CAN CHECK OPENNING AND CLOSING HOURS |  |  |
| BV: 100 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1. Click on restaurant dashboard |  |  |
| 2. Add from time to time |  |  |
| 3. Click on submit |  |  |
| 4. Display updated successfully |  |  |

| User Story No. 9 | Tasks: 2 | Priority: HIGH |
| --- | --- | --- |
| AS A BUSINESS OWNER |  |  |
| I WANT TO VIEW RESTAURANT REVENUE REPORT |  |  |
| SO THAT I CAN VIEW THE RESTAURANT'S REVENUE |  |  |
| BV: 200 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1 Select reports |  |  |
| 2 Select revenue reports |  |  |
| 3 Select to add from date |  |  |
| 4 Select region (can select all) |  |  |
| 5. Generate report |  |  |
| 6. Download report in EXCEL |  |  |

| User Story No. 10 | Tasks: 3 | Priority: HIGH |
| --- | --- | --- |
| AS A REG ADMIN |  |  |
| I WANT TO MANAGE REGIONAL RESTAURANTS |  |  |
| SO THAT I CAN TRACK THE PERFORMANCE OF REGIONAL RESTAURANTS |  |  |
| BV: 200 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1 Click on performance of restaurants |  |  |
| 2 Select from date to date |  |  |
| 3 Click on generate report which includes restaurants ID, Name, Revenue |  |  |
| 4 Click on download Report should be in EXCEL |  |  |

| User Story No. 11 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A RESTAURANT OWNER |  |  |
| I WANT TO VIEW ORDERS |  |  |
| SO THAT I CAN VIEW THE LIST OF ORDERS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| View orders, Display list of orders in the tabular form |  |  |

| User Story No. 12 | Tasks: 2 | Priority: MEDIUM |
| --- | --- | --- |
| AS ADMIN |  |  |
| I WANT TO SEE THE REGIONAL REVENUE REPORTS |  |  |
| SO THAT I CAN VIEW THE REGIONAL PERFORMANCE |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| View orders, Display list of orders in the tabular form |  |  |

| User Story No. 13 | Tasks: 2 | Priority: HIGH |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO CHAT WITH REG ADMIN |  |  |
| SO THAT I CAN REQUEST FOR REFUND |  |  |
| BV: 200 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| 1. BR-All mandatory |  |  |
| 2. Text Box fields |  |  |
| 3. Display order id |  |  |
| 4. Text Box for description |  |  |
| 5. Submit button |  |  |
| 6. Generate issue id |  |  |
| 7. Display successful |  |  |

| User Story No. 14 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO REGISTER IN SCRUM FOODS |  |  |
| SO THAT I CAN LOGIN IN SCRUM FOODS APPLICATION |  |  |
| BV: 100 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| Registration Screen, Text boxes, for username, Password, Mobile. No, Email, |  |  |
| Address, click on register button, Send successful notification to the user |  |  |

| User Story No. 15 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO LOGIN IN SCRUM FOODS |  |  |
| SO THAT I CAN USE THE SCRUM FOODS APPLICATION |  |  |
| BV: 200 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Login screen, Text boxes for username, Password, Click on login button. |  |  |

| User Story No. 16 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT SEARCH OPTION IN SCRUM FOODS APPLICATION |  |  |
| SO THAT I CAN SEARCH FOR RESTAURANTS TO ORDER FOOD |  |  |
| BV: 200 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for search menu, show restaurant details, Enable search option to |  |  |
| display list of restaurants to order foods. |  |  |

| User Story No. 17 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO VIEW RESTAURANTS MENU IN SCRUM FOODS APPLICATION |  |  |
| SO THAT I CAN SELECT FOOD TO ORDER FROM RESPECTIVE |  |  |
| RESTAURANT |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| View list of restaurants and menu cards in tabular form, Show available menu |  |  |
| card of restaurants |  |  |

| User Story No. 18 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO SELECT FOOD FROM RESTAURANTS LISTED IN SCRUM FOODS |  |  |
| SO THAT I CAN ORDER FOOD TO ORDER FROM RESPECTIVE |  |  |
| RESTAURANT |  |  |
| BV: 200 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| Login, show list of available restaurants, Display menu cards, Enable the customer |  |  |
| to select item and place order in application. |  |  |

| User Story No. 19 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO MAKE ONLINE PAYMENT |  |  |
| SO THAT I CAN MAKE ONLINE ADVANCE PAYMENT |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Login, Show payment options Net banking, UPI payments, Credit card |  |  |
| Enable the customer to select the mode of payment and proceed with the |  |  |
| payment option. |  |  |
| User Story No. 20 | Tasks: 3 | Priority: HIGHEST |  |
| AS A CUSTOMER |  |  |  |
| I WANT TO HAVE TRACKING OPTION |  |  |  |
| SO THAT I CAN TRACK MY ORDER ONLINE |  |  |  |
| BV: 500 | CP: 05 |  |  |
| ACCEPTANCE CRITERIA |  |  |  |
| Show status of delivery with the location details, and the expected time of |  |  |  |
| delivery, Enable the customer to track the delivery of placed orders and expected |  |  |  |
| time of delivery. |  |  |  |

| User Story No. 21 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT THE CANCLE OPTION |  |  |
| SO THAT I CAN CANCLE THE ORDER IN CASE OF REASON |  |  |
| BV: 500 | CP: 03 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for cancel option, order can be cancelled mentioning the reason of |  |  |
| cancellation, Display the status as cancelled and process for refund to |  |  |
| customer. |  |  |

| User Story No. 22 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT THE FEEDBACK OPTION |  |  |
| SO THAT I CAN RATE, GIVE FEEDBACK AND GIVE RATINGS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for feedback option, option to rate the delivery agent. |  |  |

| User Story No. 23 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO REGISTER |  |  |
| SO THAT I CAN ACCEPT THE ORDER AND DELIVERY |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for Username, Password, Mobile no, Email, Address, Phone Number, |  |  |
| Click on register button, Send successful notification to the user. |  |  |

| User Story No. 24 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO LOGIN IN SCRUM FOODS APPLICATION |  |  |
| SO THAT I CAN VIEW AND ACCEPT THE ORDER FOR DELIVERY |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone Number, |  |  |
| Click on login button, Send successful notification to the user. |  |  |

| User Story No. 25 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO UPDATE THE ORDER STATUS |  |  |
| SO THAT I CAN VIEW AND UPDATETHE DELIVERY STATUS |  |  |
| BV: 500 | CP: 02 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for updating of delivery status and feedback. |  |  |

| User Story No. 26 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO UPDATE THE PAYMENT STATUS |  |  |
| SO THAT I CAN VIEW AND UPDATETHE PAYMENT STATUS FOR COD |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text box for updating of payment status and feedback. |  |  |

| User Story No. 27 | Tasks: 3 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO LOGIN |  |  |
| SO THAT I CAN VIEW THE FEEDBACK FOR MY DELIVERY |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone number, |  |  |
| Click on login button, Send successful notification to the user and access to |  |  |
| delivery boy. |  |  |

| User Story No. 28 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A RESTAURANT OWNER |  |  |
| I WANT TO VIEW DETAILS |  |  |
| SO THAT I CAN VIEW THE LIST OF ORDERS AND RELATED FEEDBACK |  |  |
| FROM CUSTOMERS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone number, |  |  |
| Click on login button, Send successful notification to the user and access to |  |  |
| restaurant owner. |  |  |
| User Story No. 29 | Tasks: 2 | Priority: HIGHEST |
| AS A CUSTOMER |  |  |
| I WANT TO PAYMENT |  |  |
| SO THAT I CAN VIEW MY ORDERS AND PAYMENT RECEIPTS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for reports of placed orders and payments. |  |  |

| User Story No. 30 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A BUSINESS OWNER |  |  |
| I WANT TO REGISTER |  |  |
| SO THAT I CAN LOGIN IN SCRUM FOOD APPLICATION |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone |  |  |
| number, click on register button, Send successful notification to the user. |  |  |

| User Story No. 31 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A BUSINESS OWNER |  |  |
| I WANT TO LOGIN |  |  |
| SO THAT I CAN UPDATE VIEW ORDERS THE PAYMENTS AND OTHERS FOR |  |  |
| DETAILS RESTAURANT |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone |  |  |
| number, click on login button, Send successful notification to the user. |  |  |

| User Story No. 32 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A ADMIN |  |  |
| I WANT TO LOGIN |  |  |
| SO THAT I CAN VIEW THE RESTAURANTS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone |  |  |
| number, click on login button, Send successful notification to the user. |  |  |

| User Story No. 33 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A ADMIN |  |  |
| I WANT TO VIEW REPORTS |  |  |
| SO THAT I CAN VIEW THE REGIONAL REVENUES |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Generate the reports of orders and payments and calculate the revenue. |  |  |

| User Story No. 34 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO RAISE ISSUE |  |  |
| SO THAT I CAN UPDATE THE COMPLAINTS OF DELIVERY AGENTS OR |  |  |
| RESTAURANTS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Enable to add comments for customer regarding the ratings or any complaints |  |  |
| regarding the delivery boys or restaurants. |  |  |

| User Story No. 35 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A DELIVERY BOY |  |  |
| I WANT TO LOGIN |  |  |
| SO THAT I CAN VIEW DELIVERIES REPORTS AND REVENUE GENERATED |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Reports generated and view deliveries report and view revenue generated. |  |  |

| User Story No. 36 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A RESTAURANT OWNER |  |  |
| I WANT TO LOGIN |  |  |
| SO THAT I CAN UPDATE THE LIST OF FOODS AND AVAILABILITY |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Text boxes for Username, Password, Mobile no, Email, Address, Phone number, |  |  |
| Click on register button, Send successful notifications to the user, Update the |  |  |
| available foods and the status of availability. |  |  |

| User Story No. 37 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO UPDATE THE ADDRESS |  |  |
| SO THAT I CAN UPDATE THE NEW ADDRESS AS CURRENT ADDRESS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Modify the address and set as current address. |  |  |

| User Story No. 38 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A ADMIN |  |  |
| I WANT TO ACCESS THE FOOD APPLICATION |  |  |
| SO THAT I CAN ADD OR DELETE THE DELIVERY BOYS |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| User box to update the comments for addition or deletion of the delivery boys. |  |  |

| User Story No. 39 | Tasks: 2 | Priority: HIGHEST |
| --- | --- | --- |
| AS A REGIONAL ADMIN |  |  |
| I WANT TO VIEW REPORTS |  |  |
| SO THAT I CAN VIEW REGIONAL REVENUE |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Generate the reports regional wise and view reports |  |  |

| User Story No. 40 | Tasks: 2 | Priority: MEDIUM |
| --- | --- | --- |
| AS A CUSTOMER |  |  |
| I WANT TO VIEW THE ORDER LIST |  |  |
| SO THAT I CAN REORDER LAST ORDER |  |  |
| BV: 500 | CP: 05 |  |
| ACCEPTANCE CRITERIA |  |  |
| Display order list and enable user to reorder if order is in the stock |  |  |

Question 3– What is epic? Write 2 epics

Answer

Epic is the set of user stories or the big user story consisting of number of small user stories to complete the milestone known as Epic. Also, Epic can be said to be the set of user stories completed to achieve one task.

Example of 2 Epics is below –

- Registration –
AS A CUSTOMER,
I WANT TO REGISTER IN SCRUM FOOD APP,
SO THAT I CAN LOGIN AND PLACE ORDER.

- Login -
AS A CUSTOMER,
I WANT TO LOGIN IN SCRUM FOOD,
SO THAT I CAN ORDER THE FOOD AND MAKE PAYMENT.

Question 4 –What is the difference between BV and CP

Answer

Business Value (BV) - Business Value measures the benefit or impact a feature or task delivers to the organization or end users. It focuses on the importance and outcome of completing a task.

Complexity Points (CP) - Complexity Points estimate the effort and technical difficulty required to complete a feature or task. They focus on how challenging it is to implement.

Difference between BV and CP is below -

| Aspect | Business Value (BV) | Complexity Points (CP) |
| --- | --- | --- |
| Definition | Measures the benefit or impact a task delivers to the organization or end user. | Estimates the effort and technical difficulty required to complete a task. |
| Focus | Value delivered to the business or user. | Effort and difficulty of implementation. |
| Purpose | Helps prioritize tasks based on importance and impact. | Assists in planning and resource allocation. |
| Who defines it | Product Owner, stakeholders, or business leaders. | Development team during estimation. |
| Measurement scale | Strategic or numerical scale (e.g., 1–10, 1–100). | Relative sizing (e.g., Fibonacci: 1, 2, 3, 5, 8). |
| Examples | Revenue generation, compliance, customer satisfaction. | Technical challenges, unknowns, skill requirements. |
| When used | During prioritization of the backlog. | During sprint planning or backlog refinement. |
| Impact on work | Determines what is most valuable to deliver | Influences how much work can be accomplished in a sprint |
| Key questions | How valuable is the Task | How hard is this task to complete |

Question 5 –Explain about Sprint

Answer

Sprint - A Sprint is a core component of the Scrum framework, used in Agile software development. It is a time-boxed iteration, usually lasting 1 to 4 weeks, during which a Scrum team works to deliver a potentially shippable product increment. Sprints are designed to provide consistent, repeatable progress toward the project's goals.

Key features –

- Fixed Time Duration – A Sprint typically lasts between 1 and 4 weeks, depending on the team's preferences and project needs. The duration is consistent throughout the project.

- Goal Oriented – Each Sprint has a Sprint Goal, which is a clear, achievable objective for that iteration.

- Incremental Delivery – By the end of the Sprint, the team delivers a working increment of the product, adding value to the overall project.

- Time boxing – Sprints are time-boxed, meaning they cannot be extended. Any incomplete work is moved to the backlog for future Sprints.

Sprint Activities –

- Sprint Planning – The team plans the Sprint by selecting items from the Product Backlog to work on and defining the Sprint Goal. Tasks are broken down into smaller, manageable pieces.

- Daily Scrum (Stand up) – A short meeting to discuss what was done yesterday, what will be done today, any blocker or issues.

- Sprint Execution – The development team works collaboratively to complete the tasks committed to during Sprint Planning.

- Sprint Review – At the end of the Sprint, the team demonstrates the completed work to stakeholders to gather feedback.

- Sprint Retrospective – The team reflects on the Sprint to identify areas for improvement and discuss what went well, what didn’t, and how to improve in the next Sprint.

Sprint Artifacts –

- Sprint Backlog – A subset of the Product Backlog that the team commits to completing during the Sprint. Contains tasks and stories selected for the Sprint.

- Product Increment - The output of the Sprint, which should be a potentially shippable product increment.

Benefits –

- Focused Work: Encourages teams to work toward clear, short-term goals.

- Flexibility: Allows for iterative development and adaptation to changing requirements.

- Transparency: Frequent reviews ensure stakeholders are kept informed of progress.

- Continuous Improvement: Retrospectives foster an environment of ongoing enhancement in processes and teamwork.

What is sprint Duration: 2 Weeks – sprint Value 15

Sprint Duration – Sprint Duration refers to the fixed length of time allocated for a Sprint in the Scrum framework. During this period, a Scrum team works to complete a defined set of tasks or achieve a specific Sprint Goal, producing a potentially shippable product increment by the end.

Sprint Value – Sprint Value refers to the measurable benefit or contribution that a Sprint delivers to the overall project, stakeholders, or end-users. It represents the value created during a Sprint in terms of achieving the Sprint Goal, completing backlog items, and delivering a potentially shippable product increment.

What is scrum Duration: 1 day – scrum Value 7

Scrum Value – Scrum value defines to the topics or the team size or the number we are going to give to any issue or blocker while discussing during the scrum call.

Sprint Backlog –

| PBI | TASKS | WIP | DONE |
| --- | --- | --- | --- |
| Registration | 3 | 2 | 1 |
| Login | 2 | 2 | 0 |
| Add Restaurants | 3 | 2 | 1 |
| Order food | 3 | 0 | 3 |
| Make payment | 3 | 3 | 0 |
| Track Delivery | 3 | 3 | 0 |
| Customer Feedback | 3 | 3 | 0 |

Question 6 – Explain Product backlog and sprint back log

Answer

Product Backlog - The Product Backlog is a key artifact in the Scrum framework, representing a prioritized list of work items that the Scrum team needs to complete to deliver a product or project. It serves as the single source of truth for all the features, enhancements, bug fixes, technical requirements, and other deliverables required to achieve the product's goals.

Key characteristics –

- Dynamic and Evolving - The Product Backlog is not static; it evolves over time based on changing requirements, market needs, or feedback from stakeholders.

- Prioritized - Items are ordered by priority, with the most important and valuable items placed at the top. These are usually addressed first in Sprints.

- Refined - Items in the backlog are regularly refined or "groomed" to ensure they are ready for future Sprints.

- Owned by the Product Owner - The Product Owner is responsible for maintaining the backlog, ensuring it aligns with the product vision and stakeholder needs.

- Detailed as Needed - Items near the top (high-priority) are more detailed, while those further down can remain less defined until they approach implementation.

Benefits –

- Clarity and Focus: Provides a clear roadmap of work to be done.

- Transparency: Keeps the team and stakeholders aligned on priorities.

- Flexibility: Adapts to changing requirements or feedback.

- Facilitates Planning: Helps teams plan Sprints effectively by pulling items from the top.

Example -

| Backlog Item | Priority | Description | Effort points (Story) |
| --- | --- | --- | --- |
| User authentication | High | Implement login with email and password. | 8 |
| Password reset | Medium | Enable users to reset their password. | 5 |
| Performance optimization | Low | Improve page load times under heavy traffic. | 13 |
| Analytics dashboard | Medium | Build a dashboard for tracking user behaviour. | 8 |

Sprint Backlog - The Sprint Backlog is a key artifact in the Scrum framework that represents a subset of the Product Backlog items selected for a specific Sprint, along with the plan to deliver them. It is the team's working to-do list during the Sprint and includes all tasks required to meet the Sprint Goal.

Key characteristics –

- Subset of the Product Backlog - The Sprint Backlog is derived from the Product Backlog during Sprint Planning. It contains only the items the team commits to completing during the current Sprint.

- Owned by the Development Team - The Development Team is responsible for managing and updating the Sprint Backlog throughout the Sprint.

- Detailed and Clear - Each backlog item is broken into smaller tasks with sufficient detail for the team to understand and work on them.

- Dynamic but Stable - The Sprint Backlog may evolve slightly as tasks are refined, but the scope of the Sprint Goal should not change.

- Linked to the Sprint Goal - Every item in the Sprint Backlog contributes directly to achieving the Sprint Goal.

Benefits –

- Focus: Provides the team with a clear and actionable plan for the Sprint.

- Transparency: Helps everyone understand what the team is working on and the progress being made.

- Adaptability: Allows the team to manage their work dynamically while maintaining alignment with the Sprint Goal.

- Accountability: Ensures the team takes ownership of their commitments and progress.

Example –

| Backlog Item | Task | Status | Effort (Hours) |
| --- | --- | --- | --- |
| User login functionality | Design login page UI | In Progress | 5 |
|  | Implement login API | To do | 8 |
|  | Write unit tests for login logic | To do | 3 |
| Password reset | Create password reset workflow | Done | 6 |
|  | Send email for password reset | In Progress | 4 |

Question 7 – What is impediments log? write 2 impediments

Answer

Impediment Log - An Impediment Log in Agile is a tool or document used to track and manage obstacles, blockers, or issues that hinder the progress of an Agile team during a project. It helps ensure that impediments are identified, prioritized, and addressed promptly to maintain the team's productivity and alignment with the project goals.

Key characteristics –

Centralized Tracking - A single place to record and monitor all impediments affecting the team.

Transparency - Makes impediments visible to all team members, the Scrum Master, and stakeholders.

Prioritization - Impediments are prioritized based on their impact on the Sprint Goal or team performance.

Accountability - Each impediment is assigned an owner responsible for resolving it.

Dynamic Nature - The log evolves as new impediments are identified, and existing ones are resolved.

Example –

| ID | Description | Reported by | Impact | Owner | Status | Resolution Date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Build server is down | Developer A | Cannot test new code | Scrum Master | In progress | NA |
| 2 | Lack of clarity on requirements | Product Owner | Feature development blocked | Product Owner | Resolved | 10-12-2024 |

Question 8 – Explain Velocity of the Team

Answer

Velocity of the Team - According to Scrum, Inc., Team Velocity is a “Measure of the amount of work a team can tackle during a single sprint and is the key metric in Scrum”. When you complete a sprint, you'll total the points for all fully completed user stories and over time find the average number of points you complete per sprint.

So, Velocity means How many Complexity Points (CP) is covered in this sprint and team has covered 8 CPs hence Velocity of team is 8.

Question 9 – Draw Sprint Burn Charts n Product Burn Down Charts

Answer

Question 10 – Explain about Product Grooming

Answer

Product Grooming / Product refinement

Product Grooming is the session in which the vision or goal of the project or product is discussed and who will be your target group in which market segment does the product address. What are the needs and solution doing the product required. Also, what benefits the client will get.
Also to identify the EPICs from the product backlog. Product grooming is processes of planning the project and understanding the needs.
Thus, product grooming includes the refinement to understand what the stakeholder requires and why does it require and what is the value addition is to be done.

Question 11 – Explain the roles of Scrum Master and Product Owner

Answer

The Scrum Master is accountable for establishing Scrum as defined in the Scrum Guide. They do this by helping everyone understand Scrum theory and practice, both within the Scrum Team and the organization. The Scrum Master is accountable for the Scrum Team’s effectiveness. They do this by enabling the Scrum Team to improve its practices, within the Scrum framework.

The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. The Product Owner is one person, not a committee. The Product Owner may represent the needs of many stakeholders in the Product Backlog. Those wanting to change the Product Backlog can do so by trying to convince the Product Owner.

Scrum Master - The day-to-day activity of a Scrum Master involves servant leadership where they are involved in performance planning, coaching, self-organization, removing obstacles, resolving conflicts and serving the team.

Product Owner - The first responsibility of the product owner is customer satisfaction and this they carry out by ensuring that customer requirements are given priority and there is transparency between development team and stakeholders.

The product owner guarantees stakeholder satisfaction by ensuring product success and building a product which meets business requirements.

The Scrum Master ensures project success, by assisting the product owner and the team in using the right Scrum processes for creating the product and establishing the Agile principles. The Product Owner interacts with the users and customers, Stakeholders, the Development team and the Scrum Master to deliver a successful product.

The Product Owner and the Scrum Master are both invaluable members of a Scrum project team, as they build the perfect relation with the development team and strive to deliver the best results

Question 12 – Explain all Meetings Conducted in Scrum Project

Answer

There are five types of scrum meetings held during the scrum process which are as follows.

- Sprint Planning Meeting

- Daily Scrum Meeting

- Sprint Review Meeting

- Sprint Retrospective Meeting

- Backlog Refinement Meeting

● Sprint Planning Meeting:

This meeting begins with the Product Owner. In this meeting the PO explains their vision and how the team should go about completing this step of the project. During this meeting, team members decide the amount of work they can complete within the sprint. This is also when the team moves work from the Product Backlog to the Sprint Backlog. This step requires a lot of planning and can take several hours for the group to decide on a finalized Sprint.

● Daily Scrum Meeting:

From the planning meeting, we move into the daily scrum meetings. Every single day for 15 minutes, the team gathers together to report any issues or progress on their tasks. Though brief, this meeting is an essential part of the scrum process. It is designed to keep all group members on track in a cohesive manner. Normally the Product Owner is present during all daily scrum meetings to assist in any way daily Stand-up Meeting End of every Scrum, Scrum Developers will participate in Scrum meeting. Here they must answer 3 Questions.

a. What task did you work in this scrum?
b. What task will you work on next scrum?
c. Any Challenges/impediments? When will you complete the user story?

● Sprint Review Meeting:
This meeting is used to showcase a live demonstration of the work completed. During this meeting the Product Owner, Scrum Master, and stakeholders are present to review the product and suggest changes or improvements.

They will see the Velocity – How many CP is covered in this sprint Burn Down Chart.

● Sprint Retrospective Meeting:
This meeting is held to facilitate a team's reflection on their progress. The team speaks openly about their organizational concerns and teamwork. During this meeting, dialogue should remain friendly, non-judgmental and impartial. This review session is a key part of team building and development and it's also very important for future scrum projects. In this meeting team will discuss about Challenges faced and come up with lessons learnt. We can use these lessons learnt in Sprint planning meeting to select user stories for the next sprint.

● Backlog Refinement Meeting:
Last, is the backlog refinement meeting. In this meeting, team members focus on the quality and skill of the work involved during the sprints. This meeting is necessary for the business owners to connect with the development team and is used to assess the quality of the final product. This meeting involves important reflection on the team backlogs.

Question 13 – Explain Sprint Size and Scrum Size

Answer

Sprint Size: The whole concept of sprint is to identify User stories that the scrum team would work on and complete within a specific sprint duration. Typically known as the sprint length. Sprints can be of 1, 2, 3 or 4 weeks long at the max. Anything beyond 4 weeks is never agile scrum project management.

Scrum Size: Scrum Team size can 8 to 10 people.

- Product Owner

- Scrum Master

- Developers 8

Question 14 – Explain DOR and DOD

Answer

Definition of Ready DOR

The product owner could work together with the team to define an artifact called "the Definition of Ready" (DOR) for ensuring that items at the top of the backlog are ready to be moved into a sprint so that the development team can confidently commit and complete them by the end of a sprint.

The term "Definition of Ready" isn’t described in the Scrum Guide like the user stories and the Acceptance Criteria embedded in it. Perhaps, you may consider the Definition of Ready is an integral part of the backlog refinement activity, instead of using the Definition of Ready as a sequential and phase-gate checklist. Backlog refinement is an ongoing process; therefore, it’s not restricted to an event but considered an activity.

Definition of Done: DOD

The definition of Done is structured as a list of items, each one used to validate a user story or PBI, which exists to ensure that the Development Team agree about the quality of work they’re attempting to produce. It serves as a checklist that is used to check each Product Backlog Item (aka PBI) or User Story for completeness. Items in the definition of “Done” are intended to be applicable to all items in the Product Backlog, not just a single User Story. It can be summarized as following:

DoR and DoD are practices that are needed while improving a product. To ensure that the product meets customer expectations, certain features and ideas have to be added to it from time to time, and defining the criteria for the features to be added is necessary and that's when the DoR and DoD come into play

Question 15 – Explain Prioritization Techniques and MVP

Answer

Prioritization of requirements is an important aspect of all software development approaches, but it is especially important in Agile software development. When we talk about some of the Product Owner's activities in Scrum products, such as "Ordering items in the Product Backlog to best achieve mission and objectives", "Demonstrate what the Scrum Team would work on next", and "Streamlining the quality of the work the Developers performs", we are talking about workload prioritization. All we're attempting to do is prioritize the issues in the backlog. In essence, we are attempting to discover the user's priority tasks and rank them accordingly, while also considering certain additional characteristics. For example, we may utilize five priority factors to rank user stories, such as the importance users place on product vision, urgency, time restrictions, technical difficulty, and stakeholder interests. Projects must be correctly prioritized for both the overall project objectives and the individual activities that will fulfil the objectives to be successful. As a result, we address the prioritizing issue on two levels:

Product level: Evaluate which elements of the product might contribute more to the project's major aims.

Tasks level: Specify which work items must be completed and in what sequence during the software product development cycle.

Types of Agile Prioritisation Techniques.

Moscow Agile Prioritization technique

Moscow analysis is a business analyst prioritizing approach advocated in the IIBA BABOK and derived from the DSDM (dynamic software development method). According to this strategy, a collection of needs or user stories should be divided into four categories:

M: Must. Describes a criterion that must be met in the final solution for it to be judged successful.

S: Should. Represents a high-priority component that, if feasible, should be included in the solution. This is frequently a vital criterion, but it can be met in other ways if absolutely required.

C: Could. Describes a criterion that is desirable but not required. If time and resources allow, this will be added.

W: Would. Represents a demand that stakeholders have decided will not be executed in a particular release but will be addressed in the future.

After categorizing the needs into four groups, they are rated in order of priority within each category.

Priority Poker

Priority poker is a simple design game for ranking objects in order of importance. Priority poker is named from the fact that it is quite like arranging poker (a technique for evaluating the costs of the user stories widely used in Agile development projects).

Before the game begins, the moderator collects all the individuals who need to be engaged in the prioritizing process, such as stakeholders, product managers, strategists, programmers, domain experts, and sometimes even consumers. The moderator must also prepare a list of tasks to prioritize as well as a collection of priority cards to distribute to each player. The volume of cards in this set is determined by how many degrees of priority are useful in this specific instance. In certain circumstances, a 5-point scale (e.g., very high priority, high priority, medium priority, low priority, very low priority), a 3 point scale (e.g., high urgency, medium urgency, low urgency), or even a 10-point scale may be used. The number of cards matches to the scale's numbers.

The supervisor then reviews a piece of functionality (user story). Each participant selects the card that they believe represents the best ranking for that assignment and sets it face down on the table. After each player has made their selection, all the cards are turned over at the same time. The disparities are addressed, and the game continues until the estimations are roughly equal.

Cost Of Delay

This Agile prioritization technique is a concept that assists you in determining the amount of money you risk losing if certain features are unavailable. Essentially, you are putting yourself in the path of those who are combating fires. As a result, it is a proactive struggle to guarantee that there are no money-bleeding situations.

You may estimate how urgent they are by calculating how much money the organization would lose every day if the feature or job is delayed. Therefore, you will have a well-planned timetable that will contribute to total budget savings. As a result, this prioritizing strategy is motivated only by financial considerations and has nothing to do with user experience or customer happiness.

Although these factors may be considered when calculating the Cost of Delay, they are not the primary goal of these Agile prioritization methods. The benefits of employing this priority technique in conjunction with others would be both financially and emotionally justifiable.

Conclusion:

These Agile prioritization methods are critical components of project planning and management. You may wind up losing a lot of money on the project if you don't have appropriate Agile prioritization techniques in place. Furthermore, the initiative may have little influence on the intended clients. As a result, it is critical to employ an objective prioritizing grading system that adds to the success of an Agile product development project.

MVP (Minimum Viable Product), the Core of the Agile Methodology. An MVP is a concept from agile scrum that refers to a product that has just enough features to satisfy the needs of early customers and, more importantly, give them something to provide feedback on to shape the future of the product.

Question 16 – Difference between Business Analyst n Product Owner

Answer

Product Owner
The Product Owner has a vision of the product keeping the domain/industry experience and the market need. Their job is to ensure that the product meets the market and stakeholder needs; they conduct market analysis followed by an enterprise SWOT analysis to come up with the product vision.
The PO also works on the go-to-market strategy for the product. The PO tries to leverage their experience in the domain, need of the market, the industry or the domain, the organization's market position, and the customer expectation of the product.

Critical Responsibilities for Product Owner

- Market Analysis

- Analysis of market need/demand

- Availability of similar products in the market

- Underserved customer needs

- Potential trends in synergy with current offerings

- Enterprise Analysis

- SWOT analysis

- Due diligence on the market opportunity

- Product offering decision based on the due diligence report

- Product Vision and Roadmap

- Product vision keeping the need analysis in mind

- Product roadmap with high-level features and timeline

- Managing Product Features

- Managing stakeholder expectations and prioritizing needs

- Prioritization of the epics, stories, and features based on criticality and ROI involved

- Managing Product Backlog

- Prioritization of user stories

- Reprioritization based on stakeholders' needs

- Epics planning

- Managing Overall Iteration Progress

- Sprint progress review

- Reprioritization of sprints and epics if needed

- Sprint retrospectives with Business Analyst

Business Analyst:

As we know, Business Analysts are the change-makers, problem solvers, questioners, facilitators, the bridge between the users/stakeholders and the Agile team. They question assumptions and requirements, assess the needs, find gaps, and work closely with the stakeholders/SMEs to detail the requirements, features, user stories, and understand/elicit the requirements.
They work closely with the Product Owners to manage the user stories and epics.

- Requirements modelling and elicitation

- Data flow diagrams

- Business rules

- Dependency mapping

- Smooth execution of the sprints

- Requirements clarification to the team

- Maintaining the dependency map and the traceability matrix.

- Facilitation support for users in UAT

- Requirements elicitation

- Modelling

- Requirements walkthroughs

- Requirements workshops

- Acceptance criteria

- Often the Business Analyst is considered a Proxy Product Owner. This allows the Agile team to have a higher amount of access to the Product Owner's perspectives.

Critical Responsibilities for Business Analysts

- Managing User Stories

- Prioritizing the user stories

- Clearing the impediments if any

- Detailing the Requirements as per the Stakeholders’ Needs and Expectations

- Requirements elicitation

- Business rules

- Modelling

- Requirements walkthroughs

- Requirements workshops

- Acceptance criteria

- Clarifying the details of requirements with stakeholders

- Coordinating with the development team to get the stories developed

- Day to day support in requirements clarifications and business rules

- SPOC for the agile team for all requirements related queries

- Impact Analysis for Changes

- Maintaining the traceability matrix and dependencies

- Components mapping

- Impact analysis for changes

- Work closely with the PO on the Sprint Execution

- A representative of the PO in the Agile team in clarifying questions and issues

- Assists the PO in managing the sprint and the product backlog

- Take a lead role in the sprint retrospectives

Question 17 – Prepare a sample Resume of 3yrs exp Product Owner

Answer

Samir Sable
samirsable27@gmail.com
8055203525

Objective

Motivated and forward-thinking product owner with 3+ years of experience. Eager to support team with leadership and guidance over a wide range of product development efforts. In previous roles reduced the delivery time by 20% and was able to coordinate 95% of product completion in line with the company roadmap.

Work Experience

Agile Product Owner                                                                         2022 to Present
Deutsche Bank Pune

- Acted as liaison between business, sales and IT teams to refine the product and incorporate features based on market demands.

- Partnered with IT and product leadership to drive and manage the solution development process and ensure the product team understands the direction and vision.

- Collaborated with teams to discover and deliver the best solution to the market presented by the product team lead and the business.

- Created and maintained the solution vision, roadmap, and backlog of work through the project's life cycle.

- Translated features into user stories within the team’s backlog while managing, ranking, and prioritizing this backlog to reflect stakeholder’s requirements.

- Key achievement:
Effectively negotiated sprint goals with the team, which resulted in slashing delivery time by 20% in a single quarter.

Scrum Product Owner

- Collaborated with stakeholders to understand business problem statements and convert them into user stories.

- Articulated product vision and user stories in a way clearly understandable to development teams.

- Managed backlog of user stories for 2 products simultaneously.

- Established user story acceptance criteria and refined stories with Scrum teams.

- Created Sprint Release Plans with input from development teams.

- Applied Agile methods and processes to promote a disciplined and transparent project management process.

Key achievement:

- Planned and estimated 2-week sprints in a realistic yet time-efficient manner that allowed the teams to deliver 97% of the MVP according to the company roadmap.

- Education
PGDM (Marketing) ISBS
Pune

- B.Sc., Computer Application
Nagpur

- Key Skills

- Conceptual skills

- User-centred design processes

- Design quality standards

- Service and product design methodologies

- Agile and Scrum

- Conducting design sprints

- User validation

- Analytical skills

- Collaboration and teamwork

- Communication

- Certifications

- Certified SAFe® Product Owner.